HAI SkyStruct Platform

A-to-Z Manufacturing & Construction Guidebook

Software Configurator Manual — Stage 0 to Stage 8

Version 3.0 | March 2026

ARADA Governance | House of Architecture & Interiors

Author: Hasan Mollamahmutoglu — Chief Governance Architect

AUDIENCE: Software Configurator / Developer / System Integrator

This document tells you EXACTLY what to build, configure, and deploy at each project stage.

# Table of Contents

Chapter 1 — Executive Summary & How to Read This Document

Chapter 2 — Platform Architecture Overview

Chapter 3 — Contract Parameter Framework (Parametric Configuration)

Chapter 4 — Stage Gate Model & What Happens at Each Stage

Chapter 5 — STAGE 0: Strategic Definition / Strategic Definition

Chapter 6 — STAGE 1: Preparation & Concept Design

Chapter 7 — STAGE 2: Concept Design

Chapter 8 — STAGE 3: Developed Technical Design

Chapter 9 — STAGE 4: Technical Technical Design

Chapter 10 — STAGE 5: Construction

Chapter 11 — STAGE 6: Handover & Close-Out

Chapter 12 — STAGE 7: In Use (DLP)

Chapter 13 — STAGE 8: Post-Completion

Chapter 14 — Process Flow Catalog (All 31 PFs)

Chapter 15 — User Roles & Permissions Matrix

Chapter 16 — Escalation Framework (5-Level Model)

Chapter 17 — Reporting & Dashboard Configuration

Chapter 18 — Testing & Go-Live Checklist

Appendix A — Document Cross-Reference Index

Appendix B — Template Starter Pack Index (108 Templates)

Appendix C — Glossary & Contact

# Chapter 1 — Executive Summary

## 1.1 Purpose of This Document

This guidebook is the single source of truth for the software configurator responsible for implementing the HAI SkyStruct Platform. It explains what to configure, when to configure it (by project stage), and how it connects to every other document in the governance framework.

The platform manages dual contract types — Construction (FIDIC 1999 Red Book with Particular Conditions) and Consultancy — across the full project lifecycle from Stage 0 (Strategic Definition) through Stage 8 (Post-Completion).

## 1.2 How to Read This Document

Chapters 5 through 13 are the core of this manual. Each chapter covers one Stage (0-8) and tells you exactly:

What MODULES to activate at this stage

What PROCESS FLOWS (PFs) to configure

What TEMPLATES the users will need

What APPROVAL WORKFLOWS to set up

What DASHBOARDS and REPORTS to enable

What DATA ENTITIES to create/populate

What NOTIFICATIONS and ESCALATIONS to configure

What INTEGRATION POINTS to establish (ERP, DMS, etc.)

## 1.3 Approval Chain — Critical Rule

Every submittal, document, and approval in this platform follows a 3-party chain. There is NO separate Employer approval column.

| Role | Action | System Behaviour |
| --- | --- | --- |
| Contractor | Prepares & Submits | Initiates workflow, uploads documents |
| Lead Consultant | Reviews & Approves | Applies response code (A/B/C/D/E), triggers next step |
| ER / HAI | Endorses | Final endorsement, closes loop, archives |

## 1.4 Response Codes

| Code | Meaning | System Action |
| --- | --- | --- |
| A | Approved — No Comments | Close submittal, release to next stage |
| B | Approved with Comments | Close submittal, contractor to incorporate comments in next revision |
| C | Revise & Resubmit | Return to contractor, new revision required within SLA |
| D | Rejected | Return to contractor, full rework, new submission |
| E | For Information Only | No approval required, filed for record |

## 1.5 Platform Inventory Summary

| Category | Count | Reference Documents |
| --- | --- | --- |
| Governance Documents | 36 | HAI-GOV-001 to HAI-GOV-043, HAI-GOV-074 |
| Process Flows (.drawio) | 31 | HAI-GOV-051 to HAI-GOV-073, HAI-GOV-076 to HAI-GOV-083 |
| Templates (Starter Pack) | 108 | HAI-GOV-075 folder — 11 category sub-folders |
| Total Deliverables | 175 | All indexed in HAI-GOV-000 Document Register |

# Chapter 2 — Platform Architecture Overview

## 2.1 Dual Contract Coverage Model

The platform must handle two fundamentally different contract types simultaneously. The software configurator must ensure both paths are fully parameterised.

| Attribute | Construction Contract | Consultancy Contract |
| --- | --- | --- |
| Governing Standard | FIDIC 1999 Red Book + Qatar Particular Conditions | Bespoke Consultancy Agreement |
| Payment Mechanism | Interim Payment Certificates (IPC) | Monthly Fee Invoicing |
| Variation Mechanism | Variation Orders (VO) per FIDIC Cl. 13 | Scope Change Requests |
| Time Extension | Extension of Time (EOT) per FIDIC Cl. 8.4 | Programme Revision Requests |
| Defects Period | Defects Liability Period (DLP) per FIDIC Cl. 11 | N/A |
| Performance Bond | 10% of contract value | Professional Indemnity Insurance |
| Retention | 10% capped at 5% of contract value | N/A |
| Applicable Templates | Categories A-J (full submittal hierarchy) | Consultant-specific subset |

## 2.2 Module Architecture

The platform is structured into 8 functional modules. The configurator must build these modules sequentially per the stage-gate logic.

| Module | Function | Key PFs | Config Reference |
| --- | --- | --- | --- |
| Document Management | Submittal, correspondence, transmittal | PF-01, PF-02 | GOV-013, GOV-035 |
| Financial Control | IPC, variations, claims, bonds | PF-03, PF-08, PF-11, PF-29 | GOV-031, GOV-032 |
| Governance Control | Stage-gate, freeze, approval engine | PF-05, PF-06, PF-09 | GOV-034, GOV-033 |
| Quality & Site | Inspection, NCR, snagging | PF-10, PF-13, PF-31 | GOV-015 |
| HSE | Risk assessment, permits, incidents | N/A (template-driven) | GOV-015 |
| Contract Administration | TOC, performance cert, final account | PF-28, PF-29, PF-30 | GOV-031 |
| Handover & DLP | As-built, O&M, defects tracking | PF-15, PF-26, PF-27 | GOV-015 |
| Analytics & KPI | Dashboards, predictive, reports | PF-18, PF-21, PF-23 | GOV-016 |

## 2.3 Technology Stack

| Layer | Technology | Configuration Requirement |
| --- | --- | --- |
| Frontend | Web Application (responsive) | Role-based dashboard per GOV-016 |
| Workflow Engine | Configurable BPM | Rules per GOV-013, escalation per GOV-033 |
| Notification Engine | Email + In-app + SMS | Rules per GOV-014 |
| Document Store | DMS with version control | Numbering per GOV-035, lifecycle per PF-01 |
| Reporting | BI Dashboard + PDF export | Templates per GOV-016, frequency per GOV-036 |
| Integration | ERP bi-directional sync | Mapping per GOV-043, sync logic per PF-20 |
| Authentication | SSO + RBAC | Roles per GOV-012, 17 role types |

# Chapter 3 — Contract Parameter Framework

## 3.1 Parametric Approach

The platform does NOT hard-code contract values. Every contract-specific value is a configurable parameter. The configurator must build a parameter administration screen where HAI administrators can set values per project/contract without code changes.

## 3.2 Construction Contract Parameters

Reference: HAI-GOV-011-R0.0_System_Configuration.xlsx

| Parameter | FIDIC Clause | Default Value | Config Type |
| --- | --- | --- | --- |
| Defects Notification Period | Cl. 11.1 | 365 days | Duration (days) |
| Retention Percentage | Cl. 14.3 | 10% | Percentage |
| Retention Cap | Cl. 14.3 | 5% of Contract Price | Percentage |
| IPC Submission Frequency | Cl. 14.3 | Monthly (28 days) | Duration (days) |
| Engineer Review Period (IPC) | Cl. 14.6 | 28 days | Duration (days) |
| Employer Payment Period | Cl. 14.7 | 56 days from IPC | Duration (days) |
| Variation Approval Threshold | Cl. 13.1 | QAR 500,000 | Currency |
| EOT Claim Notice Period | Cl. 20.1 | 28 days | Duration (days) |
| DAB Referral Period | Cl. 20.4 | 84 days | Duration (days) |
| Performance Bond Value | Cl. 4.2 | 10% of Contract Price | Percentage |
| Delay Damages Rate | Cl. 8.7 | Per Particular Conditions | Currency/day |
| Advance Payment | Cl. 14.2 | Per Particular Conditions | Currency |

## 3.3 Consultancy Contract Parameters

| Parameter | Default Value | Config Type |
| --- | --- | --- |
| Monthly Fee Amount | Per Agreement | Currency |
| Invoice Submission Date | 1st of each month | Day of month |
| Payment Terms | 30 days from invoice | Duration (days) |
| Performance Assessment Frequency | Quarterly | Frequency |
| Professional Indemnity Insurance | Per Agreement | Currency |
| Key Personnel Replacement Notice | 30 days | Duration (days) |
| Scope Change Approval Authority | ER/HAI | Role |

# Chapter 4 — Stage Gate Model Overview

The project lifecycle follows 9 stages (0-8). Each stage has a gate that must be passed before proceeding. The software configurator must implement stage-gate logic as a core platform mechanism.

| Stage | Name | Gate Criteria | Key System Actions |
| --- | --- | --- | --- |
| 0 | Strategic Definition | Feasibility approved, budget allocated | Project created, parameters loaded, roles assigned |
| 1 | Preparation & Concept Design | Concept Design approved, consultants appointed | Consultant contracts registered, submission workflows activated |
| 2 | Concept Design | Concept approved by client | Technical Design submittal workflows active, review cycles begin |
| 3 | Developed Technical Design | DD freeze, cost plan approved | Freeze mechanism activated, cost tracking live |
| 4 | Technical Technical Design | TD complete, tender docs ready | Tender evaluation module active, procurement workflows |
| 5 | Construction | Contract awarded, contractor mobilised | ALL modules fully active — IPC, VO, NCR, HSE, progress reporting |
| 6 | Handover & Close-Out | TOC issued, punch list <5% open | Handover workflows, as-built compilation, O&M assembly |
| 7 | In Use (DLP) | All defects tracked, rectification monitored | DLP defect tracking, performance monitoring, retention release |
| 8 | Post-Completion | Performance Certificate issued, final account agreed | Final payment, archive, lessons learned, contract closure |

Reference: HAI-GOV-034-R0.0_Gate_Passage_Checklists.xlsx — Contains the detailed checklist for each gate.

# Chapter 5 — STAGE 0: Strategic Definition / Strategic Definition

OBJECTIVE FOR SOFTWARE CONFIGURATOR:

Establish the project in the system. Load contract parameters. Assign initial roles. No active workflows yet — this is setup only.

## 5.1 Active Modules

Project Setup

User Administration

Contract Parameter Admin

## 5.2 Process Flows to Configure

PF-05 Stage Gate (gate definition only)

PF-19 User Role Management

## 5.3 Configuration Tasks (Step-by-Step)

The configurator must complete the following tasks before this stage goes live:

| Task | Details | Reference Doc |
| --- | --- | --- |
| Create Project Record | Project name, number, location, client, contract type (Construction/Consultancy), estimated value, target dates | GOV-011 |
| Load Contract Parameters | All parameters from Chapter 3 — FIDIC durations, retention %, IPC frequency, etc. These drive ALL downstream workflows | GOV-011 |
| Configure Stage Gate Definitions | Define all 9 stages (0-8), gate names, mandatory checklist items per gate | GOV-034 |
| Set Up Role Templates | Create the 17 role types from GOV-012. Do NOT assign users yet — just create role definitions | GOV-012 |
| Assign Initial Users | HAI admin, Project Director, ER representative — minimum roles for Stage 0 | GOV-012 |
| Configure Document Numbering | Set up numbering convention: [Project]-[Category]-[Discipline]-[Sequential]-[Revision] | GOV-035 |
| Set Up Notification Rules (Basic) | Admin notifications only — system alerts, login events, audit trail | GOV-014 |

## 5.4 Templates to Distribute

None — Stage 0 is system setup only. No templates distributed yet.

## 5.5 Dashboards & Reports to Enable

Project summary card (name, value, dates, status)

System health / login audit

## 5.6 Integration Points

ERP: Create project cost centre

DMS: Create folder structure

## 5.7 Gate Exit Criteria

Project record complete, parameters loaded, roles assigned, numbering configured. Gate 0 checklist signed off by Project Director.

# Chapter 6 — STAGE 1: Preparation & Concept Design

OBJECTIVE FOR SOFTWARE CONFIGURATOR:

Consultant appointments activated. Submission workflows for design brief and programme. Correspondence management goes live.

## 6.1 Active Modules

Document Management

Correspondence

Consultant Management

## 6.2 Process Flows to Configure

PF-01 Document Review (8-step cycle)

PF-02 Correspondence

PF-05 Stage Gate

PF-09 Approval Engine

PF-25 Consultant Mobilisation

## 6.3 Configuration Tasks (Step-by-Step)

The configurator must complete the following tasks before this stage goes live:

| Task | Details | Reference Doc |
| --- | --- | --- |
| Activate Document Submission Workflow (PF-01) | 8-step review cycle: Submit → Log → Route → Review → Comment → Consolidate → Respond → Distribute. Configure SLA for each step. | GOV-013 |
| Activate Correspondence Module (PF-02) | Incoming/outgoing letter tracking, auto-numbering, response deadline alerts | GOV-013, GOV-014 |
| Configure Approval Engine (PF-09) | Define approval matrix: who approves what, at what value threshold, delegation rules | GOV-013 |
| Register Consultant Contracts | Contract value, scope, key personnel, payment schedule, insurance details | GOV-011 |
| Set Up Consultant Mobilisation Checklist (PF-25) | Appointment letter, team deployment, office setup, IT provisioning, kick-off meeting | PF-25 drawio |
| Distribute Technical Design Submittal Templates | Category A templates: DES-A00 Technical Design Submittal Cover | Templates/A-Design/ |
| Activate Transmittal Letter Workflow | Cover letters for all outgoing submissions | Templates/General/Submittal_Transmittal_Letter.docx |

## 6.4 Templates to Distribute

A-Design: DES-A00_Technical Design_Submittal_Cover.docx

General: Submittal_Transmittal_Letter.docx

General: MOM_Template.docx

General: RFI_Template.docx

General: Correspondence_Log.xlsx

General: Document_Transmittal_Log.xlsx

## 6.5 Dashboards & Reports to Enable

Consultant mobilisation tracker

Submission register (open/closed)

Correspondence log with overdue alerts

## 6.6 Integration Points

ERP: Register consultant contract, fee schedule

DMS: Enable version control on submissions

## 6.7 Gate Exit Criteria

All consultants mobilised, brief approved, programme baseline set. Gate 1 checklist signed off.

# Chapter 7 — STAGE 2: Concept Design

OBJECTIVE FOR SOFTWARE CONFIGURATOR:

Technical Design review workflows fully active. Material submittals begin. RFIs tracked. Meeting minutes recorded systematically.

## 7.1 Active Modules

Document Management

Technical Design Review

RFI Management

Meeting Management

## 7.2 Process Flows to Configure

PF-01 Document Review

PF-02 Correspondence

PF-09 Approval Engine

PF-12 Risk Register

PF-16 Meeting Action Tracking

## 7.3 Configuration Tasks (Step-by-Step)

The configurator must complete the following tasks before this stage goes live:

| Task | Details | Reference Doc |
| --- | --- | --- |
| Activate Technical Design Review Cycles | Full PF-01 with response codes A/B/C/D/E. Configure review period SLAs (typically 14 days for concept) | GOV-013 |
| Activate RFI Module | RFI submission, routing to consultant, response tracking, overdue escalation | Templates/General/RFI_Template.docx |
| Configure Risk Register (PF-12) | Risk categories, probability/impact matrix, risk owner assignment, mitigation tracking | PF-12 drawio |
| Activate Meeting Management (PF-16) | MOM template, action item tracker, follow-up alerts | Templates/General/MOM_Template.docx |
| Set Up Drawing Register | Drawing numbering, revision tracking, superseded drawing management | Templates/General/Drawing_Register.xlsx |
| Configure Site Instruction Module | SI issuance, acknowledgment tracking, cost implication flagging | Templates/General/Site_Instruction_Template.docx |

## 7.4 Templates to Distribute

A-Design: DES-A00_Technical Design_Submittal_Cover.docx

General: RFI_Template.docx + RFI_Register.xlsx

General: MOM_Template.docx + Action_Item_Tracker.xlsx

General: Site_Instruction_Template.docx + SI_Register.xlsx

General: Drawing_Register.xlsx

General: Photo_Log.xlsx

## 7.5 Dashboards & Reports to Enable

Technical Design submission tracker (by discipline)

RFI status (open/responded/overdue)

Risk register heatmap

Action item completion rate

## 7.6 Integration Points

DMS: Drawing revision control

Email: RFI notification distribution

## 7.7 Gate Exit Criteria

Concept design approved, cost estimate aligned, risk register populated. Gate 2 checklist signed off.

# Chapter 8 — STAGE 3: Developed Technical Design

OBJECTIVE FOR SOFTWARE CONFIGURATOR:

Freeze mechanism activated. Material submittals in full flow. Cost plan tracking live. Spatial Coordination approval workflows active.

## 8.1 Active Modules

Document Management

Material Submittals

Spatial Coordination & Cost

Freeze Management

## 8.2 Process Flows to Configure

PF-01 Document Review

PF-06 Freeze Exception

PF-11 Spatial Coordination Cost

PF-12 Risk Register

## 8.3 Configuration Tasks (Step-by-Step)

The configurator must complete the following tasks before this stage goes live:

| Task | Details | Reference Doc |
| --- | --- | --- |
| Activate Freeze Mechanism (PF-06) | Technical Design freeze at DD completion. Any change requires a Freeze Exception Request with justification, cost impact, and programme impact. Configure approval matrix for exceptions. | GOV-013, PF-06 drawio |
| Activate Material Submittal Workflows | Category B templates: material approval, mock-up, colour schedule, equipment data, concrete mix design | Templates/B-Material/ |
| Configure Spatial Coordination & Cost Module (PF-11) | Spatial Coordination allocation, commitment tracking, forecast vs actual, earned value | PF-11 drawio |
| Distribute Method Statement Templates | Category C: all 14 method statement templates for contractor preparation | Templates/C-Method_Statements/ |
| Configure Submittal Register | Central register tracking all submittals across categories A-J with status, dates, response codes | Templates/General/Submittal_Status_Register.xlsx |

## 8.4 Templates to Distribute

B-Material: MAT-B00 through MAT-B11 (5 templates)

C-Method Statements: MS-C01 through MS-C14 (14 templates)

General: Submittal_Status_Register.xlsx

## 8.5 Dashboards & Reports to Enable

Material submittal status by trade

Freeze exception log

Spatial Coordination vs forecast variance

Cost plan tracker

## 8.6 Integration Points

ERP: Spatial Coordination lines sync

DMS: Material approval document lifecycle

## 8.7 Gate Exit Criteria

DD complete, design frozen, cost plan approved, material submittals on track. Gate 3 checklist signed off.

# Chapter 9 — STAGE 4: Technical Technical Design

OBJECTIVE FOR SOFTWARE CONFIGURATOR:

Tender documentation finalised. Procurement workflows active. Authority submissions begin. All design submittals complete.

## 9.1 Active Modules

Document Management

Procurement

Authority Submissions

Tender Management

## 9.2 Process Flows to Configure

PF-01 Document Review

PF-04 Procurement

PF-07 Authority Submissions

PF-09 Approval Engine

## 9.3 Configuration Tasks (Step-by-Step)

The configurator must complete the following tasks before this stage goes live:

| Task | Details | Reference Doc |
| --- | --- | --- |
| Activate Procurement Module (PF-04) | RFP creation, tender evaluation, bid comparison, contract award recommendation. Configure tender evaluation criteria and scoring methodology. | PF-04 drawio |
| Activate Authority Submission Tracking (PF-07) | Track submissions to: Civil Defence, Kahramaa, Ashghal, Municipality. Each authority has different requirements and timelines. | PF-07 drawio |
| Configure Authority-Specific Trackers | Separate tracking sheets per authority with their specific requirements | Templates/J-Specialist/ |
| Distribute Specialist/Regulatory Templates | Category J: Civil Defence, Ashghal NOC, Municipality, Kahramaa, GSAS | Templates/J-Specialist/ |
| Set Up Subcontractor Approval Workflow | Subcontractor nomination, qualification review, approval by consultant and ER/HAI | Templates/G-Contractual/CON-G08_Subcontractor_Approval.xlsx |

## 9.4 Templates to Distribute

J-Specialist: REG-J00 through REG-J07 (7 templates)

G-Contractual: CON-G08_Subcontractor_Approval.xlsx

G-Contractual: CON-G00_Variation_Register.xlsx

## 9.5 Dashboards & Reports to Enable

Tender evaluation tracker

Authority submission status per authority

Procurement pipeline

Subcontractor approval status

## 9.6 Integration Points

ERP: Procurement/PO sync

Authority portals: submission status (manual or API)

## 9.7 Gate Exit Criteria

TD complete, tender awarded, authorities approved, contractor selected. Gate 4 checklist signed off.

# Chapter 10 — STAGE 5: Construction

OBJECTIVE FOR SOFTWARE CONFIGURATOR:

ALL modules fully active. This is the peak configuration stage. Every workflow, template, dashboard, and integration must be operational.

## 10.1 Active Modules

ALL MODULES ACTIVE

## 10.2 Process Flows to Configure

PF-01 Document Review

PF-02 Correspondence

PF-03 Variation Order

PF-04 Procurement

PF-05 Stage Gate

PF-06 Freeze Exception

PF-07 Authority Submissions

PF-08 IPC Processing

PF-09 Approval Engine

PF-10 Quality Supervision

PF-11 Spatial Coordination Cost

PF-12 Risk Register

PF-13 Contractor Performance

PF-14 Lessons Learned

PF-16 Meeting Action Tracking

PF-17 External Stakeholder Portal

PF-18 Report Generation Export

PF-19 User Role Management

PF-20 ERP Integration

PF-21 Dashboard Analytics

PF-22 Notification Escalation

PF-23 Predictive Analytics

## 10.3 Configuration Tasks (Step-by-Step)

The configurator must complete the following tasks before this stage goes live:

| Task | Details | Reference Doc |
| --- | --- | --- |
| Activate IPC Processing (PF-08) | Monthly IPC cycle: contractor submits → consultant reviews → ER/HAI endorses → payment. Configure per FIDIC Cl. 14 parameters. | PF-08 drawio, GOV-031 |
| Activate Variation Order Module (PF-03) | VO request → assessment → approval → instruction → measurement → payment. Configure approval thresholds per GOV-011. | PF-03 drawio |
| Activate QA/QC Module | ITP, NCR, CAR, inspection request, snag list, calibration register, commissioning | Templates/D-QAQC/ (15 templates) |
| Activate HSE Module | Risk assessment, PTW, toolbox talk, incident report, near miss, COSHH, environmental management | Templates/E-HSE/ (14 templates) |
| Activate Progress Reporting | Daily, weekly, monthly reports. Look-ahead, S-curve, resource histogram, cash flow | Templates/F-Progress/ + Templates/Reports/ |
| Configure Contractor Performance Scoring (PF-13) | KPI categories, weighting, scoring frequency, dashboard display | PF-13 drawio |
| Activate Claims & EOT Module | Claims register, EOT application, notice of delay, dispute notice | Templates/G-Contractual/ |
| Configure Full Notification Engine | All 31 PFs with SLA-based escalation per GOV-033. Five escalation levels. | GOV-014, GOV-033 |
| Activate ERP Integration (PF-20) | Bi-directional sync: IPC data, VO commitments, budget actuals, payment status | PF-20 drawio, GOV-043 |
| Activate Full Dashboard Suite (PF-21) | Executive summary, financial overview, programme status, quality KPIs, HSE statistics | GOV-016 |
| Activate Predictive Analytics (PF-23) | Cost deviation alerts, schedule risk prediction, quality trend analysis | PF-23 drawio |
| Distribute ALL Remaining Templates | Every template in the Starter Pack must be available to users by this stage | HAI-GOV-075 |

## 10.4 Templates to Distribute

ALL 108 templates across all 11 categories must be active:

D-QAQC: QA-D00 through QA-D12 (15 templates)

E-HSE: HSE-E01 through HSE-E14 (14 templates)

F-Progress: PRG-F01 through PRG-F12 (12 templates)

G-Contractual: CON-G00 through CON-G12 (14 templates)

Reports: RPT-F01, RPT-F02, RPT-F04 (Daily, Weekly, Monthly)

## 10.5 Dashboards & Reports to Enable

Executive Dashboard (cost, time, quality, HSE in one view)

Financial Dashboard (IPC status, VO commitment, cash flow, retention)

Programme Dashboard (S-curve, milestones, critical path, look-ahead)

Quality Dashboard (NCR trends, inspection pass rate, ITP compliance)

HSE Dashboard (incident rate, near miss ratio, PTW status, training compliance)

Contractor Performance Scorecard

## 10.6 Integration Points

ERP: Full bi-directional sync (IPC, VO, payments, budget)

DMS: All document types with full lifecycle

Email: All notification types active

SMS: Critical escalation alerts (Level 4-5)

## 10.7 Gate Exit Criteria

Practical completion achieved, punch list generated, TOC application submitted. Gate 5 checklist signed off.

# Chapter 11 — STAGE 6: Handover & Close-Out

OBJECTIVE FOR SOFTWARE CONFIGURATOR:

Handover workflows activated. As-built compilation. O&M manual assembly. Snagging and punch list resolution. TOC issuance.

## 11.1 Active Modules

Handover Management

Snagging

As-Built

O&M

Contract Administration

## 11.2 Process Flows to Configure

PF-15 Handover DLP

PF-28 TOC Management

PF-31 Snag List Resolution

PF-26 Final Account Settlement

## 11.3 Configuration Tasks (Step-by-Step)

The configurator must complete the following tasks before this stage goes live:

| Task | Details | Reference Doc |
| --- | --- | --- |
| Activate Snag List Module (PF-31) | Room-by-room snagging, photo documentation, priority classification, contractor assignment, re-inspection, sign-off | PF-31 drawio |
| Activate TOC Management (PF-28) | Contractor application → joint inspection → punch list → substantial completion assessment → TOC issuance → DLP start | PF-28 drawio |
| Configure As-Built Register | Track as-built drawing submission per discipline, review status, approval | Templates/H-Handover/HOV-H01_As_Built_Register.xlsx |
| Configure O&M Manual Assembly | Template for O&M manual structure, equipment schedules, maintenance procedures, spare parts lists | Templates/H-Handover/ |
| Activate Pre-Commissioning & T&C | Pre-commissioning checklists, testing procedures, commissioning certificates | Templates/H-Handover/HOV-H05_Pre_Commissioning.xlsx |
| Configure Building User Guide | End-user documentation for building systems, emergency procedures, maintenance contacts | Templates/H-Handover/HOV-H10_Building_User_Guide.docx |
| Activate Demobilisation Workflow | Contractor demobilisation plan, site clearance, equipment removal, final clean | Templates/F-Progress/PRG-F01_Mobilisation_Plan.docx |

## 11.4 Templates to Distribute

H-Handover: HOV-H00 through HOV-H11 (11 templates)

D-QAQC: QA-D07_Commissioning_Procedure.xlsx

D-QAQC: QA-D12_Snag_List.xlsx

## 11.5 Dashboards & Reports to Enable

Snag list resolution tracker (open/closed/overdue)

As-built submission progress by discipline

O&M manual assembly progress

TOC readiness checklist

## 11.6 Integration Points

DMS: As-built drawing repository

Facility Management system: O&M data handover

## 11.7 Gate Exit Criteria

TOC issued, snag list <5% open, as-built complete, O&M manuals delivered. Gate 6 checklist signed off.

# Chapter 12 — STAGE 7: In Use (Defects Liability Period)

OBJECTIVE FOR SOFTWARE CONFIGURATOR:

DLP defect tracking active. Retention release workflow. Performance monitoring. Lessons learned capture.

## 12.1 Active Modules

DLP Management

Defect Tracking

Retention Management

Lessons Learned

## 12.2 Process Flows to Configure

PF-15 Handover DLP

PF-30 Performance Certificate

PF-14 Lessons Learned

PF-27 Lessons Learned CI

## 12.3 Configuration Tasks (Step-by-Step)

The configurator must complete the following tasks before this stage goes live:

| Task | Details | Reference Doc |
| --- | --- | --- |
| Activate DLP Defect Tracking | Defect identification → notification to contractor → rectification deadline → re-inspection → sign-off. Track per FIDIC Cl. 11. | PF-15 drawio |
| Configure Retention Release Workflow | First moiety (50%) at TOC → second moiety (50%) at Performance Certificate. Automated reminders. | Templates/G-Contractual/CON-G08_Retention_Release.docx |
| Activate Performance Certificate Module (PF-30) | DLP monitoring → final inspection → all defects rectified → Performance Certificate issuance | PF-30 drawio |
| Activate Lessons Learned Module (PF-14, PF-27) | Monthly capture sessions, workshop facilitation, root cause analysis, knowledge base update | PF-14 drawio, PF-27 drawio |
| Configure Warranty Tracking | Equipment warranties, expiry alerts, contractor obligations during DLP | Templates/H-Handover/HOV-H11_Defects_Tracker.xlsx |

## 12.4 Templates to Distribute

H-Handover: HOV-H11_Defects_Tracker.xlsx

G-Contractual: CON-G08_Retention_Release.docx

## 12.5 Dashboards & Reports to Enable

DLP defect tracker (open/rectified/overdue)

Retention release schedule

Performance Certificate readiness

Lessons learned knowledge base

## 12.6 Integration Points

ERP: Retention release payment trigger

FM system: Defect reporting interface

## 12.7 Gate Exit Criteria

All defects rectified, Performance Certificate issued, second retention released. Gate 7 checklist signed off.

# Chapter 13 — STAGE 8: Post-Completion

OBJECTIVE FOR SOFTWARE CONFIGURATOR:

Final account settlement. Final Payment Certificate. Contract closure. Full project archival. Lessons learned report finalised.

## 13.1 Active Modules

Final Account

Contract Closure

Archive Management

## 13.2 Process Flows to Configure

PF-26 Final Account Settlement

PF-29 Final Payment Certificate

PF-27 Lessons Learned CI

PF-24 Post Go Live Support

## 13.3 Configuration Tasks (Step-by-Step)

The configurator must complete the following tasks before this stage goes live:

| Task | Details | Reference Doc |
| --- | --- | --- |
| Activate Final Account Module (PF-26) | Final account draft → supporting documentation → consultant review → ER/HAI endorsement → settlement letter → final payment | PF-26 drawio |
| Activate Final Payment Certificate (PF-29) | Final statement → discharge statement → engineer verification → FPC issuance → final payment → bank guarantee return | PF-29 drawio |
| Configure Project Archival | Full document compilation → digital repository → access permissions → retention policy | PF-26 drawio |
| Finalise Lessons Learned Report | Compile all lessons captured during project → categorise → create best practice library → distribute to future projects | PF-27 drawio |
| Contract Closure Workflow | Close-out letter → all bonds returned → all insurances released → final audit → project deactivated in system | Templates/G-Contractual/ |

## 13.4 Templates to Distribute

G-Contractual: CON-G12_Final_Account.xlsx

G-Contractual: CON-G00_Claims_Register.xlsx (final reconciliation)

## 13.5 Dashboards & Reports to Enable

Final account reconciliation

Contract closure checklist

Project archive status

Lessons learned summary report

## 13.6 Integration Points

ERP: Final payment, bond release, insurance release

Archive: Full digital repository closure

## 13.7 Gate Exit Criteria

Final Payment Certificate issued, all bonds returned, project archived, lessons learned published. Gate 8 checklist signed off. PROJECT COMPLETE.

# Chapter 14 — Process Flow Catalog (All 31 PFs)

Each process flow has a dedicated .drawio file for visual reference and a corresponding action sheet in HAI-GOV-021. Below is the complete catalog with the stages where each PF is active.

| PF # | Process Flow Name | GOV Ref | Active Stages | Module |
| --- | --- | --- | --- | --- |
| PF-01 | Document Review | HAI-GOV-051 | 1-8 | Document Management |
| PF-02 | Correspondence | HAI-GOV-052 | 1-8 | Document Management |
| PF-03 | Variation Order | HAI-GOV-053 | 5-8 | Financial Control |
| PF-04 | Procurement | HAI-GOV-054 | 4-5 | Procurement |
| PF-05 | Stage Gate | HAI-GOV-055 | 0-8 | Governance Control |
| PF-06 | Freeze Exception | HAI-GOV-056 | 3-5 | Governance Control |
| PF-07 | Authority Submissions | HAI-GOV-057 | 4-5 | Authority & Compliance |
| PF-08 | IPC Processing | HAI-GOV-058 | 5-8 | Financial Control |
| PF-09 | Approval Engine | HAI-GOV-059 | 1-8 | Governance Control |
| PF-10 | Quality Supervision | HAI-GOV-060 | 5-6 | Quality & Site |
| PF-11 | Spatial Coordination Cost | HAI-GOV-061 | 3-8 | Financial Control |
| PF-12 | Risk Register | HAI-GOV-062 | 2-8 | Governance Control |
| PF-13 | Contractor Performance | HAI-GOV-063 | 5-6 | KPI & Analytics |
| PF-14 | Lessons Learned | HAI-GOV-064 | 5-8 | KPI & Analytics |
| PF-15 | Handover DLP | HAI-GOV-065 | 6-7 | Handover & DLP |
| PF-16 | Meeting Action Tracking | HAI-GOV-066 | 2-8 | Governance Control |
| PF-17 | External Stakeholder Portal | HAI-GOV-067 | 5-6 | Integration & Access |
| PF-18 | Report Generation Export | HAI-GOV-068 | 5-8 | KPI & Analytics |
| PF-19 | User Role Management | HAI-GOV-069 | 0-8 | Integration & Access |
| PF-20 | ERP Integration | HAI-GOV-070 | 5-8 | Integration & Access |
| PF-21 | Dashboard Analytics | HAI-GOV-071 | 5-8 | KPI & Analytics |
| PF-22 | Notification Escalation | HAI-GOV-072 | 5-8 | Governance Control |
| PF-23 | Predictive Analytics | HAI-GOV-073 | 5-8 | KPI & Analytics |
| PF-24 | Post Go Live Support | HAI-GOV-076 | 8 | Manufacturing & Construction |
| PF-25 | Consultant Mobilisation | HAI-GOV-077 | 1 | Consultancy |
| PF-26 | Final Account Settlement | HAI-GOV-078 | 8 | Financial Control |
| PF-27 | Lessons Learned CI | HAI-GOV-079 | 7-8 | KPI & Analytics |
| PF-28 | TOC Management | HAI-GOV-080 | 6 | Contract Administration |
| PF-29 | Final Payment Certificate | HAI-GOV-081 | 8 | Financial Control |
| PF-30 | Performance Certificate | HAI-GOV-082 | 7 | Contract Administration |
| PF-31 | Snag List Resolution | HAI-GOV-083 | 6 | Quality & Site |

# Chapter 15 — User Roles & Permissions Matrix

Reference: HAI-GOV-012-R0.0_User_Roles_Permissions.xlsx

The configurator must create 17 role types in the system. Each role has specific access rights per module.

| Role | Responsibility | Module Access | Active Stages |
| --- | --- | --- | --- |
| System Administrator | Full system access, user management, configuration | All | 0-8 |
| Project Director | Project oversight, gate approval, escalation final authority | All (read) + Governance (write) | 0-8 |
| ER / HAI Representative | Endorsement authority, final sign-off on submittals | All (read) + Endorsement (write) | 1-8 |
| Lead Consultant | Technical review, approval authority, response code assignment | Document, Quality, Technical Design (write) | 1-8 |
| Technical Design Manager | Technical Design submittal management, drawing control | Document, Technical Design (write) | 1-5 |
| Project Manager (Contractor) | Programme, cost, resource management | Progress, Financial (write) | 5-8 |
| Site Engineer | Daily reporting, quality inspection, material verification | Quality, HSE, Progress (write) | 5-6 |
| QA/QC Manager | ITP management, NCR processing, commissioning | Quality (write) | 5-6 |
| HSE Manager | Risk assessment, PTW, incident management | HSE (write) | 5-6 |
| Cost / QS | IPC preparation, VO assessment, claims processing | Financial (write) | 5-8 |
| Planning Engineer | Programme updates, delay analysis, look-ahead | Progress (write) | 5-8 |
| Document Controller | Transmittal, numbering, distribution, archival | Document (write) | 1-8 |
| Contracts Manager | EOT, claims, disputes, bonds, insurance | Contractual (write) | 5-8 |
| Commissioning Manager | T&C procedures, pre-commissioning, handover | Handover (write) | 6 |
| Facility Manager | O&M, defect reporting during DLP | Handover, DLP (write) | 7-8 |
| Internal Auditor | Read-only access to all modules for compliance review | All (read only) | 0-8 |
| External Stakeholder | Limited portal access for authority submissions | Portal (read/submit) | 4-5 |

# Chapter 16 — Escalation Framework (5-Level Model)

Reference: HAI-GOV-033-R0.0_Escalation_Action_Procedures.xlsx

| Level | Trigger | Escalated To | Response SLA | Notification |
| --- | --- | --- | --- | --- |
| L1 — Reminder | SLA at 75% | Assigned User | 24 hours | In-app + Email |
| L2 — Warning | SLA at 100% | Line Manager | 24 hours | In-app + Email |
| L3 — Escalation | SLA + 48 hours | Department Head | 12 hours | In-app + Email + SMS |
| L4 — Executive | SLA + 5 days | Project Director | 4 hours | In-app + Email + SMS + Phone |
| L5 — Critical | SLA + 10 days | CEO / Board | Immediate | All channels + Meeting request |

# Chapter 17 — Reporting & Dashboard Configuration

Reference: HAI-GOV-016-R0.0_Dashboard_Reporting_Specs.xlsx

| Report | Frequency | Template | Active Stages | Distribution |
| --- | --- | --- | --- | --- |
| Daily Site Report | Daily | RPT-F01_Daily_Site_Report.xlsx | 5-6 | Contractor → Consultant → ER/HAI |
| Weekly Progress Report | Weekly | RPT-F02_Weekly_Report.xlsx | 5-6 | Contractor → Consultant → ER/HAI |
| Monthly Progress Report | Monthly | RPT-F04_Monthly_Report.xlsx | 5-8 | All stakeholders |
| IPC Summary | Monthly | System-generated | 5-8 | ER/HAI + Finance |
| HSE Statistics | Monthly | HSE-E11_Statistics.xlsx | 5-6 | All stakeholders |
| Contractor Scorecard | Quarterly | System-generated | 5-6 | ER/HAI + Client |
| Executive Summary | Quarterly | System-generated | 0-8 | Board / CEO |

# Chapter 18 — Testing & Go-Live Checklist

Reference: HAI-GOV-041-R0.0_UAT_Test_Plan.xlsx

## 18.1 UAT Requirements

| Test Category | Coverage | Pass Criteria |
| --- | --- | --- |
| Workflow Tests | All 31 PFs — happy path + exception paths | 100% pass rate |
| Role-Based Access | All 17 roles — verify permissions per GOV-012 | 100% pass rate |
| Notification Tests | All SLA triggers — verify email, in-app, SMS delivery | 95%+ delivery rate |
| Integration Tests | ERP sync — IPC, VO, payment, budget data | Zero data loss |
| Performance Tests | Concurrent users, response time, document upload | <3 sec response, 50+ concurrent |
| Regression Tests | After each configuration change | No existing functionality broken |

## 18.2 Go-Live Checklist

All 31 PFs configured and tested

All 108 templates loaded and accessible

All 17 roles created with correct permissions

All contract parameters loaded per project

Notification engine tested end-to-end

ERP integration verified with live data

Dashboard suite functional with real data

Training delivered to all user groups

Data migration completed and verified

Backup and recovery procedures tested

Support procedures documented (PF-24)

Go-live sign-off from ER/HAI and Project Director

# Appendix A — Document Cross-Reference Index

| GOV Ref | Document Title | Format | Description |
| --- | --- | --- | --- |
| HAI-GOV-000 | Document Register | XLSX | Master index of all 175 deliverables |
| HAI-GOV-001 | Manufacturing & Construction Guidebook (This Document) | DOCX | A-to-Z configurator manual, Stage 0-8 |
| HAI-GOV-002 | Manufacturing & Construction WBS & Schedule | XLSX | 55 tasks, 6 phases, 16 weeks, resource-loaded |
| HAI-GOV-003 | Process Flow Register | XLSX | All 31 PFs with SOW traceability, dependencies |
| HAI-GOV-004 | Cross-Link Index | XLSX | Document and PF dependency mapping |
| HAI-GOV-005 | Stage-Based Organisation | XLSX | Stage-PF matrix — which PFs at which stage |
| HAI-GOV-006 | Project Mind Map | HTML | Interactive map linking all 175 files by Stage 0-8 |
| HAI-GOV-007 R0.0 | Manufacturing & Construction Roadmap | DOCX | Detailed roadmap for software configurator |
| HAI-GOV-007 R1.0 | CEO Presentation | PPTX | 18-slide executive deck |
| HAI-GOV-008 | SkyStruct SOW | DOCX | Full scope of work for platform implementation |
| HAI-GOV-011 | System Configuration | XLSX | Contract parameters, system settings |
| HAI-GOV-012 | User Roles & Permissions | XLSX | 17 roles, access matrix, delegation rules |
| HAI-GOV-013 | Workflow Engine Rules | XLSX | All workflow configurations per PF |
| HAI-GOV-014 | Notification & Alert Rules | XLSX | Email, SMS, in-app notification triggers |
| HAI-GOV-015 | Form & Template Specifications | XLSX | Template design specs for all 108 templates |
| HAI-GOV-016 | Dashboard & Reporting Specs | XLSX | Dashboard layout, KPI definitions, report formats |
| HAI-GOV-021 | PF Action Sheets | XLSX | Step-by-step actions for all 31 PFs |
| HAI-GOV-022 | L1 Process Flow Narratives | DOCX | Descriptive narratives for each PF |
| HAI-GOV-023 | L2 UI Wireframe Specs | DOCX | Screen-by-screen UI specifications |
| HAI-GOV-024 | L3 Data Model | XLSX | Entity-relationship model, field specifications |
| HAI-GOV-025 | L4 Acceptance Checklists | XLSX | UAT acceptance criteria per module |
| HAI-GOV-031 | FIDIC Response Action Cards | XLSX | Clause-by-clause response procedures |
| HAI-GOV-032 | Contract Duration Matrix | XLSX | All contractual time periods mapped |
| HAI-GOV-033 | Escalation Action Procedures | XLSX | 5-level escalation model |
| HAI-GOV-034 | Gate Passage Checklists | XLSX | Gate criteria for all 9 stages |
| HAI-GOV-035 | Document Numbering System | XLSX | Numbering convention and rules |
| HAI-GOV-036 | Communication Plan | XLSX | Communication matrix and schedule |
| HAI-GOV-037 | Communication Management Plan | DOCX | Full communication strategy |
| HAI-GOV-041 | UAT Test Plan | XLSX | 150+ test cases across all modules |
| HAI-GOV-042 | Migration Specification | XLSX | Data migration mapping and rules |
| HAI-GOV-043 | Integration Specification | XLSX | ERP and external system integration specs |
| HAI-GOV-074 | Master Submittal Hierarchy | DOCX | 113 submittal types across 9 categories |
| HAI-GOV-075 | Templates Starter Pack | Folder | 108 templates in 11 sub-folders |

# Appendix B — Template Starter Pack Index (108 Templates)

All templates are in the HAI Templates Starter Pack folder (HAI-GOV-075). Organised by submittal category.

## A-Design (Active Stages: 1-5)

DES-A00_Technical Design_Submittal_Cover.docx

## B-Material (Active Stages: 3-5)

MAT-B00_Material_Submittal_Cover.docx

MAT-B06_Mock_Up.xlsx

MAT-B07_Colour_Finish_Schedule.xlsx

MAT-B08_Equipment_Data_Sheet.xlsx

MAT-B11_Concrete_Mix_Technical Design.xlsx

## C-Method Statements (Active Stages: 3-5)

MS-C01 through MS-C14 (14 method statements)

Excavation, Piling, Concrete, Steel, Waterproofing, MEP, Facade, Road, Demolition, Temp Works, Lifting, Hot Works, Hot Weather Concreting, Traffic Management

## D-QAQC (Active Stages: 5-6)

QA-D00 through QA-D12 (15 templates)

NCR, ITP, Material Inspection, Concrete Test, Welding, Pressure Test, Commissioning, CAR, Calibration, Survey, TPI, Snag List, Inspection Request, WPS

## E-HSE (Active Stages: 5-6)

HSE-E01 through HSE-E14 (14 templates)

HSE Plan, Risk Assessment, PTW, Toolbox Talk, Incident, Near Miss, Emergency Response, Environmental, Waste, Noise/Dust, Statistics, COSHH, Hazardous Material, Training

## F-Progress (Active Stages: 5-6)

PRG-F01 through PRG-F12 (12 templates)

Mobilisation, Recovery, Resource Histogram, Cash Flow, Look-Ahead, S-Curve, Procurement Schedule, Delay Analysis, Milestone, Weather, Manpower

## G-Contractual (Active Stages: 5-8)

CON-G00 through CON-G12 (14 templates)

Claims, Variations, Payment, Variation Proposal, Claim Submission, EOT, Bond, Notice of Delay, Insurance, Retention, Subcontractor, Daywork, Contractual Notice, Dispute, Final Account

## H-Handover (Active Stages: 6-7)

HOV-H00 through HOV-H11 (11 templates)

Handover Cover, As-Built Register, O&M Manual, Demobilisation, Spare Parts, Pre-Commissioning, T&C, Training Record, Building User Guide, Defects Tracker

## J-Specialist (Active Stages: 4-5)

REG-J00 through REG-J07 (7 templates)

Regulatory Cover, Civil Defence, Ashghal NOC, Municipality, Kahramaa, GSAS

## General (Active Stages: 1-8)

12 templates: MOM, Transmittal Letter, RFI, Site Instruction, Submittal Register, Document Transmittal Log, RFI Register, SI Register, Action Tracker, Correspondence Log, Drawing Register, Photo Log, Site Diary

## Reports (Active Stages: 5-8)

RPT-F01 Daily Site Report, RPT-F02 Weekly Report, RPT-F04 Monthly Report

# Appendix C — Glossary & Contact

## Glossary

| Abbreviation | Definition |
| --- | --- |
| BOQ | Bill of Quantities — priced schedule of work items |
| CAR | Corrective Action Request — issued when NCR root cause requires systemic fix |
| DAB | Dispute Adjudication Board — per FIDIC Cl. 20.4 |
| DLP | Defects Liability Period — per FIDIC Cl. 11 |
| EOT | Extension of Time — per FIDIC Cl. 8.4 |
| ER | Employer Representative — HAI acting on behalf of ARADA |
| FIDIC | Federation Internationale des Ingenieurs-Conseils — 1999 Red Book |
| GSAS | Global Sustainability Assessment System — Qatar green building standard |
| HAI | House of Architecture & Interiors — the Employer Representative entity |
| IPC | Interim Payment Certificate — per FIDIC Cl. 14.6 |
| ITP | Inspection and Test Plan — quality control schedule |
| NCR | Non-Conformance Report — quality deficiency record |
| PF | Process Flow — one of 31 configured workflows in SkyStruct |
| PTW | Permit to Work — HSE authorization for hazardous activities |
| QCS | Qatar Construction Specifications 2014 (Ashghal) |
| RFI | Request for Information — design clarification request |
| SI | Site Instruction — formal instruction to contractor |
| SLA | Service Level Agreement — response time obligation |
| SSP | SkyStruct Platform — the governance software platform |
| TOC | Taking Over Certificate — per FIDIC Cl. 10.1 |
| VO | Variation Order — per FIDIC Cl. 13 |
| WPS | Welding Procedure Specification |

## Contact & Governance

| Field | Value |
| --- | --- |
| Name | Hasan Mollamahmutoglu |
| Title | Chief Governance Architect / Employer Representative |
| Organisation | HAI — House of Architecture & Interiors / ARADA Governance |
| Authority | Full authority over platform specification, configuration standards, and governance framework |
| Accountability | Responsible for alignment of all 175 deliverables across Stage 0-8 |