## Module Permissions
HAI GROUP — SkyStruct ERP: Module Permissions Matrix
KEY: F = Full Access ¦ V = View Only ¦ E = Edit (originator only) ¦ A = Approve (when addressed) ¦ N = No Access ¦ R = Restricted
# | Module | Ref. Standard | Sub-Page / Tab | Action | C-Level (Board) | D-Level (Employer's Rep) | M-Level (Employer's Rep) | Consultant PM & DC | Consultant Officers | Contractor PM & DC | Contractor Officers | Stage
1 DASHBOARDS
1.1 | Programme Dashboard | RICS PM / RIBA 0-7 | Programme Overview | View | V | F | V | V | V | V | R | All stages
|  |  |  | Export | V | F | V | V | N | N | N | All stages
|  |  | ER Dashboard | View | V | F | V | V | R | N | N | All stages
|  |  |  | Export | V | F | V | V | N | N | N | All stages
|  |  | Cost Dashboard | View | V | F | V | V | R | R | N | Design → In-Use
|  |  |  | Export | V | F | V | R | N | N | N | Design → In-Use
|  |  | Quality Dashboard | View | V | F | V | V | V | V | R | Deliver → Handover
|  |  |  | Export | V | F | V | V | V | N | N | Deliver → Handover
|  |  | Contractor Portal | View | V | F | V | R | N | V | V | Deliver → Handover
|  |  |  | Export | V | F | V | N | N | V | N | Deliver → Handover
|  |  | Consultant Portal | View | V | F | V | V | V | N | N | Design → Handover
|  |  |  | Export | V | F | V | V | V | N | N | Design → Handover
|  |  | Governance Dashboard | View | V | F | V | V | R | R | N | All stages
|  |  |  | Export | V | F | V | R | N | N | N | All stages
1.2 | Analytics & AI | RICS PM / RIBA 0-7 | KPI Dashboard | View | V | F | V | V | R | R | N | All stages
|  |  |  | Export | V | F | V | V | N | N | N | All stages
|  |  | Predictive Analytics | View | V | F | V | R | N | N | N | Deliver → In-Use
|  |  | Risk Intelligence | View | V | F | V | V | R | R | N | Deliver → In-Use
|  |  | Custom Reports | View | V | F | V | V | R | R | N | All stages
|  |  |  | Create | N | F | F | E | N | N | N | All stages
|  |  |  | Export | V | F | V | V | N | N | N | All stages
1.3 | Notifications & Alerts | RIBA 0-7 | Notification Centre | View | V | F | V | V | V | V | V | All stages
|  |  | Alert Rules | View | V | F | V | R | N | N | N | All stages
|  |  |  | Create | N | F | F | N | N | N | N | All stages
|  |  |  | Edit | N | F | F | N | N | N | N | All stages
|  |  | Escalation Matrix | View | V | F | V | V | R | R | N | All stages
|  |  |  | Edit | N | F | F | N | N | N | N | All stages
1.4 | Directory | RIBA 0-7 | Team Directory | View | V | F | V | V | V | V | V | All stages
|  |  |  | Edit | N | F | F | N | N | N | N | All stages
|  |  | Organizations | View | V | F | V | V | V | V | V | All stages
|  |  |  | Edit | N | F | F | N | N | N | N | All stages
1.5 | Flowcharts & Workflows | RIBA 0-7 | Process Flows | View | V | F | V | V | V | V | R | All stages
|  |  |  | Create | N | F | F | E | N | N | N | All stages
|  |  |  | Edit | N | F | F | E | N | N | N | All stages
|  |  | Workflow Templates | View | V | F | V | V | R | R | N | All stages
|  |  |  | Create | N | F | F | N | N | N | N | All stages
|  |  |  | Edit | N | F | F | N | N | N | N | All stages
1.6 | Admin & Settings | System | User Management | View | V | F | V | N | N | N | N | All stages
|  |  |  | Create | N | F | V | N | N | N | N | All stages
|  |  |  | Edit | N | F | N | N | N | N | N | All stages
|  |  |  | Delete | N | F | N | N | N | N | N | All stages
|  |  | Roles & Permissions | View | V | F | V | N | N | N | N | All stages
|  |  |  | Edit | N | F | N | N | N | N | N | All stages
|  |  | System Configuration | View | V | F | R | N | N | N | N | All stages
|  |  |  | Edit | N | F | N | N | N | N | N | All stages
|  |  | Audit Log | View | V | F | V | R | N | N | N | All stages
|  |  | Notification Settings | View | V | F | V | V | V | V | V | All stages
|  |  |  | Edit | N | F | E | E | E | E | E | All stages
2 EXECUTION
2.1 | Correspondence & Transmittals | FIDIC / RICS | Inbox | View | V | F | V | V | V | V | V | All stages
|  |  |  | Reply | V | F | E | E | E | E | E | All stages
|  |  |  | Forward | V | F | E | E | N | E | N | All stages
|  |  | Sent | View | V | F | V | V | V | V | V | All stages
|  |  | Drafts | Create | N | F | E | E | E | E | E | All stages
|  |  |  | Edit | N | F | E | E | E | E | E | All stages
|  |  |  | Delete | N | F | E | N | N | N | N | All stages
|  |  | Transmittals | Create | N | F | E | E | E | E | N | All stages
|  |  |  | View | V | F | V | V | V | V | V | All stages
|  |  |  | Edit | N | F | E | E | N | E | N | All stages
|  |  |  | Approve | A | F | V | N | N | N | N | All stages
|  |  | Correspondence Log | View | V | F | V | V | V | V | V | All stages
|  |  |  | Export | V | F | V | V | N | V | N | All stages
2.2 | Document Management | QCS §1.6 / RIBA 0-7 | All Documents | View | V | F | V | V | V | V | V | All stages
|  |  |  | Upload | N | F | E | E | E | E | E | All stages
|  |  |  | Download | V | F | V | V | V | V | V | All stages
|  |  |  | Delete | N | F | N | N | N | N | N | All stages
|  |  | Drawings | View | V | F | V | V | V | V | V | Design → Handover
|  |  |  | Upload | N | F | V | E | E | E | E | Design → Handover
|  |  |  | Approve | V | F | V | V | N | N | N | Design → Handover
|  |  | Specifications | View | V | F | V | V | V | V | V | Design → Procure
|  |  |  | Upload | N | F | V | E | E | N | N | Design → Procure
|  |  |  | Approve | V | F | V | V | N | N | N | Design → Procure
|  |  | Reports | View | V | F | V | V | V | V | R | All stages
|  |  |  | Upload | N | F | E | E | E | E | N | All stages
|  |  | Method Statements | View | V | F | V | V | V | V | V | Deliver
|  |  |  | Upload | N | F | V | V | V | F | E | Deliver
|  |  |  | Approve | V | F | V | V | N | N | N | Deliver
|  |  | As-Built Drawings | View | V | F | V | V | V | V | V | Deliver → Handover
|  |  |  | Upload | N | F | V | V | V | F | E | Deliver → Handover
|  |  |  | Approve | V | F | V | N | N | N | N | Handover
2.3 | Drawing Register | RIBA 2-6 / QCS §1.6 | Drawing Register | View | V | F | V | V | V | V | V | Design → Handover
|  |  |  | Upload | N | F | V | E | E | E | E | Design → Handover
|  |  |  | Edit | N | F | V | E | E | N | N | Design → Handover
|  |  |  | Approve | V | F | V | V | N | N | N | Design → Handover
|  |  | Revisions | View | V | F | V | V | V | V | V | Design → Handover
|  |  |  | Upload | N | F | V | E | E | E | E | Design → Handover
2.4 | RFIs | FIDIC / RIBA 2-6 | RFI Register | View | V | F | V | V | V | V | V | Design → Handover
|  |  |  | Create | N | F | E | E | E | E | E | Design → Handover
|  |  |  | Edit | N | F | E | E | E | E | E | Design → Handover
|  |  | RFI Responses | View | V | F | V | V | V | V | V | Design → Handover
|  |  |  | Respond | N | F | V | E | E | N | N | Design → Handover
|  |  |  | Approve | V | F | V | N | N | N | N | Design → Handover
2.5 | Design Management | RIBA 2-4 / QCS §2 | Design Brief | View | V | F | V | V | V | R | N | Define → Design
|  |  |  | Create | N | F | E | E | N | N | N | Define
|  |  |  | Approve | V | F | V | N | N | N | N | Define
|  |  | Design Gateway Reviews | View | V | F | V | V | V | V | R | Design → Procure
|  |  |  | Create | N | F | V | E | N | N | N | Design → Procure
|  |  |  | Approve | V | F | V | V | N | N | N | Design → Procure
|  |  | Design Freeze Log | View | V | F | V | V | V | V | R | Design → Procure
|  |  |  | Create | N | F | E | E | N | N | N | Design → Procure
|  |  |  | Approve | V | F | V | N | N | N | N | Design → Procure
|  |  | Value Engineering | View | V | F | V | V | V | V | R | Design → Deliver
|  |  |  | Create | N | F | E | E | E | E | N | Design → Deliver
|  |  |  | Approve | V | F | V | N | N | N | N | Design → Deliver
2.6 | BIM / Models | RIBA 2-5 / ISO 19650 | Model Viewer | View | V | F | V | V | V | V | V | Design → Handover
|  |  | Clash Reports | View | V | F | V | V | V | V | V | Design → Deliver
|  |  |  | Create | N | F | V | E | E | N | N | Design → Deliver
|  |  | Federated Model | View | V | F | V | V | V | V | R | Design → Handover
|  |  |  | Upload | N | F | V | E | E | N | N | Design → Handover
|  |  | BIM Execution Plan | View | V | F | V | V | V | V | R | Define → Design
|  |  |  | Create | N | F | E | E | N | N | N | Define
|  |  |  | Approve | V | F | V | N | N | N | N | Define
2.7 | Submittals | QCS §1.4 / FIDIC | Material Submittals | View | V | F | V | V | V | V | V | Deliver
|  |  |  | Create | N | F | V | V | V | F | E | Deliver
|  |  |  | Edit | N | F | V | V | V | E | E | Deliver
|  |  | Shop Drawing Submittals | View | V | F | V | V | V | V | V | Deliver
|  |  |  | Create | N | F | V | V | V | F | E | Deliver
|  |  |  | Edit | N | F | V | V | V | E | E | Deliver
|  |  | Review Queue | View | V | F | V | V | V | V | V | Deliver
|  |  |  | Approve | V | F | V | A | N | N | N | Deliver
|  |  |  | Reject | V | F | V | A | N | N | N | Deliver
|  |  | Submittal Status Register | View | V | F | V | V | V | V | V | Deliver
|  |  |  | Export | V | F | V | V | V | V | N | Deliver
2.8 | Change Management | FIDIC cl.13 / RIBA | Site Instructions (SI) | View | V | F | V | V | V | V | V | Deliver
|  |  |  | Create | N | F | E | V | N | N | N | Deliver
|  |  |  | Approve | V | F | V | N | N | N | N | Deliver
|  |  | Architect Instructions (AI) | View | V | F | V | V | V | V | V | Design → Deliver
|  |  |  | Create | N | F | V | E | E | N | N | Design → Deliver
|  |  |  | Approve | V | F | V | N | N | N | N | Design → Deliver
|  |  | Change Order Log | View | V | F | V | V | R | V | R | Deliver → In-Use
|  |  |  | Create | N | F | E | E | N | E | N | Deliver → In-Use
|  |  |  | Approve | V | F | V | N | N | N | N | Deliver → In-Use
|  |  | EOT Applications | View | V | F | V | V | R | V | R | Deliver → In-Use
|  |  |  | Create | N | F | V | N | N | F | N | Deliver → In-Use
|  |  |  | Approve | V | F | V | N | N | N | N | Deliver → In-Use
|  |  | Notice of Delay | View | V | F | V | V | R | V | R | Deliver → In-Use
|  |  |  | Create | N | F | V | N | N | F | N | Deliver → In-Use
2.9 | Risk Management | RICS PM / ISO 31000 | Risk Register | View | V | F | V | V | V | V | R | All stages
|  |  |  | Create | N | F | E | E | E | E | N | All stages
|  |  |  | Edit | N | F | E | E | E | E | N | All stages
|  |  | Risk Matrix / Heat Map | View | V | F | V | V | V | V | R | All stages
|  |  | Mitigation Tracking | View | V | F | V | V | V | V | R | All stages
|  |  |  | Edit | N | F | E | E | E | E | N | All stages
2.10 | Schedule & Programme | RICS PM / FIDIC | Master Programme / Gantt | View | V | F | V | V | V | V | V | Define → In-Use
|  |  |  | Edit | N | F | E | V | N | V | N | Define → In-Use
|  |  | Milestones | View | V | F | V | V | V | V | V | Define → In-Use
|  |  |  | Edit | N | F | E | V | N | V | N | Define → In-Use
|  |  | Baseline Programme | View | V | F | V | V | R | V | R | Define → In-Use
|  |  |  | Edit | N | F | E | N | N | N | N | Define
|  |  |  | Approve | V | F | V | N | N | N | N | Define
|  |  | Progress Update | View | V | F | V | V | V | V | V | Deliver → Handover
|  |  |  | Edit | N | F | V | V | V | F | E | Deliver → Handover
|  |  | Delay Analysis | View | V | F | V | V | R | V | R | Deliver → In-Use
|  |  |  | Create | N | F | E | E | N | E | N | Deliver → In-Use
|  |  | Look-Ahead Programme | View | V | F | V | V | V | V | V | Deliver
|  |  |  | Create | N | F | V | N | N | F | E | Deliver
|  |  | S-Curve | View | V | F | V | V | V | V | R | Deliver → In-Use
|  |  |  | Export | V | F | V | V | N | V | N | Deliver → In-Use
|  |  | Resource Histogram | View | V | F | V | V | R | V | R | Deliver
|  |  |  | Edit | N | F | V | N | N | F | E | Deliver
|  |  | Cash Flow Forecast | View | V | F | V | V | R | R | N | Design → In-Use
|  |  |  | Edit | N | F | E | E | N | N | N | Design → In-Use
|  |  | Procurement Schedule | View | V | F | V | V | R | V | R | Procure → Deliver
|  |  |  | Edit | N | F | E | E | N | E | N | Procure → Deliver
2.11 | Quality Management | QCS §1.4 / ISO 9001 | Inspections | View | V | F | V | V | V | V | V | Deliver → Handover
|  |  |  | Create | N | F | E | E | E | F | E | Deliver → Handover
|  |  |  | Edit | N | F | V | V | V | E | E | Deliver → Handover
|  |  | NCR Register | View | V | F | V | V | V | V | V | Deliver → Handover
|  |  |  | Create | N | F | E | E | E | V | N | Deliver → Handover
|  |  |  | Edit | N | F | E | E | E | V | N | Deliver → Handover
|  |  |  | Close | N | F | V | V | N | N | N | Deliver → Handover
|  |  | ITP Management | View | V | F | V | V | V | V | V | Deliver
|  |  |  | Create | N | F | V | V | V | F | E | Deliver
|  |  |  | Approve | V | F | V | A | N | N | N | Deliver
|  |  | Inspection Requests (IR) | View | V | F | V | V | V | V | V | Deliver
|  |  |  | Create | N | F | V | V | V | F | E | Deliver
|  |  |  | Approve | V | F | V | A | N | N | N | Deliver
|  |  | Material Inspection | View | V | F | V | V | V | V | V | Deliver
|  |  |  | Create | N | F | V | V | V | F | E | Deliver
|  |  |  | Approve | V | F | V | A | N | N | N | Deliver
|  |  | Concrete Testing | View | V | F | V | V | V | V | V | Deliver
|  |  |  | Create | N | F | V | V | V | F | E | Deliver
|  |  | Welding Inspection | View | V | F | V | V | V | V | V | Deliver
|  |  |  | Create | N | F | V | V | V | F | E | Deliver
|  |  | Pressure Testing | View | V | F | V | V | V | V | V | Deliver → Handover
|  |  |  | Create | N | F | V | V | V | F | E | Deliver → Handover
|  |  | TPI Register | View | V | F | V | V | V | V | R | Deliver
|  |  |  | Create | N | F | E | E | N | N | N | Deliver
|  |  | Audit Reports | View | V | F | V | V | V | R | R | Deliver → In-Use
|  |  |  | Create | N | F | E | E | E | N | N | Deliver → In-Use
|  |  | Calibration Register | View | V | F | V | V | V | V | R | Deliver → Handover
|  |  |  | Edit | N | F | V | N | N | F | E | Deliver → Handover
2.12 | HSE Management | QCS §1.5 / ISO 45001/14001 | Incidents | View | V | F | V | V | V | V | V | Deliver → In-Use
|  |  |  | Create | N | F | E | E | E | F | E | Deliver → In-Use
|  |  |  | Edit | N | F | E | V | V | E | E | Deliver → In-Use
|  |  | Permits to Work | View | V | F | V | V | V | V | V | Deliver
|  |  |  | Create | N | F | V | V | N | F | E | Deliver
|  |  |  | Approve | V | F | V | V | N | N | N | Deliver
|  |  | Toolbox Talks | View | V | F | V | V | V | V | V | Deliver
|  |  |  | Create | N | F | V | V | V | F | E | Deliver
|  |  | Risk Assessments (RAMS) | View | V | F | V | V | V | V | V | Deliver
|  |  |  | Create | N | F | V | V | V | F | E | Deliver
|  |  |  | Approve | V | F | V | V | N | N | N | Deliver
|  |  | COSHH Assessments | View | V | F | V | V | V | V | V | Deliver
|  |  |  | Create | N | F | V | N | N | F | E | Deliver
|  |  | Near Miss Reports | View | V | F | V | V | V | V | V | Deliver
|  |  |  | Create | N | F | E | E | E | F | E | Deliver
|  |  | Environmental Monitoring | View | V | F | V | V | V | V | R | Deliver → In-Use
|  |  |  | Create | N | F | V | V | N | F | E | Deliver → In-Use
|  |  | Safety Statistics | View | V | F | V | V | V | V | R | Deliver → In-Use
|  |  |  | Export | V | F | V | V | N | N | N | Deliver → In-Use
|  |  | HSE Training Records | View | V | F | V | V | V | V | V | Deliver
|  |  |  | Create | N | F | V | N | N | F | E | Deliver
2.13 | Observations | RIBA 5-6 | All Observations | View | V | F | V | V | V | V | V | Deliver → Handover
|  |  |  | Create | N | F | E | E | E | E | E | Deliver → Handover
|  |  |  | Edit | N | F | E | E | E | E | E | Deliver → Handover
|  |  | My Observations | View | V | F | V | V | V | V | V | Deliver → Handover
|  |  |  | Create | N | F | E | E | E | E | E | Deliver → Handover
|  |  |  | Edit | N | F | E | E | E | E | E | Deliver → Handover
2.14 | Punch List / Snagging | RIBA 5-6 / RICS | Open Items | View | V | F | V | V | V | V | V | Deliver → Handover
|  |  |  | Create | N | F | E | E | E | V | N | Deliver → Handover
|  |  |  | Edit | N | F | E | E | E | V | N | Deliver → Handover
|  |  |  | Close | N | F | V | V | N | N | N | Deliver → Handover
|  |  | Closed Items | View | V | F | V | V | V | V | V | Deliver → In-Use
2.15 | Daily Log | RIBA 5 / FIDIC | Daily Site Reports | View | V | F | V | V | V | V | V | Deliver
|  |  |  | Create | N | F | V | V | V | F | E | Deliver
|  |  |  | Edit | N | F | V | V | V | E | E | Deliver
|  |  | Weather Log | View | V | F | V | V | V | V | V | Deliver
|  |  |  | Create | N | F | V | V | N | F | E | Deliver
|  |  | Manpower Log | View | V | F | V | V | R | V | V | Deliver
|  |  |  | Create | N | F | V | N | N | F | E | Deliver
|  |  | Equipment Log | View | V | F | V | V | R | V | V | Deliver
|  |  |  | Create | N | F | V | N | N | F | E | Deliver
2.16 | Site Photos | RIBA 5-6 | Photo Albums | View | V | F | V | V | V | V | V | Deliver → Handover
|  |  |  | Upload | N | F | E | E | E | F | E | Deliver → Handover
|  |  |  | Delete | N | F | N | N | N | N | N | Deliver → Handover
|  |  | Progress Photos | View | V | F | V | V | V | V | V | Deliver → Handover
|  |  |  | Upload | N | F | E | E | E | F | E | Deliver → Handover
2.17 | Meetings | RICS PM / RIBA 0-7 | Meeting Schedule | View | V | F | V | V | V | V | V | All stages
|  |  |  | Create | N | F | E | E | N | N | N | All stages
|  |  |  | Edit | N | F | E | E | N | N | N | All stages
|  |  | Minutes of Meeting | View | V | F | V | V | V | V | V | All stages
|  |  |  | Create | N | F | E | E | E | N | N | All stages
|  |  |  | Edit | N | F | E | E | E | N | N | All stages
|  |  |  | Approve | V | F | V | N | N | N | N | All stages
|  |  | Action Items | View | V | F | V | V | V | V | V | All stages
|  |  |  | Create | N | F | E | E | E | E | N | All stages
|  |  |  | Edit | N | F | E | E | E | E | N | All stages
|  |  |  | Close | N | F | V | V | N | N | N | All stages
2.18 | Authority & NOCs | QCS / Qatar Authorities | NOC Tracker | View | V | F | V | V | V | V | N | Design → Handover
|  |  |  | Create | N | F | E | E | N | N | N | Design → Handover
|  |  |  | Edit | N | F | E | E | N | N | N | Design → Handover
|  |  | Ashghal Submissions | View | V | F | V | V | V | N | N | Design → Deliver
|  |  |  | Create | N | F | E | E | E | N | N | Design → Deliver
|  |  | QCDD (Civil Defence) | View | V | F | V | V | V | N | N | Design → Handover
|  |  |  | Create | N | F | E | E | E | N | N | Design → Handover
|  |  | Municipality (Baladiya) | View | V | F | V | V | V | N | N | Design → Handover
|  |  |  | Create | N | F | E | E | E | N | N | Design → Handover
|  |  | Kahramaa | View | V | F | V | V | V | N | N | Deliver → Handover
|  |  |  | Create | N | F | E | E | E | N | N | Deliver → Handover
|  |  | GSAS / Sustainability | View | V | F | V | V | V | R | N | All stages
|  |  |  | Create | N | F | V | E | E | N | N | All stages
2.19 | Commissioning & Handover | QCS §10-12 / RIBA 6-7 | Commissioning Plan | View | V | F | V | V | V | V | V | Deliver → Handover
|  |  |  | Create | N | F | E | V | N | E | N | Deliver
|  |  |  | Approve | V | F | V | N | N | N | N | Deliver → Handover
|  |  | Pre-Commissioning | View | V | F | V | V | V | V | V | Deliver → Handover
|  |  |  | Create | N | F | V | V | V | F | E | Deliver → Handover
|  |  | Testing & Commissioning | View | V | F | V | V | V | V | V | Handover
|  |  |  | Create | N | F | V | V | V | F | E | Handover
|  |  |  | Approve | V | F | V | V | N | N | N | Handover
|  |  | System Turnover Packages | View | V | F | V | V | V | V | V | Handover
|  |  |  | Create | N | F | E | V | N | F | E | Handover
|  |  |  | Approve | V | F | V | N | N | N | N | Handover
|  |  | O&M Manuals | View | V | F | V | V | V | V | V | Handover
|  |  |  | Upload | N | F | V | V | V | F | E | Handover
|  |  |  | Approve | V | F | V | N | N | N | N | Handover
|  |  | Spare Parts Register | View | V | F | V | V | V | V | V | Handover
|  |  |  | Create | N | F | V | N | N | F | E | Handover
|  |  | Training Records | View | V | F | V | V | V | V | V | Handover
|  |  |  | Create | N | F | V | V | N | F | E | Handover
|  |  | Handover Certificates | View | V | F | V | V | R | V | R | Handover
|  |  |  | Create | N | F | E | N | N | N | N | Handover
|  |  |  | Approve | A | F | V | N | N | N | N | Handover
|  |  | Building User Guide | View | V | F | V | V | V | V | V | Handover → In-Use
|  |  |  | Create | N | F | E | E | N | E | N | Handover
2.20 | Defects & Warranty | FIDIC cl.11 / RIBA 7 | Defect Register | View | V | F | V | V | V | V | V | Handover → In-Use
|  |  |  | Create | N | F | E | E | E | V | N | Handover → In-Use
|  |  |  | Edit | N | F | E | E | E | V | N | Handover → In-Use
|  |  |  | Close | N | F | V | V | N | N | N | Handover → In-Use
|  |  | Warranty Tracker | View | V | F | V | V | R | V | R | Handover → In-Use
|  |  |  | Create | N | F | E | N | N | N | N | Handover
|  |  |  | Edit | N | F | E | N | N | N | N | In-Use
|  |  | Retention Release | View | V | F | V | V | R | V | R | In-Use
|  |  |  | Create | N | F | E | N | N | N | N | In-Use
|  |  |  | Approve | A | F | V | N | N | N | N | In-Use
3 COMMERCIAL
3.1 | Approvals & Workflows | FIDIC / RIBA 0-7 | Pending Approvals | View | V | F | N | V | N | V | N | All stages
|  |  |  | Approve | A | F | N | V | N | N | N | All stages
|  |  |  | Reject | A | F | N | V | N | N | N | All stages
|  |  | IPC / Interim Payments | View | V | F | N | V | N | V | N | Deliver → In-Use
|  |  |  | Create | N | F | N | N | N | F | N | Deliver → In-Use
|  |  |  | Approve | A | F | N | N | N | N | N | Deliver → In-Use
|  |  | Variations / VOs | View | V | F | N | V | N | V | N | Deliver → In-Use
|  |  |  | Create | N | F | N | E | N | F | N | Deliver → In-Use
|  |  |  | Approve | A | F | N | N | N | N | N | Deliver → In-Use
|  |  | Contract Award | View | V | F | N | R | N | R | N | Procure
|  |  |  | Create | N | F | N | N | N | N | N | Procure
|  |  |  | Approve | A | F | N | N | N | N | N | Procure
|  |  | Budget Approval | View | V | F | N | R | N | N | N | Define → Design
|  |  |  | Create | N | F | N | N | N | N | N | Define → Design
|  |  |  | Approve | A | F | N | N | N | N | N | Define → Design
3.2 | Cost Management | RICS NRM / QS Practice | Cost Plan | View | V | F | N | V | N | N | N | Define → Deliver
|  |  |  | Create | N | F | N | E | N | N | N | Define → Deliver
|  |  |  | Edit | N | F | N | E | N | N | N | Define → Deliver
|  |  |  | Approve | A | F | N | N | N | N | N | Define → Deliver
|  |  | Cost Tracking / CVR | View | V | F | N | V | N | R | N | Deliver → In-Use
|  |  |  | Edit | N | F | N | E | N | N | N | Deliver → In-Use
|  |  | Payment Certificates | View | V | F | N | V | N | V | N | Deliver → In-Use
|  |  |  | Create | N | F | N | N | N | F | N | Deliver → In-Use
|  |  |  | Approve | A | F | N | N | N | N | N | Deliver → In-Use
|  |  | Variations Register | View | V | F | N | V | N | V | N | Deliver → In-Use
|  |  |  | Create | N | F | N | E | N | F | N | Deliver → In-Use
|  |  |  | Approve | A | F | N | N | N | N | N | Deliver → In-Use
|  |  | Claims Register | View | V | F | N | V | N | V | N | Deliver → In-Use
|  |  |  | Create | N | F | N | N | N | F | N | Deliver → In-Use
|  |  |  | Approve | A | F | N | N | N | N | N | Deliver → In-Use
|  |  | Bonds & Guarantees | View | V | F | N | R | N | R | N | Procure → In-Use
|  |  |  | Upload | N | F | N | N | N | E | N | Procure → In-Use
|  |  | Insurance Register | View | V | F | N | R | N | R | N | Procure → In-Use
|  |  |  | Upload | N | F | N | N | N | E | N | Procure → In-Use
|  |  |  | Edit | N | F | N | N | N | N | N | Procure → In-Use
|  |  | Daywork Sheets | View | V | F | N | V | N | V | N | Deliver
|  |  |  | Create | N | F | N | N | N | F | N | Deliver
|  |  |  | Approve | A | F | N | N | N | N | N | Deliver
|  |  | Final Account | View | V | F | N | V | N | V | N | Handover → In-Use
|  |  |  | Create | N | F | N | E | N | N | N | Handover → In-Use
|  |  |  | Approve | A | F | N | N | N | N | N | In-Use
3.3 | Contracts | FIDIC / RICS | Contract Register | View | V | F | N | V | N | R | N | Procure → In-Use
|  |  |  | Create | N | F | N | N | N | N | N | Procure
|  |  |  | Edit | N | F | N | N | N | N | N | Procure → In-Use
|  |  | Contract Documents | View | V | F | N | V | N | V | N | Procure → In-Use
|  |  |  | Upload | N | F | N | E | N | E | N | Procure → In-Use
|  |  |  | Download | V | F | N | V | N | V | N | Procure → In-Use
|  |  | Amendments / Addenda | View | V | F | N | V | N | V | N | Deliver → In-Use
|  |  |  | Create | N | F | N | N | N | N | N | Deliver → In-Use
|  |  |  | Approve | A | F | N | N | N | N | N | Deliver → In-Use
|  |  | Subcontractor Approvals | View | V | F | N | V | N | V | N | Deliver
|  |  |  | Create | N | F | N | N | N | F | N | Deliver
|  |  |  | Approve | V | F | N | N | N | N | N | Deliver
|  |  | Contractual Notices | View | V | F | N | V | N | V | N | Deliver → In-Use
|  |  |  | Create | N | F | N | E | N | F | N | Deliver → In-Use
3.4 | Tenders & Procurement | RICS / FIDIC | Tender Register | View | V | F | N | V | N | N | N | Procure
|  |  |  | Create | N | F | N | N | N | N | N | Procure
|  |  |  | Edit | N | F | N | N | N | N | N | Procure
|  |  | Bid Evaluation | View | V | F | N | V | N | N | N | Procure
|  |  |  | Create | N | F | N | E | N | N | N | Procure
|  |  |  | Approve | A | F | N | N | N | N | N | Procure
|  |  | Award Recommendation | View | V | F | N | R | N | N | N | Procure
|  |  |  | Create | N | F | N | N | N | N | N | Procure
|  |  |  | Approve | A | F | N | N | N | N | N | Procure
|  |  | Procurement Log | View | V | F | N | V | N | R | N | Design → Deliver
|  |  |  | Create | N | F | N | E | N | N | N | Design → Deliver
|  |  |  | Edit | N | F | N | E | N | N | N | Design → Deliver

## Stage Gate Requirements
HAI GROUP — SkyStruct ERP: Stage Gate Closure Requirements (RIBA 0-7 / HAI 6-Stage Lifecycle)
Gate | Stage Name (RIBA / HAI) | Actions to Close Before Next Stage | Document / Template Required | Responsible Role | ERP Module | Authority
Gate 0 | Strategic Definition (HAI: Define) | Employer's Requirements finalised | ER Brief / Employer's Requirements.docx | C-Level → D-Level | Documents
|  | Project budget approved | Cost Plan — Feasibility.xlsx | C-Level → D-Level | Cost Management
|  | Feasibility study completed | Feasibility Study Report.docx | D-Level / Consultant PM | Documents
|  | Risk register initiated (min. 10 risks) | HSE-E02_Risk_Assessment.xlsx | D-Level | Risk Management
|  | Communication plan approved | Communication Management Plan.docx | D-Level | Meetings
|  | Roles & permissions configured | User_Roles_Permissions_Matrix.xlsx | D-Level | Admin & Settings
|  | Document numbering system established | Document_Numbering_System.xlsx | M-Level | Document Management
|  | SkyStruct system initialised | System_Configuration_Document.xlsx | D-Level | Admin & Settings
|  | GSAS pre-assessment (if applicable) | REG-J07_GSAS.xlsx | Consultant PM | Authority & NOCs | GSAS Trust
Gate 1 | Preparation & Briefing (HAI: Define) | Project brief signed off | Project Brief.docx | C-Level → D-Level | Documents
|  | Consultant appointments finalised | Appointment Letters | D-Level | Contracts
|  | Contract terms loaded into system | Contract Register + Docs | D-Level | Contracts
|  | Master programme (baseline) approved | Master Programme.mpp/.xlsx | D-Level | Schedule & Programme
|  | Procurement strategy approved | PRG-F09_Procurement_Schedule.xlsx | D-Level | Tenders & Procurement
|  | Process flows activated (PF-01 to PF-23) | Process_Flow_Register.xlsx | M-Level | Flowcharts & Workflows
|  | BIM Execution Plan approved | BIM Execution Plan.docx | D-Level | BIM / Models
|  | Insurance & bond requirements defined | CON-G07_Insurance_Register.xlsx | D-Level | Cost Management
Gate 2 | Concept Design (HAI: Design) | Concept design approved | DES-A00_Design_Submittal_Cover.docx | D-Level / Consultant PM | Design Management
|  | Cost Plan L1 (Order of Cost) approved | Cost Plan L1.xlsx | D-Level | Cost Management | RICS NRM1
|  | Planning permission submitted | REG-J04_Municipality.xlsx | M-Level | Authority & NOCs | Baladiya
|  | Risk register reviewed and updated | Risk Register.xlsx | D-Level | Risk Management
|  | Change control procedures activated | Change Order Log + SI Register | M-Level | Change Management
|  | Design brief frozen | Design Brief — Approved.docx | D-Level | Design Management
Gate 3 | Spatial Coordination (HAI: Design) | Coordinated design package complete | Drawing Register + Specs | Consultant PM | Drawing Register
|  | Cost Plan L2 (Elemental) approved | Cost Plan L2.xlsx | D-Level | Cost Management | RICS NRM1
|  | Clash detection report issued | Clash Report.pdf | Consultant PM | BIM / Models
|  | Fire strategy submitted to QCDD | REG-J01_Civil_Defence.xlsx | M-Level | Authority & NOCs | QCDD
|  | Building permit submitted | REG-J01_Civil_Defence.xlsx | M-Level | Authority & NOCs | QCDD
|  | All open RFIs < 14 days | RFI_Register.xlsx | M-Level | RFIs
|  | All Consultant NCRs closed | QA-D00_NCR_Register.xlsx | Consultant PM | Quality Management
Gate 3.1 | Developed Technical Design (HAI: Design → Procure) | Technical design frozen | Design Freeze Log — Approved | D-Level | Design Management
|  | Design gateway review passed | Design Gateway Review Report | D-Level / Consultant PM | Design Management | RIBA
|  | QA plan drafted for construction | QA-D01_Project_Quality_Plan.docx | Consultant PM | Quality Management | QCS §1.4
|  | Cost Plan L3 (Approx. Quantities) | Cost Plan L3.xlsx | D-Level | Cost Management | RICS NRM2
|  | Preliminary ITP programme drafted | QA-D02_ITP_Template.xlsx | Consultant PM | Quality Management | QCS §1.7
Gate 4 | Technical Design (HAI: Procure) | Technical design complete for tender | Full Drawing Package + Specs | Consultant PM | Drawing Register | RIBA
|  | Tender documents prepared | Tender Package (BoQ + Conditions) | D-Level | Tenders & Procurement | RICS NRM2
|  | Pre-qualification complete | Bid Evaluation.xlsx | D-Level | Tenders & Procurement
|  | Cost Plan L4 (Firm BoQ) finalised | Bills of Quantities.xlsx | D-Level | Cost Management | RICS NRM2
|  | All authority approvals for construction | NOC Tracker — all approved | M-Level | Authority & NOCs | Various
|  | Cash flow forecast approved | PRG-F05_Cash_Flow.xlsx | D-Level | Schedule & Programme
|  | GSAS design-stage docs submitted | REG-J07_GSAS.xlsx | Consultant PM | Authority & NOCs | GSAS Trust
Gate 5 | Manufacturing & Construction (HAI: Deliver) | Contract signed and loaded | Contract Register — Executed | D-Level | Contracts | FIDIC
|  | Mobilisation plan approved | PRG-F01_Mobilisation_Plan.docx | D-Level | Schedule & Programme
|  | HSE plan approved | HSE-E01_Project_HSE_Plan.docx | D-Level | HSE Management | QCS §1.5
|  | Quality plan approved | QA-D01_Project_Quality_Plan.docx | D-Level | Quality Management | QCS §1.4
|  | Environmental mgmt plan approved | HSE-E08_Environmental_Management_Plan.docx | D-Level | HSE Management | QCS §1.5
|  | Site access protocol complete | Site Handover Protocol.docx | M-Level | Daily Log
|  | ITPs submitted for major works | QA-D02_ITP_Template.xlsx (per discipline) | Contractor PM | Quality Management | QCS §1.7
|  | Performance bond received | CON-G05_Bond_Register.xlsx | D-Level | Cost Management | FIDIC
|  | Insurance certificates received | CON-G07_Insurance_Register.xlsx | D-Level | Cost Management | FIDIC
|  | Method statements approved (Phase 1) | MS-C01 to MS-C14 (applicable) | M-Level | Document Management | QCS
|  | Progress reporting cadence set | RPT-F02 Weekly + RPT-F04 Monthly | M-Level | Programme Dashboard
|  | Subcontractor approvals obtained | CON-G08_Subcontractor_Approval.xlsx | D-Level | Contracts | FIDIC
|  | NCR register cleared | QA-D00_NCR_Register.xlsx | M-Level | Quality Management
|  | Kahramaa electrical design approved | REG-J05_Kahramaa.xlsx | Consultant PM | Authority & NOCs | Kahramaa
|  | Concrete mix designs approved | MAT-B11_Concrete_Mix_Design.xlsx | Contractor PM | Quality Management | QCS §4
|  | PC criteria defined | PC Criteria Document.docx | D-Level | Commissioning & Handover | FIDIC
|  | Open claims assessed | CON-G00_Claims_Register.xlsx | D-Level | Cost Management | FIDIC
|  | All IPCs current | Payment Certificate Register | M-Level | Cost Management | FIDIC
|  | Snagging protocol defined | QA-D12_Snag_List.xlsx (template) | M-Level | Punch List / Snagging
Gate 6 | Handover (HAI: Handover) | Practical completion achieved | PC Certificate.docx | D-Level / Architect | Commissioning & Handover | FIDIC cl.10
|  | Snagging list < 5% items open | QA-D12_Snag_List.xlsx — final | M-Level | Punch List / Snagging
|  | All NCRs closed | QA-D00_NCR_Register.xlsx — zero open | M-Level | Quality Management
|  | As-built drawings approved | HOV-H01_As_Built_Register.xlsx | Contractor PM → D-Level | Document Management
|  | O&M manuals submitted | HOV-H02_OM_Manual_Template.docx | Contractor PM | Commissioning & Handover | QCS
|  | All systems commissioned | HOV-H05_Testing_Commissioning.xlsx | M-Level / Contractor | Commissioning & Handover | QCS §10-12
|  | Training delivered | HOV-H07_Training_Record.xlsx | Contractor PM | Commissioning & Handover
|  | Building User Guide issued | HOV-H10_Building_User_Guide.docx | Consultant PM / D-Level | Commissioning & Handover
|  | Spare parts register submitted | HOV-H04_Spare_Parts.xlsx | Contractor PM | Commissioning & Handover
|  | Fire safety inspection passed | REG-J01 — approved | M-Level | Authority & NOCs | QCDD
|  | Municipality completion cert | REG-J04 — approved | M-Level | Authority & NOCs | Baladiya
|  | Kahramaa connection complete | REG-J05 — approved | M-Level | Authority & NOCs | Kahramaa
|  | Final IPC submitted | CON-G01_Payment_Application.docx | Contractor PM | Cost Management | FIDIC
|  | DLP start date recorded | Warranty Tracker + Contract Register | D-Level | Defects & Warranty | FIDIC cl.11
|  | All NOCs closed | NOC Tracker — all closed | M-Level | Authority & NOCs | Various
|  | Demobilisation plan approved | HOV-H01_Demobilisation_Plan.docx | D-Level | Commissioning & Handover
|  | Handover certificates signed | HOV-H00_Handover_Cover.docx | C-Level / D-Level | Commissioning & Handover | FIDIC
Gate 7 | In-Use & DLP (HAI: In-Use) | Final account agreed | CON-G12_Final_Account.xlsx | D-Level | Cost Management | RICS / FIDIC
|  | Retention half-release processed | CON-G08_Retention_Release.docx | D-Level | Defects & Warranty | FIDIC
|  | All DLP defects closed | HOV-H11_Defects_Tracker.xlsx — zero open | M-Level | Defects & Warranty | FIDIC cl.11
|  | Performance bond released | CON-G05_Bond_Register.xlsx — released | D-Level | Cost Management | FIDIC
|  | Final retention release | CON-G08_Retention_Release.docx (final) | D-Level | Defects & Warranty | FIDIC
|  | Warranties transferred to FM | Warranty Tracker — Transferred | D-Level | Defects & Warranty
|  | GSAS construction cert (if applicable) | REG-J07_GSAS.xlsx — certified | Consultant PM | Authority & NOCs | GSAS Trust
|  | All claims resolved | CON-G00_Claims_Register.xlsx — zero open | D-Level | Cost Management | FIDIC
Gate 8 | Post-Completion (HAI: Close-Out) | Lessons learned finalised | Lessons Learned Report — Final.docx | D-Level | Meetings
|  | Project archive completed | Document Register — archived | M-Level | Document Management
|  | Audit trail exported | Audit Log Export.xlsx | D-Level | Admin & Settings
|  | SkyStruct set to read-only | System Configuration — archived | D-Level | Admin & Settings
|  | Close-out report issued | Project Close-Out Report.docx | D-Level → C-Level | Documents
|  | Dispute resolutions concluded | CON-G12_Dispute_Notice.docx — Closed | D-Level / Legal | Cost Management | FIDIC

## Role Summary
Module | C-Level (Board) | D-Level (Employer's Rep) | M-Level (Employer's Rep) | Consultant PM & DC | Consultant Officers | Contractor PM & DC | Contractor Officers
1 DASHBOARDS
1.1 Programme Dashboard | V | F | V | V | V | V | V
1.2 Analytics & AI | V | F | V | V | R | R | N
1.3 Notifications & Alerts | V | F | F | V | V | V | V
1.4 Directory | V | F | F | V | V | V | V
1.5 Flowcharts & Workflows | V | F | F | V | V | V | R
1.6 Admin & Settings | V | F | V | V | V | V | V
2 EXECUTION
2.1 Correspondence & Transmittals | A | F | E | E | V | E | V
2.2 Document Management | V | F | V | V | V | V | V
2.3 Drawing Register | V | F | V | V | E | V | V
2.4 RFIs | V | F | V | E | E | V | V
2.5 Design Management | V | F | V | V | V | V | R
2.6 BIM / Models | V | F | V | V | V | V | V
2.7 Submittals | V | F | V | A | V | V | V
2.8 Change Management | V | F | V | V | V | V | V
2.9 Risk Management | V | F | V | V | V | V | R
2.10 Schedule & Programme | V | F | V | V | V | V | V
2.11 Quality Management | V | F | V | A | V | V | E
2.12 HSE Management | V | F | V | V | V | V | E
2.13 Observations | V | F | E | E | E | E | E
2.14 Punch List / Snagging | V | F | V | V | V | V | V
2.15 Daily Log | V | F | V | V | V | F | E
2.16 Site Photos | V | F | V | V | V | F | V
2.17 Meetings | V | F | E | E | E | V | V
2.18 Authority & NOCs | V | F | V | E | V | V | N
2.19 Commissioning & Handover | A | F | V | V | V | V | V
2.20 Defects & Warranty | A | F | V | V | E | V | V
3 COMMERCIAL
3.1 Approvals & Workflows | A | F | N | V | N | V | N
3.2 Cost Management | A | F | N | V | N | V | N
3.3 Contracts | A | F | N | V | N | V | N
3.4 Tenders & Procurement | A | F | N | V | N | R | N

## Instructions
HOW TO USE THIS FILE
STRUCTURE
All 30 modules are grouped under 3 main headers:
1 DASHBOARDS — Programme visibility, analytics, system config, directory, workflows, admin (6 modules)
2 EXECUTION — Design, BIM, documents, RFIs, submittals, schedule, change, risk, quality, HSE, site ops, handover, defects (20 modules)
3 COMMERCIAL — Approvals/workflows, cost management, contracts, tenders/procurement (4 modules)
PERMISSION LOGIC (v4 — Corrected)
1. Originator-only editing: whoever creates a document has the right to edit it. No one else can edit.
2. Reviewers/commenters can ONLY review and comment — they receive View (V) access.
3. D-Level (Employer's Rep PM) has Full Access (F) to everything, without exception.
4. Documents flow back to originator through DCs as per process flowcharts.
5. C-Level (Board) can ONLY approve when explicitly addressed. Otherwise View (V) only.
6. Officers and M-Level managers have NO ACCESS (N) to the entire Commercial section.
PERMISSION CODES
F = Full Access — create, edit, approve, delete (D-Level default)
V = View Only — read and download only
E = Edit — create/modify own documents only (originator privilege)
A = Approve — review and approve/reject when addressed (implies View)
N = No Access — module/action hidden from this role
R = Restricted — summary/aggregated view only, limited detail
REFERENCE STANDARDS
RIBA Plan of Work 2020 — Stages 0-7 → HAI: Define / Design / Procure / Deliver / Handover / In-Use
QCS 2014 — §1.4 QA, §1.5 HSE, §1.6 DocControl, §1.7 QualityRecords, §2 Site, §4 Concrete, §5 Steel, §8-9 MEP, §10-12 Commissioning
RICS — NRM1/NRM2 cost management, PM standards, QS practice
FIDIC — cl.10 Taking Over, cl.11 Defects, cl.13 Variations, cl.14 Payment
ISO 31000 Risk / ISO 9001 Quality / ISO 45001 OHS / ISO 14001 Env / ISO 19650 BIM