## WBS Schedule
WBS Code | Task ID | Task Name | Level | Duration (days) | Start Date | End Date | Predecessors | Resource | Status | % Complete | Deliverable/Output | Notes
PHASE 0
0.1 | 1 | Project Kickoff | 2 | 2 | 2026-03-15 | 2026-03-16 |  | Hasan Mollamahmutoglu |  |  | Kickoff minutes, project charter
0.2 | 2 | Requirements Validation | 2 | 3 | 2026-03-17 | 2026-03-19 | 1FS | Hasan Mollamahmutoglu |  |  | Validated requirements against contract
0.3 | 3 | Stakeholder Alignment | 2 | 2 | 2026-03-22 | 2026-03-23 | 2FS | Hasan Mollamahmutoglu |  |  | Stakeholder register, RACI
0.4 | 4 | Platform Access Setup | 2 | 3 | 2026-03-17 | 2026-03-19 | 1FS | Hasan Mollamahmutoglu |  |  | Environment ready, credentials issued
PHASE 1
1.1 | 5 | System Configuration | 2 | 3 | 2026-03-22 | 2026-03-24 | 4FS | Hasan Mollamahmutoglu |  |  | HAI_System_Configuration_Document.xlsx
1.2 | 6 | Document Numbering Setup | 2 | 2 | 2026-03-25 | 2026-03-26 | 5FS | Hasan Mollamahmutoglu |  |  | HAI_A068_Document_Numbering_System.xlsx
1.3 | 7 | User Roles & Permissions | 2 | 3 | 2026-03-25 | 2026-03-29 | 5FS | Hasan Mollamahmutoglu |  |  | HAI_User_Roles_Permissions_Matrix.xlsx
1.4 | 8 | Workflow Engine Rules | 2 | 4 | 2026-03-30 | 2026-04-02 | 7FS | Hasan Mollamahmutoglu |  |  | HAI_Workflow_Engine_Rules.xlsx
1.5 | 9 | Notification & Alert Rules | 2 | 3 | 2026-04-05 | 2026-04-07 | 8FS | Hasan Mollamahmutoglu |  |  | HAI_Notification_Alert_Rules.xlsx
1.6 | 10 | Form & Template Config | 2 | 3 | 2026-03-30 | 2026-04-01 | 8SS | Hasan Mollamahmutoglu |  |  | HAI_Form_Template_Specifications.xlsx
1.7 | 11 | Stage Gate Configuration | 2 | 2 | 2026-03-25 | 2026-03-26 | 5FS | Hasan Mollamahmutoglu |  |  | HAI_Stage_Based_Organization.xlsx
1.8 | 12 | Foundation Review & Sign-off | 2 | 1 | 2026-04-08 | 2026-04-08 | 9FS,10FS,11FS | Hasan Mollamahmutoglu |  |  | Gate 0 passage checklist signed
PHASE 2
2.1 | 13 | PF-01 Document Submission & Review | 2 | 3 | 2026-04-09 | 2026-04-13 | 12FS | Hasan Mollamahmutoglu |  |  | PF-01 configured, flowchart verified
2.2 | 14 | PF-02 Correspondence Management | 2 | 3 | 2026-04-14 | 2026-04-16 | 13FS | Hasan Mollamahmutoglu |  |  | PF-02 configured, FIDIC timers set
2.3 | 15 | PF-03 Variation Order (SC 13.1 Parallel) | 2 | 4 | 2026-04-19 | 2026-04-22 | 14FS | Hasan Mollamahmutoglu |  |  | PF-03 dual track configured
2.4 | 16 | PF-08 IPC Processing | 2 | 4 | 2026-04-19 | 2026-04-22 | 14FS | Hasan Mollamahmutoglu |  |  | PF-08 configured, retention rules set
2.5 | 17 | PF-09 Approval Workflow Engine | 2 | 3 | 2026-04-23 | 2026-04-27 | 15FS,16FS | Hasan Mollamahmutoglu |  |  | Approval thresholds configured
2.6 | 18 | PF-11 Spatial Coordination & Cost Management | 2 | 3 | 2026-04-23 | 2026-04-27 | 16FS | Hasan Mollamahmutoglu |  |  | RICS cost plan levels configured
2.7 | 19 | PF-22 Notification & Escalation Engine | 2 | 3 | 2026-04-28 | 2026-04-30 | 17FS | Hasan Mollamahmutoglu |  |  | L1-L5 escalation configured
2.8 | 20 | Core Module Review | 2 | 2 | 2026-05-03 | 2026-05-04 | 17FS,18FS,19FS | Hasan Mollamahmutoglu |  |  | Core modules tested & signed off
PHASE 3
3.1 | 21 | PF-04 Procurement RFP to Contract Award | 2 | 2 | 2026-05-05 | 2026-05-06 | 20FS | Hasan Mollamahmutoglu |  |  | PF-04 configured
3.2 | 22 | PF-05 Stage Gate Progression | 2 | 2 | 2026-05-05 | 2026-05-06 | 20FS | Hasan Mollamahmutoglu |  |  | PF-05 gate logic configured
3.3 | 23 | PF-06 Freeze Exception Workflow | 2 | 2 | 2026-05-07 | 2026-05-10 | 22FS | Hasan Mollamahmutoglu |  |  | PF-06 freeze rules configured
3.4 | 24 | PF-07 Authority Submission Tracking | 2 | 2 | 2026-05-07 | 2026-05-10 | 21FS | Hasan Mollamahmutoglu |  |  | PF-07 regulatory tracker configured
3.5 | 25 | PF-10 Quality & Site Supervision | 2 | 3 | 2026-05-11 | 2026-05-13 | 23FS | Hasan Mollamahmutoglu |  |  | PF-10 NCR, inspection configured
3.6 | 26 | PF-12 Risk Register Management | 2 | 2 | 2026-05-14 | 2026-05-17 | 25FS | Hasan Mollamahmutoglu |  |  | PF-12 P×I matrix configured
3.7 | 27 | PF-13 Contractor Performance Scoring | 2 | 2 | 2026-05-14 | 2026-05-17 | 25FS | Hasan Mollamahmutoglu |  |  | PF-13 KPI scorecards configured
3.8 | 28 | PF-14 Lessons Learned | 2 | 1 | 2026-05-18 | 2026-05-18 | 26FS | Hasan Mollamahmutoglu |  |  | PF-14 capture form configured
3.9 | 29 | PF-15 Handover & DLP Management | 2 | 2 | 2026-05-18 | 2026-05-19 | 27FS | Hasan Mollamahmutoglu |  |  | PF-15 snagging, DLP configured
3.10 | 30 | PF-16 Meeting & Action Tracking | 2 | 2 | 2026-05-19 | 2026-05-20 | 28FS | Hasan Mollamahmutoglu |  |  | PF-16 meeting templates configured
3.11 | 31 | PF-17 External Stakeholder Portal | 2 | 3 | 2026-05-20 | 2026-05-24 | 29FS | Hasan Mollamahmutoglu |  |  | PF-17 contractor portal configured
3.12 | 32 | PF-18 Report Generation & Export | 2 | 2 | 2026-05-21 | 2026-05-24 | 30FS | Hasan Mollamahmutoglu |  |  | PF-18 report templates configured
3.13 | 33 | PF-19 User & Role Management | 2 | 1 | 2026-03-30 | 2026-03-30 | 7FS | Hasan Mollamahmutoglu |  |  | Already done in Phase 1, verify only
3.14 | 34 | PF-20 ERP Integration | 2 | 4 | 2026-05-25 | 2026-05-28 | 31FS | Hasan Mollamahmutoglu |  |  | PF-20 API endpoints configured
PHASE 4
4.1 |  | Configure PF-24 Mobilization Management |  | 2 |  |  | Hasan | Phase 4 |  |  | PF configuration and testing
4.2 |  | Configure PF-25 Testing & Commissioning / GSAS |  | 2 |  |  | Hasan | Phase 4 |  |  | PF configuration and testing
4.3 |  | Configure PF-26 Post-Occupancy Services |  | 2 |  |  | Hasan | Phase 4 |  |  | PF configuration and testing
4.4 |  | Configure PF-27 Consultant Performance & Payment |  | 2 |  |  | Hasan | Phase 4 |  |  | PF configuration and testing
4.5 |  | Configure PF-28 Taking Over Certificate (TOC) |  | 1 |  |  | Hasan | Phase 4 |  |  | PF configuration and testing
4.6 |  | Configure PF-29 Final Account & Final Payment |  | 2 |  |  | Hasan | Phase 4 |  |  | PF configuration and testing
4.7 |  | Configure PF-30 Performance Certificate |  | 2 |  |  | Hasan | Phase 4 |  |  | PF configuration and testing
4.8 |  | Configure PF-31 Snag List Creation & Resolution |  | 1 |  |  | Hasan | Phase 4 |  |  | PF configuration and testing
4.9 |  | Consultancy Contract Parameter Setup |  | 2 |  |  | Hasan | Phase 4 |  |  | PF configuration and testing
4.10 |  | SkyStruct Integration Configuration |  | 2 |  |  | Hasan | Phase 4 |  |  | PF configuration and testing
3.15 | 35 | PF-21 Dashboard & Analytics | 2 | 3 | 2026-05-25 | 2026-05-27 | 32FS | Hasan Mollamahmutoglu |  |  | PF-21 dashboards configured
3.16 | 36 | PF-23 Audit Trail & Compliance | 2 | 2 | 2026-05-31 | 2026-06-01 | 34FS | Hasan Mollamahmutoglu |  |  | PF-23 audit log verified
3.17 | 37 | Extended Module Review | 2 | 2 | 2026-06-02 | 2026-06-03 | 34FS,35FS,36FS | Hasan Mollamahmutoglu |  |  | All 23 PFs configured & tested
PHASE 4
4.1 | 38 | ERP Integration Testing | 2 | 4 | 2026-06-04 | 2026-06-09 | 37FS | Hasan Mollamahmutoglu |  |  | HAI_Integration_Specification.xlsx verified
4.2 | 39 | Data Migration - Assessment | 2 | 2 | 2026-06-04 | 2026-06-07 | 37FS | Hasan Mollamahmutoglu |  |  | Migration scope confirmed
4.3 | 40 | Data Migration - Cleansing | 2 | 3 | 2026-06-08 | 2026-06-10 | 39FS | Hasan Mollamahmutoglu |  |  | Source data cleaned
4.4 | 41 | Data Migration - Trial Run | 2 | 2 | 2026-06-11 | 2026-06-14 | 40FS | Hasan Mollamahmutoglu |  |  | Trial migration validated
4.5 | 42 | Data Migration - Production | 2 | 2 | 2026-06-15 | 2026-06-16 | 41FS | Hasan Mollamahmutoglu |  |  | HAI_Migration_Specification.xlsx complete
4.6 | 43 | Integration Review | 2 | 1 | 2026-06-17 | 2026-06-17 | 38FS,42FS | Hasan Mollamahmutoglu |  |  | Integration & migration signed off
PHASE 5
5.1 | 44 | Smoke Testing | 2 | 2 | 2026-06-18 | 2026-06-21 | 43FS | Hasan Mollamahmutoglu |  |  | Basic functionality confirmed
5.2 | 45 | Module Testing (PF-01 to PF-23) | 2 | 8 | 2026-06-22 | 2026-07-01 | 44FS | Hasan Mollamahmutoglu |  |  | All module tests passed
5.3 | 46 | Integration Testing | 2 | 4 | 2026-07-02 | 2026-07-07 | 45FS | Hasan Mollamahmutoglu |  |  | Cross-module tests passed
5.4 | 47 | End-to-End Testing | 2 | 4 | 2026-07-08 | 2026-07-13 | 46FS | Hasan Mollamahmutoglu |  |  | Full workflow scenarios passed
5.5 | 48 | Regression Testing | 2 | 2 | 2026-07-14 | 2026-07-15 | 47FS | Hasan Mollamahmutoglu |  |  | No regressions
5.6 | 49 | UAT Sign-off | 2 | 2 | 2026-07-16 | 2026-07-19 | 48FS | Hasan Mollamahmutoglu |  |  | HAI_UAT_Test_Plan.xlsx signed
PHASE 6
6.1 | 50 | Training Material Preparation | 2 | 3 | 2026-07-08 | 2026-07-12 | 47SS | Hasan Mollamahmutoglu |  |  | Training docs prepared
6.2 | 51 | User Training Sessions | 2 | 3 | 2026-07-20 | 2026-07-22 | 49FS,50FS | Hasan Mollamahmutoglu |  |  | All users trained
6.3 | 52 | Go-Live Readiness Review | 2 | 1 | 2026-07-23 | 2026-07-23 | 51FS | Hasan Mollamahmutoglu |  |  | Go/No-Go decision
6.4 | 53 | Production Go-Live | 2 | 1 | 2026-07-26 | 2026-07-26 | 52FS | Hasan Mollamahmutoglu |  |  | System live
6.5 | 54 | Post Go-Live Support | 2 | 5 | 2026-07-27 | 2026-08-02 | 53FS | Hasan Mollamahmutoglu |  |  | Issues resolved, system stable
6.6 | 55 | Project Closure | 2 | 2 | 2026-08-03 | 2026-08-04 | 54FS | Hasan Mollamahmutoglu |  |  | Final report, lessons learned, archive

## Gantt Chart
Task ID | Task Name | Week 1 | Week 2 | Week 3 | Week 4 | Week 5 | Week 6 | Week 7 | Week 8 | Week 9 | Week 10 | Week 11 | Week 12 | Week 13 | Week 14 | Week 15 | Week 16
1 | Project Kickoff
2 | Requirements Validation
3 | Stakeholder Alignment
4 | Platform Access Setup
5 | System Configuration
6 | Document Numbering Setup
7 | User Roles & Permissions
8 | Workflow Engine Rules
9 | Notification & Alert Rules
10 | Form & Template Config
11 | Stage Gate Configuration
12 | Foundation Review & Sign-off
13 | PF-01 Document Submission & Review
14 | PF-02 Correspondence Management
15 | PF-03 Variation Order (SC 13.1 Parallel)
16 | PF-08 IPC Processing
17 | PF-09 Approval Workflow Engine
18 | PF-11 Spatial Coordination & Cost Management
19 | PF-22 Notification & Escalation Engine
20 | Core Module Review
21 | PF-04 Procurement RFP to Contract Award
22 | PF-05 Stage Gate Progression
23 | PF-06 Freeze Exception Workflow
24 | PF-07 Authority Submission Tracking
25 | PF-10 Quality & Site Supervision
26 | PF-12 Risk Register Management
27 | PF-13 Contractor Performance Scoring
28 | PF-14 Lessons Learned
29 | PF-15 Handover & DLP Management
30 | PF-16 Meeting & Action Tracking
31 | PF-17 External Stakeholder Portal
32 | PF-18 Report Generation & Export
33 | PF-19 User & Role Management
34 | PF-20 ERP Integration
35 | PF-21 Dashboard & Analytics
36 | PF-23 Audit Trail & Compliance
37 | Extended Module Review
38 | ERP Integration Testing
39 | Data Migration - Assessment
40 | Data Migration - Cleansing
41 | Data Migration - Trial Run
42 | Data Migration - Production
43 | Integration Review
44 | Smoke Testing
45 | Module Testing (PF-01 to PF-23)
46 | Integration Testing
47 | End-to-End Testing
48 | Regression Testing
49 | UAT Sign-off
50 | Training Material Preparation
51 | User Training Sessions
52 | Go-Live Readiness Review
53 | Production Go-Live
54 | Post Go-Live Support
55 | Project Closure

## Resource Summary
Phase | Tasks | Duration (days) | Start | End | Resource | Utilization %
Phase 0: Project Initiation | 4 | 10 | 2026-03-15 | 2026-03-23 | Hasan Mollamahmutoglu | 100%
Phase 1: Foundation Configuration | 8 | 23 | 2026-03-22 | 2026-04-08 | Hasan Mollamahmutoglu | 100%
Phase 2: Core Module Configuration | 8 | 24 | 2026-04-09 | 2026-05-04 | Hasan Mollamahmutoglu | 100%
Phase 3: Extended Module Configuration | 17 | 43 | 2026-03-30 | 2026-06-03 | Hasan Mollamahmutoglu | 100%
Phase 4: Integration & Migration | 6 | 15 | 2026-06-04 | 2026-06-17 | Hasan Mollamahmutoglu | 100%
Phase 5: Testing | 6 | 22 | 2026-06-18 | 2026-07-19 | Hasan Mollamahmutoglu | 100%
Phase 6: Go-Live & Handover | 6 | 12 | 2026-07-08 | 2026-08-04 | Hasan Mollamahmutoglu | 100%

## Milestone Register
Milestone ID | Milestone | Target Date | Predecessor | Deliverable | Status
M1 | Foundation Complete |  | 12FS | Gate 0 passage checklist signed | Pending
M2 | Core Modules Complete |  | 20FS | Core modules tested & signed off | Pending
M3 | All PFs Complete |  | 37FS | All 23 PFs configured & tested | Pending
M4 | Migration Complete |  | 42FS | HAI_Migration_Specification.xlsx complete | Pending
M5 | Integration Complete |  | 43FS | Integration & migration signed off | Pending
M6 | UAT Sign-off |  | 49FS | HAI_UAT_Test_Plan.xlsx signed | Pending
M7 | Go-Live |  | 52FS | System live | Pending
M8 | Project Closure |  | 55FS | Final report, lessons learned, archive | Pending

## Critical Path
Task ID | Task Name | Duration (days) | Predecessors | Float | Status
1 | Project Kickoff | 2 |  | 0 | Critical
4 | Platform Access Setup | 3 | 1FS | 0 | Critical
5 | System Configuration | 3 | 4FS | 0 | Critical
8 | Workflow Engine Rules | 4 | 7FS | 0 | Critical
9 | Notification & Alert Rules | 3 | 8FS | 0 | Critical
12 | Foundation Review & Sign-off | 1 | 9FS,10FS,11FS | 0 | Critical
13 | PF-01 Document Submission & Review | 3 | 12FS | 0 | Critical
14 | PF-02 Correspondence Management | 3 | 13FS | 0 | Critical
16 | PF-08 IPC Processing | 4 | 14FS | 0 | Critical
20 | Core Module Review | 2 | 17FS,18FS,19FS | 0 | Critical
34 | PF-20 ERP Integration | 4 | 31FS | 0 | Critical
37 | Extended Module Review | 2 | 34FS,35FS,36FS | 0 | Critical
45 | Module Testing (PF-01 to PF-23) | 8 | 44FS | 0 | Critical
46 | Integration Testing | 4 | 45FS | 0 | Critical
47 | End-to-End Testing | 4 | 46FS | 0 | Critical
49 | UAT Sign-off | 2 | 48FS | 0 | Critical
51 | User Training Sessions | 3 | 49FS,50FS | 0 | Critical
52 | Go-Live Readiness Review | 1 | 51FS | 0 | Critical
53 | Production Go-Live | 1 | 52FS | 0 | Critical
54 | Post Go-Live Support | 5 | 53FS | 0 | Critical