## Process Flow Register
PF-ID | Process Flow Name | Category | SOW Module(s) | SOW Req Ref(s) | RIBA Stage(s) | Primary Actor(s) | Key Decision Points | Freeze Interaction | ERP Sync Required | Phase | Priority | Est. Steps | Predecessor PF(s) | Downstream PF(s) | Workshop Ref | Status | Owner | Notes / Scope Boundary
PF-01 | Document Review | Document Management | M1: EDMS, M2: Doc Workflow | D.1–D.9, SG.1 | 0–8 (All) | Contractor DC, HAI-DC, HAI Engineer, HAI PM | QC Pass/Fail (×2), Review Status (APP/REJ/APP-COM/INFO), Consolidation Validation | Regulatory Freeze blocks design resubmission | No | Ph1 | Critical | 8 | — | PF-03, PF-05, PF-07 | W2, W10 | To Be Developed | HAI PMO | Full 8-step closed-loop per SOW §4. Includes cover page validation, auto-numbering, SLA timers D+3/D+5/D+7, PDF markup, transmittal register.
PF-02 | Correspondence | Document Management | M3: Correspondence | C.1, C.2 | 4–6 (Execution–Handover) | HAI PM, Contractor, Consultant | Notice validity check, Response deadline, Determination trigger | None direct; supports claims defense | No | Ph1 | Critical | 6 | PF-01 | PF-03, PF-11 | W2 | To Be Developed | HAI PMO | Letter registry, HAI templates, FIDIC Notice→Response→Determination sequence, email capture, linked to project/contract.
PF-03 | Variation Order | Financial Control | M7: Quality & Site, M15: ERP | G.6, E.1, K.3 | 5 (Construction) | Contractor, HAI QS, HAI PM, HAI Finance, Approver | QS verification, PM endorsement, Finance review, Spatial Coordination breach check, Final approval | Budget Freeze: IPC cannot exceed frozen baseline without variation | Yes — push to ERP for payment | Ph1 | Critical | 6 | PF-01, PF-09 | PF-15 | W3 | To Be Developed | HAI PMO | Per SOW Roadmap PF-02. BOQ pull, retention calc, advance recovery, threshold flags, KPI: processing time.
PF-04 | Procurement | Financial Control | M7: Execution, M4: Governance | G.1–G.4, G.6, SG.6 | 3–5 (Technical Design–Construction) | PM/Contractor (originator), HAI PM, HAI QS, HAI Finance, Approval Authority | Validity check, Freeze check (triggers PF-06 if frozen), Pricing assessment, Spatial Coordination impact, Value-based delegation | Scope/Technical Design/Budget Freeze: variation on frozen scope triggers PF-06 | Yes — budget baseline update to ERP | Ph1 | Critical | 6 | PF-06, PF-01 | PF-03, PF-15 | W4 | To Be Developed | HAI PMO | Per SOW Roadmap PF-03. Variation register, contract value adjustment, ERP commitment update, KPI: variation % trend.
PF-05 | Stage Gate | Financial Control | M4: Governance, M15: ERP | G.1, G.5, G.6, E.2 | 0–2 (Pre-Freeze) | HAI PM, HAI Finance, CEO/Management | Spatial Coordination envelope approval, Cost plan level sign-off (L0→L4), Spatial Coordination freeze activation | This flow ACTIVATES Budget Freeze at Gate 3 | Yes — budget baseline lock to ERP | Ph1 | Critical | 5 | PF-08 | PF-04, PF-06, PF-09 | W6, W9 | To Be Developed | HAI PMO | Covers budget approval at each stage gate. Distinct from variation (PF-04) which modifies post-freeze baseline.
PF-06 | Freeze Exception | Governance Control | M4: Governance Gateways | G.1–G.4, SG.6, SG.7 | 3–6 (Post-Freeze stages) | Requester, HAI PM, HAI Finance, Employer/Senior Authority | Freeze type identification, Technical assessment, Financial impact, Higher-authority approval, Scope-limited lift | Core freeze mechanism — controls all 4 freeze types (Spatial Coordination/Technical Design/Scope/Regulatory) | Yes — if budget freeze exception | Ph1 | Critical | 5 | PF-05, PF-08 | PF-04, PF-09 | W7 | To Be Developed | HAI PMO | Per SOW Roadmap PF-06. Per-item exception only, not blanket. Freeze reinstated after incorporation. Audit trail mandatory.
PF-07 | Authority Submissions | Procurement | M6: Procurement | P.1–P.3, G.6 | 4 (Tender/RFP) | HAI PM, HAI Procurement, HAI Contracts, Approval Authority | RFP preparation, Bid compliance check, Comparison sheet, Recommendation, Value-based approval, Contract/Contract generation | Budget Freeze must be passed (Gate 3) before procurement module unlocks | Yes — Contract/PO push to ERP | Ph2 | High | 8 | PF-05, PF-06, PF-08 | PF-03, PF-15 | W5 | To Be Developed | HAI PMO | Per SOW Roadmap PF-04. Supplier database, weighted scoring, template-based Contract/contract generation, ERP PO creation.
PF-08 | IPC Processing | Governance Control | M4: Governance Gateways | SG.1–SG.7, G.5, G.10 | 0–8 (All stages) | HAI PM, Gate Approver(s), System | Exit checklist validation (all items), Gate approval routing, Freeze activation, Next-stage entry verification | Activates applicable freeze rules per stage (Technical Design @ Stg2, Scope/Spatial Coordination @ Stg3, Regulatory @ Stg3.1, All @ Stg4) | No direct; triggers ERP locks via PF-05/PF-06 | Ph1 | Critical | 4 | PF-01, PF-09, PF-11 | PF-05, PF-06, PF-07 | W6 | To Be Developed | HAI PMO | Per SOW Roadmap PF-05. Master governance flow. 10 gates (0,1,2,3,3.1,4,5,6,7,8). RIBA/RICS/Qatar/GSAS checklist per gate.
PF-09 | Approval Engine | Governance Control | M5: Approval Matrix | G.5–G.9 | 0–8 (All stages) | Requester, System (auto-route), Approver, Delegate | Workflow type identification (7 types), Value threshold check, Delegation check, SLA timer start | Freeze state affects which approval authority is required (higher for exceptions) | No | Ph1 | Critical | 5 | — | PF-03, PF-04, PF-05, PF-07, PF-08 | W9 | To Be Developed | HAI PMO | 7 workflow types: Spatial Coordination, Comparison, Contract, Advance, IPC, Variation, Technical Design/Gateway. Single approver logic. SLA + escalation.
PF-10 | Quality Supervision | Authority & Compliance | M8: Authority Coordination | A.1, SG.4 | 2–6 (Schematic→BCC) | HAI Technical Design Mgr, HAI PM, System | Package completeness check, Submission authorization, Response tracking, Condition clearance, Gate checklist auto-update | Authority approval feeds stage gate exit criteria; Regulatory Freeze activated at Stage 3.1 | No | Ph2 | High | 6 | PF-01, PF-08 | PF-08 | W8 | To Be Developed | HAI PMO | Per SOW Roadmap PF-07. QCDD/Kahramaa/Ashghal/Civil Defense. Status board, SLA tracking, condition action items.
PF-11 | Spatial Coordination Cost | Authority & Compliance | M4: Governance, M8: Authority | SG.5 | 0–7 (Registration→Operations) | HAI Technical Design Mgr, HAI PM, GSAS Trust (external) | Registration, Technical Design Assessment (Part 1 & 2), LoC application, Construction audit, Final certificate | GSAS milestones are stage gate exit criteria; no freeze interaction | No | Ph2 | High | 5 | PF-08, PF-10 | PF-08 | W6, W8 | To Be Developed | HAI PMO | Tracks GSAS lifecycle: registration→concept→design→LoC→construction audit→final cert→operations. Feeds gate checklists.
PF-12 | Risk Register | Quality & Site | M7: Quality & Site | Q.1 | 5 (Construction) | Contractor, HAI QA/QC Engineer, HAI PM | IR submission, Inspection pass/fail, NCR issuance (if fail), Corrective action, Re-inspection, Closure | None direct; NCR closure feeds stage gate exit criteria | No | Ph2 | Critical | 7 | PF-01 | PF-08, PF-14 | W11 | To Be Developed | HAI PMO | Mandatory fields, linked to project/trade/location. NCR tracks: root cause, corrective action, re-inspection, close-out.
PF-13 | Contractor Performance | Quality & Site | M7: Quality & Site | Q.2, Q.3 | 5 (Construction) | Contractor Site Eng, HAI Site PM | Template submission, Photo upload, Progress % entry, S-curve auto-update | None | No | Ph2 | High | 4 | — | PF-08, PF-17 | W11 | To Be Developed | HAI PMO | Templates for daily/weekly. Progress photos mandatory. S-curve: planned vs actual % complete, earned value.
PF-14 | Lessons Learned | Handover & DLP | M9: Handover & DLP | H.1 | 5–6 (Construction→BCC) | Contractor, HAI PM, HAI Technical Design Mgr, FM Team | Package completeness check (as-builts, O&M, warranties, test reports), FM review, BCC prerequisite check | Contract close-out freeze: no further variations unless defect-related | No | Ph3 | High | 6 | PF-01, PF-12 | PF-08, PF-16 | W12 | To Be Developed | HAI PMO | Digital Handover Package in SkyStruct. Links: as-builts, O&M manuals, test reports, warranties, training records.
PF-15 | Handover DLP | Handover & DLP | M9: Handover & DLP | H.2 | 7 (DLP & In Use) | FM Team, HAI PM, Contractor | Defect identification, Assignment to contractor, Rectification, Re-inspection, Closure, Retention release trigger | None; operational phase | Yes — retention release to ERP | Ph3 | High | 6 | PF-14, PF-08 | PF-17 | W12 | To Be Developed | HAI PMO | Defect: create→assign→rectify→re-inspect→close. Warranty expiry alerts. Links to retention release and Final Certificate.
PF-16 | Meeting Action Tracking | Handover & DLP | M9: Handover & DLP | H.3 | 6–8 (BCC→End of Life) | FM Team, HAI PM | O&M document registration, Warranty entry, Expiry alert trigger, Search/retrieval | None; operational phase | No | Ph3 | High | 4 | PF-14 | PF-15 | W12 | To Be Developed | HAI PMO | Searchable by system/equipment. Warranty tracking with alerts. Feeds into Stage 8 EOL decisions.
PF-17 | External Stakeholder Portal | KPI & Analytics | M10: KPI Dashboards, M11: Bottleneck | K.1–K.4 | 0–8 (Continuous) | System (auto), HAI PM, Department Heads | Data aggregation trigger, KPI calculation, RAG status assignment, Bottleneck flag, Dashboard publish | None; reporting layer | Yes — pulls ERP actuals for cost KPIs | Ph2 | Critical | 5 | PF-03, PF-04, PF-08, PF-09, PF-13 | — | W11, W12 | To Be Developed | HAI PMO | 6 core KPIs: approval turnaround, stage compliance, cost deviation, variation trend, IPC time, submittal metrics. Bottleneck: stalled, overloaded, recurring.
PF-18 | Report Generation Export | KPI & Analytics | M12: Contractor Scoring | K.5 | 5–7 (Construction→DLP) | System (auto), HAI PM, HAI Contracts | Score calculation (timeliness, variation rate, defect rate, claims, response time), Scorecard publish, Supplier database update | None; analytical | No | Ph3 | High | 4 | PF-03, PF-04, PF-12, PF-15 | PF-07 | W12 | To Be Developed | HAI PMO | 5 scoring dimensions. Auto-calculated from transactional data. Feeds supplier database for future procurement.
PF-19 | User Role Management | KPI & Analytics | M13: Lessons Learned | K.6 | 0–8 (All stages) | HAI PM, Department Heads, System | Lesson identification, Root cause categorization, Stage linkage, Preventive rule proposal, Rule activation (if converted) | Converted rules may become new gate checklist items or approval conditions | No | Ph2 | High | 5 | PF-08, PF-12, PF-17 | PF-08, PF-09 | W11 | To Be Developed | HAI PMO | Categorized by root cause. Linked to stage. Convertible to preventive workflow rules. Feeds future project gate checklists.
PF-20 | ERP Integration | Integration & Access | M15: ERP Integration | E.1, E.2 | 0–8 (Continuous) | System (auto), HAI IT, ERP Team | Sync trigger (event-based), Data validation, Conflict resolution, Failure fallback (manual + IT alert) | Budget Freeze enforced in both systems simultaneously | Yes — this IS the ERP flow | Ph3 | Critical | 6 | PF-03, PF-04, PF-05, PF-07 | — | W13 | To Be Developed | HAI PMO | Rule: SkyStruct governs decision; ERP executes transaction. Covers: Spatial Coordination, PO, IPC, Actuals, HR. Bi-directional validation.
PF-21 | Dashboard Analytics | Integration & Access | M16: External Access | E.3 | 0–8 (As needed) | HAI PM, HAI IT/Admin, System | Access request, Role assignment (contractor/consultant/authority), Project scoping, Permission grant, Deactivation on project close | None | No | Ph2 | High | 5 | — | PF-01, PF-03, PF-07 | W11 | To Be Developed | HAI PMO | Controlled per party/project. Contractor, consultant, authority access levels. Auto-deactivation on project closure.
PF-22 | Notification Escalation | Predictive Analytics | M14: Analytics | K.7 | 4–5 (Execution) | System (ML/rule-based), HAI PM, HAI Finance | Deviation pattern detection, Alert generation, Risk flag, Escalation recommendation | Flags potential breach of frozen budget baseline | Yes — pulls ERP actuals | Ph4 | High | 4 | PF-17, PF-03, PF-04 | PF-06 | — | To Be Developed | HAI PMO | Rule-based in Ph2, ML in Ph4. Predictive alerts based on variation trends, IPC trajectory, contractor behavior.
PF-23 | Predictive Analytics | Predictive Analytics | M14: Analytics | K.8 | 0–8 (Continuous) | System (ML/rule-based), HAI PM | Anomaly detection (bypass, unsigned deliverable, SLA breach pattern), Flag, Investigation trigger | Detects potential freeze violations or gate bypass attempts | No | Ph4 | High | 4 | PF-08, PF-09, PF-17 | PF-06 | — | To Be Developed | HAI PMO | Bypass flagging, unsigned deliverables, SLA breach patterns, approval timing anomalies. Phase 4 advanced analytics.
PF-24 | Post Go Live Support | Mobilization | MOD023 | Mobilization clause | Stage 0-1 | Contractor, Consultant PM, Resident Engineer, Site Engineers, Safety Officer | Approval of mobilization plan, site setup adequacy, temporary works approval | Technical Design freeze before site establishment | Procurement, Resource Mgmt | Mobilization | High | 12-15 | PF-01 | PF-02, PF-03 | Workshop Phase 1 | Active | Resident Engineer | Starts with contract execution; ends with substantial mobilization completion
PF-25 | Consultant Mobilisation | Testing & Compliance | MOD024 | T&C and GSAS clause | Stage 6-7 | QA/QC Manager, Authority Representatives, Technical Design Manager, Contractor, Engineer (HAI) | System acceptance, GSAS requirements compliance, authority inspection results, certificate issuance | Technical Design freeze before T&C phase | Quality Management, Compliance | Completion | Critical | 18-22 | PF-20, PF-21 | PF-26 | Workshop Phase 3 | Active | QA/QC Manager | Starts 4 weeks before practical completion; ends with all certificates and GSAS certification
PF-26 | Final Account Settlement | Handover | MOD025 | Post-occupancy clause | Stage 7-8 | Facility Manager, Resident Engineer, QA/QC Manager, Contractor, End-Users | Complaint categorization, warranty claim acceptance, snagging resolution, FM handover approval | DLP period baseline setting | Facility Mgmt, Asset Mgmt | DLP & Handover | High | 14-18 | PF-25 | PF-23 | Workshop Phase 3 | Active | Facility Manager | Starts at practical completion; extends through [365 CD] DLP and post-occupancy period
PF-27 | Lessons Learned CI | Payment & Performance | MOD026 | Consultant payment clause | All stages | Consultant PM, Consultant Staff, Finance, Consultant Approval Authority, QS/Cost Manager | Timesheet approval, KPI score verification, deduction justification, payment release authorization | Monthly financial close | AP, Payroll, Performance Mgmt | All phases | High | 10-12 | PF-05 | PF-11 | Workshop Phase 2 | Active | Consultant PM | Starts with each monthly billing cycle; ends with payment posting to GL
PF-28 | TOC Management | Handover | Handover Management | 6 | High | Construction | Manage the complete TOC process from pre-inspection through certificate issuance per FIDIC SC 10.1 | Engineer (HAI), Contractor, Employer, QA/QC Manager, Resident Engineer | 8 | Application completeness, Inspection readiness, Substantial completion determination, Certificate issuance | TOC issuance time, Defect rate on inspection, Certificate cycle time
PF-29 | Final Payment Certificate | Cost | Cost Management | 7 | High | Construction | Manage the final account settlement process from draft final statement through final payment certificate per FIDIC SC 14.11-14.13 | Contractor, QS/Cost Manager, Engineer (HAI), Employer | 8 | Final account review, Contract value determination, Final payment certification | Final account processing time, Payment cycle time, Claim resolution rate
PF-30 | Performance Certificate | Handover | Handover Management | 7-8 | High | Construction | Manage issuance of Performance Certificate upon completion of DLP obligations per FIDIC SC 11.9 | Engineer (HAI), Contractor, QA/QC Manager, Resident Engineer | 7 | DLP expiry verification, Defect completion status, Performance certificate issuance | PC issuance time, DLP defect closure rate, Certificate cycle time
PF-31 | Snag List Resolution | Quality | Quality Management | 5-7 | Medium | Both | Systematic creation, tracking, and resolution of construction defects/snags throughout project lifecycle | QA/QC Manager, Site Engineers, Contractor, Resident Engineer, Consultant PM | 8 | Snag severity classification, Rectification plan approval, Re-inspection acceptance | Snag creation rate, Closure rate, Average resolution time, Cost of snags
PF-24 | Post Go Live Support | [14 empty] | Issued
PF-25 | Consultant Mobilisation | [14 empty] | Issued
PF-26 | Final Account Settlement | [14 empty] | Issued
PF-27 | Lessons Learned CI | [14 empty] | Issued
PF-28 | TOC Management | [14 empty] | Issued
PF-29 | Final Payment Certificate | [14 empty] | Issued
PF-30 | Performance Certificate | [14 empty] | Issued
PF-31 | Snag List Resolution | [14 empty] | Issued

## Summary
Metric | Value
Total Process Flows
── BY PHASE ──
Phase 1 (Foundation)
Phase 2 (Pilot + Ops)
Phase 3 (ERP + Rollout)
Phase 4 (Analytics)
── BY PRIORITY ──
Critical
High
Medium
── BY CATEGORY ──
Document Management
Financial Control
Procurement
Governance Control
Authority & Compliance
Quality & Site
Handover & DLP
KPI & Analytics
Integration & Access
Predictive Analytics
── ERP INTEGRATION ──
Flows requiring ERP sync
Flows without ERP sync
── ESTIMATED TOTAL STEPS ──
Total process steps (all flows)
── SOW TRACEABILITY ──
Total SOW Requirements covered | 60
Stage Gate requirements (SG.1–SG.7) | 7
EDMS & Workflow requirements (D.1–D.9) | 9
Governance & Approval requirements (G.1–G.10) | 10
Correspondence/Procurement/Quality (C, P, Q) | 8
KPI & Analytics (K.1–K.8) | 8
ERP & Access (E.1–E.4) | 4
Handover & DLP (H.1–H.3) | 3
Authority (A.1) | 1

## SOW Traceability
SOW Ref | Requirement Description | Module | Mapped PF-ID(s) | Phase | Coverage Status
SG.1 | RIBA-aligned entry/exit criteria per stage | Gate | PF-08 | Ph1 | Covered
SG.2 | Stage-gate progression blocking | Gate | PF-08 | Ph1 | Covered
SG.3 | RICS Cost Plan checkpoints per stage | Gate | PF-05, PF-08 | Ph1 | Covered
SG.4 | Qatar authority gate tracking | Gate | PF-10 | Ph1 | Covered
SG.5 | GSAS checkpoint integration | Gate | PF-11 | Ph2 | Covered
SG.6 | Freeze enforcement (Spatial Coordination/Technical Design/Scope/Regulatory) | Gate | PF-06, PF-08 | Ph1 | Covered
SG.7 | Gate exception workflow | Gate | PF-06 | Ph1 | Covered
D.1 | Structured repository by project/discipline/type | EDMS | PF-01 | Ph1 | Covered
D.2 | Automated version control | EDMS | PF-01 | Ph1 | Covered
D.3 | Automated document numbering (HAI convention) | EDMS | PF-01 | Ph1 | Covered
D.4 | Cover page validation | EDMS | PF-01 | Ph1 | Covered
D.5 | 8-step document submission/review cycle | Workflow | PF-01 | Ph1 | Covered
D.6 | Review SLA timers (D+3/D+5/D+7) | Workflow | PF-01, PF-09 | Ph1 | Covered
D.7 | Review status codes | Workflow | PF-01 | Ph1 | Covered
D.8 | Transmittal register (in/out) | EDMS | PF-01 | Ph1 | Covered
D.9 | PDF markup | EDMS | PF-01 | Ph1 | Covered
G.1 | Budget Freeze gateway | Freeze | PF-05, PF-06 | Ph1 | Covered
G.2 | Design Freeze gateway | Freeze | PF-06, PF-08 | Ph1 | Covered
G.3 | Scope Freeze gateway | Freeze | PF-06, PF-08 | Ph1 | Covered
G.4 | Regulatory Freeze gateway | Freeze | PF-06, PF-10 | Ph1 | Covered
G.5 | Single accountable approver per stage/process | Approval | PF-09 | Ph1 | Covered
G.6 | 7 configurable workflow types | Approval | PF-09 | Ph1 | Covered
G.7 | SLA timers + escalation | Approval | PF-09, PF-01 | Ph1 | Covered
G.8 | Authority delegation | Approval | PF-09 | Ph1 | Covered
G.9 | Digital signatures | Approval | PF-09 | Ph1 | Covered
G.10 | Full audit trail for every action | Audit | PF-08, PF-09, PF-20 | Ph1 | Covered
C.1 | Letter registry linked to projects | Correspondence | PF-02 | Ph1 | Covered
C.2 | FIDIC correspondence sequence | Correspondence | PF-02 | Ph2 | Covered
P.1 | Supplier/contractor database | Procurement | PF-07, PF-18 | Ph2 | Covered
P.2 | RFP, evaluation, recommendation workflow | Procurement | PF-07 | Ph2 | Covered
P.3 | Contract Award/contract register with alerts | Procurement | PF-07 | Ph2 | Covered
Q.1 | IR/NCR digital forms | Quality | PF-12 | Ph2 | Covered
Q.2 | Daily/weekly site reports with photos | Quality | PF-13 | Ph2 | Covered
Q.3 | S-curve progress tracking | Quality | PF-13 | Ph2 | Covered
A.1 | QCDD/Kahramaa/Ashghal/CD tracker | Authority | PF-10 | Ph2 | Covered
H.1 | Digital Handover Package | Handover | PF-14 | Ph3 | Covered
H.2 | Defect list with assignment/closure | DLP | PF-15 | Ph3 | Covered
H.3 | Warranty/O&M database | DLP | PF-16 | Ph3 | Covered
K.1 | Approval turnaround per department | KPI | PF-17 | Ph2 | Covered
K.2 | Cost deviation from baseline | KPI | PF-17 | Ph2 | Covered
K.3 | IPC processing time | KPI | PF-17, PF-03 | Ph2 | Covered
K.4 | Bottleneck flagging | KPI | PF-17 | Ph2 | Covered
K.5 | Contractor scorecard | Score | PF-18 | Ph3 | Covered
K.6 | Lessons learned database | Lessons | PF-19 | Ph2 | Covered
K.7 | Predictive cost deviation | Analytics | PF-22 | Ph2/4 | Covered
K.8 | Compliance anomaly detection | Analytics | PF-23 | Ph4 | Covered
E.1 | Bi-directional ERP integration | ERP | PF-20 | Ph3 | Covered
E.2 | Financial lock via ERP | ERP | PF-05, PF-20 | Ph3 | Covered
E.3 | External user access | Access | PF-21 | Ph2 | Covered
E.4 | Meeting/calendar + Outlook | Calendar | — | Ph3 | Not Mapped

## Dependency Map
PF-ID | Process Flow Name | Predecessor PF(s) | Downstream PF(s) | Phase | Critical Path?
PF-01 | Document Submission & Review (8-Step Cycle) | — | PF-03, PF-05, PF-07 | Ph1 | YES
PF-02 | Correspondence Management (FIDIC Sequence) | PF-01 | PF-03, PF-11 | Ph1 | No
PF-03 | IPC Certification & Payment | PF-01, PF-09 | PF-15 | Ph1 | No
PF-04 | Variation / Change Order Approval | PF-06, PF-01 | PF-03, PF-15 | Ph1 | No
PF-05 | Spatial Coordination Approval Workflow | PF-08 | PF-04, PF-06, PF-09 | Ph1 | YES
PF-06 | Freeze Exception Workflow | PF-05, PF-08 | PF-04, PF-09 | Ph1 | YES
PF-07 | Procurement (RFP to Contract Award/Contract) | PF-05, PF-06, PF-08 | PF-03, PF-15 | Ph2 | No
PF-08 | Stage-Gate Progression | PF-01, PF-09, PF-11 | PF-05, PF-06, PF-07 | Ph1 | YES
PF-09 | Approval Matrix Routing | — | PF-03, PF-04, PF-05, PF-07, PF-08 | Ph1 | YES
PF-10 | Authority Submission Tracking (DC1/DC2/BCC/NOC) | PF-01, PF-08 | PF-08 | Ph2 | No
PF-11 | GSAS Sustainability Checkpoint Tracking | PF-08, PF-10 | PF-08 | Ph2 | No
PF-12 | Inspection Request (IR) & Non-Conformance Report (NCR) Lifecycle | PF-01 | PF-08, PF-14 | Ph2 | No
PF-13 | Daily/Weekly Site Reporting | — | PF-08, PF-17 | Ph2 | No
PF-14 | Handover Package Assembly | PF-01, PF-12 | PF-08, PF-16 | Ph3 | No
PF-15 | DLP Defect Lifecycle | PF-14, PF-08 | PF-17 | Ph3 | No
PF-16 | Warranty & O&M Database Management | PF-14 | PF-15 | Ph3 | No
PF-17 | KPI Calculation & Dashboard Refresh | PF-03, PF-04, PF-08, PF-09, PF-13 | — | Ph2 | No
PF-18 | Contractor Scoring | PF-03, PF-04, PF-12, PF-15 | PF-07 | Ph3 | No
PF-19 | Lessons Learned Capture & Rule Conversion | PF-08, PF-12, PF-17 | PF-08, PF-09 | Ph2 | No
PF-20 | ERP Bi-Directional Sync Logic | PF-03, PF-04, PF-05, PF-07 | — | Ph3 | YES
PF-21 | External User Access Provisioning | — | PF-01, PF-03, PF-07 | Ph2 | No
PF-22 | Predictive Cost Deviation Alert | PF-17, PF-03, PF-04 | PF-06 | Ph4 | No
PF-23 | Compliance Anomaly Detection | PF-08, PF-09, PF-17 | PF-06 | Ph4 | No

## Document Control
Document Title | HAI Process Flow Register — Master Inventory
Document Reference | HAI-SS-PFR-2026-001
Version | 1.0 — DRAFT
Date | 27 February 2026
Author | HAI PMO
Classification | Confidential — Internal HAI Working Document
Purpose | Master inventory of all process flows required for SkyStruct Platform customization. Every Level 1–4 deliverable traces back to this register.
Traceability | All 60 SOW requirements (Schedule B) are mapped to at least one process flow. See 'SOW Traceability' sheet for full mapping.
Coverage Gap | E.4 (Meeting/Calendar + Outlook) — not mapped to a process flow. This is a configuration item, not a workflow. Handled in platform setup, not a PF deliverable.
Approval
Prepared by: | [HAI PMO — Name]
Reviewed by: | [HAI Project Director — Name]
Approved by: | [CEO / ED — Name]
Date: | [___________]