## Stage-PF Matrix
Stage Gate | Gate Name | PF-01 | PF-02 | PF-03 | PF-04 | PF-05 | PF-06 | PF-07 | PF-08 | PF-09 | PF-10 | PF-11 | PF-12 | PF-13 | PF-14 | PF-15 | PF-16 | PF-17 | PF-18 | PF-19 | PF-20 | PF-21 | PF-22 | PF-23
Gate 0 | Strategic Definition | bar: PF-01 to PF-23
Gate 1 | Preparation & Briefing | P | P | N | N | P | N | N | N | N | N | N | S | N | N | N | P | N | N | N | N | S | N | N
Gate 2 | Concept Design | bar: PF-01 to PF-23
Gate 3 | Spatial Coordination | bar: PF-01 to PF-23
Gate 3.1 | Developed Technical Design | P | N | S | N | N | P | N | N | N | S | N | P | N | N | N | N | N | N | N | N | N | N | N
Gate 4 | Technical Design | P | N | S | P | N | P | N | N | N | N | P | N | N | N | N | N | N | N | N | N | N | N | N
Gate 5 | Manufacturing & Construction | bar: PF-01 to PF-23
Gate 6 | Handover | bar: PF-01 to PF-23
Gate 7 | In Use & DLP | N | P | S | N | N | N | N | P | N | N | P | N | N | P | P | N | N | N | N | N | N | N | N
Gate 8 | Post-Completion | N | N | N | N | N | N | N | N | N | N | N | N | N | P | S | N | N | P | N | N | N | N | P

## Stage-Document Matrix
Stage Gate | Gate Name | Document | Doc Reference | Type | Owner | Status
Gate 0 | Strategic Definition | HAI_A068_Contract_Duration_Matrix.xlsx | HAI-SS-CDM-2026-001 | Configuration | Project Manager | Active
Gate 0 | Strategic Definition | HAI_A068_Communication_Plan.xlsx | HAI-SS-CP-2026-001 | Planning | Communications Officer | Active
Gate 0 | Strategic Definition | HAI_A068_Communication_Management_Plan.docx | HAI-SS-CMP-2026-001 | Planning | Communications Officer | Active
Gate 0 | Strategic Definition | HAI_A068_Document_Numbering_System.xlsx | HAI-SS-DNS-2026-001 | Configuration | Documentation Officer | Active
Gate 0 | Strategic Definition | HAI_Process_Flow_Register.xlsx | HAI-SS-PFR-2026-001 | Reference | Process Owner | Active
Gate 0 | Strategic Definition | HAI_Level1_Process_Flow_Diagrams_CONTRACTUAL.docx | HAI-SS-L1-2026-001 | Technical | Systems Architect | Contractual
Gate 0 | Strategic Definition | HAI_Level2_UI_Wireframe_Specifications_CONTRACTUAL.docx | HAI-SS-L2-2026-001 | Technical | UI/UX Technical Designer | Contractual
Gate 0 | Strategic Definition | HAI_Level3_Data_Model_CONTRACTUAL.xlsx | HAI-SS-L3-2026-001 | Technical | Data Architect | Contractual
Gate 0 | Strategic Definition | HAI_Level4_Acceptance_Checklists_CONTRACTUAL.xlsx | HAI-SS-L4-2026-001 | Acceptance | QA Lead | Contractual
Gate 0 | Strategic Definition | HAI_User_Roles_Permissions_Matrix.xlsx | HAI-SS-URP-2026-001 | Configuration | Security Officer | Active
Gate 0 | Strategic Definition | HAI_Workflow_Engine_Rules.xlsx | HAI-SS-WER-2026-001 | Configuration | Process Owner | Active
Gate 0 | Strategic Definition | HAI_Notification_Alert_Rules.xlsx | HAI-SS-NAR-2026-001 | Configuration | Systems Administrator | Active
Gate 0 | Strategic Definition | HAI_Form_Template_Specifications.xlsx | HAI-SS-FTS-2026-001 | Configuration | Business Analyst | Active
Gate 0 | Strategic Definition | HAI_Dashboard_Reporting_Specifications.xlsx | HAI-SS-DRS-2026-001 | Configuration | BI Lead | Active
Gate 0 | Strategic Definition | HAI_System_Configuration_Document.xlsx | HAI-SS-SCD-2026-001 | Configuration | Systems Architect | Active
Gate 0 | Strategic Definition | HAI_Integration_Specification.xlsx | HAI-SS-IS-2026-001 | Technical | Integration Lead | Active
Gate 0/1 | Strategic Definition/Preparation & Briefing | HAI_Migration_Specification.xlsx | HAI-SS-MS-2026-001 | Technical | Data Lead | Active
Gate 0/1 | Strategic Definition/Preparation & Briefing | HAI_UAT_Test_Plan.xlsx | HAI-SS-UTP-2026-001 | Testing | QA Lead | Active
Gate 0 | Strategic Definition | HAI_Stage_Based_Organization.xlsx | HAI-SS-SBO-2026-001 | Reference | Project Manager | Active
Gate 1 | Preparation & Briefing | Process Flow Diagrams (PF-01-23) | HAI-SS-PF-2026-001 | Technical | Process Owner | Active
Gate 0 | Strategic Definition | HAI_Cross_Link_Index.xlsx | HAI-SS-CLI-2026-001 | Reference | Documentation Officer | Active

## Configurator Checklist
Stage Gate | Configuration Task | Module/PF | Priority | Predecessor | Estimated Effort | Notes
Gate 0 | Create project and initialize system | System | Critical | None | 4 hours | Set up project structure
Gate 0 | Set up user roles and permissions | PF-19 | Critical | Create project | 6 hours | Configure role matrix
Gate 0 | Configure document numbering system | PF-01 | Critical | Create project | 3 hours | Import DNS configuration
Gate 0 | Set up workflow engine rules | PF-05 | Critical | User roles | 8 hours | Program stage gate logic
Gate 0 | Configure notification/alert rules | PF-22 | Critical | Workflow rules | 4 hours | Set SLA timers
Gate 0 | Import contract data | PF-02 | High | Document system | 3 hours | Load contract terms
Gate 0 | Configure stage gates and transitions | PF-05 | Critical | Workflows | 6 hours | Set gate prerequisites
Gate 0 | Set up integrations | All | High | Project setup | 8 hours | API/middleware config
Gate 0 | Configure dashboard/reporting | PF-21 | High | Data model | 6 hours | Set up KPI tiles
Gate 0 | Run smoke tests | System | High | All config | 4 hours | Verify basic functions
Gate 1 | Activate PF-01 (Document Management) | PF-01 | Critical | Gate 0 complete | 2 hours | Enable document uploads
Gate 1 | Activate PF-02 (Correspondence) | PF-02 | Critical | Gate 0 complete | 2 hours | Enable messaging
Gate 1 | Activate PF-05 (Gate Progression) | PF-05 | Critical | Gate 0 complete | 1 hour | Verify progression rules
Gate 1 | Verify PF-16 (Meetings) setup | PF-16 | High | Gate 0 complete | 2 hours | Test meeting creation
Gate 1 | Run Gate 1 acceptance tests | System | High | All activations | 4 hours | Preparation & Briefing checklist
Gate 2 | Activate PF-04 (Procurement) | PF-04 | Critical | Gate 1 complete | 3 hours | Procurement workflows
Gate 2 | Activate PF-11 (Spatial Coordination Management) | PF-11 | Critical | Gate 1 complete | 3 hours | Spatial Coordination setup
Gate 2 | Activate PF-12 (Risk Management) | PF-12 | Critical | Gate 1 complete | 2 hours | Risk register
Gate 2 | Run Gate 2 acceptance tests | System | High | All activations | 4 hours | Concept Design checklist
Gate 3 | Verify PF-08 (IPC) configuration | PF-08 | Critical | Gate 2 complete | 2 hours | Initial IPC template
Gate 3 | Activate PF-11 budget approval | PF-11 | Critical | Gate 2 complete | 2 hours | Approval workflow
Gate 3 | Run Gate 3 acceptance tests | System | High | All activations | 4 hours | Spatial Coordination checklist
Gate 3.1 | Activate PF-06 (Design Freeze Mgmt) | PF-06 | Critical | Gate 3 complete | 3 hours | Freeze controls
Gate 3.1 | Activate PF-10 (Quality) | PF-10 | High | Gate 3 complete | 2 hours | QA workflows
Gate 3.1 | Run Gate 3.1 acceptance tests | System | High | All activations | 4 hours | Technical Design Dev checklist
Gate 4 | Finalize PF-04 tender documents | PF-04 | Critical | Gate 3.1 complete | 4 hours | Tender package
Gate 4 | Finalize PF-06 design freeze | PF-06 | Critical | Gate 3.1 complete | 2 hours | Lock design
Gate 4 | Run Gate 4 acceptance tests | System | High | All activations | 4 hours | Technical Design checklist
Gate 5 | Activate all process flows | All | Critical | Gate 4 complete | 4 hours | Full system active
Gate 5 | Activate PF-07 (Site Management) | PF-07 | Critical | Gate 4 complete | 3 hours | Site features
Gate 5 | Activate PF-13 (Quality Scoring) | PF-13 | Critical | Gate 4 complete | 3 hours | Scoring matrix
Gate 5 | Run Gate 5 acceptance tests | System | High | All activations | 4 hours | Manufacturing & Construction checklist
Gate 6 | Activate PF-15 (Handover) | PF-15 | Critical | Gate 5 complete | 3 hours | Handover workflows
Gate 6 | Activate PF-10 (Snagging) | PF-10 | Critical | Gate 5 complete | 2 hours | Snagging list
Gate 6 | Run Gate 6 acceptance tests | System | High | All activations | 4 hours | Handover checklist
Gate 7 | Activate PF-15 (DLP) | PF-15 | Critical | Gate 6 complete | 2 hours | DLP tracking
Gate 7 | Finalize PF-08 (Final IPC) | PF-08 | Critical | Gate 6 complete | 2 hours | Final payment
Gate 7 | Run Gate 7 acceptance tests | System | High | All activations | 4 hours | DLP checklist
Gate 8 | Activate PF-14 (Lessons Learned) | PF-14 | Critical | Gate 7 complete | 2 hours | Archive prep
Gate 8 | Finalize archive and audit | PF-23 | High | Gate 7 complete | 3 hours | Complete audit
Gate 8 | Run Gate 8 acceptance tests | System | High | All activations | 4 hours | Post-Completion checklist

## Gate Prerequisites
Gate | Prerequisite | Evidence Required | Responsible | Verification Method | PF Reference
Gate 1 | Project initialization complete | Project code assigned, users created | Project Manager | System verification | PF-19
Gate 1 | Communication plan approved | Signed communication plan | Communications Officer | Document review | PF-02
Gate 1 | Contract terms loaded | Contract extracted and verified | Legal/Contracts | Data audit | PF-02
Gate 2 | Gate 1 completion verified | Gate 1 sign-off report | Project Manager | Report review | PF-05
Gate 2 | Consultant appointments finalized | Appointment letters received | Project Manager | Document review | PF-04
Gate 2 | Risk register initiated | Risk register created with 10+ risks | Risk Manager | System check | PF-12
Gate 3 | Gate 2 completion verified | Gate 2 sign-off report | Project Manager | Report review | PF-05
Gate 3 | Spatial Coordination L1-L2 approved | Approved cost plan | Finance Director | Document review | PF-11
Gate 3 | Change control procedures active | CCN register established | Change Manager | System check | PF-06
Gate 3.1 | Gate 3 completion verified | Gate 3 sign-off report | Project Manager | Report review | PF-05
Gate 3.1 | Preliminary design complete | Technical Design documents reviewed | Technical Design Lead | Document review | PF-01
Gate 3.1 | Technical Design freeze criteria defined | Freeze matrix documented | Technical Design Manager | Document review | PF-06
Gate 4 | Gate 3.1 completion verified | Gate 3.1 sign-off report | Project Manager | Report review | PF-05
Gate 4 | Technical Design ready for tender | Technical Design freeze confirmation | Technical Design Lead | System confirmation | PF-06
Gate 4 | Tender documents prepared | Tender package complete | Procurement Lead | Document review | PF-04
Gate 5 | Gate 4 completion verified | Gate 4 sign-off report | Project Manager | Report review | PF-05
Gate 5 | Contractor appointed | Contract signed | Contracts Lead | Document review | PF-04
Gate 5 | Site access confirmed | Site handover protocol completed | Site Manager | System check | PF-07
Gate 6 | Gate 5 completion verified | Gate 5 sign-off report | Project Manager | Report review | PF-05
Gate 6 | Practical completion approved | PC certificate issued | Architect | Document review | PF-15
Gate 6 | Snagging list cleared | Final snagging report | QA Lead | Document review | PF-10
Gate 7 | Gate 6 completion verified | Gate 6 sign-off report | Project Manager | Report review | PF-05
Gate 7 | Final account agreed | Final account document signed | Finance Director | Document review | PF-11
Gate 7 | DLP expiry date set | DLP end date confirmed | Contracts Lead | System check | PF-15
Gate 8 | Gate 7 completion verified | Gate 7 sign-off report | Project Manager | Report review | PF-05
Gate 8 | Lessons learned documented | Lessons report completed | Project Manager | Document review | PF-14
Gate 8 | Project archive complete | Archive sign-off | Documentation Officer | System check | PF-23

## Cross-Reference
Document ID | Document Name | Primary Stage | Related Stages | PF References | Owner | Location
HAI-SS-SBO-2026-001 | Stage-Based Organization | Gate 0 | All | All | Project Manager | /mnt/ERP/
HAI-SS-L1-2026-001 | Level 1 Process Flows (CONTRACTUAL) | Gate 0 | Gates 1-8 | PF-01 to PF-23 | Process Owner | /mnt/ERP/
HAI-SS-L2-2026-001 | Level 2 UI Wireframes (CONTRACTUAL) | Gate 0 | Gates 2-6 | PF-01, PF-16, PF-21 | UI/UX Technical Designer | /mnt/ERP/
HAI-SS-L3-2026-001 | Level 3 Data Model (CONTRACTUAL) | Gate 0 | Gates 1-8 | All PFs | Data Architect | /mnt/ERP/
HAI-SS-L4-2026-001 | Level 4 Acceptance Checklists (CONTRACTUAL) | Gate 0 | Gates 0-8 | All PFs | QA Lead | /mnt/ERP/
HAI-SS-CDM-2026-001 | Contract Duration Matrix | Gate 0 | All | PF-05 | Project Manager | /mnt/ERP/
HAI-SS-CP-2026-001 | Communication Plan | Gate 0 | All | PF-02, PF-16 | Communications Officer | /mnt/ERP/
HAI-SS-CMP-2026-001 | Communication Management Plan | Gate 0 | All | PF-02, PF-16 | Communications Officer | /mnt/ERP/
HAI-SS-DNS-2026-001 | Document Numbering System | Gate 0 | All | PF-01 | Documentation Officer | /mnt/ERP/
HAI-SS-PFR-2026-001 | Process Flow Register | Gate 0 | All | All PFs | Process Owner | /mnt/ERP/
HAI-SS-URP-2026-001 | User Roles & Permissions | Gate 0 | Gates 0-8 | PF-19 | Security Officer | /mnt/ERP/
HAI-SS-WER-2026-001 | Workflow Engine Rules | Gate 0 | Gates 1-8 | PF-05 | Process Owner | /mnt/ERP/
HAI-SS-NAR-2026-001 | Notification/Alert Rules | Gate 0 | Gates 1-8 | PF-22 | Systems Admin | /mnt/ERP/
HAI-SS-FTS-2026-001 | Form Template Specifications | Gate 0 | Gates 1-8 | All PFs | Business Analyst | /mnt/ERP/
HAI-SS-DRS-2026-001 | Dashboard/Reporting Specs | Gate 0 | Gates 1-8 | PF-21 | BI Lead | /mnt/ERP/
HAI-SS-SCD-2026-001 | System Configuration Document | Gate 0 | Gates 0-8 | All PFs | Systems Architect | /mnt/ERP/
HAI-SS-IS-2026-001 | Integration Specification | Gate 0 | Gates 0-8 | All PFs | Integration Lead | /mnt/ERP/
HAI-SS-MS-2026-001 | Migration Specification | Gate 0/1 | Gates 0-1 | PF-01, PF-02 | Data Lead | /mnt/ERP/
HAI-SS-UTP-2026-001 | UAT Test Plan | Gate 0/1 | Gates 0-8 | All PFs | QA Lead | /mnt/ERP/
HAI-SS-CLI-2026-001 | Cross-Link Index | Gate 0 | All | All | Documentation Officer | /mnt/ERP/
HAI-SS-PF-2026-001 | Process Flow Diagrams (PF-01-23) | Gate 1 | Gates 1-8 | All | Process Owner | /mnt/ERP/Flowcharts/