## Slide 1
HOUSE OF ARCHITECTURE & INTERIORS
ARADA GOVERNANCE
From Drawing to Breathing
Governance as Amanah
Stages 0 through 8 | RIBA Plan of Work 2020 | 31 Process Flows
“Indeed, Allah commands you to render trusts to whom they are due.”
— An-Nisa 4:58
Presented by: Hasan Mollamahmutoglu
Chief Governance Architect | Employer's Representative
March 2026
1/18

## Slide 2
AGENDA
ARADA GOVERNANCE
1
The Challenge
Why governance matters for HAI projects
2
The Solution
SkyStruct Platform — what it does
3
Full Lifecycle Coverage
Stages 0–8, mapped to RIBA/RICS
4
31 Process Flows
Every governance process, categorized
5
Dual Contract Architecture
Construction + Consultancy coverage
6
Governance Framework
Approvals, escalation, stage gates, freezes
7
Deliverables & Implementation
48+ documents, phased rollout
8
Next Steps & Q&A
Discussion
TIME ALLOCATION
Presentation: ~30 min
Q&A Session: ~10 min
Total: 40 min
HAI | ARADA Governance | SkyStruct Platform | Confidential
2/18

## Slide 3
THE CHALLENGE
ARADA GOVERNANCE
Fragmented Controls
Spreadsheets, emails, and manual tracking across construction and consultancy contracts. No single source of truth.
Time-Bar Risk
FIDIC contractual deadlines (28-day, 42-day, 56-day notices) managed manually — missed deadlines mean forfeited rights.
No Stage Visibility
No structured gate-based progression. Projects jump from design to construction without formal checkpoints.
Dual Contract Complexity
Both construction (FIDIC Red Book) and supervision consultancy contracts require parallel governance — currently unlinked.
HAI | ARADA Governance | SkyStruct Platform | Confidential
3/18

## Slide 4
THE SOLUTION: FROM DRAWING TO BREATHING
ARADA GOVERNANCE
A single, integrated platform that governs every decision, document, and deadline — from pre-inception to post-completion.
31
Process Flows
Every governance process
codified and automated
10
Stage Gates
0 through 8 checkpoints
RIBA/RICS aligned
5
Escalation Levels
L1 to L5 with
auto-triggered alerts
48+
Documents
Complete implementation
package delivered
KEY DIFFERENTIATOR
Parametric contract configuration — zero hardcoded values. Every contractual threshold, duration, and deadline is configurable per project. Supports both FIDIC 1999 Red Book (construction) and bespoke consultancy contracts simultaneously.
HAI | ARADA Governance | SkyStruct Platform | Confidential
4/18

## Slide 5
FULL LIFECYCLE COVERAGE: STAGES 0–8
ARADA GOVERNANCE
Every stage of the project lifecycle is governed — aligned to RIBA Plan of Work and RICS lifecycle stages.
Gate 0
Strategic Def.
RIBA 0
Strategic
Definition
Gate 1
Prep & Brief
RIBA 1
Preparation
& Briefing
Gate 2
Concept Design
RIBA 2
Concept
Design
Gate 3
Spatial Coord.
RIBA 3
Spatial
Coordination
Gate 3.1
Developed Dsgn
RIBA 3+
Developed
Design
Gate 4
Technical Dsgn
RIBA 4
Technical
Design
Gate 5
Construction
RIBA 5
Manufacturing
& Construction
Gate 6
Handover
RIBA 6
Handover
Gate 7
Use
RIBA 7
Use
Gate 8
Post-Completion
Post-RIBA
Review &
Lessons
HAI STAGE GATES
RIBA / RICS ALIGNMENT
RIBA PLAN OF WORK 2020 ALIGNMENT
Stage 0: Strategic Definition | Stage 1: Preparation & Briefing | Stage 2: Concept Design | Stage 3: Spatial Coordination | Stage 4: Technical Design | Stage 5: Manufacturing & Construction | Stage 6: Handover | Stage 7: Use
Each gate has RIBA-defined outcomes, formal prerequisites, exit checklists, freeze activation triggers, and configurable approval routing — all automated within SkyStruct.
HAI | ARADA Governance | SkyStruct Platform | Confidential
5/18

## Slide 6
STAGES 0–2: DEFINITION, BRIEFING & CONCEPT
ARADA GOVERNANCE
RIBA 0–2
Stage 0 — Strategic Definition
● Business case & strategic brief developed
✓ Project budget & programme aligned
● Site information gathered & appraised
● Platform initialized: 60+ configurable parameters
● Contract terms loaded (construction + consultancy)
Stage 1 — Preparation & Briefing
● Project Brief developed and approved
✓ Feasibility studies completed
● Procurement strategy defined
● Project team assembled, roles assigned (PF-19)
● Document management & correspondence live (PF-01/02)
Stage 2 — Concept Design
○ Concept Design prepared and approved
○ Cost Plan aligned to project budget (PF-05)
○ Outline structural & building services design
○ Planning strategy agreed
● Risk register initiated with design risks (PF-12)
✓ GREEN = Approved ● AMBER = In Progress ○ = Pending
HAI | ARADA Governance | SkyStruct Platform | Confidential
6/18

## Slide 7
STAGES 3–4: COORDINATION & TECHNICAL DESIGN
ARADA GOVERNANCE
RIBA 3–4
Stage 3 — Spatial Coordination
○ Spatially coordinated design completed
○ Updated Cost Plan & cost checks (PF-05)
○ Architectural, structural & MEP coordinated
○ Planning application submitted (if applicable)
✓ Budget Freeze workflow defined (PF-06)
Stage 3+ — Developed Design
● Design Freeze Exception workflow defined (PF-06)
● Quality supervision process defined (PF-12)
○ Specialist subcontractor design coordination
● Design freeze criteria formally defined
● Change control procedures established
Stage 4 — Technical Design
○ Technical design for manufacture & construction
○ Construction strategy determined
○ Specialist subcontractor designs completed
● Procurement workflow defined: RFP to award (PF-07)
● Variation/change order workflow defined (PF-04)
✓ GREEN = Approved ● AMBER = In Progress ○ = Pending
HAI | ARADA Governance | SkyStruct Platform | Confidential
7/18

## Slide 8
STAGE 5: MANUFACTURING & CONSTRUCTION
ARADA GOVERNANCE
RIBA 5
The most process-intensive stage — all 31 process flows are active. Two parallel execution tracks operate simultaneously.
TRACK A: EXECUTION
PF-01 Document Review & Submission
PF-02 FIDIC Correspondence
PF-10 Authority Submissions (DC1/DC2/BCC/NOC)
PF-12 Inspection Requests & NCR Lifecycle
PF-13 Daily/Weekly Site Reporting
PF-24 Mobilization Management
PF-31 Snag List Creation & Resolution
TRACK B: COMMERCIAL
PF-03 IPC Certification & Payment
PF-04 Variation / Change Order
PF-05 Budget Approval
PF-06 Freeze Exception
PF-09 Approval Matrix Routing
PF-27 Consultant Performance & Payment
PF-22 Predictive Cost Deviation Alerts
HAI | ARADA Governance | SkyStruct Platform | Confidential
8/18

## Slide 9
STAGES 6–8: HANDOVER, USE & POST-COMPLETION
ARADA GOVERNANCE
RIBA 6–7+
Stage 6 — Handover
○ Building handed over to Employer
● TOC management workflow defined (PF-28)
● Handover package workflow defined (PF-14)
● Snag list workflow defined (PF-31)
● T&C / GSAS compliance workflow defined (PF-25)
Stage 7 — Use
○ Building in use — FM active
● DLP defect lifecycle workflow defined (PF-15)
● Post-Occupancy workflow defined (PF-26)
● Final Account workflow defined (PF-29)
● Performance Certificate workflow defined (PF-30)
Stage 8 — Post-Completion Review
● Lessons learned workflow defined (PF-19)
● Contractor scoring workflow defined (PF-18)
● Compliance anomaly detection defined (PF-23)
○ Project archive sign-off & audit trail
○ Outcomes fed back to future project briefs
✓ GREEN = Approved ● AMBER = In Progress ○ = Pending
HAI | ARADA Governance | SkyStruct Platform | Confidential
9/18

## Slide 10
31 PROCESS FLOWS — ALL BUILT
ARADA GOVERNANCE
Document & Correspondence
● PF-01 Document Review (8-Step Cycle)
● PF-02 FIDIC Correspondence
Financial Control
● PF-03 IPC Certification & Payment
● PF-04 Variation / Change Order
● PF-05 Budget Approval
● PF-29 Final Account & Payment
Governance & Approval
● PF-06 Freeze Exception
● PF-08 Stage-Gate Progression
● PF-09 Approval Matrix Routing
Procurement & Site
● PF-07 Procurement (RFP to Award)
● PF-10 Authority Submissions
● PF-11 GSAS Compliance
● PF-24 Mobilization Management
Quality & Inspection
● PF-12 IR & NCR Lifecycle
● PF-13 Site Reporting
● PF-25 Testing & Commissioning
● PF-31 Snag List Management
Handover & DLP
● PF-14 Handover Package
● PF-15 DLP Defect Lifecycle
● PF-16 Warranty & O&M Database
● PF-26 Post-Occupancy Services
● PF-28 TOC Management
● PF-30 Performance Certificate
KPI & Analytics
● PF-17 KPI Dashboard
● PF-18 Contractor Scoring
● PF-19 Lessons Learned
● PF-22 Predictive Cost Alerts
● PF-23 Compliance Anomaly Detection
Integration & Access
● PF-20 ERP Bi-Directional Sync
● PF-21 External User Access
● PF-27 Consultant Performance
HAI | ARADA Governance | SkyStruct Platform | Confidential
10/18

## Slide 11
DUAL CONTRACT ARCHITECTURE
ARADA GOVERNANCE
Both construction and consultancy contracts are governed in parallel through a unified platform — not separate systems.
CONSTRUCTION CONTRACT
• FIDIC 1999 Red Book with Particular Conditions
• Interim Payment Certificates (IPC) — Track B
• Variation Orders with freeze-check logic
• Time-bar management: 28/42/56/84-day notices
• Contractor performance scoring (5 dimensions)
• Taking Over Certificate, Final Account, Performance Certificate
• Snagging, DLP defect lifecycle, retention release
CONSULTANCY CONTRACT
• Supervision consultancy (25 articles, 15 mgmt areas)
• Consultant monthly payment & KPI scoring (PF-27)
• Timesheet verification and deduction logic
• Staff mobilization/demobilization tracking
• Deliverable quality assessment
• Insurance, liability, and warranty compliance
• Contract close-out and final account
HAI | ARADA Governance | SkyStruct Platform | Confidential
11/18

## Slide 12
GOVERNANCE FRAMEWORK
ARADA GOVERNANCE
Stage Gate
Progression
10 gates (0–8)
with formal prerequisites,
exit checklists,
and automated
freeze activation.
4-Type
Freeze Control
Budget, Design,
Scope, Regulatory.
Exception-only changes
with higher-authority
approval required.
5-Level
Escalation
L1: D-2 (gentle)
L2: D-5 (formal)
L3: D-10 (senior)
L4: 24h (critical)
L5: 48h (time-bar)
7-Type
Approval Matrix
Budget, Comparison,
Contract, Advance,
IPC, Variation,
Design/Scope.
Value-threshold routing.
HAI | ARADA Governance | SkyStruct Platform | Confidential
12/18

## Slide 13
DELIVERABLES: 48+ DOCUMENTS — ALL BUILT
ARADA GOVERNANCE
Master Governance
(001–008)
8 documents
● Implementation Guidebook
● WBS Schedule
● Process Flow Register
● Cross-Link Index
● Stage-Based Organization
● Interactive Mind Map
● Roadmap & SkyStruct SOW
Configuration
(011–016)
6 documents
● System Configuration (60+ params)
● User Roles & Permissions
● Workflow Engine Rules
● Notification/Alert Rules
● Form Template Specs
● Dashboard/Reporting Specs
Process Documentation
(021–029)
9 documents
● PF Action Sheets (31 PFs)
● L1 Process Flow Narratives
● L2 UI Wireframe Specs
● L3 Data Model
● L4 Acceptance Checklists
● (Both standard + legacy versions)
Contract & FIDIC
(031–037)
7 documents
● FIDIC Response Action Cards
● Contract Duration Matrix
● Escalation Procedures
● Gate Passage Checklists
● Document Numbering System
● Communication Plan & CMP
HAI | ARADA Governance | SkyStruct Platform | Confidential
13/18

## Slide 14
IMPLEMENTATION ROADMAP
ARADA GOVERNANCE
Phase 1 | Weeks 1–8
Core Platform
PF-01, 02, 03, 04, 05, 06, 08, 09
Document management, correspondence,
financial controls, stage gates,
approval matrix, freeze controls
Phase 2 | Weeks 9–16
Extended Modules
PF-07, 10, 11, 12, 13, 17, 19, 21
Procurement, authorities, GSAS,
quality, site reporting, KPI,
lessons learned, external access
Phase 3 | Weeks 17–22
Handover & DLP
PF-14, 15, 16, 18, 20, 24, 25
Handover package, DLP defects,
warranty, contractor scoring,
ERP sync, mobilization, T&C
Phase 4 | Weeks 23–28
Advanced Analytics
PF-22, 23, 26, 27, 28, 29, 30, 31
Predictive analytics, compliance AI,
post-occupancy, consultant payment,
TOC, final account, snag list
TOTAL: 28 weeks | 4 phases | Incremental activation | UAT at each gate | Full platform operational by Gate 5
Each phase includes configuration, testing, training, and formal acceptance before proceeding to the next.
HAI | ARADA Governance | SkyStruct Platform | Confidential
14/18

## Slide 15
IMPLEMENTATION SCHEDULE — GANTT CHART
ARADA GOVERNANCE
M1
M2
M3
M4
M5
M6
M7
M8
M9
M10
Phase 1 — Core Platform
PF-01–09: Docs, Finance, Gates, Approvals
UAT & Sign-off
Phase 2 — Extended Modules
PF-07–21: Procurement, Quality, KPI
UAT & Sign-off
Phase 3 — Handover & DLP
PF-14–25: Handover, DLP, Mobil, T&C
Phase 4 — Advanced Analytics
PF-22–31: Predictive, Compliance, Final
SkyStruct Platform Integration
ERP Integration (Finance/Procurement)
Training & Onboarding (All Teams)
Pilot Project (1st Live Project)
★ FULL OPERATIONAL GO-LIVE
▼ TODAY
█ Navy = Core █ Teal = Extended █ Amber = Handover █ Gold = Analytics █ Purple = SkyStruct █ Red = ERP █ Green = Pilot | 40 weeks total
HAI | ARADA Governance | SkyStruct Platform | Confidential
15/18

## Slide 16
WHERE WE ARE TODAY
ARADA GOVERNANCE
● BUILT — Governance Framework In Progress
● 31 Process Flows
All defined, documented with action sheets, narratives, wireframes, data models, acceptance checklists
● 48+ Documents
Implementation Guidebook, System Configuration, FIDIC Action Cards, Gate Checklists, Communication Plans
✓ Feasibility Studies
Completed and approved by CEO
✓ Budget & Programme
Aligned and approved — budget freeze baseline established
✓ Schedule
WBS and implementation roadmap approved
● 10 Stage Gates
RIBA Plan of Work 2020 aligned, prerequisites defined, freeze triggers mapped
● 23 Process Flow Diagrams
Visual flowcharts (.drawio) for PF-01 through PF-23
● Interactive Mind Map
D3.js live navigation of entire governance structure
○ NEXT — Implementation & Execution
○ Submittal Cover Page Templates
Master hierarchy of all submittal types mapped to FIDIC clauses and QCS 2014
○ SkyStruct Platform Configuration
Load all 60+ parameters, workflow rules, notification triggers into live system
○ User Training & Onboarding
Role-based training for PM, QS, Site, Finance, Admin teams
○ UAT Execution
Run acceptance checklists per gate, validate each PF in live environment
○ ERP Integration Go-Live
Bi-directional sync activation with finance/procurement ERP
○ RIBA Correction to Source Docs
Propagate RIBA 2020 stage names to all source documents
○ Project-Specific Configuration
Load actual contract values, milestones, team assignments per project
○ Pilot Project Launch
First project goes live on SkyStruct with full governance
HAI | ARADA Governance | SkyStruct Platform | Confidential
16/18

## Slide 17
EXPECTED OUTCOMES
ARADA GOVERNANCE
Zero Time-Bar
Exposure
Every contractual deadline
automatically tracked.
5-level escalation ensures
no notice is ever missed.
Full Audit
Trail
Every decision, approval, and
change logged with timestamp,
user, and rationale.
Claims-ready documentation.
Real-Time
Visibility
CEO/Board dashboards with
live KPIs: cost deviation,
schedule variance, approval
turnaround, risk status.
Scalable
Governance
Parametric configuration means
the same platform governs any
HAI project — residential,
commercial, mixed-use.
BOTTOM LINE
From Drawing to Breathing — every stage covered, every deadline enforced, every decision traceable. This is governance as amanah.
HAI | ARADA Governance | SkyStruct Platform | Confidential
17/18

## Slide 18
Questions & Discussion
“And do good. Indeed, Allah loves the doers of good.”
— Al-Baqarah 2:195
Thank you for your time.
Hasan Mollamahmutoglu
Chief Governance Architect | Employer's Representative
House of Architecture & Interiors | ARADA Governance | Qatar
18/18