## Contract Parameters
Parameter Name | Construction Contract Default | Consultancy Contract Default | Description | Contractual Basis
IPC Certification Period | [28 CD] | [4 CD] | Interim Payment Certificate certification timeframe | FIDIC 1999 Clause 14.2 / Consultancy T&C
Payment Period After Certification | [56 CD] | [15 WD] | Time allowed for payment after IPC certification | FIDIC 1999 Clause 14.3
Claims Notice Period | [28 CD] | [28 CD] | Notice period for submission of contractual claims | FIDIC 1999 Clause 20.1
Claims Detailed Particulars Period | [42 CD] | [42 CD] | Period to submit detailed particulars after notice | FIDIC 1999 Clause 20.1
Variation Notice Period | [14 CD] | [14 CD] | Notice period for issuing variation instructions | FIDIC 1999 Clause 13.2
NOD Period | [56 CD] | [56 CD] | Notice of Dispute response timeframe | FIDIC 1999 Clause 20.4
DLP Period | [365 CD] | [365 CD] | Defects Liability Period after practical completion | FIDIC 1999 Clause 18.4
Retention Percentage | [10%] | [5%] | Percentage of IPC value retained | FIDIC 1999 Clause 14.4
Retention Release After TOC | [50%] | [50%] | Retention released at Taking Over of Contract | FIDIC 1999 Clause 14.4
Retention Release After DLP | [50%] | [50%] | Remaining retention released after DLP completion | FIDIC 1999 Clause 14.4
Delay Damages Rate | [Rate/Day] | [Rate/Day] | Daily penalty for schedule delay | FIDIC 1999 Clause 8.8
Contract Value | [Amount] | [Amount] | Total contract value in QAR | FIDIC 1999 Clause 14.1
Completion Period | [Duration in CD] | [Duration in CD] | Overall project completion timeframe | FIDIC 1999 Clause 8.2
Time-bar Period for Claims | [28 CD] | [28 CD] | Maximum period to submit claims after occurrence | FIDIC 1999 Clause 20.1
Court Filing Period | [Jurisdiction-specific] | [Jurisdiction-specific] | Deadline for court filing after arbitration | Qatar Civil Code
Consultant Monthly Payment Window | [15 WD after approval] | [15 WD after approval] | Payment window for monthly consultant invoices | Consultancy T&C Clause 5
Consultant Performance Deduction Rate | [% per KPI failure] | [% per KPI failure] | Performance-based payment deduction per KPI | Performance Agreement
GSAS Compliance Target | [Star Rating] | [Star Rating] | GSAS certification target level | Qatar Building Code
Mobilization Period | [Duration] | [Duration] | Time allowed for contractor/consultant mobilization | Contract conditions
Demobilization Period | [Duration] | [Duration] | Time allowed for demobilization after completion | Contract conditions
Post-Occupancy Service Period | [Duration] | [Duration] | Warranty and maintenance period post-handover | Contract conditions
Testing & Commissioning Window | [Duration] | [Duration] | Time allocated for T&C and GSAS verification | FIDIC 1999 Clause 12
Escalation L1 Trigger | [D-2] | [D-2] | First escalation at D-2 (2 days before deadline) | Project Control Procedure
Escalation L2 Trigger | [D+0] | [D+0] | Second escalation at deadline (D+0) | Project Control Procedure
Escalation L3 Trigger | [D+3] | [D+3] | Third escalation at D+3 | Project Control Procedure
Escalation L4 Trigger | [D+7] | [D+7] | Fourth escalation at D+7 | Project Control Procedure
Escalation L5 Trigger | [48h before time-bar] | [48h before time-bar] | Final escalation 48 hours before time-bar | Project Control Procedure

## User Roles
Role ID | Role Name | Department | Description | Key Responsibilities | Permissions Level
R001 | Engineer (HAI) | Technical | HAI engineering oversight and approval authority | Technical review, approval of submissions, site inspections | Senior
R002 | Project Director | Management | Overall project execution and strategic oversight | Project planning, stakeholder management, key approvals | Executive
R003 | Resident Engineer | Site | Day-to-day site engineering supervision | Daily site monitoring, instruction issuance, inspection | Senior
R004 | QA/QC Manager | Quality | Quality assurance and control management | Testing coordination, quality approvals, compliance | Senior
R005 | QS/Cost Manager | Finance | Quantity surveying and cost management | Cost tracking, variation quantification, budget management | Senior
R006 | Planning Engineer | Planning | Schedule management and control | Schedule updates, progress tracking, delay analysis | Senior
R007 | Document Controller | Administration | Document management and control | Document filing, version control, distribution | Standard
R008 | Safety Officer | Safety | Health and safety compliance | Safety inspections, incident reporting, compliance | Senior
R009 | Contract Administrator | Legal | Contract administration and compliance | Contract interpretation, claims handling, correspondence | Senior
R010 | Site Engineer (Civil) | Site | Civil works supervision | Civil inspection, material testing, work approval | Standard
R011 | Site Engineer (Arch) | Site | Architectural works supervision | Architectural inspection, finishes approval | Standard
R012 | Site Engineer (MEP-M) | Site | Mechanical MEP supervision | MEP-M inspection, commissioning oversight | Standard
R013 | Site Engineer (MEP-E) | Site | Electrical MEP supervision | MEP-E inspection, electrical testing, commissioning | Standard
R014 | Technical Design Manager | Technical Design | Technical Design coordination and approval | Technical Design review, RFI coordination, change management | Senior
R015 | IT Administrator | IT | System administration and support | User management, system maintenance, data backup | Executive
R016 | Consultant PM | Consultancy | Consultant project management | Team coordination, deliverable tracking, client liaison | Senior
R017 | Consultant Staff | Consultancy | Consultant technical staff | Task execution, technical delivery, reporting | Standard

## Module Configuration
Module ID | Module Name | Status | Description | Key Features | Required Roles
MOD001 | Document Management | Enabled | Central document repository and version control | File storage, version tracking, metadata, audit trail | Document Controller, all
MOD002 | Correspondence | Enabled | Project correspondence tracking and management | Letter tracking, distribution, filing, archiving | Contract Administrator, Engineer
MOD003 | Variation Orders | Enabled | Variation instruction and tracking system | VO creation, costing, approval workflow, tracking | Engineer, QS/Cost Manager
MOD004 | Procurement | Enabled | Procurement management and tracking | RFQ, PO, delivery tracking, vendor management | QA/QC Manager, Contract Administrator
MOD005 | Stage Gate | Enabled | Project stage gate management | Stage definition, gate reviews, approval workflow | Project Director, Engineer
MOD006 | Freeze Management | Enabled | Technical Design freeze and baseline management | Freeze creation, change control, impact analysis | Technical Design Manager, Engineer
MOD007 | Authority Submissions | Enabled | Authority approvals tracking | Submission logging, approval tracking, compliance | Engineer, Document Controller
MOD008 | IPC Processing | Enabled | Interim Payment Certificate processing | IPC creation, certification, payment tracking | QS/Cost Manager, Engineer
MOD009 | Approval Engine | Enabled | Configurable approval workflows | Workflow definition, multi-level approvals, notifications | IT Administrator, Project Director
MOD010 | Quality/Site Supervision | Enabled | Quality and site supervision tracking | Inspections, testing, non-conformance, corrective action | QA/QC Manager, Site Engineers
MOD011 | Spatial Coordination/Cost | Enabled | Spatial Coordination and cost tracking | Cost tracking, forecasting, variance analysis, reporting | QS/Cost Manager, Finance
MOD012 | Risk Register | Enabled | Risk management and tracking | Risk identification, assessment, mitigation, monitoring | Project Director, Engineer
MOD013 | Performance Scoring | Enabled | Contractor and consultant performance | KPI tracking, scoring, reporting, benchmarking | Project Director, Consultant PM
MOD014 | Lessons Learned | Enabled | Project learning capture | Capture, categorization, sharing, continuous improvement | Project Director, all
MOD015 | Handover/DLP | Enabled | Handover and Defects Liability Period | Snagging, DLP period tracking, warranty management | Resident Engineer, QA/QC Manager
MOD016 | Claims/Disputes | Enabled | Claims and dispute management | Claim registration, tracking, settlement, ADR | Contract Administrator, Engineer
MOD017 | Reporting | Enabled | Comprehensive reporting and dashboards | Report templates, KPIs, analytics, visualization | Project Director, all
MOD018 | Master Data | Enabled | Master data management | Project setup, contract master, resource master | IT Administrator, Project Director
MOD019 | Scheduling | Enabled | Project scheduling and tracking | Schedule development, baseline, progress tracking, forecasting | Planning Engineer, all
MOD020 | Predictive Analytics | Enabled | Predictive analytics and forecasting | Cost forecasting, schedule forecasting, risk prediction | Project Director, Planning Engineer
MOD021 | Communication Management | Enabled | Project communication coordination | Meeting scheduling, minutes, action tracking, distribution | Project Director, all
MOD022 | Document Numbering | Enabled | Document numbering scheme management | Auto-numbering, prefix management, sequence control | Document Controller, IT Administrator
MOD023 | Mobilization Management | Enabled | Contractor/consultant mobilization tracking | Resource mobilization, site setup, temporary works | Resident Engineer, Safety Officer
MOD024 | Testing & Commissioning/GSAS | Enabled | T&C and GSAS compliance tracking | T&C scheduling, authority inspections, GSAS certification | QA/QC Manager, Engineer
MOD025 | Post-Occupancy Services | Enabled | Post-occupancy service management | Complaint tracking, warranty claims, snagging, FM handover | Resident Engineer, QA/QC Manager
MOD026 | Consultant Performance & Payment | Enabled | Consultant payment and performance | Timesheet approval, performance scoring, payment processing | Consultant PM, QS/Cost Manager

## Notification Templates
Template ID | Trigger Event | Recipients | Channel | Priority | Template Text
NT001 | IPC Ready for Certification | Engineer, QS/Cost Manager | Email | High | IPC [IPC_NUMBER] for [PERIOD] is ready for certification. Value: [AMOUNT]. Due: [DATE]
NT002 | IPC Certified | Contractor, Finance | Email | Standard | IPC [IPC_NUMBER] has been certified. Payment due: [DATE]
NT003 | Variation Order Issued | Contractor, Site Engineers | Email/SMS | High | VO [VO_NUMBER] issued: [TITLE]. Impacts: Cost [COST_IMPACT], Time [TIME_IMPACT]
NT004 | Claims Notice Submitted | Engineer, Contract Admin | Email | High | Claim notice received: [CLAIM_ID]. Time-bar: [TIMEBARDATE]
NT005 | Non-Conformance Identified | Site Engineer, QA/QC | In-App | Standard | NCR [NCR_ID] raised: [DESCRIPTION]. Corrective action required by [DATE]
NT006 | Safety Incident Reported | Safety Officer, Project Director | SMS/Email | Critical | Safety incident [INCIDENT_ID]: [SEVERITY]. Immediate action required.
NT007 | Schedule Delay Warning | Planning Engineer, Project Director | Email | High | Activity [ACTIVITY] delayed by [DAYS] days. Recovery plan required.
NT008 | Budget Variance Alert | QS/Cost Manager, Project Director | Email | High | Cost variance detected: [VARIANCE]% against budget. Forecast at completion: [FAC]
NT009 | Technical Design Change Request | Technical Design Manager, Engineer | Email | Standard | DCR [DCR_ID]: [TITLE]. Impact assessment due: [DATE]
NT010 | Authority Submission Approved | Engineer, Document Controller | Email | Standard | Authority approval received: [DOCUMENT]. Reference: [REF_NUMBER]
NT011 | Consultant Invoice Received | Consultant PM, Finance | Email | Standard | Invoice [INV_NUMBER] from [CONSULTANT] received. Amount: [AMOUNT]. Review due: [DATE]
NT012 | Performance KPI Alert | Consultant PM, Project Director | Email | High | Performance alert for [CONSULTANT]: [KPI] below target. Current: [VALUE]%
NT013 | DLP Period Approaching End | QA/QC Manager, Resident Engineer | Email | Standard | DLP period ending [DATE]. Final inspections due by [FINALDATE]
NT014 | Document Upload Overdue | Document Controller, Team | Email | Standard | [DOCUMENT_TYPE] [REF] overdue for submission. Due date was [DATE]
NT015 | Approval Escalation L1 | Approver, Manager | Email | High | Approval action [ACTION] due [DATE]. Escalation L1 triggered.
NT016 | Approval Escalation L2 | Project Director, Executive | Email/SMS | Critical | Critical approval overdue: [ACTION]. Escalation L2. Director intervention required.
NT017 | Test & Commissioning Ready | QA/QC Manager, Authority | Email | Standard | T&C for [SYSTEM] scheduled [DATE]. Authority notification: [NOTIF_DATE]
NT018 | GSAS Certification Status | Engineer, Project Director | Email | Standard | GSAS certification: [STATUS]. Score: [SCORE]. Status: [DETAILS]
NT019 | Post-Occupancy Complaint | Facility Manager, Resident Engineer | In-App | Standard | End-user complaint [COMPLAINT_ID]: [ISSUE]. Response due: [DATE]
NT020 | Risk Escalation | Risk Owner, Project Director | Email | High | Risk [RISK_ID] escalated to [LEVEL]. Mitigation action required: [ACTION]

## Integration Points
Integration ID | System Name | Type | Status | Key Features | Data Flow
INT001 | SkyStruct ERP | Enterprise System | Configured | Project master, financial data, contract master, reporting | Bi-directional: Project setup, costs, payments, budget
INT002 | Email Gateway | Communication | Configured | Email sending, receipt, tracking, attachment handling | Outbound: Notifications, approvals; Inbound: Document receipt
INT003 | SMS Gateway | Communication | Configured | SMS sending for critical alerts, escalations | Outbound: Critical alerts, escalations, reminders
INT004 | Cloud Storage | Storage | Configured | Document storage, backup, archival, version control | Bi-directional: Document upload/download, backup
INT005 | Calendar System | Scheduling | Configured | Meeting scheduling, resource calendar, milestone dates | Bi-directional: Event creation, calendar sync
INT006 | BIM Platform | Technical Design | Configured | 3D models, clash detection, design coordination | Inbound: Technical Design updates; Outbound: Technical Design approvals
INT007 | Scheduling Tool (Primavera/MS Project) | Planning | Configured | Schedule development, baseline, progress tracking, forecasting | Bi-directional: Schedule import/export, progress updates
INT008 | Financial System | Finance | Configured | General ledger, AP/AR, cost allocation, budget control | Outbound: Cost posting, payment recording
INT009 | GSAS Portal | Compliance | Configured | GSAS certification requirements, score tracking | Inbound: GSAS requirements; Outbound: Compliance data
INT010 | Municipality Portals | Authority | Configured | Permit submissions, approvals, compliance tracking | Bi-directional: Submissions, approvals, inspections

## Dashboard Configuration
Dashboard ID | Dashboard Name | Audience | Refresh Frequency | Key KPIs | Data Sources
DASH001 | Executive Summary | Executive, Project Director | Weekly | Schedule Performance, Cost Performance, Quality Score, Risk Status | Schedule, Cost, QA/QC, Risk Register
DASH002 | Project Status | All Staff | Daily | Progress %, Schedule Variance, Key Milestones, Critical Path | Schedule, Progress Tracking
DASH003 | Cost & Spatial Coordination | Finance, QS/Cost Manager | Weekly | Actual vs Spatial Coordination, Forecast at Completion, Cost Variance, Cash Flow | IPC, Cost Tracking, Spatial Coordination
DASH004 | Quality & Compliance | QA/QC, Compliance | Weekly | NCR Status, Test Results, Compliance Score, Authority Approvals | QA/QC, Authority Submissions, GSAS
DASH005 | Risk & Claims | Risk Owner, Contract Admin | Bi-weekly | Active Risks, Risk Exposure, Pending Claims, Claim Value | Risk Register, Claims Management
DASH006 | Consultant Performance | Consultant PM, Project Director | Monthly | Performance Score, KPI Achievements, Payment Status, Deliverables | Performance Scoring, Consultant Payment, Deliverables
DASH007 | Document Tracker | Document Controller, All | Daily | Overdue Documents, Submission Status, Document Count, Archival | Document Management, Authority Submissions
DASH008 | Predictive Analytics | Planning, Finance, Director | Weekly | Cost Forecast, Schedule Forecast, Risk Probability, Trend Analysis | Predictive Analytics Engine, Historical Data