## Role Definitions
Role ID | Role Name | Department | Description | System Access Level | Reports To | Contract Authority Limit (QAR)
R01 | HAI Programme Director | Executive | Executive oversight, all system access, strategic governance | Full System Access | Employer | [Contract Value]
R02 | HAI Project Manager | Project Management | Day-to-day project management, full project access | Full Project Access | Programme Director | 500,000
R03 | HAI Contracts Manager | Contracts | Contract administration and contractual module management | Contract Modules | Project Manager | 200,000
R04 | HAI Design Manager | Design | Design oversight and management, EDMS and Design modules | Design & Document Modules | Project Manager | 100,000
R05 | HAI Cost Manager | Finance/Cost Control | Cost control and financial management, Cost and IPC modules | Cost Management Modules | Project Manager | 100,000
R06 | HAI QA/QC Manager | Quality Assurance | Quality assurance and quality control oversight | Quality & Site Modules | Project Manager | N/A
R07 | HAI Document Controller | Administration | Document management and EDMS administration | EDMS Module | Project Manager | N/A
R08 | HAI Site Engineer | Site Operations | Site supervision and site quality oversight | Site & Quality Modules | QA/QC Manager | N/A
R09 | HAI Planning Engineer | Planning | Programme and schedule management, planning module | Planning Module | Project Manager | N/A
R10 | Contractor PM | Contractor | Contractor portal access for submission and collaboration | Limited Portal Access | Contractor Entity | Per Contract
R11 | Contractor Doc Controller | Contractor | Contractor document submission and management | Submission Portal | Contractor Entity | N/A
R12 | Consultant Lead | Consultant | Consultant review and feedback access | Review Portal Access | Consultant Firm | N/A
R13 | Employer Representative | Employer | Employer approval authority and contract oversight | Read & Approve | Employer | [Contract Value]
R14 | System Administrator | IT/Administration | Platform configuration, user management, system maintenance | Full System Access | IT Department | N/A
R15 | Auditor | Audit | Read-only audit access across all modules | Audit Read-Only | External Audit Body | N/A

## Module Access Matrix
Module | Code | Description | R01 | R02 | R03 | R04 | R05 | R06 | R07 | R08 | R09 | R10 | R11 | R12 | R13 | R14 | R15
EDMS | PF-01 | Document Management System | F | E | E | E | E | V | F | V | V | S | S | V | F | F | V
Correspondence | PF-02 | Letter and correspondence tracking | F | E | E | V | V | V | E | V | V | S | S | V | A | F | V
Variations | PF-03 | Change variation management | F | E | E | V | V | V | V | V | V | S | N | V | A | F | V
Procurement | PF-04 | Procurement and purchase orders | F | E | E | V | E | V | V | V | V | S | N | V | A | F | V
Stage Gates | PF-05 | Project stage gate control | F | E | V | V | V | V | V | V | E | S | N | V | A | F | V
Freeze Management | PF-06 | Design freeze management | F | E | V | E | V | V | V | V | V | N | N | V | A | F | V
Authority Submissions | PF-07 | Authority and approvals | F | E | E | V | V | V | E | V | V | S | N | V | A | F | V
IPC Processing | PF-08 | Interim Payment Certificate processing | F | E | E | V | E | V | V | V | V | S | N | V | A | F | V
Approval Engine | PF-09 | Approval workflow engine | F | E | V | V | V | V | V | V | V | N | N | N | A | F | V
Quality/Site | PF-10 | Quality assurance and site management | F | E | V | V | V | E | V | E | V | S | N | N | A | F | V
Budget/Cost | PF-11 | Budget and cost control | F | E | V | V | E | V | V | V | V | V | N | V | A | F | V
Risk Register | PF-12 | Project risk management | F | E | V | V | V | E | V | V | V | V | N | V | A | F | V
Contractor Scoring | PF-13 | Contractor performance scoring | F | E | V | V | V | E | V | V | V | N | N | N | A | F | V
Lessons Learned | PF-14 | Project lessons learned | F | E | V | V | V | V | V | V | V | S | S | V | A | F | V
Handover/DLP | PF-15 | Handover and defect liability period | F | E | V | V | V | V | V | V | V | S | S | V | A | F | V
Meetings | PF-16 | Meeting and minutes management | F | E | V | V | V | V | V | V | V | S | N | V | A | F | V
Stakeholder Portal | PF-17 | Stakeholder collaboration portal | F | E | V | V | V | V | V | V | V | F | F | F | A | F | V
Reports | PF-18 | Reporting and analytics | F | E | V | V | E | V | V | V | E | V | N | V | A | F | V
User Management | PF-19 | User and role management | F | V | V | V | V | V | V | V | V | N | N | N | V | F | N
ERP Integration | PF-20 | ERP system integration | F | E | E | V | E | V | V | V | V | N | N | N | V | F | V
Dashboard | PF-21 | Executive dashboards and KPIs | F | E | E | E | E | E | V | V | E | V | N | V | E | F | V
Notifications | PF-22 | Notification engine | bar: F F to V V
Audit Trail | PF-23 | Audit and compliance logging | F | E | V | V | V | V | V | V | V | N | N | N | E | F | F

## Approval Authority Matrix
Action Type | Threshold (QAR) | L1 Approver | L2 Approver | L3 Approver | Contract Ref
Document Approval | Any | HAI Document Controller | HAI Project Manager | HAI Programme Director | FIDIC 1999 Red Book
Variation <50K | <50,000 | HAI Contracts Manager | HAI Project Manager | N/A | Section 13.1
Variation 50-200K | 50,000-200,000 | HAI Project Manager | HAI Programme Director | Employer Representative | Section 13.1
Variation 200-500K | 200,000-500,000 | HAI Programme Director | Employer Representative | Employer Authority | Section 13.1
Variation >500K | >500,000 | Employer Representative | Employer Authority | Employer Board | Section 13.1
IPC Certification | Per IPC value | HAI Cost Manager | HAI Project Manager | Employer Representative | Section 14
Procurement <100K | <100,000 | HAI Contracts Manager | HAI Project Manager | N/A | Section 4
Procurement 100-500K | 100,000-500,000 | HAI Project Manager | HAI Programme Director | Employer Representative | Section 4
Procurement >500K | >500,000 | HAI Programme Director | Employer Representative | Employer Authority | Section 4
Design Freeze Exception | Any | HAI Design Manager | HAI Project Manager | HAI Programme Director | Design Control
Stage Gate Progression | Stage dependent | HAI Project Manager | HAI Programme Director | Employer Representative | PF-05
Risk Escalation | Risk rating dependent | HAI Project Manager | HAI Programme Director | Employer Representative | PF-12
Claims Assessment | <500,000 | HAI Contracts Manager | HAI Project Manager | Employer Representative | Section 20
Extension of Time | Any | HAI Planning Engineer | HAI Project Manager | Employer Representative | Section 8.4
Contractor Score Override | Performance rating | HAI Project Manager | HAI Programme Director | Employer Representative | PF-13

## Data Access Controls
Data Category | Sensitivity | R01 | R02 | R03 | R04 | R05 | R06 | R07 | R08 | R09 | R10 | R11 | R12 | R13 | R14 | R15
Contract Documents | High | R/W | R/W | R/W | R | R | R | R/W | R | R | R | R | R | R/W | R/W | R
Financial Data | High | R/W | R/W | R/W | R | R/W | R | R | R | R | R | N | R | R/W | R/W | R
Claims Records | High | R/W | R/W | R/W | R | R | R | R | R | R | R | N | R | R/W | R/W | R
Personnel Data | Confidential | R/W | R | R | N | N | N | N | N | N | N | N | N | R | R/W | N
Audit Logs | High | R/W | R | R | R | R | R | R | R | R | N | N | N | R | R/W | R/W
Correspondence | Medium | R/W | R/W | R/W | R | R | R | R/W | R | R | R | R | R | R/W | R/W | R
Meeting Minutes | Medium | R/W | R/W | R | R | R | R | R/W | R | R | R | N | R | R/W | R/W | R
Risk Register | Medium | R/W | R/W | R | R | R | R/W | R | R/W | R | R | N | R | R/W | R/W | R
Performance Scores | Medium | R/W | R/W | R | R | R | R/W | R | R | R | N | N | N | R | R/W | R
Design Documents | High | R/W | R/W | R | R/W | R | R | R/W | R | R | R | R | R | R/W | R/W | R

## Cross-Reference
Document/Module | Reference ID | Relationship | Details
Approval Engine | PF-09 | Authority and approval workflow | Integrated with all approval authority thresholds
User Management | PF-19 | Role and permission configuration | Central system for all role definitions and access control
Notification Engine | PF-22 | Approval and action notifications | Sends alerts for threshold-based approvals and role-based updates
Audit Trail | PF-23 | Compliance and audit logging | Records all role-based access and approval actions for compliance
HAI_Level4_Acceptance_Checklists_CONTRACTUAL.xlsx | HAI-SS-CHK-2026 | Contractual acceptance requirements | Cross-reference for approval authority and document sign-off procedures