## Workflow Rules Register
Rule ID | PF Reference | Rule Name | Trigger Event | Condition | Action | SLA (Days) | Escalation Level | Contract Clause | Priority
WR-001 | PF-01 | Document Review SLA | On submission | Always | Route to reviewer | 5/3 | L2 on breach | SC 4.28.1 | High
WR-002 | PF-02 | Correspondence Response | On receipt | Contractual letter | Start timer | 14 | L3 on D+7 | SC 1.3 | Critical
WR-003 | PF-03 | Variation Execution | On VO instruction | SC 13.1 | Fork to dual track (execute + commercial) | 0 | L4 if delayed | SC 13.3.1 | Critical
WR-004 | PF-08 | IPC Certification | On IPC submission | Monthly cycle | Start 28d timer | 28 | L4 on breach | SC 14.6 | Critical
WR-005 | PF-01 | Design Freeze Lock | On freeze date | Technical Design stage complete | Lock PF-01 for modifications | 0 | L2 on attempt | SC 1.1.2.32 | High
WR-006 | PF-04 | Stage Gate Approval | On stage completion | All prerequisites met | Route for approval | 5 | L3 on breach | SC 1.1 | High
WR-007 | PF-05 | Spatial Coordination Threshold Alert | On expenditure update | Amount > 10% variance | Escalate to Finance Manager | 1 | L2 immediate | SC 14.3 | High
WR-008 | PF-06 | RFI Response Timeout | On RFI issued | 7d elapsed | Auto-escalate to Architect | 7 | L3 on D+7 | SC 6.3 | Critical
WR-009 | PF-07 | Material Approval Request | On submission | New material type | Route to Technical approval | 3 | L2 on breach | SC 13.2 | High
WR-010 | PF-09 | Approval Limit Exceeded | On approval request | Amount > £100,000 | Route to Director level | 2 | L4 mandatory | SC 14.1 | Critical
WR-011 | PF-10 | Time-bar Notice (28d) | On claim instruction | Contractual claim | Send 28d notice | 28 | L5 at D+21 | SC 20.2.1 | Critical
WR-012 | PF-10 | Time-bar Notice (7d) | On 28d notice issued | Claim details required | Send 7d detailed notice | 7 | L5 at D+5 | SC 20.2.4 | Critical
WR-013 | PF-11 | Variation Notice (3WD) | On variation order | SC 13 instruction | Issue 3WD notice | 3 | L3 on breach | SC 3.3 | Critical
WR-014 | PF-12 | NOD Protocol (48h) | On event occurrence | Notifiable delay event | Issue 48h NOD | 0.2 | L4 mandatory | SC 1.1.2.32 | Critical
WR-015 | PF-13 | Auto-escalation Timer | On assignment | After 2d inactivity | Escalate to manager | 2 | L2 auto | SC 1.3 | High
WR-016 | PF-14 | Dashboard Refresh | On status update | Any PF change | Trigger dashboard update | 0.1 | None | Internal | Medium
WR-017 | PF-15 | ERP Sync Trigger | On transaction commit | Financial data change | Sync to ERP system | 0.1 | L2 on failure | SC 14.6 | High
WR-018 | PF-16 | Audit Log Entry | On any modification | User action recorded | Log to audit trail | 0 | None | Internal | Medium
WR-019 | PF-17 | Notification Trigger | On status change | Assigned user involved | Send notification | 0 | None | Internal | Low
WR-020 | PF-18 | Duplicate Detection | On data entry | Matching record exists | Flag for review | 1 | L2 auto | Internal | Medium
WR-021 | PF-19 | Mandatory Field Validation | On form submission | Required field empty | Reject submission | 0 | L1 notification | Internal | High
WR-022 | PF-20 | Version Control Lock | On approval | Document approved | Lock previous versions | 0 | None | SC 1.1.2.32 | Medium
WR-023 | PF-21 | Access Control Enforcement | On login | Role-based access | Apply permission matrix | 0 | L2 on violation | Internal | High
WR-024 | PF-22 | Notification Routing | On event trigger | Multi-recipient rule | Route by role + level | 0 | None | SC 1.3 | Medium
WR-025 | PF-03 | Commercial Register Entry | On VO + commercial flag | Value > £5,000 | Auto-create commercial claim | 0 | L3 on omission | SC 20.1 | Critical
WR-026 | PF-04 | Progress Reporting SLA | On month-end | Reporting period close | Generate progress report | 3 | L2 on late | SC 6.2.4 | High
WR-027 | PF-05 | Cost Control Alert | On cost update | Cumulative cost > budget | Flag overrun to PM | 0.5 | L3 mandatory | SC 14.3 | Critical
WR-028 | PF-06 | Technical Design Coordination RFI | On coordination clash | BIM or 2D conflict | Issue coordinated RFI | 7 | L2 on breach | SC 6.3 | High
WR-029 | PF-08 | Interim Payment Certificate | On IPC issuance | Monthly cycle triggered | Route to Employer approval | 7 | L4 on delay | SC 14.6 | Critical
WR-030 | PF-09 | Contractor Approval | On submission | Contractor-required action | Route to Site Agent | 2 | L2 on breach | SC 1.1.2.3 | High
WR-031 | PF-02 | Correspondence Archival | On closure | Correspondence thread closed | Archive to document register | 0 | None | Internal | Low
WR-032 | PF-10 | Claim Time-bar Expiry | On D+28 or D+35 | Time-bar limit reached | Close claim without prejudice | 28 | L5 mandatory | SC 20.2 | Critical
WR-033 | PF-11 | Variation Commitment | On instruction received | VO issued | Commit to cost/time register | 0 | L3 if omitted | SC 13.1 | Critical
WR-034 | PF-12 | Project Manager Instruction | On PMI instruction | Change or clarification | Log instruction + notify Contractor | 0.5 | L2 on breach | SC 3.4 | High
WR-035 | PF-13 | Task Assignment Escalation | On task creation | After 5d no assignment | Auto-assign to manager | 5 | L3 auto | Internal | High
WR-036 | PF-14 | SLA Monitoring Report | On daily run | Scheduled report | Generate SLA breach report | 1 | None | SC 1.3 | Medium
WR-037 | PF-15 | Invoice Sync to ERP | On invoice approval | IPC certified | Sync payment authorization | 0.1 | L2 on failure | SC 14.6 | High
WR-038 | PF-16 | Change Audit Trail | On any data change | Full audit required | Log user/time/action/values | 0 | None | Internal | Medium
WR-039 | PF-17 | Email Notification Queue | On trigger event | Batch send enabled | Queue and send notifications | 0.1 | L2 on failure | Internal | Low
WR-040 | PF-18 | Data Validation Rules | On entry | Field-level validation | Validate format/range | 0 | L1 prompt | Internal | High
WR-041 | PF-19 | Handover Checklist | On handover phase | Stage gate completed | Unlock handover tasks | 0 | L2 if locked | SC 1.1.2.32 | High
WR-042 | PF-20 | Document Version Tracking | On upload | New version added | Increment version number | 0 | None | Internal | Medium
WR-043 | PF-21 | Role-based Task Visibility | On task assignment | User role defined | Filter task list by role | 0 | None | Internal | Low
WR-044 | PF-22 | Escalation Notification | On escalation trigger | Overdue threshold reached | Notify escalation recipient | 0 | Auto-send | SC 1.3 | Critical
WR-045 | PF-01 | Submission SLA Timer | On document submission | Technical Design/compliance doc | Start SLA countdown | 5 | L2 on D+4 | SC 4.28.1 | High
WR-046 | PF-03 | VO Dual-track Execution | On VO issuance | Variation order flagged | Parallel: execution + financial | 0 | L4 if diverged | SC 13.3.1 | Critical
WR-047 | PF-08 | Retention Money Calc | On IPC certification | Contractual holdback | Calculate retention from IPC | 28 | L4 on breach | SC 14.10 | High
WR-048 | PF-10 | Claim Commercial Register | On claim notice | Time-bar active | Link to commercial register | 28 | L3 on breach | SC 20.1 | Critical
WR-049 | PF-15 | Real-time Dashboard Update | On status change | Any workflow update | Push to dashboard in real-time | 0 | L2 on failure | Internal | Medium
WR-050 | PF-22 | Multi-level Notification | On critical event | Critical priority PF | Notify all 5 escalation levels | 0 | Auto-send | SC 1.3 | Critical
WR-051 | PF-02 | Contract Correspondence Log | On receipt | Official correspondence | Create correspondence register entry | 1 | L2 on breach | SC 1.1 | High
WR-052 | PF-04 | Stage Gate Review Report | On stage completion | Review meeting held | Generate stage gate report | 2 | L3 on late | SC 1.1.2.32 | High

## Escalation Rules
Escalation ID | Trigger | Level | Recipient Role | Time Offset | Action | Auto/Manual
ESC-L1-001 | Task unassigned | L1 | Task Assignee | D-2 | Reminder notification | Auto
ESC-L1-002 | Document awaiting review | L1 | Assigned Reviewer | D-1 | Review reminder | Auto
ESC-L1-003 | Approval request pending | L1 | Assigned Approver | D-1 | Approval reminder | Auto
ESC-L2-001 | Deadline reached | L2 | Assignee + Manager | D+0 | Deadline alert | Auto
ESC-L2-002 | SLA breach imminent | L2 | Manager + PM | D-1 | SLA warning | Auto
ESC-L2-003 | Spatial Coordination threshold exceeded | L2 | Finance Manager | D+0 | Spatial Coordination alert | Auto
ESC-L2-004 | RFI response overdue | L2 | Technical Design Manager | D+0 | RFI overdue alert | Auto
ESC-L3-001 | Task overdue (3 days) | L3 | Department Head | D+3 | Escalation escalation | Auto
ESC-L3-002 | Approval delayed (3 days) | L3 | Department Head | D+3 | Approval escalation | Auto
ESC-L3-003 | Variation instruction delayed | L3 | Project Manager | D+3 | VO processing delay | Auto
ESC-L3-004 | Commercial claim at risk | L3 | Contracts Manager | D+3 | Claim time-bar warning | Auto
ESC-L4-001 | Critical breach (7 days) | L4 | Programme Director | D+7 | Critical escalation | Auto
ESC-L4-002 | IPC delay (7 days) | L4 | Project Director | D+7 | Payment delay escalation | Auto
ESC-L4-003 | Technical Design freeze violation | L4 | Programme Director | D+1 | Technical Design lock violation | Auto
ESC-L4-004 | VO commitment missed | L4 | Programme Director | D+7 | Commercial register delay | Auto
ESC-L5-001 | Time-bar (48h before expiry) | L5 | Legal + Contracts + Employer Rep | D+26 (28d notice) | Critical legal action required | Auto + Manual
ESC-L5-002 | Final time-bar (7d deadline) | L5 | Legal + Contracts + Employer Rep | D+33 (35d notice) | Final legal escalation | Auto + Manual
ESC-L5-003 | Claim closure imminent | L5 | Legal + PM + Contracts | D+27 | Pre-closure escalation | Manual
ESC-L5-004 | Dispute threshold reached | L5 | Project Director + Legal | On event | Dispute escalation protocol | Manual

## Business Rules Engine
BR ID | Category | Rule Description | Input Fields | Output/Action | Validation Logic
BR-FIN-001 | Financial Thresholds | Approval limit - up to £10,000 | Amount | Assign to Finance Officer | Amount <= 10000
BR-FIN-002 | Financial Thresholds | Approval limit - £10,001 to £50,000 | Amount | Assign to Finance Manager | Amount > 10000 AND Amount <= 50000
BR-FIN-003 | Financial Thresholds | Approval limit - £50,001 to £100,000 | Amount | Assign to Financial Controller | Amount > 50000 AND Amount <= 100000
BR-FIN-004 | Financial Thresholds | Approval limit - over £100,000 | Amount | Assign to Director | Amount > 100000
BR-FIN-005 | Financial Thresholds | Retention money calculation (5%) | IPC Amount | Calculate retention = Amount * 0.05 | Retention <= IPC Amount
BR-FIN-006 | Financial Thresholds | Cumulative cost variance alert | Spatial Coordination, Actual Cost | Flag if variance > 10% | ABS((Actual - Spatial Coordination) / Spatial Coordination) > 0.10
BR-TIME-001 | Time Calculations | Working day calculation (excluding weekends) | Start Date, Days | Add working days excluding Sat/Sun | Validate business days only
BR-TIME-002 | Time Calculations | Calendar day calculation (includes all days) | Start Date, Days | Add calendar days including weekends | Validate calendar days
BR-TIME-003 | Time Calculations | SLA calculation from submission | Submission Date, SLA Days | Calculate deadline = Submission Date + SLA | Deadline >= Submission Date
BR-TIME-004 | Time Calculations | Time-bar calculation (28 days) | Event Date | Calculate = Event Date + 28 calendar days | Time-bar expires on D+28
BR-TIME-005 | Time Calculations | Time-bar calculation (7 days from notice) | Notice Date | Calculate = Notice Date + 7 calendar days | Second deadline expires on D+7
BR-TIME-006 | Time Calculations | NOD protocol (48 hours) | Event Occurrence | Deadline = Event Date + 48 hours | NOD must be issued within 48h
BR-TIME-007 | Time Calculations | Variation notice (3 working days) | Variation Date | Calculate = Variation Date + 3 working days | Notice must be 3 WD from variation
BR-STAT-001 | Status Transitions | Document submission status | Current: Created, Action: Submit | Transition to: Under Review | Validate: Created -> Under Review
BR-STAT-002 | Status Transitions | Approval status change | Current: Under Review, Action: Approve | Transition to: Approved | Validate: Under Review -> Approved
BR-STAT-003 | Status Transitions | Rejection status change | Current: Under Review, Action: Reject | Transition to: Rejected | Validate: Under Review -> Rejected
BR-STAT-004 | Status Transitions | Variation order status progression | Current: Instruction, Action: Execute | Transition to: In Progress | Validate: Instruction -> In Progress
BR-STAT-005 | Status Transitions | Claim lifecycle status | Current: Notified, Action: Close | Transition to: Closed | Validate: Time-bar expired
BR-STAT-006 | Status Transitions | IPC certification status | Current: Submitted, Action: Certify | Transition to: Certified | Validate: All conditions met
BR-STAT-007 | Status Transitions | Task completion status | Current: In Progress, Action: Complete | Transition to: Completed | Validate: Required fields filled
BR-ACC-001 | Access Control | Role-based task visibility | User Role, PF Assignment | Show/Hide task based on role | Enforce role permissions
BR-ACC-002 | Access Control | Approval authority enforcement | User Role, Approval Amount | Allow/Deny approval authority | Amount <= Role Authority Limit
BR-ACC-003 | Access Control | Document edit access control | User Role, Document Status | Allow/Deny edit based on role | Enforce status-based locks
BR-ACC-004 | Access Control | Technical Design freeze lock enforcement | Technical Design Status, User Action | Prevent modifications post-freeze | Block edits if frozen = True
BR-ACC-005 | Access Control | Contractor view restrictions | User Organisation, PF Type | Filter data by org permissions | Show only relevant data
BR-VAL-001 | Data Validation | Mandatory field validation | Form Submission, Required Fields | Reject if field empty | NOT EMPTY(Field)
BR-VAL-002 | Data Validation | Email format validation | Email Address | Validate email format | REGEX: ^[a-zA-Z0-9._%+-]+@[a-zA-Z0-9.-]+\.[a-zA-Z]{2,}$
BR-VAL-003 | Data Validation | Date format validation | Date Field | Validate YYYY-MM-DD format | REGEX: ^\d{4}-\d{2}-\d{2}$
BR-VAL-004 | Data Validation | Amount format validation | Currency Field | Validate decimal (2 places max) | REGEX: ^\d+(\.\d{1,2})?$
BR-VAL-005 | Data Validation | Reference number uniqueness | Reference ID, Existing Records | Check for duplicate | NOT EXISTS(Reference in Table)
BR-VAL-006 | Data Validation | Contract clause reference validation | Clause Reference | Validate against FIDIC 1999 | EXISTS(Clause in Contract Glossary)
BR-VAL-007 | Data Validation | PF reference validation | PF Code | Validate against 23 PF list | EXISTS(PF in Master List)
BR-VAL-008 | Data Validation | Percentage range validation | Percentage Value | Validate 0-100% | Value >= 0 AND Value <= 100
BR-VAL-009 | Data Validation | Date range validation | Start Date, End Date | Validate end >= start | End Date >= Start Date
BR-VAL-010 | Data Validation | Duplicate detection - Correspondence | Sender, Date, Content Hash | Flag potential duplicates | COUNT(matching records) > 1
BR-VAL-011 | Data Validation | Duplicate detection - RFI | RFI Number, Subject | Check if RFI already exists | NOT EXISTS(RFI in Register)
BR-VAL-012 | Data Validation | Version control - Document versioning | Document ID, Version Number | Auto-increment on upload | Version = MAX(Previous Version) + 1
BR-VAL-013 | Data Validation | Cost commitment validation | VO Amount, Spatial Coordination Remaining | Validate commitment within budget | VO Amount <= Spatial Coordination Remaining
BR-VAL-014 | Data Validation | Time commitment validation | VO Duration, Contract Duration | Validate time extension possible | Duration <= Contract Limit

## Automation Rules
Auto ID | Trigger | Frequency | Action | Target Module | Dependencies
AUTO-001 | Daily 06:00 UTC | Daily | Generate SLA Monitoring Report | Workflow Engine | PF Status Data
AUTO-002 | Daily 08:00 UTC | Daily | Generate Escalation Report | Escalation Engine | Escalation Rules
AUTO-003 | Weekly Monday 09:00 UTC | Weekly | Generate Progress Report | Reporting Module | All PF statuses
AUTO-004 | On month-end (28th) | Monthly | Close off monthly reporting period | Financial Module | IPC Data
AUTO-005 | Every 5 minutes | Real-time | Dashboard refresh (status widgets) | Dashboard | PF Status updates
AUTO-006 | Every 1 hour | Hourly | ERP sync - Financial transactions | ERP Integration | Financial Module
AUTO-007 | Every 2 hours | Bi-hourly | ERP sync - Project status | ERP Integration | Status Module
AUTO-008 | Daily 22:00 UTC | Daily | Automatic backup of all documents | Backup System | Document Store
AUTO-009 | Daily 23:30 UTC | Daily | Backup of database | Database Backup | Central Database
AUTO-010 | Weekly Sunday 02:00 UTC | Weekly | Archive completed documents | Document Archival | Closed PF records
AUTO-011 | On IPC certification | Event-driven | Sync payment data to ERP | ERP Integration | Financial Module
AUTO-012 | Every 24 hours | Daily | Purge old audit logs (>6 months) | Audit System | Audit Log Table
AUTO-013 | On status change | Real-time | Update document version control | Version Control | Document Registry
AUTO-014 | Every 6 hours | Quarterly | Reconcile financial records | Accounting Module | GL Data
AUTO-015 | Daily 07:00 UTC | Daily | Generate SLA breach warning report | Workflow Engine | SLA Timers
AUTO-016 | On claim notice issuance | Event-driven | Auto-populate time-bar tracking | Claims Module | Claim Register
AUTO-017 | On VO issuance | Event-driven | Auto-create dual-track execution | VO Module | Commercial Register
AUTO-018 | Every 4 hours | Quarterly | Clean up temporary workflow files | File System | Temp Directory
AUTO-019 | On document approval | Event-driven | Lock previous document versions | Document Control | Version Registry
AUTO-020 | Daily 06:30 UTC | Daily | Generate time-bar expiry alerts | Claims Module | Claim Database

## Cross-Reference
Reference Type | Code/ID | Description | Related Sheets | Related Files | Notes
Process Flow | PF-01 | Document Control & Review | Workflow Rules Register | HAI_A068_Document_Control.xlsx | Core document management
Process Flow | PF-02 | Correspondence Management | Workflow Rules Register | HAI_A068_Correspondence_Log.xlsx | Formal & informal letters
Process Flow | PF-03 | Variation Order Management | Workflow Rules Register, Business Rules Engine | HAI_A068_VO_Register.xlsx | Dual-track execution
Process Flow | PF-04 | Stage Gate & Milestone Reviews | Workflow Rules Register | HAI_A068_Project_Timeline.xlsx | Project phase gates
Process Flow | PF-05 | Spatial Coordination & Cost Control | Business Rules Engine | HAI_A068_Spatial Coordination_Matrix.xlsx | Financial thresholds
Process Flow | PF-06 | RFI & Technical Design Coordination | Workflow Rules Register | HAI_A068_RFI_Register.xlsx | Technical Design clarifications
Process Flow | PF-07 | Material & Supplier Approval | Workflow Rules Register | HAI_A068_Approved_Suppliers.xlsx | Technical approvals
Process Flow | PF-08 | Interim Payment & Certification | Workflow Rules Register, Business Rules Engine | HAI_A068_IPC_Register.xlsx | Monthly payment cycle
Process Flow | PF-09 | Approval Engine | Workflow Rules Register, Business Rules Engine | HAI_A068_Approval_Matrix.xlsx | Authority limits & routing
Process Flow | PF-10 | Claims & Time-bar Management | Escalation Rules | HAI_A068_Claims_Register.xlsx | SC 20.2 time-bars
Process Flow | PF-11 | Variation Commitment Register | Workflow Rules Register | HAI_A068_Commercial_Register.xlsx | Cost & time impacts
Process Flow | PF-12 | Notification of Delay (NOD) | Escalation Rules | HAI_A068_NOD_Register.xlsx | SC 1.1.2.32 protocol
Process Flow | PF-13 | Task Assignment & Tracking | Workflow Rules Register | HAI_A068_Task_Tracker.xlsx | Workflow execution
Process Flow | PF-14 | Monitoring & Reporting | Automation Rules | HAI_A068_KPI_Dashboard.xlsx | Real-time metrics
Process Flow | PF-15 | ERP Integration & Sync | Automation Rules | HAI_A068_ERP_Mapping.xlsx | SAP/Oracle sync
Process Flow | PF-16 | Audit Logging & Trail | Automation Rules | HAI_A068_Audit_Trail.xlsx | Compliance & traceability
Process Flow | PF-17 | Notification & Alerting | Automation Rules, Escalation Rules | HAI_A068_Notification_Rules.xlsx | Email, SMS, dashboard alerts
Process Flow | PF-18 | Data Quality & Validation | Business Rules Engine | HAI_A068_Data_Validation.xlsx | Input controls
Process Flow | PF-19 | Handover & Closeout | Workflow Rules Register | HAI_A068_Handover_Checklist.xlsx | Final delivery tasks
Process Flow | PF-20 | Document Version Control | Business Rules Engine | HAI_A068_Version_Registry.xlsx | Document lifecycle
Process Flow | PF-21 | Access Control & Security | Business Rules Engine | HAI_User_Roles_Permissions_Matrix.xlsx | Role-based permissions
Process Flow | PF-22 | Notification Engine (advanced) | Escalation Rules, Automation Rules | HAI_A068_Notification_Engine.xlsx | Multi-channel notifications
Process Flow | PF-23 | Contract Duration & Milestones | Business Rules Engine | HAI_A068_Contract_Duration_Matrix.xlsx | Schedule management
FIDIC Reference | SC 1.1 | General Obligations | Workflow Rules Register | N/A | Project commencement
FIDIC Reference | SC 1.1.2.32 | Notices & Notifications | Workflow Rules Register, Escalation Rules | N/A | NOD & time-bars
FIDIC Reference | SC 1.3 | Communication & Correspondence | Workflow Rules Register, Escalation Rules | N/A | Formal correspondence
FIDIC Reference | SC 3.3 | Variation Notice | Workflow Rules Register | N/A | 3 working day notice
FIDIC Reference | SC 3.4 | Project Manager Instructions | Workflow Rules Register | N/A | Documented instructions
FIDIC Reference | SC 4.28.1 | Document Submission SLA | Workflow Rules Register | N/A | Compliance documentation
FIDIC Reference | SC 6.2.4 | Progress Reports | Workflow Rules Register | N/A | Monthly reporting
FIDIC Reference | SC 6.3 | RFI Response | Workflow Rules Register | N/A | Technical Design clarifications
FIDIC Reference | SC 13.1 | Variation Orders | Workflow Rules Register | N/A | Cost & time variations
FIDIC Reference | SC 13.2 | Material Changes | Workflow Rules Register | N/A | Specification changes
FIDIC Reference | SC 13.3.1 | VO Dual-track | Workflow Rules Register | N/A | Execute + commercial
FIDIC Reference | SC 14.1 | Approval Authorities | Business Rules Engine | N/A | Contractor approvals
FIDIC Reference | SC 14.3 | Cost Control | Business Rules Engine | N/A | Spatial Coordination management
FIDIC Reference | SC 14.6 | IPC & Payment | Workflow Rules Register | N/A | Interim certification
FIDIC Reference | SC 14.10 | Retention Money | Business Rules Engine | N/A | 5% holdback calc
FIDIC Reference | SC 20.1 | Claims - General | Workflow Rules Register | N/A | Commercial claims
FIDIC Reference | SC 20.2 | Claims - Time-bar | Workflow Rules Register, Escalation Rules | N/A | 28d/7d/35d limits
FIDIC Reference | SC 20.2.1 | Claims - 28d Notice | Workflow Rules Register | N/A | Initial notice period
FIDIC Reference | SC 20.2.4 | Claims - 7d Detail | Workflow Rules Register | N/A | Detailed claim period
Related Document | HAI_A068_Contract_Duration_Matrix.xlsx | Contract schedule & milestones | All sheets | Primary reference | Master schedule
Related Document | HAI_User_Roles_Permissions_Matrix.xlsx | User roles & access rights | Business Rules Engine | Primary reference | Access control matrix
Contract | [Project Reference] | Qatar HAI SkyStruct IGP - Contract [Project Reference] | All sheets | Contract document | FIDIC 1999 Red Book