## Notification Rules Register
NR ID | PF Reference | Event Trigger | Notification Type | Recipients (Role IDs) | Channel | Template Ref | Priority | SLA Warning | Contract Clause
NR-001 | PF-01 | Document uploaded | Submission Confirmation | DOC-ADM,PM | Email,In-App | TMPL-001 | High | 30 min | SC 1.1.2
NR-002 | PF-01 | Document submitted for review | Review Assignment | DOC-REV,PM | Email,Push | TMPL-002 | High | 1 hour | SC 1.1.2
NR-003 | PF-01 | Review deadline approaching | Deadline Warning D-2 | DOC-REV | Email,SMS | TMPL-003 | Medium | 2 days | SC 1.1.2
NR-004 | PF-01 | Review deadline breached | Deadline Breach Alert | DOC-REV,PM,PC | Email,SMS,Push | TMPL-004 | Critical | Immediate | SC 1.1.2
NR-005 | PF-01 | Document approved | Approval Confirmation | DOC-ADM,ORIGINATOR | Email,In-App | TMPL-005 | Medium | 1 hour | SC 1.1.2
NR-006 | PF-02 | Correspondence received | Correspondence Receipt | PM,DOC-ADM | Email,In-App | TMPL-006 | High | 30 min | SC 1.1.3
NR-007 | PF-02 | Response deadline approaching | Deadline Warning D-2 | PM,CONTR-ADM | Email,SMS | TMPL-003 | High | 2 days | SC 1.1.3
NR-008 | PF-02 | Response deadline breached | Deadline Breach Alert | PM,CONTR-ADM,PC | Email,SMS,Push | TMPL-004 | Critical | Immediate | SC 1.1.3
NR-009 | PF-03 | Variation instruction issued | VI Issued Notification | CONTR,PM,FIN | Email,Push | TMPL-009 | High | 1 hour | SC 13.1
NR-010 | PF-03 | VI acceptance deadline approaching | Deadline Warning D-2 | CONTR | Email,SMS | TMPL-003 | High | 2 days | SC 13.1
NR-011 | PF-03 | VI accepted/rejected | VI Response Notification | PM,FIN | Email,In-App | TMPL-010 | Medium | 1 hour | SC 13.1
NR-012 | PF-03 | VI commercial evaluation started | VI Commercial Review | FIN,PM | Email,In-App | TMPL-011 | Medium | 2 hours | SC 13.1
NR-013 | PF-03 | VI commercial approval/rejection | VI Commercial Decision | PM,CONTR,FIN | Email,Push | TMPL-012 | High | 1 hour | SC 13.1
NR-014 | PF-05 | Stage gate readiness check | Stage Gate Notification | PM,PC | Email,In-App | TMPL-013 | High | 3 days | SC 8.4
NR-015 | PF-05 | Stage gate approved/rejected | Stage Gate Decision | PM,CONTR | Email,Push | TMPL-014 | High | 1 hour | SC 8.4
NR-016 | PF-06 | Design freeze violation attempt | Compliance Alert | PM,DESIGN-MGR | Email,SMS,Push | TMPL-015 | Critical | Immediate | SC 5.1
NR-017 | PF-06 | Design change submitted during freeze | Design Change Alert | DESIGN-MGR,PM | Email,Push | TMPL-016 | High | 2 hours | SC 5.1
NR-018 | PF-08 | IPC submitted | IPC Submission Notification | PM,FIN,PC | Email,In-App | TMPL-017 | High | 1 hour | SC 14.6
NR-019 | PF-08 | IPC review deadline approaching | Deadline Warning D-2 | FIN,PC | Email,SMS | TMPL-003 | High | 2 days | SC 14.6
NR-020 | PF-08 | IPC certified | IPC Certification Notification | PM,CONTR,FIN | Email,Push,In-App | TMPL-018 | High | 1 hour | SC 14.6
NR-021 | PF-08 | IPC payment processing | Payment Processing Notice | FIN,CONTR | Email,In-App | TMPL-019 | Medium | 2 hours | SC 14.6
NR-022 | PF-08 | IPC payment released | Payment Released Notification | CONTR,FIN | Email,Push | TMPL-020 | Medium | 30 min | SC 14.6
NR-023 | PF-09 | Approval threshold notification | Approval Threshold Alert | APR-MGR,PM | Email,Push | TMPL-021 | High | 2 hours | SC 3.1
NR-024 | PF-09 | Approval granted | Approval Confirmation | ORIGINATOR,PM | Email,In-App | TMPL-005 | Medium | 30 min | SC 3.1
NR-025 | PF-09 | Approval rejected with comments | Approval Rejection Notice | ORIGINATOR,PM | Email,Push | TMPL-022 | High | 1 hour | SC 3.1
NR-026 | PF-12 | Risk escalated to L1 | Risk Escalation L1 | PM,PC | Email,In-App | TMPL-023 | High | 1 hour | SC 9.4
NR-027 | PF-12 | Risk escalated to L2 | Risk Escalation L2 | PM,PC,EXEC | Email,SMS,Push | TMPL-024 | Critical | 30 min | SC 9.4
NR-028 | PF-12 | Risk escalated to L3 | Risk Escalation L3 | EXEC,PC | Email,SMS,Push | TMPL-025 | Critical | Immediate | SC 9.4
NR-029 | PF-13 | Contractor performance score updated | Score Alert | PM,CONTR-MGR | Email,In-App | TMPL-026 | Medium | 2 hours | SC 4.2
NR-030 | PF-13 | Contractor score below threshold | Performance Alert | PM,CONTR-MGR,EXEC | Email,SMS,Push | TMPL-027 | High | 1 hour | SC 4.2
NR-031 | PF-15 | Handover milestone initiated | Milestone Notification | PM,CONTR,HO-MGR | Email,Push | TMPL-028 | High | 1 hour | SC 18.1
NR-032 | PF-15 | Handover checklist task assigned | Task Assignment | CONTR,HO-MGR | Email,In-App | TMPL-029 | Medium | 2 hours | SC 18.1
NR-033 | PF-15 | Handover checklist completion deadline | Deadline Warning D-2 | CONTR | Email,SMS | TMPL-003 | High | 2 days | SC 18.1
NR-034 | PF-15 | Handover defects list finalized | Defects Notification | PM,CONTR,HO-MGR | Email,Push | TMPL-030 | High | 1 hour | SC 18.1
NR-035 | PF-16 | Meeting scheduled | Meeting Scheduled | INVITEES | Email,Push | TMPL-031 | Medium | 3 days | SC 20.1
NR-036 | PF-16 | Meeting action assigned | Action Assignment | ACTION-OWNER | Email,In-App | TMPL-032 | Medium | 2 hours | SC 20.1
NR-037 | PF-16 | Action due date approaching | Deadline Warning D-2 | ACTION-OWNER | Email,SMS | TMPL-003 | Medium | 2 days | SC 20.1
NR-038 | PF-16 | Action overdue | Action Overdue Alert | ACTION-OWNER,PM | Email,SMS,Push | TMPL-033 | High | 1 hour | SC 20.1
NR-039 | PF-21 | Dashboard anomaly detected | Anomaly Alert | PM,SYS-ADM | Email,Push | TMPL-034 | Medium | 1 hour | SC 1.1.1
NR-040 | PF-21 | Dashboard critical alert | Critical System Alert | SYS-ADM,EXEC | Email,SMS,Push | TMPL-035 | Critical | Immediate | SC 1.1.1
NR-041 | PF-20 | Claim notice of default received | NOD Received | PM,CONTR-MGR,LEGAL | Email,SMS,Push | TMPL-036 | Critical | Immediate | SC 1.1.2.32
NR-042 | PF-20 | NOD response deadline 48h warning | Deadline Warning D-2 | CONTR,LEGAL | Email,SMS | TMPL-003 | Critical | 48 hours | SC 1.1.2.32
NR-043 | PF-20 | NOD response deadline approaching 12h | Deadline Critical Warning | CONTR,LEGAL | Email,SMS | TMPL-037 | Critical | 12 hours | SC 1.1.2.32
NR-044 | PF-20 | NOD response deadline breached | Deadline Breach Alert | PM,CONTR,LEGAL,EXEC | Email,SMS,Push | TMPL-004 | Critical | Immediate | SC 1.1.2.32
NR-045 | PF-20 | Claim 28-day notice period initiated | Time-Bar Notice | CONTR,LEGAL | Email,SMS,Push | TMPL-038 | High | 1 hour | SC 20.2.1
NR-046 | PF-20 | Claim 28-day notice period D-7 | Time-Bar Warning D-7 | CONTR,LEGAL | Email,SMS,Push | TMPL-039 | Critical | 7 days | SC 20.2.1
NR-047 | PF-20 | Claim 28-day notice period D-3 | Time-Bar Warning D-3 | CONTR,LEGAL | Email,SMS | TMPL-040 | Critical | 3 days | SC 20.2.1
NR-048 | PF-20 | Claim 28-day notice period expiring | Time-Bar Critical | CONTR,LEGAL,PM | Email,SMS,Push | TMPL-041 | Critical | Immediate | SC 20.2.1
NR-049 | PF-20 | Claim detailed submission deadline | Detailed Claim Due | CONTR,LEGAL | Email,SMS,Push | TMPL-042 | High | 1 hour | SC 20.2.4
NR-050 | PF-20 | Claim detailed submission D-7 | Time-Bar Warning D-7 | CONTR,LEGAL | Email,SMS,Push | TMPL-039 | Critical | 7 days | SC 20.2.4
NR-051 | PF-20 | Claim detailed submission D-3 | Time-Bar Warning D-3 | CONTR,LEGAL | Email,SMS | TMPL-040 | Critical | 3 days | SC 20.2.4
NR-052 | PF-20 | Claim detailed submission expiring | Time-Bar Critical | CONTR,LEGAL,PM | Email,SMS,Push | TMPL-041 | Critical | Immediate | SC 20.2.4
NR-053 | PF-02 | Correspondence attachment received | Attachment Notification | PM,DOC-ADM | Email,In-App | TMPL-043 | Medium | 1 hour | SC 1.1.3
NR-054 | PF-03 | VI financial impact > threshold | Financial Impact Alert | FIN,PM,EXEC | Email,Push | TMPL-044 | High | 2 hours | SC 13.1
NR-055 | PF-08 | IPC discrepancy identified | IPC Review Alert | FIN,PC,PM | Email,Push | TMPL-045 | High | 1 hour | SC 14.6
NR-056 | PF-12 | Risk register updated | Risk Update Notification | PM,PC | Email,In-App | TMPL-046 | Medium | 2 hours | SC 9.4
NR-057 | PF-13 | Contractor KPI threshold breach | KPI Alert | CONTR-MGR,PM | Email,SMS,Push | TMPL-047 | High | 1 hour | SC 4.2
NR-058 | PF-15 | Handover defect remediation overdue | Defect Overdue Alert | CONTR,PM,HO-MGR | Email,SMS,Push | TMPL-048 | High | 1 hour | SC 18.1
NR-059 | PF-21 | System maintenance window scheduled | Maintenance Notice | ALL-USERS,SYS-ADM | Email,In-App | TMPL-049 | Medium | 3 days | SC 1.1.1
NR-060 | PF-21 | System backup completion | Backup Confirmation | SYS-ADM | Email | TMPL-050 | Low | 2 hours | SC 1.1.1

## Alert Templates
Template ID | Template Name | Subject Line | Body Template | Variables | Channel
TMPL-001 | Submission Confirmation | Document Submitted: {DOC-NAME} | Your document '{DOC-NAME}' has been successfully submitted to {SYSTEM}. Reference: {DOC-ID}. Please retain for your records. | {DOC-NAME},{DOC-ID},{SYSTEM},{SUBMIT-TIME} | Email,In-App
TMPL-002 | Review Assignment | Review Required: {DOC-NAME} | Document '{DOC-NAME}' has been assigned to you for review. Deadline: {DUE-DATE}. Access via: {LINK} | {DOC-NAME},{DUE-DATE},{LINK},{REVIEWER} | Email,Push
TMPL-003 | Deadline Warning D-2 | DEADLINE REMINDER: {ACTION-NAME} due in 2 days | Reminder: {ACTION-NAME} is due by {DUE-DATE} at {DUE-TIME}. Time remaining: ~48 hours. Please complete to avoid escalation. | {ACTION-NAME},{DUE-DATE},{DUE-TIME},{ITEM-REF} | Email,SMS
TMPL-004 | Deadline Breach Alert | URGENT: {ACTION-NAME} OVERDUE | URGENT: {ACTION-NAME} (Ref: {ITEM-REF}) is now OVERDUE as of {BREACH-TIME}. Immediate action required. Escalation: L{ESCALATION-LEVEL} | {ACTION-NAME},{ITEM-REF},{BREACH-TIME},{ESCALATION-LEVEL},{OWNER} | Email,SMS,Push
TMPL-005 | Approval Confirmation | {ITEM-NAME} Approved | {ITEM-NAME} (Ref: {ITEM-ID}) has been approved by {APPROVER}. Status: APPROVED. You may proceed with next steps. | {ITEM-NAME},{ITEM-ID},{APPROVER},{APPROVAL-DATE} | Email,In-App
TMPL-006 | Correspondence Receipt | Correspondence Received: {CORR-SUBJECT} | Incoming correspondence received from {SENDER} on {RECEIVE-DATE}. Subject: {CORR-SUBJECT}. Action required by: {ACTION-DUE} | {CORR-SUBJECT},{SENDER},{RECEIVE-DATE},{ACTION-DUE},{CORR-ID} | Email,In-App
TMPL-009 | VI Issued Notification | Variation Instruction Issued: {VI-ID} | Variation Instruction {VI-ID} has been issued for your review. Description: {VI-DESC}. Value impact: {VALUE-IMPACT}. Review deadline: {DUE-DATE}. | {VI-ID},{VI-DESC},{VALUE-IMPACT},{DUE-DATE},{ISSUED-BY} | Email,Push
TMPL-010 | VI Response Notification | Variation Instruction {VI-ID} Response Received | Your response to VI {VI-ID} has been recorded as: {RESPONSE}. Submitted: {RESPONSE-DATE}. Next step: Commercial evaluation. | {VI-ID},{RESPONSE},{RESPONSE-DATE},{RESPONDER} | Email,In-App
TMPL-011 | VI Commercial Review | VI {VI-ID} Commercial Evaluation Commenced | Variation Instruction {VI-ID} has been forwarded for commercial evaluation. Current value: {CURRENT-VALUE}. Updated value: {PROPOSED-VALUE}. Review deadline: {DUE-DATE}. | {VI-ID},{CURRENT-VALUE},{PROPOSED-VALUE},{DUE-DATE} | Email,In-App
TMPL-012 | VI Commercial Decision | VI {VI-ID} Commercial Decision: {DECISION} | Variation Instruction {VI-ID} has been {DECISION} at commercial review. Final value: {FINAL-VALUE}. Next steps: {NEXT-STEPS}. | {VI-ID},{DECISION},{FINAL-VALUE},{NEXT-STEPS} | Email,Push
TMPL-013 | Stage Gate Notification | Stage Gate {GATE-NAME} Readiness Check | Stage Gate {GATE-NAME} readiness check has been initiated. Current status: {STATUS}. Checklist items pending: {PENDING-COUNT}. Review deadline: {DUE-DATE}. | {GATE-NAME},{STATUS},{PENDING-COUNT},{DUE-DATE} | Email,In-App
TMPL-014 | Stage Gate Decision | Stage Gate {GATE-NAME} Decision: {DECISION} | Stage Gate {GATE-NAME} has been {DECISION}. {DECISION-REASON}. Next stage: {NEXT-STAGE}. Proceed with caution if conditional approval. | {GATE-NAME},{DECISION},{DECISION-REASON},{NEXT-STAGE} | Email,Push
TMPL-015 | Compliance Alert | CRITICAL: Design Freeze Violation Attempt | CRITICAL ALERT: An attempt to modify design during freeze period has been detected. Item: {ITEM-NAME}. Requested by: {REQUESTER}. Action: BLOCKED. Escalating to design manager. | {ITEM-NAME},{REQUESTER},{FREEZE-PERIOD},{BLOCKED-TIME} | Email,SMS,Push
TMPL-016 | Design Change Alert | Design Change Submitted During Freeze Period | Design change request {DCR-ID} submitted by {REQUESTER} during active freeze period. Status: PENDING REVIEW. Freeze ends: {FREEZE-END-DATE}. Forwarding to design authority. | {DCR-ID},{REQUESTER},{FREEZE-PERIOD},{FREEZE-END-DATE} | Email,Push
TMPL-017 | IPC Submission Notification | Interim Payment Certificate {IPC-ID} Submitted | IPC {IPC-ID} has been submitted for certification. Period: {CERT-PERIOD}. Amount claimed: {CLAIMED-AMOUNT}. Review deadline: {DUE-DATE}. | {IPC-ID},{CERT-PERIOD},{CLAIMED-AMOUNT},{DUE-DATE},{SUBMITTED-BY} | Email,In-App
TMPL-018 | IPC Certification Notification | IPC {IPC-ID} Certified - {CERT-AMOUNT} | Interim Payment Certificate {IPC-ID} has been certified for period {CERT-PERIOD}. Certified amount: {CERT-AMOUNT}. Payment processing initiated. Expected payment date: {PAYMENT-DATE}. | {IPC-ID},{CERT-PERIOD},{CERT-AMOUNT},{PAYMENT-DATE} | Email,Push,In-App
TMPL-019 | Payment Processing Notice | IPC {IPC-ID} Payment Processing | Payment for certified IPC {IPC-ID} (Amount: {CERT-AMOUNT}) is being processed. Expected release: {PAYMENT-DATE}. Reference: {PAYMENT-REF}. | {IPC-ID},{CERT-AMOUNT},{PAYMENT-DATE},{PAYMENT-REF} | Email,In-App
TMPL-020 | Payment Released Notification | IPC {IPC-ID} Payment Released - {PAYMENT-AMOUNT} | Payment for IPC {IPC-ID} has been released. Amount: {PAYMENT-AMOUNT}. Transaction reference: {TXN-REF}. Check your account for credit confirmation. | {IPC-ID},{PAYMENT-AMOUNT},{TXN-REF},{PAYMENT-DATE} | Email,Push
TMPL-021 | Approval Threshold Alert | {ITEM-TYPE} {ITEM-ID} Exceeds Approval Threshold | {ITEM-TYPE} {ITEM-ID} exceeds the auto-approval threshold by {ITEM-VALUE}. Requires approval from: {APPROVER-ROLE}. Forwarded for review. Deadline: {DUE-DATE}. | {ITEM-TYPE},{ITEM-ID},{ITEM-VALUE},{APPROVER-ROLE},{DUE-DATE} | Email,Push
TMPL-022 | Approval Rejection Notice | {ITEM-NAME} Approval Rejected | Your submission '{ITEM-NAME}' (Ref: {ITEM-ID}) has been rejected by {REJECTOR}. Reason: {REJECTION-REASON}. Please address feedback and resubmit. | {ITEM-NAME},{ITEM-ID},{REJECTOR},{REJECTION-REASON},{FEEDBACK-LINK} | Email,Push
TMPL-023 | Risk Escalation L1 | Risk {RISK-ID} Escalated to Level 1 | Risk {RISK-ID} has been escalated to Level 1 (Project Manager escalation). Title: {RISK-TITLE}. Impact: {IMPACT-LEVEL}. Escalation reason: {ESCALATION-REASON}. | {RISK-ID},{RISK-TITLE},{IMPACT-LEVEL},{ESCALATION-REASON} | Email,In-App
TMPL-024 | Risk Escalation L2 | URGENT: Risk {RISK-ID} Escalated to Level 2 | URGENT: Risk {RISK-ID} has been escalated to Level 2 (Program Control escalation). Title: {RISK-TITLE}. Impact: {IMPACT-LEVEL}. Immediate review required. | {RISK-ID},{RISK-TITLE},{IMPACT-LEVEL},{ESCALATION-REASON} | Email,SMS,Push
TMPL-025 | Risk Escalation L3 | CRITICAL: Risk {RISK-ID} Escalated to Level 3 | CRITICAL: Risk {RISK-ID} has been escalated to Level 3 (Executive escalation). Requires immediate intervention. Title: {RISK-TITLE}. Impact: {IMPACT-LEVEL}. Escalation: {ESCALATION-REASON}. | {RISK-ID},{RISK-TITLE},{IMPACT-LEVEL},{ESCALATION-REASON} | Email,SMS,Push
TMPL-026 | Score Alert | Contractor Performance Score Updated | Contractor {CONTR-NAME} performance score has been updated. New Score: {NEW-SCORE}/100. Previous Score: {PREV-SCORE}. Updated: {UPDATE-DATE}. Trend: {TREND}. | {CONTR-NAME},{NEW-SCORE},{PREV-SCORE},{UPDATE-DATE},{TREND} | Email,In-App
TMPL-027 | Performance Alert | ALERT: Contractor {CONTR-NAME} Score Below Threshold | ALERT: Contractor {CONTR-NAME} performance score ({CURRENT-SCORE}) is below acceptable threshold ({THRESHOLD}). Trend: {TREND}. Review and corrective action plan required. | {CONTR-NAME},{CURRENT-SCORE},{THRESHOLD},{TREND},{CORRECTIVE-ACTION-DUE} | Email,SMS,Push
TMPL-028 | Milestone Notification | Handover Milestone {MILESTONE-ID} Initiated | Handover milestone '{MILESTONE-NAME}' has been initiated. Expected completion: {TARGET-DATE}. Status: IN PROGRESS. Checklist items: {TOTAL-ITEMS}. Pending: {PENDING-ITEMS}. | {MILESTONE-ID},{MILESTONE-NAME},{TARGET-DATE},{TOTAL-ITEMS},{PENDING-ITEMS} | Email,Push
TMPL-029 | Task Assignment | Handover Task {TASK-ID} Assigned to You | Handover task '{TASK-NAME}' has been assigned. Milestone: {MILESTONE-NAME}. Due date: {DUE-DATE}. Description: {TASK-DESC}. Access via: {LINK} | {TASK-ID},{TASK-NAME},{MILESTONE-NAME},{DUE-DATE},{TASK-DESC},{LINK} | Email,In-App
TMPL-030 | Defects Notification | Handover Defects List Finalized: {DEFECT-COUNT} Items | Handover defects list for {MILESTONE-NAME} has been finalized. Total defects: {DEFECT-COUNT}. Critical: {CRIT-COUNT}, Major: {MAJ-COUNT}, Minor: {MIN-COUNT}. Remediation deadline: {REMEDIATION-DUE}. | {MILESTONE-NAME},{DEFECT-COUNT},{CRIT-COUNT},{MAJ-COUNT},{MIN-COUNT},{REMEDIATION-DUE} | Email,Push
TMPL-031 | Meeting Scheduled | Meeting Scheduled: {MEETING-TITLE} | Meeting invitation: {MEETING-TITLE}. Date: {MEETING-DATE} at {MEETING-TIME}. Location/Link: {LOCATION}. Attendees: {ATTENDEE-COUNT}. Please RSVP. | {MEETING-TITLE},{MEETING-DATE},{MEETING-TIME},{LOCATION},{ATTENDEE-COUNT} | Email,Push
TMPL-032 | Action Assignment | Meeting Action Assigned: {ACTION-TITLE} | Action from meeting has been assigned to you. Action: {ACTION-TITLE}. Due: {ACTION-DUE}. Owner: {ACTION-OWNER}. Meeting: {MEETING-TITLE}. Details: {ACTION-DESC}. | {ACTION-TITLE},{ACTION-DUE},{ACTION-OWNER},{MEETING-TITLE},{ACTION-DESC} | Email,In-App
TMPL-033 | Action Overdue Alert | OVERDUE: Meeting Action {ACTION-ID} Past Due | OVERDUE: Action {ACTION-ID} '{ACTION-TITLE}' was due {DAYS-OVERDUE} days ago on {DUE-DATE}. Immediate completion required. Escalating to project manager. Status: {STATUS} | {ACTION-ID},{ACTION-TITLE},{DAYS-OVERDUE},{DUE-DATE},{STATUS},{OWNER} | Email,SMS,Push
TMPL-034 | Anomaly Alert | Dashboard Anomaly Detected | System detected an anomaly in {MODULE-NAME}. Type: {ANOMALY-TYPE}. Severity: {SEVERITY}. Affected KPI: {KPI-NAME}. Threshold: {THRESHOLD}, Current: {CURRENT-VALUE}. Review required. | {MODULE-NAME},{ANOMALY-TYPE},{SEVERITY},{KPI-NAME},{THRESHOLD},{CURRENT-VALUE} | Email,Push
TMPL-035 | Critical System Alert | CRITICAL: System Alert - {ALERT-TYPE} | CRITICAL SYSTEM ALERT: {ALERT-TYPE}. Module: {MODULE-NAME}. Status: {STATUS}. Impact: {IMPACT}. Action: {REQUIRED-ACTION}. Timestamp: {ALERT-TIME}. Escalating to system administrator. | {ALERT-TYPE},{MODULE-NAME},{STATUS},{IMPACT},{REQUIRED-ACTION},{ALERT-TIME} | Email,SMS,Push
TMPL-036 | NOD Received | CRITICAL: Notice of Default Received - {NOD-ID} | CRITICAL: Notice of Default {NOD-ID} received from {SENDER}. Date received: {RECEIVE-DATE}. Response deadline: {RESPONSE-DUE} ({HOURS-TO-DUE} hours). Details: {NOD-SUMMARY}. Escalating to legal and management. | {NOD-ID},{SENDER},{RECEIVE-DATE},{RESPONSE-DUE},{HOURS-TO-DUE},{NOD-SUMMARY} | Email,SMS,Push
TMPL-037 | Deadline Critical Warning | CRITICAL: {ACTION-NAME} Deadline in 12 HOURS | CRITICAL DEADLINE: {ACTION-NAME} is due in approximately 12 HOURS at {DUE-DATE} {DUE-TIME}. Immediate action required to avoid breach. Status: {CURRENT-STATUS}. Reference: {ITEM-REF}. | {ACTION-NAME},{DUE-DATE},{DUE-TIME},{CURRENT-STATUS},{ITEM-REF} | Email,SMS
TMPL-038 | Time-Bar Notice | Claim Time-Bar Period Initiated: {CLAIM-ID} | Claim time-bar period has been initiated for {CLAIM-ID}. Notice date: {NOTICE-DATE}. Notice period: 28 days. Detailed claim due by: {CLAIM-DUE}. Failure to submit within timeframe may forfeit claim rights. Reference: SC 20.2.1 | {CLAIM-ID},{NOTICE-DATE},{CLAIM-DUE},{CLAIM-TITLE} | Email,SMS,Push
TMPL-039 | Time-Bar Warning D-7 | URGENT: Claim Time-Bar Expires in 7 Days - {CLAIM-ID} | URGENT: Time-bar period for claim {CLAIM-ID} expires in 7 DAYS. Final deadline: {FINAL-DUE} at {FINAL-TIME}. Detailed claim submission must be completed by this deadline to preserve claim rights. Reference: SC 20.2.1 / SC 20.2.4 | {CLAIM-ID},{FINAL-DUE},{FINAL-TIME},{DAYS-REMAINING} | Email,SMS,Push
TMPL-040 | Time-Bar Warning D-3 | CRITICAL: Claim Time-Bar Expires in 3 Days - {CLAIM-ID} | CRITICAL: Time-bar period for claim {CLAIM-ID} expires in 3 DAYS. Final deadline: {FINAL-DUE} at {FINAL-TIME}. Submission deadline approaching. Immediate action required. Reference: SC 20.2.1 / SC 20.2.4 | {CLAIM-ID},{FINAL-DUE},{FINAL-TIME},{DAYS-REMAINING} | Email,SMS
TMPL-041 | Time-Bar Critical | CRITICAL: Claim Time-Bar EXPIRING - {CLAIM-ID} | CRITICAL: Time-bar period for claim {CLAIM-ID} is EXPIRING. Final deadline: {FINAL-DUE} at {FINAL-TIME}. Less than 24 hours remaining. IMMEDIATE submission required or claim rights will be forfeited. Reference: SC 20.2.1 / SC 20.2.4 | {CLAIM-ID},{FINAL-DUE},{FINAL-TIME},{HOURS-REMAINING} | Email,SMS,Push
TMPL-042 | Detailed Claim Due | Detailed Claim Submission Due: {CLAIM-ID} | Detailed claim submission is now due for {CLAIM-ID}. Due date: {CLAIM-DUE} at {CLAIM-TIME}. Please submit complete claim documentation within the prescribed timeframe. Reference: SC 20.2.4 | {CLAIM-ID},{CLAIM-DUE},{CLAIM-TIME},{SUPPORTING-DOCS-REQUIRED} | Email,SMS,Push
TMPL-043 | Attachment Notification | Correspondence Attachment Received | Correspondence {CORR-ID} includes attachment: {ATTACH-NAME}. File type: {FILE-TYPE}. Size: {FILE-SIZE}. Received: {RECEIVE-DATE}. Action required by: {ACTION-DUE}. Download via: {LINK} | {CORR-ID},{ATTACH-NAME},{FILE-TYPE},{FILE-SIZE},{RECEIVE-DATE},{ACTION-DUE} | Email,In-App
TMPL-044 | Financial Impact Alert | VI {VI-ID} Financial Impact Alert - {VALUE-IMPACT} | Variation Instruction {VI-ID} has estimated financial impact of {VALUE-IMPACT}, exceeding threshold of {THRESHOLD}. Commercial evaluation priority escalated. Review deadline: {DUE-DATE}. Requires senior financial approval. | {VI-ID},{VALUE-IMPACT},{THRESHOLD},{DUE-DATE} | Email,Push
TMPL-045 | IPC Review Alert | IPC {IPC-ID} Discrepancy Identified | Discrepancy identified in IPC {IPC-ID} during certification review. Issue: {DISCREPANCY-DESC}. Amount impact: {AMOUNT-VARIANCE}. Corrective action required. Forwarded to {REVIEWER}. Review deadline: {DUE-DATE}. | {IPC-ID},{DISCREPANCY-DESC},{AMOUNT-VARIANCE},{REVIEWER},{DUE-DATE} | Email,Push
TMPL-046 | Risk Update Notification | Risk Register Updated: {RISK-ID} | Risk register has been updated. Risk {RISK-ID}: {RISK-TITLE}. Change: {CHANGE-DESC}. New status: {NEW-STATUS}. Updated by: {UPDATED-BY}. Updated: {UPDATE-DATE}. | {RISK-ID},{RISK-TITLE},{CHANGE-DESC},{NEW-STATUS},{UPDATED-BY},{UPDATE-DATE} | Email,In-App
TMPL-047 | KPI Alert | Contractor {CONTR-NAME} KPI Threshold Breach | Key Performance Indicator breach alert for contractor {CONTR-NAME}. KPI: {KPI-NAME}. Threshold: {THRESHOLD}. Current: {CURRENT-VALUE}. Variance: {VARIANCE}. Corrective action plan due: {CAP-DUE}. | {CONTR-NAME},{KPI-NAME},{THRESHOLD},{CURRENT-VALUE},{VARIANCE},{CAP-DUE} | Email,SMS,Push
TMPL-048 | Defect Overdue Alert | OVERDUE: Handover Defect Remediation {DEFECT-ID} | Remediation for defect {DEFECT-ID} is OVERDUE. Original deadline: {ORIG-DUE}. Days overdue: {DAYS-OVERDUE}. Status: {STATUS}. Escalating to project manager and contractor management. New deadline: {NEW-DUE}. | {DEFECT-ID},{ORIG-DUE},{DAYS-OVERDUE},{STATUS},{NEW-DUE} | Email,SMS,Push
TMPL-049 | Maintenance Notice | System Maintenance Scheduled: {MAINT-WINDOW} | System maintenance window scheduled. Date: {MAINT-DATE} from {MAINT-START} to {MAINT-END}. Expected downtime: {DOWNTIME}. Systems affected: {AFFECTED-SYSTEMS}. Impact: {IMPACT}. During this time: {DURING-MSG}. | {MAINT-WINDOW},{MAINT-DATE},{MAINT-START},{MAINT-END},{DOWNTIME},{AFFECTED-SYSTEMS},{IMPACT} | Email,In-App
TMPL-050 | Backup Confirmation | System Backup Completed Successfully | Automatic system backup completed successfully. Backup timestamp: {BACKUP-TIME}. Data backed up: {DATA-SIZE}. Backup location: {BACKUP-LOC}. Next scheduled backup: {NEXT-BACKUP}. No action required. | {BACKUP-TIME},{DATA-SIZE},{BACKUP-LOC},{NEXT-BACKUP} | Email

## Escalation Notification Matrix
Escalation Level | Time Offset | Primary Channel | Secondary Channel | Recipient Roles | Auto-Escalate | Requires Acknowledgement
L1 | Immediate (0 min) | Email | In-App | PM,DOC-ADM,CONTR-ADM | Yes | No
L1 | 2 hours | Email | In-App | PM,CONTR-ADM | Yes | No
L1 | 4 hours | Email,Push | SMS | PM,CONTR-ADM | Yes | No
L2 | 6 hours | Email,SMS,Push | In-App | PM,PC,FIN | Yes | Yes
L2 | 12 hours | Email,SMS,Push | In-App | PM,PC,FIN,EXEC | Yes | Yes
L3 | 24 hours | Email,SMS,Push | In-App | EXEC,PC,LEGAL | Yes | Yes
L4 | 48 hours | Email,SMS,Push | Phone | EXEC,LEGAL,OWNER | Auto | Yes
L5 | 72 hours | Email,SMS,Push,Phone | Escalation call | OWNER,BOARD | Halt | Yes
Critical | Immediate | SMS,Push,Email | Phone | PC,EXEC,LEGAL,CONTR-MGR | Yes | Yes

## Notification Preferences
Role ID | Role Name | Email | SMS | In-App | Push | Digest Frequency | Quiet Hours | Override for Critical
PM | Project Manager | Yes | Yes | Yes | Yes | Daily | 22:00-07:00 (SGT) | Yes
PC | Project Control | Yes | Yes | Yes | Yes | Daily | 22:00-07:00 (SGT) | Yes
DOC-ADM | Document Administrator | Yes | No | Yes | No | Hourly | None | Yes
DOC-REV | Document Reviewer | Yes | Yes | Yes | Yes | Daily | 22:00-07:00 (SGT) | Yes
CONTR-ADM | Contractor Administrator | Yes | Yes | Yes | Yes | Daily | 22:00-07:00 (SGT) | Yes
CONTR | Contractor Representative | Yes | Yes | Yes | Yes | Daily | 22:00-07:00 (SGT) | Yes
FIN | Finance Manager | Yes | Yes | Yes | Yes | Daily | 22:00-07:00 (SGT) | Yes
APR-MGR | Approval Manager | Yes | Yes | Yes | Yes | Daily | 22:00-07:00 (SGT) | Yes
DESIGN-MGR | Design Manager | Yes | Yes | Yes | Yes | Daily | 22:00-07:00 (SGT) | Yes
HO-MGR | Handover Manager | Yes | Yes | Yes | Yes | Daily | 22:00-07:00 (SGT) | Yes
CONTR-MGR | Contractor Manager | Yes | Yes | Yes | Yes | Daily | 22:00-07:00 (SGT) | Yes
LEGAL | Legal Advisor | Yes | Yes | Yes | Yes | Daily | 22:00-07:00 (SGT) | Yes
EXEC | Executive Sponsor | Yes | Yes | Yes | Yes | Daily | 22:00-07:00 (SGT) | Yes
SYS-ADM | System Administrator | Yes | Yes | Yes | Yes | Real-time | None | Yes
ORIGINATOR | Document Originator | Yes | Yes | Yes | Yes | Daily | 22:00-07:00 (SGT) | Yes

## Cross-Reference
Reference | Type | Target System/Document | Purpose | Link/Location | Last Updated
HAI-SS-NAR-2026-001 | Register | Notification Alert Rules Register | Primary notification rules governance | This workbook - Sheet 1: Notification Rules Register | 2026-03-01
HAI-SS-ATP-2026-001 | Templates | Alert Templates Library | Standardized notification templates for consistent communication | This workbook - Sheet 2: Alert Templates | 2026-03-01
HAI-SS-ENM-2026-001 | Matrix | Escalation Notification Matrix | Escalation paths and response times per severity level | This workbook - Sheet 3: Escalation Notification Matrix | 2026-03-01
HAI-SS-NPR-2026-001 | Preferences | Notification Preferences Registry | Per-role notification channel preferences and quiet hours | This workbook - Sheet 4: Notification Preferences | 2026-03-01
PF-22 | Module | Notification Engine | Intelligent notification delivery system for HAI platform | HAI_Notification_Engine_Rules.xlsx | 2026-02-28
WF-ENG | Related Document | Workflow Engine Rules | Document state machine and process flow definitions | HAI_Workflow_Engine_Rules.xlsx | 2026-02-15
URD-MATRIX | Related Document | User Roles & Permissions Matrix | Role definitions and permission mappings for access control | HAI_User_Roles_Permissions_Matrix.xlsx | 2026-02-20
COMM-PLAN | Related Document | Communication Plan | Project communication strategy and stakeholder engagement | HAI_A068_Communication_Plan.xlsx | 2026-02-10
SC 1.1.2 | Contract Reference | FIDIC 1999 Red Book Section 1.1.2 | Document management and submission requirements | Contract [Project Reference] Section 1.1.2 | Reference
SC 1.1.2.32 | Contract Reference | FIDIC 1999 Red Book Section 1.1.2.32 | Notice of Default procedures and timeframes | Contract [Project Reference] Section 1.1.2.32 | Reference
SC 1.1.3 | Contract Reference | FIDIC 1999 Red Book Section 1.1.3 | Correspondence and communications procedures | Contract [Project Reference] Section 1.1.3 | Reference
SC 3.1 | Contract Reference | FIDIC 1999 Red Book Section 3.1 | Engineer's approval and certification powers | Contract [Project Reference] Section 3.1 | Reference
SC 4.2 | Contract Reference | FIDIC 1999 Red Book Section 4.2 | Contractor's performance obligations | Contract [Project Reference] Section 4.2 | Reference
SC 5.1 | Contract Reference | FIDIC 1999 Red Book Section 5.1 | Design requirements and change management | Contract [Project Reference] Section 5.1 | Reference
SC 8.4 | Contract Reference | FIDIC 1999 Red Book Section 8.4 | Stage gate and progress milestones | Contract [Project Reference] Section 8.4 | Reference
SC 9.4 | Contract Reference | FIDIC 1999 Red Book Section 9.4 | Risk management and contractor risk responsibility | Contract [Project Reference] Section 9.4 | Reference
SC 13.1 | Contract Reference | FIDIC 1999 Red Book Section 13.1 | Variation instruction procedures (parallel commercial tracks) | Contract [Project Reference] Section 13.1 | Reference
SC 14.6 | Contract Reference | FIDIC 1999 Red Book Section 14.6 | Payment certificates and interim payment procedures | Contract [Project Reference] Section 14.6 | Reference
SC 18.1 | Contract Reference | FIDIC 1999 Red Book Section 18.1 | Handover and defects liability | Contract [Project Reference] Section 18.1 | Reference
SC 20.1 | Contract Reference | FIDIC 1999 Red Book Section 20.1 | Claims procedures - general | Contract [Project Reference] Section 20.1 | Reference
SC 20.2.1 | Contract Reference | FIDIC 1999 Red Book Section 20.2.1 | Claims notice period (28 days from event) | Contract [Project Reference] Section 20.2.1 | Reference
SC 20.2.4 | Contract Reference | FIDIC 1999 Red Book Section 20.2.4 | Detailed claim submission timeframe (7 days from notice) | Contract [Project Reference] Section 20.2.4 | Reference