## Form Register
Form ID | Form Name | PF Reference | Module | Purpose | Mandatory Fields | Optional Fields | Validation Rules | Approval Required | Template Available | Status
FRM-001 | Document Submission Form | PF-01 | Document Management | Submit technical documents for review | doc ref, title, discipline, type, revision, originator, date | description, file attachment | File format validation, date format check | Yes | Yes | Active
FRM-002 | Document Review Form | PF-01 | Document Management | Review and approve submitted documents | reviewer, status code, document ref | comments, markup file | Status code validation (A/B/C/D) | Yes | Yes | Active
FRM-003 | Correspondence Template | PF-02 | Communication | Record project correspondence | ref no, to, from, subject, date | body, attachments, response deadline | Email format validation, date sequence | No | Yes | Active
FRM-004 | Variation Order Form | PF-03 | Change Control | Request and track design/scope variations | VO number, description, initiator, estimated value | drawings affected, SC 13.1 indicator | Numeric validation, reference format | Yes | Yes | Active
FRM-005 | RFP Template | PF-04 | Procurement | Issue Request for Proposals | procurement ref, scope, budget, deadline | evaluation criteria, vendor list | Currency format (QAR), date validation | Yes | Yes | Active
FRM-006 | Stage Gate Checklist | PF-05 | Project Controls | Verify completion of stage gate prerequisites | gate number, prerequisites, evidence | reviewer sign-off, notes | Gate sequence validation | Yes | Yes | Active
FRM-007 | Freeze Exception Request | PF-06 | Baseline Control | Request exception to design freeze | exception ref, justification, impact | approval chain, risk rating | Reference format, impact assessment | Yes | Yes | Active
FRM-008 | Authority Submission Cover | PF-07 | Regulatory | Cover sheet for regulatory submissions | authority name, submission type, reference, date | status, notes | Authority code validation | Yes | Yes | Active
FRM-009 | IPC Application Form | PF-08 | Financial | Monthly progress payment application | IPC number, period, claimed amount, retention | previous certified, current claim | Currency validation, retention calculation | Yes | Yes | Active
FRM-010 | Approval Request Form | PF-09 | Approvals | Request approval for deliverables | request type, value, documents | approver chain, deadline | Approval hierarchy validation | Yes | Yes | Active
FRM-011 | Quality Inspection Form | PF-10 | Quality | Record quality inspections and test results | inspection ref, scope, date, inspector | observations, defects, photos | Result code validation | Yes | Yes | Active
FRM-012 | Budget Change Request | PF-11 | Budget Control | Request budget allocation changes | change ref, department, amount, reason | cost breakdown, justification | Amount validation, budget code format | Yes | Yes | Active
FRM-013 | Risk Assessment Form | PF-12 | Risk Management | Identify and assess project risks | risk ID, description, probability, impact | mitigation strategy, owner | Probability/Impact matrix validation | Yes | Yes | Active
FRM-014 | Contractor Scorecard | PF-13 | Performance | Evaluate contractor performance metrics | contractor name, period, score, rating | comments, corrective actions | Score range (0-100) validation | Yes | Yes | Active
FRM-015 | Lesson Learned Report | PF-14 | Knowledge Mgmt | Document lessons learned from activities | lesson ref, category, description, impact | recommendations, owner | Category list validation | No | Yes | Active
FRM-016 | Handover Certificate | PF-15 | Closeout | Certify completion and handover of work | handover ref, scope, date, certifier | defect list, punch list | Signature requirement validation | Yes | Yes | Active
FRM-017 | Meeting Minutes Template | PF-16 | Communication | Record meeting outcomes and actions | meeting ref, date, attendees, location | agenda, decisions, action items, next meeting | Date/attendee format validation | No | Yes | Active
FRM-018 | Stakeholder Query Form | PF-17 | Communication | Capture stakeholder questions/concerns | query ref, stakeholder, date, subject | description, response, resolution date | Status tracking validation | No | Yes | Active
FRM-019 | Report Request Form | PF-18 | Reporting | Request generation of project reports | request ID, report type, frequency, recipient | format, distribution list | Report type code validation | Yes | Yes | Active
FRM-020 | User Access Request | PF-19 | Administration | Request system user account access | user name, email, department, role | manager approval, access level | Role code validation, email format | Yes | Yes | Active
FRM-021 | Integration Event Log | PF-20 | Systems | Log integration events and data transfers | event ID, timestamp, source, destination | record count, status code | Timestamp format, data validation | No | Yes | Active
FRM-022 | Dashboard Configuration | PF-21 | Analytics | Configure reporting dashboards | dashboard ID, owner, widgets, refresh rate | filters, permissions | Widget ID validation | Yes | Yes | Active
FRM-023 | Notification Configuration | PF-22 | Administration | Set up system notifications | notification ID, trigger, recipients, template | frequency, escalation | Trigger code validation, recipient format | Yes | Yes | Active
FRM-024 | Audit Query Form | PF-23 | Compliance | Submit audit-related queries | audit ref, question, category, date | response, supporting docs | Category validation, date sequence | Yes | Yes | Active
FRM-025 | Design Change Notice | PF-03 | Change Control | Communicate design changes to stakeholders | DCN number, change description, affected areas | implementation date, revision summary | DCN sequence validation | Yes | Yes | Active
FRM-026 | Technical Submittal | PF-01 | Document Management | Submit technical submittals for approval | submittal number, item, model/spec, quantity | remarks, approval status | Submittal numbering format | Yes | Yes | Active
FRM-027 | Shop Drawing Transmittal | PF-02 | Communication | Transmit shop drawings for review | transmittal number, drawings attached, remarks | revision level, date received | Drawing reference format | Yes | Yes | Active
FRM-028 | Inspection Report | PF-10 | Quality | Document on-site quality inspections | inspection ID, location, date, category | findings, photos, corrective actions | Location code validation | Yes | Yes | Active
FRM-029 | Material Testing Certificate | PF-10 | Quality | Record material test results | test ID, material, test type, result | laboratory ref, date tested, certification | Test type code validation | Yes | Yes | Active
FRM-030 | Site Progress Report | PF-18 | Reporting | Weekly/monthly construction progress | report period, activities, completion %, issues | schedule status, forecast | Date range validation, percentage checks | Yes | Yes | Active
FRM-031 | Safety Incident Report | PF-14 | Safety | Report safety incidents and near-misses | incident ID, date, location, description | severity level, corrective action | Severity code validation | Yes | Yes | Active
FRM-032 | Environmental Compliance Form | PF-12 | Compliance | Track environmental compliance activities | compliance ref, item, status, date | evidence, certifier | Status code validation | Yes | Yes | Active
FRM-033 | Budget Forecast Update | PF-11 | Budget Control | Update project cost forecast | forecast date, total cost, variance, reason | breakdown by category | Currency format, variance range | Yes | Yes | Active
FRM-034 | Schedule Update Form | PF-05 | Project Controls | Update project schedule and milestones | update date, activities, start/end dates | critical path impact, delays | Date sequence validation | Yes | Yes | Active
FRM-035 | Claim Notification Form | PF-08 | Financial | Notify potential contractual claims | claim ref, date, basis, estimated value | supporting documents, timeline | Claim code validation | Yes | Yes | Active
FRM-036 | Time Sheet Template | PF-08 | Financial | Record labor hours and costs | employee, week of, hours, rate, total | cost code allocation | Hour/rate format validation | Yes | Yes | Active
FRM-037 | Material Receipt Form | PF-04 | Procurement | Record receipt of purchased materials | receipt ID, PO ref, items, quantity, date | condition assessment, storage location | Quantity validation, reference format | Yes | Yes | Active
FRM-038 | Purchase Order Template | PF-04 | Procurement | Create purchase orders | PO number, vendor, items, quantity, price | delivery terms, specifications | Amount validation, vendor code format | Yes | Yes | Active
FRM-039 | Subcontractor Agreement Form | PF-04 | Procurement | Manage subcontractor agreements | SC number, scope, rate/lump sum, duration | insurance requirements, performance bonds | Amount/date validation | Yes | Yes | Active
FRM-040 | Insurance Certificate Request | PF-07 | Regulatory | Request proof of insurance | certificate ref, contractor, policy type, amount | expiration date, issuer | Amount format, date validation | No | Yes | Active
FRM-041 | Permit Application Form | PF-07 | Regulatory | Apply for regulatory permits | permit type, application ref, scope, cost | required documents, authority | Reference format, cost validation | Yes | Yes | Active
FRM-042 | Non-Conformance Report | PF-10 | Quality | Report quality non-conformances | NCR number, description, severity, area | root cause, corrective action, close-out | Severity code, sequence validation | Yes | Yes | Active
FRM-043 | Corrective Action Plan | PF-12 | Compliance | Define and track corrective actions | CAP ID, issue, action, owner, due date | status, completion evidence | Date validation, status tracking | Yes | Yes | Active
FRM-044 | Knowledge Base Entry | PF-14 | Knowledge Mgmt | Document technical knowledge | entry ID, topic, content, author, date | keywords, related items | Format validation, content requirements | No | Yes | Active
FRM-045 | Training Record Form | PF-19 | Administration | Record employee training completion | training ID, employee, course, date, result | certifications, expiration | Date format, result validation | No | Yes | Active
FRM-046 | Change Request Form | PF-03 | Change Control | Request scope or requirement changes | CR number, description, business case, impact | cost impact, schedule impact, priority | Reference format, impact assessment | Yes | Yes | Active
FRM-047 | Configuration Baseline | PF-05 | Project Controls | Record configuration baseline versions | baseline ID, items included, date, approver | version number, release notes | Sequence validation | Yes | Yes | Active
FRM-048 | Performance Metrics Dashboard | PF-21 | Analytics | Track key performance indicators | metric ID, name, target, actual, period | trend, variance, forecast | Numeric validation, date range | No | Yes | Active
FRM-049 | Risk Register Export | PF-12 | Risk Management | Extract and export risk register | export date, risk count, filter criteria | format (Excel/PDF/CSV) | Date/format validation | No | Yes | Active
FRM-050 | Stakeholder Communication Plan | PF-02 | Communication | Define stakeholder engagement strategy | plan ID, stakeholders, frequency, channels | responsibilities, escalation rules | Frequency code validation | Yes | Yes | Active
Document Ref: HAI-SS-FTS-2026-001 ¦ Platform: HAI SkyStruct ¦ Contract: [Project Reference] ¦ FIDIC 1999 Red Book ¦ Qatar

## Field Specifications
Field ID | Field Name | Form(s) Used In | Data Type | Max Length | Required | Validation Rule | Default Value | Dropdown Options
FLD-001 | Document Reference | FRM-001, FRM-002 | Text | 50 | Yes | Format: [DISC]-[TYPE]-[YY]-[####]
FLD-002 | Document Title | FRM-001, FRM-026 | Text | 200 | Yes | Min 10 chars, no special chars
FLD-003 | Discipline | FRM-001, FRM-026 | Dropdown | 30 | Yes | Must match discipline list |  | Structural¦Architectural¦MEP¦Civil¦HVAC¦Electrical¦Fire Safety¦Safety¦Cost¦Schedule
FLD-004 | Document Type | FRM-001 | Dropdown | 30 | Yes | Predefined list |  | Drawing¦Specification¦Report¦Schedule¦Manual¦Calculation¦Procedure
FLD-005 | Revision Level | FRM-001, FRM-027 | Text | 5 | Yes | Format: A, B, C, D... or 0, 1, 2...
FLD-006 | Originator | FRM-001, FRM-009 | User Lookup | 100 | Yes | Valid project team member
FLD-007 | Date | FRM-001, FRM-003, FRM-006, FRM-008 | Date |  | Yes | Format: DD/MM/YYYY
FLD-008 | File Attachment | FRM-001, FRM-002, FRM-027 | File Upload | 500MB | Conditional | PDF, DOCX, XLSX, DWG, JPG only
FLD-009 | Reviewer | FRM-002 | User Lookup | 100 | Yes | Active system user
FLD-010 | Status Code | FRM-002, FRM-021 | Dropdown | 1 | Yes | A=Approved, B=Branded, C=Conditional, D=Disapproved |  | A¦B¦C¦D
FLD-011 | Comments | FRM-002, FRM-006, FRM-018, FRM-031 | Rich Text | 5000 | No | Plain text or formatted
FLD-012 | Markup File | FRM-002 | File Upload | 250MB | No | PDF or DWG with markups
FLD-013 | Correspondence Reference | FRM-003 | Text | 50 | Yes | Format: CORR-YY-[####]
FLD-014 | To | FRM-003, FRM-008, FRM-027 | Text | 200 | Yes | Email or role name
FLD-015 | From | FRM-003 | User Lookup | 100 | Yes | Project team member
FLD-016 | Subject | FRM-003, FRM-018 | Text | 250 | Yes | Min 5 chars
FLD-017 | Body | FRM-003 | Rich Text | 10000 | Yes | Min 20 chars
FLD-018 | Attachments | FRM-003, FRM-035, FRM-041 | File Upload | 100MB | No | Multiple files allowed
FLD-019 | Response Deadline | FRM-003 | Date |  | No | Must be after issue date
FLD-020 | VO Number | FRM-004 | Text | 30 | Yes | Format: VO-[YY]-[####]
FLD-021 | Change Description | FRM-004, FRM-025, FRM-046 | Rich Text | 5000 | Yes | Min 50 chars, technical detail
FLD-022 | Initiator | FRM-004 | User Lookup | 100 | Yes | Valid user
FLD-023 | Estimated Value | FRM-004, FRM-005, FRM-012, FRM-035 | Currency | 15 | Yes | QAR format, >= 0 | 0.00
FLD-024 | Drawings Affected | FRM-004, FRM-025 | Text | 500 | No | Comma-separated drawing refs
FLD-025 | SC 13.1 Indicator | FRM-004 | Checkbox | 1 | No | Parallel track Y/N | N
FLD-026 | Procurement Reference | FRM-005, FRM-037 | Text | 50 | Yes | Format: PROC-YY-[####]
FLD-027 | Scope | FRM-005, FRM-039 | Rich Text | 5000 | Yes | Detailed requirements
FLD-028 | Budget | FRM-005, FRM-012, FRM-033 | Currency | 15 | Yes | QAR format, > 0
FLD-029 | Deadline | FRM-005, FRM-019 | Date |  | Yes | Future date required
FLD-030 | Evaluation Criteria | FRM-005 | Rich Text | 2000 | Yes | Selection methodology
FLD-031 | Gate Number | FRM-006, FRM-034 | Dropdown | 3 | Yes | G1-G10 standard gates |  | G1¦G2¦G3¦G4¦G5¦G6¦G7¦G8¦G9¦G10
FLD-032 | Prerequisites | FRM-006 | Text | 1000 | Yes | List of required items
FLD-033 | Evidence Uploaded | FRM-006 | Checkbox | 1 | Yes | All proof submitted Y/N | N
FLD-034 | Reviewer Sign-off | FRM-006, FRM-010 | User Lookup | 100 | Yes | Authorized reviewer
FLD-035 | Exception Reference | FRM-007 | Text | 50 | Yes | Format: EXCEPT-YY-[####]
FLD-036 | Justification | FRM-007, FRM-043 | Rich Text | 3000 | Yes | Business justification required
FLD-037 | Impact Assessment | FRM-007, FRM-012 | Rich Text | 2000 | Yes | Technical/commercial impact
FLD-038 | Approval Chain | FRM-007, FRM-010 | Text | 500 | Yes | List of approvers in sequence
FLD-039 | Authority Name | FRM-008, FRM-041 | Dropdown | 100 | Yes | Qatar regulatory body |  | Ministry of Municipality¦Qatar Rail¦QNCC¦DocsGov¦Municipality
FLD-040 | Submission Type | FRM-008 | Dropdown | 50 | Yes | Type of submission |  | Permit¦Certificate¦Approval¦License¦Variance
FLD-041 | IPC Number | FRM-009 | Text | 30 | Yes | Format: IPC-[YYYY]-[###]
FLD-042 | Period | FRM-009, FRM-036, FRM-048 | Text | 20 | Yes | Format: MM/YYYY or Week No
FLD-043 | Claimed Amount | FRM-009, FRM-023 | Currency | 15 | Yes | QAR format, >= 0 | 0.00
FLD-044 | Retention | FRM-009 | Currency | 15 | Yes | QAR format, <= Claimed Amount | 0.00
FLD-045 | Previous Certified | FRM-009 | Currency | 15 | Yes | QAR format, read-only calc | 0.00
FLD-046 | Current Claim | FRM-009 | Currency | 15 | Yes | QAR format, auto-calc | 0.00
FLD-047 | Request Type | FRM-010 | Dropdown | 50 | Yes | Type of approval needed |  | Design¦Construction¦Material¦Change¦Waiver¦Exemption
FLD-048 | Value | FRM-010, FRM-012, FRM-023 | Currency | 15 | No | QAR format
FLD-049 | Documents | FRM-010 | File Upload | 500MB | Yes | Supporting documentation
FLD-050 | Approver Chain | FRM-010 | Text | 500 | Yes | Sequential approvers
FLD-051 | Inspection Reference | FRM-011, FRM-028 | Text | 50 | Yes | Format: INSP-YY-[####]
FLD-052 | Inspection Scope | FRM-011, FRM-028 | Rich Text | 2000 | Yes | What was inspected
FLD-053 | Inspector | FRM-011, FRM-028 | User Lookup | 100 | Yes | Qualified inspector
FLD-054 | Observations | FRM-011 | Rich Text | 3000 | No | Inspection findings
FLD-055 | Defects | FRM-011, FRM-016, FRM-042 | Text | 2000 | No | Identified defects
FLD-056 | Photos | FRM-011, FRM-028 | File Upload | 500MB | No | JPG or PNG format
FLD-057 | Change Reference | FRM-012, FRM-046 | Text | 50 | Yes | Format: CHG-YY-[####]
FLD-058 | Department | FRM-012 | Dropdown | 50 | Yes | Project org structure |  | Design¦Construction¦Safety¦Quality¦Finance¦HR
FLD-059 | Reason | FRM-012, FRM-025 | Rich Text | 1500 | Yes | Why change is needed
FLD-060 | Cost Breakdown | FRM-012 | Rich Text | 2000 | No | Detailed cost categories
FLD-061 | Risk ID | FRM-013 | Text | 30 | Yes | Format: RISK-[YY]-[####]
FLD-062 | Risk Description | FRM-013, FRM-049 | Rich Text | 2000 | Yes | Detailed risk statement
FLD-063 | Probability | FRM-013 | Dropdown | 5 | Yes | 1=Low, 2=Medium, 3=High |  | 1-Low¦2-Medium¦3-High
FLD-064 | Impact | FRM-013 | Dropdown | 5 | Yes | 1=Low, 2=Medium, 3=High |  | 1-Low¦2-Medium¦3-High
FLD-065 | Mitigation Strategy | FRM-013 | Rich Text | 2000 | No | Risk response plan
FLD-066 | Owner | FRM-013, FRM-014, FRM-043 | User Lookup | 100 | Yes | Responsible party
FLD-067 | Contractor Name | FRM-014 | Text | 150 | Yes | Legal business name
FLD-068 | Score | FRM-014 | Number | 3 | Yes | 0-100, 2 decimal places
FLD-069 | Rating | FRM-014 | Dropdown | 20 | Yes | Performance classification |  | Excellent¦Good¦Acceptable¦Poor¦Unsatisfactory
FLD-070 | Lesson Reference | FRM-015 | Text | 50 | Yes | Format: LESSON-YY-[####]
FLD-071 | Category | FRM-015, FRM-023 | Dropdown | 30 | Yes | Knowledge classification |  | Technical¦Process¦Commercial¦Safety¦Quality¦Risk
FLD-072 | Impact | FRM-015 | Rich Text | 1000 | No | What was the impact
FLD-073 | Recommendations | FRM-015, FRM-043 | Rich Text | 2000 | No | Suggested improvements
FLD-074 | Handover Reference | FRM-016 | Text | 50 | Yes | Format: HO-YY-[####]
FLD-075 | Handover Scope | FRM-016 | Rich Text | 2000 | Yes | What is being handed over
FLD-076 | Certifier | FRM-016 | User Lookup | 100 | Yes | Authorized certifier
FLD-077 | Defect List | FRM-016 | Text | 3000 | No | Known issues at handover
FLD-078 | Punch List | FRM-016 | Text | 3000 | No | Items to be completed
FLD-079 | Meeting Reference | FRM-017 | Text | 50 | Yes | Format: MTG-YY-[####]
FLD-080 | Attendees | FRM-017, FRM-018 | Text | 500 | Yes | List of participants
FLD-081 | Location | FRM-017, FRM-028, FRM-031 | Dropdown | 100 | No | Physical or virtual meeting location |  | Site¦Office¦Virtual¦Conference Room A¦Conference Room B
FLD-082 | Agenda | FRM-017 | Rich Text | 2000 | Yes | Meeting topics
FLD-083 | Decisions | FRM-017 | Rich Text | 2000 | No | Outcomes and decisions
FLD-084 | Action Items | FRM-017 | Rich Text | 2000 | No | Tasks assigned with owners
FLD-085 | Next Meeting | FRM-017 | Date |  | No | Scheduled next meeting date
FLD-086 | Query Reference | FRM-018 | Text | 50 | Yes | Format: QRY-YY-[####]
FLD-087 | Stakeholder | FRM-018 | Text | 150 | Yes | Stakeholder name/org
FLD-088 | Response | FRM-018, FRM-041 | Rich Text | 2000 | No | Answer to query
FLD-089 | Resolution Date | FRM-018 | Date |  | No | When resolved
FLD-090 | Report Type | FRM-019 | Dropdown | 50 | Yes | Type of report |  | Progress¦Safety¦Budget¦Schedule¦Risk¦Quality¦Compliance
FLD-091 | Frequency | FRM-019, FRM-050 | Dropdown | 20 | Yes | Report generation frequency |  | Daily¦Weekly¦Monthly¦Quarterly¦As Needed
FLD-092 | Recipient | FRM-019 | Text | 200 | Yes | Email or role
FLD-093 | Format | FRM-019, FRM-049 | Dropdown | 20 | Yes | Output format |  | Excel¦PDF¦PowerPoint¦CSV¦Web
FLD-094 | Distribution List | FRM-019 | Text | 500 | No | Comma-separated recipients
FLD-095 | User Name | FRM-020 | Text | 100 | Yes | System login username
FLD-096 | Email | FRM-020, FRM-036 | Text | 100 | Yes | Valid email format
FLD-097 | Access Level | FRM-020 | Dropdown | 30 | Yes | System permission level |  | Read Only¦Contributor¦Approver¦Administrator
FLD-098 | Event ID | FRM-021 | Text | 50 | Yes | Format: EVT-YY-[####]
FLD-099 | Timestamp | FRM-021 | Date |  | Yes | Format: DD/MM/YYYY HH:MM
FLD-100 | Source System | FRM-021 | Text | 100 | Yes | Originating system name

## Template Library
Template ID | Template Name | Category | Format | PF Reference | Last Updated | Version | Description
TPL-001 | Official Letter Template | Letters | DOCX | PF-02 | 2026-02-15 | 2.1 | Standard letterhead with compliance footer
TPL-002 | Memorandum Format | Letters | DOCX | PF-02 | 2026-02-10 | 1.8 | Internal memo layout with distribution list
TPL-003 | Cover Letter for Submissions | Cover Pages | DOCX | PF-01, PF-07 | 2026-02-20 | 3.0 | Professional cover page for regulatory submissions
TPL-004 | Transmittal Slip | Transmittals | DOCX | PF-02 | 2026-02-12 | 2.2 | Document transmittal with revision tracking
TPL-005 | Inspection Report Standard | Reports | DOCX | PF-10 | 2026-02-18 | 4.1 | Comprehensive inspection documentation template
TPL-006 | Progress Report Format | Reports | XLSX | PF-18 | 2026-02-19 | 3.5 | Monthly progress tracking with charts
TPL-007 | Risk Register Template | Checklists | XLSX | PF-12 | 2026-02-17 | 2.9 | Risk identification and assessment matrix
TPL-008 | Meeting Minutes Standard | Meeting Minutes | DOCX | PF-16 | 2026-02-14 | 3.3 | Formatted minutes with action tracking
TPL-009 | Checklist - Quality Gate 1 | Checklists | DOCX | PF-05 | 2026-02-16 | 2.0 | G1 prerequisites and sign-off
TPL-010 | Checklist - Quality Gate 2 | Checklists | DOCX | PF-05 | 2026-02-16 | 2.0 | G2 prerequisites and sign-off
TPL-011 | Variation Order Template | Forms | XLSX | PF-03 | 2026-02-13 | 1.5 | VO issuance and valuation form
TPL-012 | Change Request Form | Forms | DOCX | PF-03 | 2026-02-11 | 2.3 | Formal change request with impact analysis
TPL-013 | Non-Conformance Report | Forms | DOCX | PF-10 | 2026-02-15 | 3.2 | Quality NCR with corrective action plan
TPL-014 | Handover Certificate | Certificates | DOCX | PF-15 | 2026-02-20 | 1.9 | Formal completion and handover certification
TPL-015 | Inspection Certificate | Certificates | DOCX | PF-10 | 2026-02-18 | 2.1 | Certified inspection results
TPL-016 | Insurance Certificate Request | Certificates | DOCX | PF-07 | 2026-02-17 | 1.7 | Proof of insurance requirement form
TPL-017 | Payment Certificate Template | Certificates | XLSX | PF-08 | 2026-02-19 | 4.2 | IPC certification with retention tracking
TPL-018 | Claim Notice Template | Claims Notices | DOCX | PF-08 | 2026-02-12 | 2.5 | Formal contractual claim notification
TPL-019 | Safety Incident Report | Reports | DOCX | PF-14 | 2026-02-14 | 3.4 | Safety incident documentation and follow-up
TPL-020 | Environmental Compliance Checklist | Checklists | XLSX | PF-12 | 2026-02-13 | 1.8 | Environmental compliance tracking
TPL-021 | Permit Application - Municipal | Forms | DOCX | PF-07 | 2026-02-16 | 2.2 | Municipality construction permit application
TPL-022 | Permit Application - Railway | Forms | DOCX | PF-07 | 2026-02-16 | 1.5 | Qatar Rail crossing/interface permit
TPL-023 | Subcontract Template | Forms | DOCX | PF-04 | 2026-02-10 | 3.1 | Standard subcontract with FIDIC 1999 RB terms
TPL-024 | PO Template - Materials | Forms | XLSX | PF-04 | 2026-02-11 | 2.0 | Material purchase order
TPL-025 | PO Template - Services | Forms | XLSX | PF-04 | 2026-02-11 | 2.0 | Service purchase order
TPL-026 | Time Sheet - Labor | Forms | XLSX | PF-08 | 2026-02-12 | 1.9 | Weekly labor tracking and cost allocation
TPL-027 | Material Receipt Form | Forms | DOCX | PF-04 | 2026-02-08 | 1.6 | Material receipt and inspection
TPL-028 | Design Change Notice | Cover Pages | DOCX | PF-03 | 2026-02-09 | 2.4 | DCN issuance and distribution
TPL-029 | Shop Drawing Transmittal | Transmittals | DOCX | PF-02 | 2026-02-07 | 2.8 | Shop drawing submission and tracking
TPL-030 | Technical Submittal Form | Forms | DOCX | PF-01 | 2026-02-06 | 3.3 | Equipment/material submittal approval

## Workflow Mapping
Form ID | Submission Route | Review Route | Approval Route | Archive Route | SLA | Escalation Rule Ref
FRM-001 | Originator → Document Manager | Doc Manager → Reviewer | Reviewer → Approval Board | Archive after 7 year retention | 5 business days | ESC-001
FRM-002 | Reviewer → Archive | Parallel review by QA team | N/A (informational) | Archive on completion | 2 business days | N/A
FRM-003 | Sender → Recipient | Recipient acknowledges receipt | N/A (communication) | Archive by month | Same day | ESC-002
FRM-004 | Initiator → Change Control | Change Control Board review | CM Lead approval → Contractor | Archive with contract amendments | 10 business days | ESC-003
FRM-005 | Procurement → Vendor selection | Evaluation committee scores | Finance Director + PM approval | Archive by fiscal year | 15 business days | ESC-004
FRM-006 | PM → Gate Manager | Gate Manager verification | Steering Committee sign-off | Archive per project phase | 3 business days | ESC-005
FRM-007 | Requester → Baseline Admin | Technical review by design lead | Baseline Control Board approval | Archive with approved variances | 7 business days | ESC-006
FRM-008 | Submitter → Regulatory Affairs | Authority document preparation | Director + Authority submission | Archive per authority file | 20 business days | ESC-007
FRM-009 | Contractor → Finance | Finance review and certification | PM + Finance Director approval | Archive by contract year | 5 business days | ESC-008
FRM-010 | Requester → Approver | Approval verification | Sequential approver chain | Archive by approval type | 2 business days | ESC-009
FRM-011 | Inspector → QA Manager | QA data review and analysis | QA Lead certification | Archive by location/activity | 1 business day | ESC-010
FRM-012 | Dept → Finance Analyst | Finance review of impact | Finance Director + CFO approval | Archive by budget cycle | 8 business days | ESC-011
FRM-013 | Risk Owner → Risk Officer | Risk assessment review | Risk Committee approval | Archive per risk lifecycle | 5 business days | ESC-012
FRM-014 | PM → HR/Procurement | Performance data validation | Contractor review → Approval | Archive by contract period | Monthly | ESC-013
FRM-015 | Project team → Knowledge Mgmt | KM officer review | Informational only | Archive to knowledge base | 3 business days | N/A
FRM-016 | Contractor → PM | PM verification of scope | Client + PM final sign-off | Archive with project closeout | 2 business days | ESC-014
FRM-017 | Meeting organizer → Attendees | Action owner verification | PM review for accuracy | Archive by meeting series | Same day | ESC-015
FRM-018 | Stakeholder → PM | PM investigation | Response preparation and approval | Archive by stakeholder | 5 business days | ESC-016
FRM-019 | Requester → Reporting team | Report generation | PM review and distribution | Archive by report type | As per frequency | ESC-017
FRM-020 | Requester → IT Admin | IT security review | IT Director approval | Archive per user lifecycle | 3 business days | ESC-018
FRM-021 | Source system → Integration Log | Data validation | Integration manager review | Archive per system interface | Real-time | ESC-019
FRM-022 | Dashboard owner → Analytics | Analytics review | BI Lead approval | Archive per dashboard version | 5 business days | ESC-020
FRM-023 | Admin → Notification Engine | Engine configuration | IT approval → Implementation | Archive per notification type | 2 business days | ESC-021
FRM-024 | Internal audit → Audit team | Audit trail review | Audit manager + CFO approval | Archive per audit cycle | 10 business days | ESC-022
FRM-025 | Design lead → Change control | CCB technical review | Design Director + Client approval | Archive with design records | 8 business days | ESC-023
FRM-026 | Supplier → Procurement | QA verification | PM + Approver sign-off | Archive by item type | 3 business days | ESC-024
FRM-027 | Contractor → Design team | Discipline lead review | Design lead approval → Return | Archive by drawing set | 5 business days | ESC-025
FRM-028 | Inspector → Site QA Manager | QA analysis | QA lead certification | Archive by location | 1 business day | ESC-026
FRM-029 | Lab → Materials engineer | Test result validation | Materials lead certification | Archive per material lot | 2 business days | ESC-027
FRM-030 | Site manager → PM | Schedule coordination | PM review and distribution | Archive by week/month | Weekly | ESC-028

## Cross-Reference
Reference Type | Document/System | Location/Link | Version | Last Updated | PF Coverage
Process Framework | PF-01 Document Management | /HAI_Process_Frameworks/PF_01_Document_Management.docx | 1.3 | 2026-02-18 | FRM-001, FRM-002, FRM-026
Process Framework | PF-02 Communication & Correspondence | /HAI_Process_Frameworks/PF_02_Communication.docx | 1.2 | 2026-02-17 | FRM-003, FRM-017, FRM-027, FRM-050
Process Framework | PF-03 Change Control | /HAI_Process_Frameworks/PF_03_Change_Control.docx | 2.1 | 2026-02-20 | FRM-004, FRM-025, FRM-046
Process Framework | PF-04 Procurement | /HAI_Process_Frameworks/PF_04_Procurement.docx | 1.5 | 2026-02-19 | FRM-005, FRM-037, FRM-038, FRM-039
Process Framework | PF-05 Project Controls & Stage Gates | /HAI_Process_Frameworks/PF_05_Project_Controls.docx | 2.0 | 2026-02-16 | FRM-006, FRM-034, FRM-047
Process Framework | PF-06 Baseline & Design Freeze | /HAI_Process_Frameworks/PF_06_Baseline_Management.docx | 1.4 | 2026-02-15 | FRM-007
Process Framework | PF-07 Regulatory & Authority Submissions | /HAI_Process_Frameworks/PF_07_Regulatory.docx | 1.6 | 2026-02-14 | FRM-008, FRM-040, FRM-041
Process Framework | PF-08 Financial & Payments | /HAI_Process_Frameworks/PF_08_Financial.docx | 2.2 | 2026-02-13 | FRM-009, FRM-035, FRM-036
Process Framework | PF-09 Approvals & Sign-offs | /HAI_Process_Frameworks/PF_09_Approvals.docx | 1.3 | 2026-02-12 | FRM-010
Process Framework | PF-10 Quality Assurance | /HAI_Process_Frameworks/PF_10_Quality.docx | 3.1 | 2026-02-11 | FRM-011, FRM-028, FRM-029, FRM-042
Process Framework | PF-11 Budget Control | /HAI_Process_Frameworks/PF_11_Budget_Control.docx | 1.8 | 2026-02-10 | FRM-012, FRM-032, FRM-033
Process Framework | PF-12 Risk Management | /HAI_Process_Frameworks/PF_12_Risk_Management.docx | 2.3 | 2026-02-09 | FRM-013, FRM-043, FRM-049
Process Framework | PF-13 Performance Management | /HAI_Process_Frameworks/PF_13_Performance.docx | 1.5 | 2026-02-08 | FRM-014
Process Framework | PF-14 Knowledge Management & Lessons Learned | /HAI_Process_Frameworks/PF_14_Knowledge_Mgmt.docx | 2.0 | 2026-02-07 | FRM-015, FRM-031, FRM-044
Process Framework | PF-15 Closeout & Handover | /HAI_Process_Frameworks/PF_15_Closeout.docx | 1.7 | 2026-02-06 | FRM-016
Process Framework | PF-16 Meeting Management | /HAI_Process_Frameworks/PF_16_Meetings.docx | 1.4 | 2026-02-05 | FRM-017
Process Framework | PF-17 Stakeholder Management | /HAI_Process_Frameworks/PF_17_Stakeholder.docx | 1.3 | 2026-02-04 | FRM-018
Process Framework | PF-18 Reporting | /HAI_Process_Frameworks/PF_18_Reporting.docx | 2.1 | 2026-02-03 | FRM-019, FRM-030
Process Framework | PF-19 Administration & Access Control | /HAI_Process_Frameworks/PF_19_Administration.docx | 1.6 | 2026-02-02 | FRM-020, FRM-045
Process Framework | PF-20 System Integration | /HAI_Process_Frameworks/PF_20_Integration.docx | 1.2 | 2026-02-01 | FRM-021
Process Framework | PF-21 Analytics & Dashboards | /HAI_Process_Frameworks/PF_21_Analytics.docx | 1.5 | 2026-01-31 | FRM-022, FRM-048
Process Framework | PF-22 Notification & Alerts | /HAI_Process_Frameworks/PF_22_Notifications.docx | 1.3 | 2026-01-30 | FRM-023
Process Framework | PF-23 Audit & Compliance | /HAI_Process_Frameworks/PF_23_Audit.docx | 2.0 | 2026-01-29 | FRM-024
Related Document | HAI_A068_Document_Numbering_System.xlsx | /ERP/Governance/HAI_A068_Document_Numbering_System.xlsx | 3.2 | 2026-02-15 | All - Document ID generation
Related Document | HAI_Workflow_Engine_Rules.xlsx | /ERP/Systems/HAI_Workflow_Engine_Rules.xlsx | 2.5 | 2026-02-12 | Workflow routing rules
Related Document | HAI_Level2_UI_Wireframe_Specifications_CONTRACTUAL.docx | /ERP/Design/HAI_Level2_UI_Wireframe_Specifications_CONTRACTUAL.docx | 4.1 | 2026-02-10 | UI implementation for forms
Contract Reference | FIDIC 1999 Red Book - Section 13.1 | Project Contract [Project Reference] | Official | Effective | VO tracking (FRM-004)
Contract Reference | FIDIC 1999 Red Book - Clause 1.1 | Project Contract [Project Reference] | Official | Effective | Definitions and interpretations
Master Reference | HAI SkyStruct Platform - Overall Spec | /ERP/Master/HAI_SkyStruct_Platform_Specification.docx | 1.0 | 2026-02-20 | Complete system specification