## Dashboard Register
Dashboard ID | Dashboard Name | Target Audience (Role IDs) | PF References | Widgets | Refresh Frequency | Data Sources | Access Level
DB-01 | Executive Overview | R01, R13 | All PFs | KPI cards, programme status, financial summary, risk heatmap, contractor score | Real-time | All modules | Full
DB-02 | Project Manager Dashboard | R02 | All PFs | Task queue, SLA tracker, correspondence tracker, open items, upcoming deadlines | Real-time | PM module, Task module | Full
DB-03 | Contracts Dashboard | R03 | PF-02,03,08,20 | Variation tracker, claims status, IPC progress, time-bar countdown, contractual obligations | Real-time | Contracts module, Financial module | Full
DB-04 | Cost Dashboard | R05 | PF-08,11 | Budget vs actual, cashflow forecast, IPC tracker, variation cost impact, RICS cost plan | Daily | Financial module, IPC module | Full
DB-05 | Design Manager Dashboard | R04 | PF-01,06 | Document status, review SLA, freeze status, submission tracker | Real-time | Design module, Document module | Full
DB-06 | Quality Dashboard | R06,R08 | PF-10 | NCR tracker, inspection schedule, defect heatmap, quality KPIs | Real-time | Quality module, Inspection module | Full
DB-07 | Contractor Portal Dashboard | R10,R11 | PF-01,02,03,08 | Submissions pending, correspondence, IPC status, VO status | Real-time | Submissions module, Correspondence module | Portal
DB-08 | Audit & Compliance | R15 | PF-23 | Audit log viewer, compliance score, exception register, SLA breach log | On-demand | Audit module, Compliance module | Restricted

## Report Register
Report ID | Report Name | PF Reference | Frequency | Format | Recipients | Content | Auto/Manual | Distribution Channel
RPT-01 | Monthly Progress Report | All | Monthly | PDF | PM, Employer | Executive summary, milestones, cost, risk, quality, claims, actions | Auto | Email, Portal
RPT-02 | Weekly Status Report | All | Weekly | PDF | PM | Task status, SLA compliance, upcoming deadlines, open items | Auto | Email
RPT-03 | IPC Certificate | PF-08 | Monthly | PDF | PM, Cost, Contractor | Certified amount, retention, deductions, net payment | Auto | Email, Portal
RPT-04 | Variation Register Report | PF-03 | On-demand | Excel | Contracts | All VOs, status, value, SC 13 compliance | Manual | Email, Portal
RPT-05 | Claims Register | PF-02,03 | On-demand | Excel | Contracts | All claims, time-bar status, assessment | Manual | Email, Portal
RPT-06 | Document Status Report | PF-01 | Weekly | PDF | Design, PM | Document submission status, review SLA, freeze status | Auto | Email
RPT-07 | Correspondence Log | PF-02 | Weekly | PDF | PM, Contracts | All correspondence, response times, status, actions | Auto | Email, Portal
RPT-08 | Risk Register | All | Weekly | Excel | PM, Employer | All risks, mitigation status, responsible party, residual score | Auto | Email, Portal
RPT-09 | Contractor Scorecard | All | Monthly | PDF | PM, Employer, Contractor | Performance metrics, safety, quality, schedule compliance | Auto | Email, Portal
RPT-10 | Stage Gate Report | PF-06 | On-demand | PDF | PM, Design, Employer | Gate readiness, approvals, sign-off status | Manual | Email, Portal
RPT-11 | Meeting Minutes Compilation | All | As-needed | PDF | All participants | Decisions, action items, owner, due dates | Manual | Email
RPT-12 | Lessons Learned Register | All | Quarterly | Excel | PM, Employer | Lessons captured, category, implementation status | Auto | Email, Portal
RPT-13 | Handover Status Report | PF-20 | Monthly | PDF | PM, Employer | Handover checklist completion, defects, outstanding items | Auto | Email
RPT-14 | DLP Defects Report | PF-10 | Bi-weekly | PDF | Quality, Contractor | Defects by location, severity, corrective actions, closure status | Auto | Email
RPT-15 | Audit Trail Export | All | On-demand | Excel | Audit, Compliance | User actions, system changes, timestamp, approvals | Manual | Email, Secure Download
RPT-16 | User Activity Report | All | Monthly | Excel | System Admin | Login activity, document access, actions performed | Auto | Email, Portal
RPT-17 | Notification Delivery Report | All | Weekly | PDF | System Admin | Sent notifications, delivery status, failed deliveries | Auto | Email
RPT-18 | Budget Variance Report | PF-08,11 | Monthly | Excel | Cost, PM, Employer | Budget vs actual, variance %, forecast, commitments | Auto | Email, Portal
RPT-19 | Cashflow Forecast | PF-08 | Monthly | Excel | Cost, Finance, Employer | Projected cash outflows, IPCs, retention, VAT | Auto | Email, Portal
RPT-20 | NCR Summary Report | PF-10 | Weekly | PDF | Quality, Contractor | NCRs raised, status, response time, closure | Auto | Email
RPT-21 | Inspection Schedule | PF-10 | Monthly | PDF | Quality, Design, Contractor | Upcoming inspections, scope, assigned inspector | Auto | Email, Portal
RPT-22 | Design Freeze Status | PF-01,06 | Weekly | PDF | Design, PM | Frozen areas, pending approvals, change control status | Auto | Email
RPT-23 | Submission Tracker | PF-01 | Weekly | Excel | Design, PM, Contractor | Outstanding submissions, due dates, status | Auto | Email, Portal
RPT-24 | SLA Compliance Report | All | Weekly | PDF | PM, Employer | SLA metrics, compliant/non-compliant items, breaches | Auto | Email
RPT-25 | Variation Cost Impact | PF-03,08 | On-demand | Excel | Contracts, Cost, PM | VO financial impact, program effect, schedule impact | Manual | Email, Portal
RPT-26 | IPC Progress Report | PF-08 | Monthly | PDF | Cost, Finance, Employer | IPCs issued, certified values, trends, payment schedule | Auto | Email, Portal
RPT-27 | Contractual Obligations Register | PF-20 | Monthly | Excel | Contracts, PM | Key obligations, due dates, responsible party, status | Auto | Email, Portal
RPT-28 | Quality KPI Dashboard | PF-10 | Weekly | PDF | Quality, PM | First time approval rate, defect density, rework hours | Auto | Email
RPT-29 | System Performance Report | All | Monthly | PDF | System Admin | Uptime %, response times, error rates, system health | Auto | Email
RPT-30 | Compliance Exceptions Report | PF-23 | Weekly | Excel | Compliance, Audit | Non-compliant items, remediation plan, owner, due date | Auto | Email, Portal

## KPI Definitions
KPI ID | KPI Name | PF Reference | Formula | Target | Warning Threshold | Critical Threshold | Unit | Frequency | Owner Role
KPI-01 | Document Review Cycle Time | PF-01 | Avg(approval date - submission date) | ≤5d | 7d | 10d | Days | Weekly | R04
KPI-02 | First-Time Approval Rate | PF-01 | Count(Status A) / Total | ≥70% | 60% | 50% | % | Monthly | R04
KPI-03 | Correspondence Response Compliance | PF-02 | On-time responses / Total | ≥95% | 90% | 85% | % | Weekly | R03
KPI-04 | Variation Execution Time | PF-03 | Avg(execution start - VO instruction) | ≤3d | 5d | 7d | Days | Monthly | R03
KPI-05 | IPC Certification Compliance | PF-08 | On-time certifications / Total | 100% | 95% | 90% | % | Monthly | R05
KPI-06 | Claims Time-Bar Compliance | PF-02 | Protected claims / Total | 100% | - | 99% | % | Weekly | R03
KPI-07 | Budget Variance | PF-08,11 | ¦(Actual - Budget) / Budget¦ | ±5% | ±10% | ±15% | % | Monthly | R05
KPI-08 | Risk Resolution Rate | All | Closed risks / Total | ≥80% | 70% | 60% | % | Weekly | R13
KPI-09 | Contractor Performance Score | All | Weighted composite of safety, quality, schedule | ≥75% | ≥65% | <65% | Score | Monthly | R02
KPI-10 | Stage Gate On-Time Delivery | PF-06 | Gate completion within schedule | 100% | 95% | 90% | % | As-needed | R02
KPI-11 | Quality Defect Rate | PF-10 | Number of defects per 1000 items | ≤5 | ≤10 | >15 | Defects/1000 | Weekly | R06
KPI-12 | Meeting Action Closure Rate | All | Closed actions / Total | ≥90% | ≥80% | ≥70% | % | Weekly | R02
KPI-13 | Stakeholder Query Response Time | All | Avg(response date - query date) | ≤1d | 2d | 3d | Days | Weekly | R02
KPI-14 | System Uptime | All | Available hours / Total hours | ≥99.5% | ≥99% | <99% | % | Daily | R14
KPI-15 | Notification Delivery Rate | All | Delivered notifications / Triggered | ≥99% | ≥98% | <98% | % | Daily | R14
KPI-16 | Audit Compliance Score | PF-23 | Compliant items / Total | 100% | 95% | 90% | % | Monthly | R15
KPI-17 | Document Submission On-Time Rate | PF-01 | Submitted on-time / Total | ≥95% | ≥90% | ≥80% | % | Weekly | R04
KPI-18 | NCR Response Time | PF-10 | Avg(response date - NCR date) | ≤3d | 5d | 7d | Days | Weekly | R06
KPI-19 | Inspection Schedule Compliance | PF-10 | Planned inspections completed / Total | 100% | 95% | 90% | % | Monthly | R06
KPI-20 | Design Freeze Compliance | PF-01,06 | Non-compliant changes / Total | 0% | ≤2% | >5% | % | Weekly | R04
KPI-21 | IPC Payment Timeliness | PF-08 | Avg(payment date - certificate date) | ≤14d | 21d | 28d | Days | Monthly | R05
KPI-22 | Variation Approval Cycle Time | PF-03 | Avg(approval date - submission date) | ≤7d | 10d | 14d | Days | Monthly | R03
KPI-23 | Claims Assessment Timeliness | PF-02 | Avg(decision date - submission date) | ≤21d | 30d | 42d | Days | Monthly | R03
KPI-24 | Program Schedule Variance | All | ¦(Planned - Actual) / Planned¦ | ±3% | ±5% | >±10% | % | Weekly | R02
KPI-25 | Rework Cost as % of Total | PF-10,11 | Rework cost / Total cost | ≤1% | ≤2% | >3% | % | Monthly | R05
KPI-26 | Safety Incident Rate | All | Incidents per 100,000 hours | 0 | ≤1 | >2 | Rate | Weekly | R06
KPI-27 | Correspondence Backlog | PF-02 | Outstanding correspondence items | 0 | ≤5 | >10 | Count | Daily | R03
KPI-28 | Design Review Completion Rate | PF-01,06 | Completed reviews / Scheduled | 100% | 95% | 90% | % | Weekly | R04
KPI-29 | Handover Defects Outstanding | PF-20 | Outstanding defects / Total identified | 0% | ≤5% | >10% | % | Monthly | R02
KPI-30 | System User Adoption Rate | All | Active users / Total users | ≥90% | ≥80% | <80% | % | Monthly | R14
KPI-31 | Data Integrity Score | All | Validated records / Total records | 100% | 99% | 98% | % | Weekly | R14
KPI-32 | Approval Workflow Cycle Time | All | Avg(final approval - submission) | ≤2d | 3d | 5d | Days | Weekly | R02
KPI-33 | Retention Release Rate | PF-08 | Released retention / Total | ≥80% | ≥70% | <70% | % | Monthly | R05
KPI-34 | Cost Forecast Accuracy | PF-08,11 | ¦Forecast - Final / Final¦ | ±3% | ±5% | ±10% | % | Monthly | R05
KPI-35 | Contractor Claim Rate | All | Claims submitted / Month | Baseline | Baseline+20% | Baseline+50% | Count | Monthly | R03
KPI-36 | Quality Inspection Pass Rate | PF-10 | First-pass inspections / Total | ≥95% | ≥90% | ≥80% | % | Weekly | R06
KPI-37 | Document Access Audit Trail Completeness | All | Logged accesses / Total accesses | 100% | 99% | 98% | % | Daily | R15
KPI-38 | Change Control Approval Rate | All | Approved changes / Total | ≥95% | ≥90% | ≥85% | % | Weekly | R02
KPI-39 | Employer Query Resolution Time | All | Avg(resolution date - query date) | ≤3d | 5d | 7d | Days | Weekly | R02
KPI-40 | System Feature Utilization | All | Features used / Available features | ≥70% | ≥60% | <60% | % | Quarterly | R14

## Widget Specifications
Widget ID | Widget Name | Type | Data Source | Configuration | Dashboard(s) Used In
W-01 | KPI Summary Card | Card | KPI module | Display: value, target, variance; Color: red/yellow/green; Refresh: Real-time | DB-01, DB-04, DB-06
W-02 | Programme Status Timeline | Chart | Schedule module | Type: Gantt; Group by: Phase; Show: Actual vs Planned; Drill-down: WBS | DB-01
W-03 | Financial Summary | Card | Financial module | Display: Budget, Actual, Forecast, Variance; Currency: QAR; Precision: 2dp | DB-01, DB-04
W-04 | Risk Heatmap | Map | Risk module | X-axis: Probability; Y-axis: Impact; Color by: Risk ID; Size: Score | DB-01
W-05 | Contractor Performance Score | Gauge | Contractor module | Range: 0-100; Thresholds: 65 (red), 75 (yellow); Refresh: Daily | DB-01
W-06 | Task Queue | Table | Task module | Columns: Task ID, Title, Owner, Due Date, Status; Sortable: all; Filterable: Status, Owner | DB-02
W-07 | SLA Tracker | Chart | SLA module | Type: Bar; Group by: SLA Item; Show: Compliant/Non-compliant; Trend line | DB-02
W-08 | Correspondence Tracker | Table | Correspondence module | Columns: Ref, Subject, From, Date, Response Due, Status; Color code: overdue | DB-02
W-09 | Open Items Register | Table | Issues module | Columns: ID, Title, Owner, Due Date, Priority, Status; Filter: Open only | DB-02
W-10 | Upcoming Deadlines | Table | Calendar module | Show next 14 days; Sort: by date; Color: overdue (red), today (orange), future (green) | DB-02
W-11 | Variation Tracker | Table | Variation module | Columns: VO ID, Title, Status, Value, SC13 Impact; Drill-down: details | DB-03
W-12 | Claims Status | Chart | Claims module | Type: Pie; Categories: Submitted, Agreed, In Progress, Closed; Refresh: Real-time | DB-03
W-13 | IPC Progress Timeline | Chart | IPC module | Type: Line; Y: Cumulative value; X: Month; Show: Certified, Paid | DB-03
W-14 | Time-Bar Countdown | Card | Schedule module | Display: Months remaining for claims; Color: red if <3mo, orange if <6mo | DB-03
W-15 | Contractual Obligations | Table | Contracts module | Columns: Obligation, Due Date, Owner, Status; Filter: Upcoming | DB-03
W-16 | Budget vs Actual | Chart | Financial module | Type: Column; Categories: Cost Centers; Show: Budget, Actual, Forecast; Variance % | DB-04
W-17 | Cashflow Forecast | Chart | Cashflow module | Type: Area; X: Month; Y: Cash; Show: Forecast, Actual; Stack: Inflow/Outflow | DB-04
W-18 | Variation Cost Impact | Table | Variation module | Columns: VO ID, Base Cost, VO Cost, Total Impact, % of Budget | DB-04
W-19 | RICS Cost Plan Tracker | Table | Cost module | Columns: Element, Budget, Committed, Actual, Forecast, Variance % | DB-04
W-20 | NCR Tracker | Table | Quality module | Columns: NCR ID, Description, Status, Owner, Due Date, % Complete | DB-06
W-21 | Inspection Schedule | Calendar | Inspection module | Show: Planned inspections; Color by: Type; Drill-down: details | DB-06
W-22 | Defect Heatmap | Map | Quality module | Geographic/area heatmap; Color: severity; Size: count; Drill-down: list | DB-06
W-23 | Quality KPI Dashboard | Card | Quality module | Display: Pass rate, Defect density, NCR count, Rework %; Target vs Actual | DB-06
W-24 | Document Status Tracker | Table | Document module | Columns: Doc ID, Title, Status, Owner, Due Date, % Complete; Filter: Pending | DB-05
W-25 | Review SLA Monitor | Chart | Document module | Type: Gauge array; Show: Cycle time vs target for each document type | DB-05

## Cross-Reference
Reference Type | Document/Standard | Description | Link/Location
Process Framework | PF-01 | Design Management | HAI_Level4_Process_Frameworks.xlsx
Process Framework | PF-02 | Correspondence Management | HAI_Level4_Process_Frameworks.xlsx
Process Framework | PF-03 | Variation Management | HAI_Level4_Process_Frameworks.xlsx
Process Framework | PF-06 | Stage Gates & Approvals | HAI_Level4_Process_Frameworks.xlsx
Process Framework | PF-08 | Financial Management & IPCs | HAI_Level4_Process_Frameworks.xlsx
Process Framework | PF-10 | Quality Management | HAI_Level4_Process_Frameworks.xlsx
Process Framework | PF-11 | Cost Planning & Control | HAI_Level4_Process_Frameworks.xlsx
Process Framework | PF-20 | Handover & Closeout | HAI_Level4_Process_Frameworks.xlsx
Process Framework | PF-23 | Audit & Compliance | HAI_Level4_Process_Frameworks.xlsx
Related Document | HAI_Workflow_Engine_Rules.xlsx | Workflow automation rules and triggers | /ERP/Documentation/
Related Document | HAI_User_Roles_Permissions_Matrix.xlsx | User roles (R01-R15) and access controls | /ERP/Documentation/
Related Document | HAI_Level4_Acceptance_Checklists_CONTRACTUAL.xlsx | FIDIC Red Book compliance checklists | /ERP/Documentation/
Related Document | HAI_Dashboard_Configuration_Guide.xlsx | Detailed dashboard setup and customization | /ERP/Documentation/
Contract Standard | FIDIC 1999 Red Book | Contract conditions and obligations | Contractual framework
Contract Reference | Contract [Project Reference] | Qatar HAI SkyStruct Platform project | Project baseline
System Component | Reports Module (PF-18) | Automated and ad-hoc reporting | Core platform
System Component | Dashboard Module (PF-21) | Real-time dashboards and visualization | Core platform
Document Reference | HAI-SS-DRS-2026-001 | This Dashboard Reporting Specifications document | Current document
Standards | SC-13 Variation Control | FIDIC variation procedures per Contract [Project Reference] | Contract [Project Reference] Clause 13
Standards | Time-Bar Provisions | Claims notification and procedural time limits per FIDIC | Contract [Project Reference]