## KPI Definitions
KPI ID | KPI Name | Category | Description | Formula / Calculation | Unit | Target | Warning Threshold | Critical Threshold | Measurement Frequency | Data Source (PF) | Dashboard | Owner Role | Stage Applicability
KPI-001 | Submittal Response Time | Document Management | Average time from submittal receipt to response issuance |  | Calendar Days | ≤14 CD | 15-21 CD | >21 CD | Weekly | PF-01 | ER Dashboard | R07 Document Controller | Stage 1-6
KPI-002 | Correspondence Turnaround | Correspondence | Average time from letter receipt to formal reply |  | Calendar Days | ≤7 CD | 8-14 CD | >14 CD | Weekly | PF-02 | PM Dashboard | R02 Project Manager | Stage 4-7
KPI-003 | Variation Processing Time | Financial Control | Time from variation instruction to final approval |  | Calendar Days | ≤28 CD | 29-42 CD | >42 CD | Monthly | PF-03 | Cost Dashboard | R03 Contracts Manager | Stage 5
KPI-004 | IPC Certification Cycle | Financial Control | Time from contractor application to certified IPC issuance |  | Calendar Days | ≤28 CD (FIDIC 14.6) | 29-35 CD | >35 CD | Monthly | PF-08 | Cost Dashboard | R05 Cost Manager | Stage 5-7
KPI-005 | Stage Gate Compliance | Governance | Percentage of gate prerequisites completed before progression |  | % | 100% | 90-99% | <90% | Per Gate | PF-05 | Governance Dashboard | R02 Project Manager | Stage 0-8
KPI-006 | NCR Closure Rate | Quality | Percentage of NCRs closed within SLA period |  | % | ≥95% | 85-94% | <85% | Monthly | PF-10 | Quality Dashboard | R06 QA/QC Manager | Stage 5-6
KPI-007 | Contractor Performance Score | Contractor Mgmt | Composite weighted score across 5 dimensions |  | Score 0-100 | ≥80 | 60-79 | <60 | Monthly | PF-13 | PM Dashboard | R02 Project Manager | Stage 5-7
KPI-008 | Risk Register Currency | Risk | Percentage of risks reviewed within last 30 days |  | % | ≥90% | 75-89% | <75% | Monthly | PF-12 | Risk Dashboard | R02 Project Manager | Stage 1-7
KPI-009 | Design Freeze Exception Rate | Governance | Number of freeze exceptions per month as % of total scope items |  | % | ≤2% | 2-5% | >5% | Monthly | PF-06 | Governance Dashboard | R04 Technical Design Manager | Stage 3-5
KPI-010 | Budget Variance | Financial Control | Difference between forecast cost and approved budget baseline |  | % | ≤5% | 5-10% | >10% | Monthly | PF-11 | Cost Dashboard | R05 Cost Manager | Stage 3-7
KPI-011 | Approval Workflow Efficiency | Governance | Percentage of approvals completed within SLA |  | % | ≥90% | 80-89% | <80% | Weekly | PF-09 | Governance Dashboard | R01 Programme Director | Stage 0-8
KPI-012 | HSE Incident Rate | HSE | Lost time incidents per 200,000 man-hours |  | Rate | 0 | 0.1-0.5 | >0.5 | Monthly | PF-10 | HSE Dashboard | R06 QA/QC Manager | Stage 5-6
KPI-013 | Document Revision Index | Document Mgmt | Average number of revisions per submittal before approval |  | Count | ≤2.0 | 2.1-3.0 | >3.0 | Monthly | PF-01 | ER Dashboard | R07 Document Controller | Stage 1-6
KPI-014 | Handover Package Completeness | Handover | Percentage of required handover items submitted |  | % | 100% | 90-99% | <90% | Per Handover | PF-15 | Handover Dashboard | R02 Project Manager | Stage 6-7
KPI-015 | Snag Closure Rate | Quality | Percentage of snags closed within defined period |  | % | ≥95% | 85-94% | <85% | Weekly | PF-31 | Quality Dashboard | R06 QA/QC Manager | Stage 6-7

## SLA Definitions
SLA ID | Action Type | FIDIC Reference | Contractual Period | System SLA (Calendar Days) | Warning Alert (CD before) | Escalation L1 (CD overdue) | Escalation L2 (CD overdue) | Escalation L3 (CD overdue) | Auto-Action on Breach | Responsible Role | Approver Role | Stage Applicability | PF Reference
SLA-001 | Submittal Review (Standard) | N/A | 14 CD | 14 | 3 | 1 | 3 | 7 | Auto-escalate to PM | R07 | R02 | Stage 1-6 | PF-01
SLA-002 | Submittal Review (Urgent) | N/A | 7 CD | 7 | 2 | 1 | 2 | 4 | Auto-escalate to PM | R07 | R02 | Stage 1-6 | PF-01
SLA-003 | Correspondence Reply | N/A | 7 CD | 7 | 2 | 1 | 2 | 5 | Auto-escalate to Dir | R02 | R01 | Stage 4-7 | PF-02
SLA-004 | FIDIC Notice Response | 1.3 | 28 CD | 28 | 7 | 1 | 7 | 14 | Flag as deemed accepted | R03 | R02 | Stage 4-7 | PF-02
SLA-005 | Variation Assessment | 13.1 | 28 CD | 28 | 7 | 1 | 7 | 14 | Auto-escalate to Dir | R03 | R02 | Stage 5 | PF-03
SLA-006 | IPC Certification | 14.6 | 28 CD | 28 | 7 | 1 | 3 | 7 | Finance alert + interest calc | R05 | R02 | Stage 5-7 | PF-08
SLA-007 | Claim Determination | 20.1 | 42 CD | 42 | 14 | 1 | 7 | 14 | Flag for DAB referral | R03 | R01 | Stage 5-7 | PF-03
SLA-008 | EOT Determination | 8.4 | 42 CD | 42 | 14 | 1 | 7 | 14 | Flag for DAB referral | R09 | R02 | Stage 5-7 | PF-03
SLA-009 | NCR Closure | N/A | 14 CD | 14 | 3 | 1 | 3 | 7 | Block next IPC | R06 | R02 | Stage 5-6 | PF-10
SLA-010 | RFI Response | N/A | 7 CD | 7 | 2 | 1 | 2 | 5 | Auto-escalate to PM | R04 | R02 | Stage 4-6 | PF-01
SLA-011 | Gate Checklist Completion | N/A | 5 CD before gate | 5 | 2 | 1 | 2 | 3 | Block gate progression | R02 | R01 | Stage 0-8 | PF-05
SLA-012 | Freeze Exception Decision | N/A | 14 CD | 14 | 3 | 1 | 3 | 7 | Auto-escalate to Dir | R02 | R01 | Stage 3-5 | PF-06
SLA-013 | Snag Rectification | N/A | 7 CD (minor) / 14 CD (major) | 14 | 3 | 1 | 3 | 7 | Block TOC issuance | R06 | R02 | Stage 6-7 | PF-31
SLA-014 | TOC Inspection | 10.1 | 14 CD from application | 14 | 3 | 1 | 3 | 7 | Auto-escalate to Dir | R02 | R01 | Stage 6 | PF-28
SLA-015 | Performance Certificate | 11.9 | 28 CD after DLP | 28 | 7 | 1 | 7 | 14 | Deemed issued per FIDIC | R02 | R01 | Stage 7-8 | PF-30

## Escalation Matrix
Level | Trigger | Escalated To | Response Time | Authority | Notification Method
L1 - Alert | SLA Warning threshold reached | Assigned User + Direct Supervisor | Same day | Reminder only | Email + In-app notification
L2 - Escalation | 1 CD past SLA deadline | Department Head / HAI PM | 4 hours | Can reassign or extend SLA | Email + SMS + In-app
L3 - Management | 3 CD past SLA deadline | HAI Programme Director | 2 hours | Can override, impose penalties | Email + SMS + Phone call
L4 - Executive | 7 CD past SLA deadline | Employer Representative | 1 hour | Full contractual authority | Email + SMS + Phone + Meeting
L5 - Contract | 14 CD past SLA deadline | Employer Board / Legal | Immediate | Contractual enforcement, DAB referral | Formal notice per FIDIC