## Summary
PF ID | PF Name | Total Steps | Decision Points | Time-critical Steps | Primary Module | Contract Type Coverage | RIBA Stage(s)
PF-01 | Document Review | 7 | 1 | 7 | Doc Management | Both | All
PF-02 | Correspondence | 7 | 2 | 7 | Correspondence Module | Both | All
PF-03 | Variation Order | 7 | 2 | 7 | Variation Module | Construction | Stages D-G
PF-04 | Procurement | 7 | 2 | 7 | Procurement Module | Both | Stages C-D
PF-05 | Stage Gate | 7 | 2 | 7 | Stage Gate Module | Both | All
PF-06 | Freeze Exception | 7 | 2 | 7 | Change Control Module | Construction | Stages D-G
PF-07 | Authority Submissions | 7 | 3 | 7 | Compliance Module | Both | All
PF-08 | IPC Processing | 8 | 3 | 8 | Finance Module | Both | Stages D-G
PF-09 | Approval Engine | 7 | 1 | 7 | Workflow Module | Both | All
PF-10 | Quality Supervision | 7 | 2 | 7 | QA/QC Module | Construction | Stages D-G
PF-11 | Budget Cost | 7 | 2 | 7 | Finance Module | Both | All
PF-12 | Risk Register | 7 | 2 | 7 | Risk Module | Both | All
PF-13 | Contractor Performance | 7 | 2 | 7 | Performance Module | Construction | Stages D-G
PF-14 | Lessons Learned | 7 | 1 | 7 | Knowledge Module | Both | All
PF-15 | Handover DLP | 8 | 2 | 8 | Project Closure Module | Construction | Stage G-Post G
PF-16 | Meeting Action Tracking | 7 | 3 | 7 | Claims Module | Both | All
PF-17 | External Stakeholder Portal | 7 | 2 | 7 | Reporting Module | Both | All
PF-18 | Report Generation Export | 7 | 2 | 7 | Data Governance Module | Both | All
PF-19 | User Role Management | 7 | 2 | 7 | Planning Module | Both | All
PF-20 | ERP Integration | 7 | 1 | 7 | Analytics Module | Both | All
PF-21 | Dashboard Analytics | 7 | 1 | 7 | Communication Module | Both | All
PF-22 | Notification Escalation | 7 | 0 | 7 | Doc Management Module | Both | All
PF-23 | Predictive Analytics | 7 | 1 | 7 | Meeting Module | Both | All
PF-24 | Post Go Live Support | 7 | 1 | 7 | Mobilization Module | Both | Stages A-C
PF-25 | Consultant Mobilisation | 8 | 3 | 8 | T&C Module | Construction | Stages F-G
PF-26 | Final Account Settlement | 7 | 1 | 7 | Facility Management Module | Construction | Post-G
PF-27 | Lessons Learned CI | 7 | 2 | 7 | Finance Module | Consultancy | All
PF-28 | TOC Management
PF-29 | Final Payment Certificate
PF-30 | Performance Certificate
PF-31 | Snag List Resolution

## PF-01
Step # | Action Description | Responsible Role | Input Document | Output Document | Decision Point (Y/N) | Time Limit | Escalation Rule | System Module | Contractual Basis (FIDIC/Consultancy clause) | Notes
1 | Document received and logged | Document Controller | Incoming Document | Document Registry Entry | N | 1 BD | Manager escalation if >24hrs | Doc Management | FIDIC/Consultancy General
2 | Route to relevant approver(s) | Coordinator | Document Registry Entry | Approval Routing List | N | 2 BD | Auto-escalate if unassigned >24hrs | Doc Management | FIDIC/Consultancy General
3 | Reviewer examines document | Engineer/Consultant | Document with context | Review Comments | N | 5 BD | Escalate to Manager if blocker identified | Doc Management | FIDIC/Consultancy General
4 | Approval decision | Approver | Review Comments | Approval Status | Y | 2 BD | Escalate to Employer's Rep if rejected | Doc Management | FIDIC/Consultancy General | Decision on approval or conditional approval
5 | Apply approval stamp/workflow status | Document Controller | Approval Status | Approved Document | N | 1 BD | Manager escalation if delayed | Doc Management | FIDIC/Consultancy General
6 | Update document registry and notify stakeholders | Coordinator | Approved Document | Notification Log | N | 1 BD | Escalate if distribution fails | Doc Management | FIDIC/Consultancy General
7 | Archive document with metadata | Document Controller | Approved Document | Document Archive Entry | N | 1 BD | Manager review if archiving fails | Doc Management | FIDIC/Consultancy General

## PF-02
Step # | Action Description | Responsible Role | Input Document | Output Document | Decision Point (Y/N) | Time Limit | Escalation Rule | System Module | Contractual Basis (FIDIC/Consultancy clause) | Notes
1 | Incoming correspondence received | Coordinator | Email/Letter | Correspondence Log Entry | N | 1 BD | Auto-escalate if unlogged >24hrs | Correspondence Module | FIDIC/Consultancy General
2 | Classify and tag correspondence | Document Controller | Correspondence Log Entry | Tagged Correspondence | N | 2 BD | Manager escalation if misclassified | Correspondence Module | FIDIC/Consultancy General
3 | Determine action type (response/notification/escalation) | Coordinator | Tagged Correspondence | Action Type Assignment | Y | 1 BD | Escalate to Manager for complex matters | Correspondence Module | FIDIC/Consultancy General | Decision on escalation required
4 | Assign response responsibility | Manager | Action Type Assignment | Responsibility Matrix Output | N | 1 BD | Manager escalation if not assigned | Correspondence Module | FIDIC/Consultancy General
5 | Draft response with reference to contract | Engineer/Consultant | Correspondence with contract ref | Draft Response | N | 5 BD | Escalate to Manager if contract conflict found | Correspondence Module | FIDIC/Consultancy Article references
6 | Review and approve response | Approver | Draft Response | Approved Response | Y | 2 BD | Escalate to Employer's Rep if high-risk | Correspondence Module | FIDIC/Consultancy General
7 | Send response and update register | Coordinator | Approved Response | Correspondence Register Update | N | 1 BD | Manager escalation if dispatch fails | Correspondence Module | FIDIC/Consultancy General

## PF-03
Step # | Action Description | Responsible Role | Input Document | Output Document | Decision Point (Y/N) | Time Limit | Escalation Rule | System Module | Contractual Basis (FIDIC/Consultancy clause) | Notes
1 | VO request received and registered | Coordinator | VO Request | VO Register Entry | N | 1 BD | Auto-escalate if unregistered >2 hrs | Variation Module | FIDIC Red Book Sub-Clause 13.1
2 | Assess eligibility against contract | Engineer | VO Request with contract terms | Eligibility Assessment | Y | 3 BD | Escalate to Employer's Rep if non-conformant | Variation Module | FIDIC Red Book Sub-Clause 13.1 | Decision on contractual eligibility
3 | Determine cost and time impacts | QS | Eligible VO Request | Cost & Time Assessment | N | [Completion Period] basis | Manager escalation if DAP impacts >10% | Variation Module | FIDIC Red Book Sub-Clause 13.1 | Use [Delay Damages Rate] if applicable
4 | Prepare VO document with [Contract Value] baseline | QS | Cost & Time Assessment | Draft VO Document | N | 5 BD | Manager escalation if exceeds budget | Variation Module | FIDIC Red Book Sub-Clause 13.1
5 | Review VO for commercial terms | Approver | Draft VO Document | Approved VO | Y | 3 BD | Escalate to Employer's Rep for [Contract Value] impact >5% | Variation Module | FIDIC Red Book Sub-Clause 13.1 | Decision on commercial approval
6 | Issue VO to Contractor | Coordinator | Approved VO | VO Issued Log | N | 1 BD | Manager escalation if issuance delayed | Variation Module | FIDIC Red Book Sub-Clause 13.1
7 | Monitor VO execution and close-out | Engineer | VO Issued Log | VO Completion Report | N | Per VO timeframe | Escalate to Manager if variance >15% | Variation Module | FIDIC Red Book Sub-Clause 13.1

## PF-04
Step # | Action Description | Responsible Role | Input Document | Output Document | Decision Point (Y/N) | Time Limit | Escalation Rule | System Module | Contractual Basis (FIDIC/Consultancy clause) | Notes
1 | Procurement requisition created with contract reference | Project Manager | Project Requirement | Procurement Requisition | N | 3 BD | Manager escalation if unclear specs | Procurement Module | FIDIC/Consultancy General | Reference [Contract Value] baseline
2 | Prepare RFP with contract terms and clauses | QS/Procurement | Procurement Requisition | Draft RFP Document | N | 10 BD | Manager escalation if budget constraints exceed | Procurement Module | FIDIC/Consultancy Terms Incorporation
3 | Approve RFP and identify vendors | Approver | Draft RFP Document | Approved RFP & Vendor List | Y | 3 BD | Escalate to Employer's Rep if sole-source required | Procurement Module | FIDIC/Consultancy General | Decision on vendor selection
4 | Issue RFP to vendors | Procurement | Approved RFP & Vendor List | RFP Issuance Log | N | 1 BD | Auto-escalate if distribution fails | Procurement Module | FIDIC/Consultancy General
5 | Evaluate quotations and manage clarifications | QS/Procurement | Received Quotations | Evaluation Report | N | 7 BD | Manager escalation if no compliant bids received | Procurement Module | FIDIC/Consultancy General
6 | Recommend and approve supplier | Approver | Evaluation Report | Supplier Approval | Y | 3 BD | Escalate to Employer's Rep if [Contract Value] impact | Procurement Module | FIDIC/Consultancy General
7 | Issue Contract and update contracts register | Procurement | Supplier Approval | Contract & Contracts Register Update | N | 1 BD | Manager escalation if signature delayed | Procurement Module | FIDIC/Consultancy General

## PF-05
Step # | Action Description | Responsible Role | Input Document | Output Document | Decision Point (Y/N) | Time Limit | Escalation Rule | System Module | Contractual Basis (FIDIC/Consultancy clause) | Notes
1 | Stage completion review initiated | Project Manager | Deliverables Checklist | Stage Review Register | N | 5 BD | Manager escalation if reviews pending | Stage Gate Module | FIDIC/Consultancy General
2 | Assess completion against KPIs and contractual milestones | Engineer/Consultant | Stage Deliverables | Assessment Report | N | 5 BD | Escalate to Manager if KPIs not met | Stage Gate Module | FIDIC/Consultancy Milestone Schedule
3 | Review budget and schedule alignment | QS/Planner | Cost & Schedule Reports | Alignment Assessment | N | 3 BD | Manager escalation if variance >10% | Stage Gate Module | FIDIC/Consultancy Schedule Management
4 | Management gate review and decision | Steering Committee | Assessment Report & Alignment | Gate Decision | Y | 2 BD | Escalate to Employer's Rep if not approved | Stage Gate Module | FIDIC/Consultancy General | Decision to proceed or hold
5 | Approve stage closure and sign-off | Approver | Gate Decision | Stage Sign-Off | Y | 1 BD | Escalate if conditional sign-off | Stage Gate Module | FIDIC/Consultancy General
6 | Update master schedule and financial records | Planner/QS | Stage Sign-Off | Updated Schedule & Budget | N | 2 BD | Manager escalation if records not updated | Stage Gate Module | FIDIC/Consultancy General
7 | Communicate stage progression to stakeholders | Coordinator | Updated Schedule & Budget | Stakeholder Notification Log | N | 1 BD | Manager escalation if communication fails | Stage Gate Module | FIDIC/Consultancy General

## PF-06
Step # | Action Description | Responsible Role | Input Document | Output Document | Decision Point (Y/N) | Time Limit | Escalation Rule | System Module | Contractual Basis (FIDIC/Consultancy clause) | Notes
1 | Freeze exception request received | Project Manager | Exception Request | Exception Register Entry | N | 1 BD | Auto-escalate if unlogged >2 hrs | Change Control Module | FIDIC Red Book General
2 | Assess exception against freeze rules | Engineer | Exception Request & Freeze Rules | Eligibility Assessment | Y | 2 BD | Escalate to Employer's Rep if contract risk identified | Change Control Module | FIDIC Red Book Sub-Clause 13 | Decision on eligibility
3 | Evaluate impact on schedule and [Completion Period] | Planner | Eligible Exception Request | Impact Assessment | N | 3 BD | Manager escalation if delay >5 days | Change Control Module | FIDIC Red Book Schedule Management
4 | Determine cost impact and contingency status | QS | Impact Assessment | Cost Assessment | N | 3 BD | Manager escalation if budget impact >5% | Change Control Module | FIDIC Red Book Sub-Clause 13
5 | Review exception against commercial terms | Approver | Cost Assessment | Approval Recommendation | Y | 2 BD | Escalate to Employer's Rep for major exceptions | Change Control Module | FIDIC Red Book General | Decision on approval
6 | Issue exception approval or rejection | Manager | Approval Recommendation | Exception Decision Notice | N | 1 BD | Escalate if delayed | Change Control Module | FIDIC Red Book General
7 | Update change log and progress tracking | Coordinator | Exception Decision Notice | Updated Change Register | N | 1 BD | Manager escalation if not recorded | Change Control Module | FIDIC Red Book General

## PF-07
Step # | Action Description | Responsible Role | Input Document | Output Document | Decision Point (Y/N) | Time Limit | Escalation Rule | System Module | Contractual Basis (FIDIC/Consultancy clause) | Notes
1 | Submission requirement identified and registered | Coordinator | Regulatory/Contractual Requirement | Submission Register Entry | N | 2 BD | Manager escalation if overdue >1 week | Compliance Module | FIDIC/Consultancy Contract Terms
2 | Prepare submission package with required documents | Engineer/Consultant | Submission Requirements | Draft Submission Package | N | 7 BD | Manager escalation if completeness issues | Compliance Module | FIDIC/Consultancy Document Requirements
3 | Technical review and approval of submission content | Engineer/Technical Lead | Draft Submission Package | Technical Approval | Y | 3 BD | Escalate to Manager if deficiencies found | Compliance Module | FIDIC/Consultancy Technical Standards | Decision on submission readiness
4 | Legal/compliance review of submission terms | Legal/Compliance | Technical Approval | Compliance Approval | Y | 2 BD | Escalate to Employer's Rep if legal issues | Compliance Module | FIDIC/Consultancy Contract Compliance
5 | Obtain final authorization for submission | Approver | Compliance Approval | Authorization Signature | Y | 1 BD | Escalate to Employer's Rep if withheld | Compliance Module | FIDIC/Consultancy Authority
6 | Submit to authority and obtain receipt | Coordinator | Authorization Signature | Submission Receipt & Tracking ID | N | 1 BD | Manager escalation if submission fails | Compliance Module | FIDIC/Consultancy General
7 | Monitor authority response and manage follow-up | Coordinator/Engineer | Submission Receipt & Tracking ID | Authority Response Log | N | [Regulatory Timeline] | Escalate if authority raises objections | Compliance Module | FIDIC/Consultancy General

## PF-08
Step # | Action Description | Responsible Role | Input Document | Output Document | Decision Point (Y/N) | Time Limit | Escalation Rule | System Module | Contractual Basis (FIDIC/Consultancy clause) | Notes
1 | IPC/Payment Application received [28 CD for Contractor / 15 WD for Consultant] | Coordinator | IPC/Timesheet with supporting docs | IPC Register Entry | N | 1 BD | Auto-escalate if unlogged >24 hrs | Finance Module | FIDIC Red Book 14.3 / Consultancy Art. 15 | Construction: [28 Calendar Days] review period
2 | Verify certificate validity and submission compliance | QS/Finance | IPC Register Entry | Compliance Check Report | Y | 3 BD | Escalate to Manager if non-compliant submission | Finance Module | FIDIC Red Book 14.3 / Consultancy Art. 15 | Decision on submission acceptance
3 | Review back-up documentation and invoices | QS/HR | IPC with supporting documents | Documentation Review Report | N | 5 BD | Manager escalation if docs incomplete | Finance Module | FIDIC Red Book 14.3 / Consultancy Art. 15 | Construction: assess interim progress; Consultant: verify timesheet accuracy
4 | Assess contractual entitlement and calculate payment | QS | Documentation Review Report | Interim Assessment | N | 5 BD | Manager escalation if [Contract Value] disputes | Finance Module | FIDIC Red Book 14.3 / Consultancy Art. 15 | Use [Completion Period] for milestone calculations
5 | Determine deductions and withholding | Finance | Interim Assessment | Deduction Schedule | Y | 2 BD | Escalate to Manager for deductions >5% | Finance Module | FIDIC Red Book 14.3 / Consultancy Art. 21 | Decision on retention and deductions
6 | Prepare IPC certificate for approval | QS/Finance | Deduction Schedule | Draft IPC Certificate | N | 2 BD | Manager escalation if certificate errors | Finance Module | FIDIC Red Book 14.3 / Consultancy Art. 15
7 | Approve and issue IPC certificate; process payment | Approver | Draft IPC Certificate | Issued IPC & Payment Authorization | Y | 1 BD | Escalate if delayed payment authorization | Finance Module | FIDIC Red Book 14.3 / Consultancy Art. 15 | Final approval before payment
8 | Record payment in accounts and notify payee | Finance | Issued IPC & Payment Authorization | Payment Record & Notification | N | 1 BD | Manager escalation if payment not processed | Finance Module | FIDIC Red Book 14.3 / Consultancy Art. 15

## PF-09
Step # | Action Description | Responsible Role | Input Document | Output Document | Decision Point (Y/N) | Time Limit | Escalation Rule | System Module | Contractual Basis (FIDIC/Consultancy clause) | Notes
1 | Approval request submitted with documentation | Any Role | Request + Supporting Docs | Approval Queue Entry | N | 1 BD | Auto-escalate if unqueued >2 hrs | Workflow Module | FIDIC/Consultancy General
2 | Route request based on approval matrix | Workflow System | Approval Queue Entry | Routing Assignment | N | 1 BD | Auto-escalate if routing fails | Workflow Module | FIDIC/Consultancy Authority Levels
3 | Notify approver and track engagement | Coordinator | Routing Assignment | Notification Log | N | 1 BD | Auto-escalate if approver unresponsive >24 hrs | Workflow Module | FIDIC/Consultancy General
4 | Approver reviews and makes decision | Designated Approver | Request + Documentation | Approval Decision | Y | 3 BD | Escalate to higher authority if withheld | Workflow Module | FIDIC/Consultancy Authority Levels | Decision: Approve/Reject/Conditional
5 | Apply conditional requirements (if applicable) | Coordinator | Approval Decision | Conditional Task Log | N | Per condition timeline | Manager escalation if conditions not met | Workflow Module | FIDIC/Consultancy General
6 | Issue approval certificate/notification | Workflow System | Approval Decision | Approval Certificate | N | 1 BD | Auto-escalate if issuance fails | Workflow Module | FIDIC/Consultancy General
7 | Log approval and update audit trail | Document Controller | Approval Certificate | Audit Trail Entry | N | 1 BD | Manager escalation if audit trail incomplete | Workflow Module | FIDIC/Consultancy Compliance

## PF-10
Step # | Action Description | Responsible Role | Input Document | Output Document | Decision Point (Y/N) | Time Limit | Escalation Rule | System Module | Contractual Basis (FIDIC/Consultancy clause) | Notes
1 | Site inspection scheduled and notified | Engineer | Inspection Schedule | Inspection Register Entry | N | 2 BD | Manager escalation if not scheduled | QA/QC Module | FIDIC Red Book Sub-Clause 7
2 | Conduct site inspection and document findings | Site Engineer/Inspector | Inspection Checklist | Inspection Report | N | 1 BD | Manager escalation if findings critical | QA/QC Module | FIDIC Red Book Sub-Clause 7
3 | Assess compliance against specifications | Engineer | Inspection Report & Specs | Compliance Assessment | Y | 1 BD | Escalate to Manager if non-conformance found | QA/QC Module | FIDIC Red Book Sub-Clause 7 | Decision on conformance
4 | Identify defects and generate NCR (if needed) | Engineer | Compliance Assessment | Defect List / NCR | N | 1 BD | Manager escalation for critical defects | QA/QC Module | FIDIC Red Book Sub-Clause 11
5 | Issue corrective action notice to Contractor | Engineer | Defect List / NCR | CAR Notice | N | 1 BD | Escalate if Contractor non-responsive >5 days | QA/QC Module | FIDIC Red Book Sub-Clause 11
6 | Monitor Contractor correction activities | Site Engineer | CAR Notice | Completion Evidence | N | [Completion Period] per CAR | Manager escalation if not completed timely | QA/QC Module | FIDIC Red Book Sub-Clause 11
7 | Close defects and sign-off quality | Engineer | Completion Evidence | Quality Sign-Off | Y | 1 BD | Escalate if defects remain | QA/QC Module | FIDIC Red Book Sub-Clause 7

## PF-11
Step # | Action Description | Responsible Role | Input Document | Output Document | Decision Point (Y/N) | Time Limit | Escalation Rule | System Module | Contractual Basis (FIDIC/Consultancy clause) | Notes
1 | Monthly cost data collected from all sources | Finance/QS | Invoices, timesheets, payroll | Cost Collection Report | N | 5 BD | Manager escalation if data incomplete | Finance Module | FIDIC/Consultancy Financial Management | Aggregates all [Contract Value] related costs
2 | Reconcile costs against budget baseline | QS | Cost Collection Report & Budget | Reconciliation Report | N | 3 BD | Manager escalation if variance >5% | Finance Module | FIDIC/Consultancy Financial Management
3 | Identify cost drivers and variance causes | QS | Reconciliation Report | Variance Analysis | Y | 2 BD | Escalate to Manager if critical variance identified | Finance Module | FIDIC/Consultancy Financial Management | Decision on escalation required
4 | Forecast outturn and contingency impact | QS | Variance Analysis | Outturn Forecast | N | 3 BD | Manager escalation if overrun >10% | Finance Module | FIDIC/Consultancy Financial Management
5 | Approve contingency releases (if applicable) | Approver | Outturn Forecast | Contingency Release Authorization | Y | 2 BD | Escalate to Employer's Rep for large releases | Finance Module | FIDIC/Consultancy Financial Management
6 | Update financial records and stakeholder reporting | Finance | Contingency Release Authorization | Financial Report & Update | N | 2 BD | Manager escalation if records not updated | Finance Module | FIDIC/Consultancy Financial Management
7 | Communicate budget status to steering committee | Finance/PM | Financial Report & Update | Stakeholder Communication Log | N | 1 BD | Manager escalation if communication delayed | Finance Module | FIDIC/Consultancy Financial Management

## PF-12
Step # | Action Description | Responsible Role | Input Document | Output Document | Decision Point (Y/N) | Time Limit | Escalation Rule | System Module | Contractual Basis (FIDIC/Consultancy clause) | Notes
1 | Risk identified and submitted for registration | Any Role | Risk Identification Report | Risk Register Entry | N | 2 BD | Manager escalation if high-risk unregistered >24 hrs | Risk Module | FIDIC/Consultancy Risk Management
2 | Conduct risk assessment (probability × impact) | Risk Manager/Engineer | Risk Register Entry | Risk Assessment Report | N | 3 BD | Manager escalation if assessment method unclear | Risk Module | FIDIC/Consultancy Risk Management
3 | Determine risk category and priority | Risk Manager | Risk Assessment Report | Risk Classification | Y | 1 BD | Escalate to Manager if priority unclear | Risk Module | FIDIC/Consultancy Risk Management | Decision on risk tier
4 | Assign risk owner and mitigation strategy | Project Manager | Risk Classification | Risk Ownership & Mitigation Plan | N | 2 BD | Manager escalation if owner not identified | Risk Module | FIDIC/Consultancy Risk Management
5 | Approve mitigation plan and resource allocation | Approver | Risk Ownership & Mitigation Plan | Approved Mitigation Plan | Y | 2 BD | Escalate to Manager if resources insufficient | Risk Module | FIDIC/Consultancy Risk Management
6 | Monitor risk and track mitigation progress | Risk Owner | Approved Mitigation Plan | Progress Report | N | Ongoing (monthly review) | Escalate if risk escalates or mitigation fails | Risk Module | FIDIC/Consultancy Risk Management
7 | Review and update risk register monthly | Risk Manager | Progress Report | Updated Risk Register | N | 1 BD | Manager escalation if register not updated | Risk Module | FIDIC/Consultancy Risk Management

## PF-13
Step # | Action Description | Responsible Role | Input Document | Output Document | Decision Point (Y/N) | Time Limit | Escalation Rule | System Module | Contractual Basis (FIDIC/Consultancy clause) | Notes
1 | Collect performance data monthly | Site Engineer/Coordinator | Site reports, quality records, timesheets | Performance Data Collection | N | 5 BD | Manager escalation if data incomplete | Performance Module | FIDIC Red Book Performance Monitoring
2 | Score against KPI categories (Quality, Safety, Schedule, Cost) | Site Engineer | Performance Data Collection | KPI Scoring Sheet | N | 3 BD | Manager escalation if scoring inconsistent | Performance Module | FIDIC Red Book Performance Monitoring
3 | Calculate weighted composite score | QS | KPI Scoring Sheet | Composite Performance Score | N | 1 BD | Manager escalation if calculation errors | Performance Module | FIDIC Red Book Performance Monitoring
4 | Review score and identify trends | Engineer/Manager | Composite Performance Score | Performance Analysis | Y | 2 BD | Escalate to Manager if trend negative | Performance Module | FIDIC Red Book Performance Monitoring | Decision on corrective action need
5 | Issue performance notification to Contractor | Manager | Performance Analysis | Performance Notification | N | 1 BD | Escalate if Contractor disputes score | Performance Module | FIDIC Red Book Performance Monitoring
6 | Record score in contract management system | Coordinator | Performance Notification | System Update Log | N | 1 BD | Manager escalation if not recorded | Performance Module | FIDIC Red Book Performance Monitoring
7 | Update contingency deductions (if applicable) | QS | System Update Log | Updated Deduction Schedule | Y | 1 BD | Escalate if deductions exceed 10% | Finance Module | FIDIC Red Book Sub-Clause 14

## PF-14
Step # | Action Description | Responsible Role | Input Document | Output Document | Decision Point (Y/N) | Time Limit | Escalation Rule | System Module | Contractual Basis (FIDIC/Consultancy clause) | Notes
1 | Trigger event identified (milestone, issue, closure) | Any Role | Event Notification | Lessons Log Entry | N | 2 BD | Manager escalation if trigger unlogged | Knowledge Module | FIDIC/Consultancy Continuous Improvement
2 | Facilitate lessons learned workshop/review | Project Manager/Facilitator | Lessons Log Entry | Workshop Report | N | 5 BD | Manager escalation if workshop not conducted | Knowledge Module | FIDIC/Consultancy Continuous Improvement
3 | Document lessons in structured format | Facilitator | Workshop Report | Lessons Document | N | 3 BD | Manager escalation if lessons unclear | Knowledge Module | FIDIC/Consultancy Continuous Improvement
4 | Categorize lessons (process, technical, commercial, safety) | Project Manager | Lessons Document | Categorized Lessons | N | 2 BD | Manager escalation if categorization issues | Knowledge Module | FIDIC/Consultancy Continuous Improvement
5 | Develop action plans for improvement | Responsible Parties | Categorized Lessons | Action Plan | Y | 3 BD | Escalate if action owners not identified | Knowledge Module | FIDIC/Consultancy Continuous Improvement | Decision on follow-up actions
6 | Approve action plans and assign owners | Manager | Action Plan | Approved Action Plan | N | 2 BD | Manager escalation if not approved | Knowledge Module | FIDIC/Consultancy Continuous Improvement
7 | Share lessons across organization and update procedures | Knowledge Manager | Approved Action Plan | Organizational Knowledge Update | N | 5 BD | Manager escalation if not distributed | Knowledge Module | FIDIC/Consultancy Continuous Improvement

## PF-15
Step # | Action Description | Responsible Role | Input Document | Output Document | Decision Point (Y/N) | Time Limit | Escalation Rule | System Module | Contractual Basis (FIDIC/Consultancy clause) | Notes
1 | Prepare handover checklist with contractual requirements | Engineer | Contract Requirements & Project Scope | Handover Checklist | N | 15 BD | Manager escalation if checklist incomplete | Project Closure Module | FIDIC Red Book Sub-Clause 10.1
2 | Conduct defects liability period (DLP) inspections | Engineer | Handover Checklist | DLP Inspection Reports | N | As per DLP [Completion Period] | Manager escalation if defects found | Project Closure Module | FIDIC Red Book Sub-Clause 11
3 | Document defects and issue punch-list to Contractor | Engineer | DLP Inspection Reports | Punch List | N | 2 BD post-inspection | Escalate if Contractor non-responsive | Project Closure Module | FIDIC Red Book Sub-Clause 11
4 | Monitor Contractor rectification of defects | Engineer | Punch List | Rectification Evidence | N | Per DLP period | Escalate to Manager if not completed timely | Project Closure Module | FIDIC Red Book Sub-Clause 11
5 | Verify all defects rectified and DLP requirements met | Engineer | Rectification Evidence | Completion Verification | Y | 1 BD | Escalate if defects remain | Project Closure Module | FIDIC Red Book Sub-Clause 11 | Decision on DLP sign-off
6 | Prepare handover documentation and certificates | Project Manager | Completion Verification | Handover Documentation | N | 3 BD | Manager escalation if docs incomplete | Project Closure Module | FIDIC Red Book Sub-Clause 10.1
7 | Execute formal handover and obtain client sign-off | Employer's Representative | Handover Documentation | Handover Sign-Off Certificate | Y | 1 BD | Escalate if client has outstanding issues | Project Closure Module | FIDIC Red Book Sub-Clause 10.1
8 | Finalize DLP closure and release retention hold | Finance/Manager | Handover Sign-Off Certificate | Retention Release Authorization | N | 1 BD | Manager escalation if release delayed | Finance Module | FIDIC Red Book Sub-Clause 14

## PF-16
Step # | Action Description | Responsible Role | Input Document | Output Document | Decision Point (Y/N) | Time Limit | Escalation Rule | System Module | Contractual Basis (FIDIC/Consultancy clause) | Notes
1 | Claim received and registered with contractual reference | Coordinator | Claim Notice | Claims Register Entry | N | 1 BD | Auto-escalate if unlogged >24 hrs | Claims Module | FIDIC Red Book Sub-Clause 20 / Consultancy Dispute
2 | Validate claim against contract conditions and time limits | Engineer/Legal | Claims Register Entry & Contract | Validity Assessment | Y | 5 BD | Escalate to Legal if complex | Claims Module | FIDIC Red Book Sub-Clause 20 / Consultancy Dispute | Decision on prima facie validity
3 | Compile supporting evidence and documentation | Project Team | Validity Assessment | Evidence Package | N | 7 BD | Manager escalation if evidence gaps | Claims Module | FIDIC Red Book Sub-Clause 20 / Consultancy Dispute
4 | Prepare response to claim with technical analysis | Engineer/QS | Evidence Package | Response Draft | N | 7 BD | Manager escalation if response timeline tight | Claims Module | FIDIC Red Book Sub-Clause 20 / Consultancy Dispute
5 | Legal review of response and settlement options | Legal | Response Draft | Legal Opinion | Y | 3 BD | Escalate to Employer's Rep if settlement recommended | Claims Module | FIDIC Red Book Sub-Clause 20 / Consultancy Dispute
6 | Approve response or negotiate settlement | Approver | Legal Opinion | Approved Response/Settlement | Y | 2 BD | Escalate to Employer's Rep for major decisions | Claims Module | FIDIC Red Book Sub-Clause 20 / Consultancy Dispute
7 | Issue response to claimant and initiate dispute resolution | Legal/Manager | Approved Response/Settlement | Dispute Resolution Register | N | 1 BD | Escalate to Legal for escalation path | Claims Module | FIDIC Red Book Sub-Clause 20 / Consultancy Dispute

## PF-17
Step # | Action Description | Responsible Role | Input Document | Output Document | Decision Point (Y/N) | Time Limit | Escalation Rule | System Module | Contractual Basis (FIDIC/Consultancy clause) | Notes
1 | Identify reporting requirement and frequency | PM/Coordinator | Regulatory/Contractual Requirement | Report Registry Entry | N | 2 BD | Manager escalation if requirement unclear | Reporting Module | FIDIC/Consultancy Reporting Requirements
2 | Extract and verify data from source systems | Data Specialist | Report Registry Entry | Data Extraction Report | N | 3 BD | Manager escalation if data integrity issues | Reporting Module | FIDIC/Consultancy Data Management
3 | Validate data accuracy and completeness | QS/Finance | Data Extraction Report | Data Validation Report | Y | 2 BD | Escalate to Manager if validation issues found | Reporting Module | FIDIC/Consultancy Data Management | Decision on data readiness
4 | Generate report using approved template and format | Data Specialist/Analyst | Data Validation Report | Draft Report | N | 3 BD | Manager escalation if format issues | Reporting Module | FIDIC/Consultancy Reporting Format
5 | Review report for accuracy and compliance | Manager/Approver | Draft Report | Reviewed Report | Y | 2 BD | Escalate to Employer's Rep if content issues | Reporting Module | FIDIC/Consultancy Compliance | Decision on approval
6 | Approve report for distribution | Authorized Approver | Reviewed Report | Approved Report | N | 1 BD | Manager escalation if approval withheld | Reporting Module | FIDIC/Consultancy Authority
7 | Distribute report to recipients and maintain distribution log | Coordinator | Approved Report | Distribution Log | N | 1 BD | Manager escalation if distribution fails | Reporting Module | FIDIC/Consultancy Communication

## PF-18
Step # | Action Description | Responsible Role | Input Document | Output Document | Decision Point (Y/N) | Time Limit | Escalation Rule | System Module | Contractual Basis (FIDIC/Consultancy clause) | Notes
1 | Master data requirement identified or change requested | Any Role | Data Request/Business Case | MDM Queue Entry | N | 2 BD | Manager escalation if not queued | Data Governance Module | FIDIC/Consultancy Data Management
2 | Validate request against MDM governance rules | Data Steward | MDM Queue Entry | Validation Report | Y | 2 BD | Escalate if rule violation found | Data Governance Module | FIDIC/Consultancy Data Management | Decision on eligibility
3 | Update master record with approved data changes | Data Administrator | Validation Report | Updated Master Record | N | 1 BD | Manager escalation if update fails | Data Governance Module | FIDIC/Consultancy Data Management
4 | Propagate changes to dependent systems | Data Administrator | Updated Master Record | System Sync Report | N | 2 BD | Manager escalation if sync fails | Data Governance Module | FIDIC/Consultancy Data Management
5 | Verify data consistency across systems | Data Steward | System Sync Report | Verification Report | Y | 1 BD | Escalate if inconsistencies found | Data Governance Module | FIDIC/Consultancy Data Management | Decision on data quality
6 | Communicate data changes to affected users | Coordinator | Verification Report | Communication Log | N | 1 BD | Manager escalation if communication fails | Data Governance Module | FIDIC/Consultancy Communication
7 | Archive old records and maintain audit trail | Data Administrator | Communication Log | Audit Trail Entry | N | 1 BD | Manager escalation if audit incomplete | Data Governance Module | FIDIC/Consultancy Compliance

## PF-19
Step # | Action Description | Responsible Role | Input Document | Output Document | Decision Point (Y/N) | Time Limit | Escalation Rule | System Module | Contractual Basis (FIDIC/Consultancy clause) | Notes
1 | Update schedule with latest progress data | Planner | Progress Reports, Status Updates | Updated Schedule | N | 5 BD | Manager escalation if updates delayed | Planning Module | FIDIC/Consultancy Schedule Management | Reference [Completion Period] baseline
2 | Calculate critical path and identify constraints | Planner | Updated Schedule | CPM Analysis Report | N | 3 BD | Manager escalation if CPM methodology unclear | Planning Module | FIDIC/Consultancy Schedule Management
3 | Assess schedule variance against baseline | Planner | CPM Analysis Report & Baseline | Variance Analysis Report | Y | 2 BD | Escalate to Manager if delay >5% | Planning Module | FIDIC/Consultancy Schedule Management | Decision on corrective action
4 | Develop recovery/remedial schedule if needed | Planner/PM | Variance Analysis Report | Recovery Plan | N | 5 BD | Manager escalation if recovery infeasible | Planning Module | FIDIC/Consultancy Schedule Management | Assess impact on [Completion Period]
5 | Review schedule and recovery plan for approval | Manager/Approver | Recovery Plan | Approval Recommendation | Y | 3 BD | Escalate to Employer's Rep if [Completion Period] at risk | Planning Module | FIDIC/Consultancy Schedule Management
6 | Communicate updated schedule to all stakeholders | Coordinator | Approval Recommendation | Communication Log | N | 1 BD | Manager escalation if communication delayed | Planning Module | FIDIC/Consultancy Communication
7 | Update baseline (if approved) and monitor execution | Planner | Communication Log | Baseline Update Log | N | Ongoing (bi-weekly review) | Escalate if actual <planned >1 week | Planning Module | FIDIC/Consultancy Schedule Management

## PF-20
Step # | Action Description | Responsible Role | Input Document | Output Document | Decision Point (Y/N) | Time Limit | Escalation Rule | System Module | Contractual Basis (FIDIC/Consultancy clause) | Notes
1 | Collect real-time data from all project systems | Data Integration System | Live data feeds | Consolidated Data Pool | N | Continuous (hourly) | Alert if data feed interrupted >2 hrs | Analytics Module | FIDIC/Consultancy Data Management
2 | Apply predictive models for cost, schedule, risk | Analytics Engine | Consolidated Data Pool | Predictive Analysis Output | N | Continuous (daily) | Alert if model error rate >5% | Analytics Module | FIDIC/Consultancy Analytics
3 | Generate trend insights and forecast indicators | Data Analyst | Predictive Analysis Output | Trend Report | N | 3 BD | Manager escalation if anomaly detected | Analytics Module | FIDIC/Consultancy Analytics
4 | Validate forecast accuracy against historical actuals | Data Analyst | Trend Report & Historical Data | Validation Report | Y | 2 BD | Escalate if forecast accuracy <80% | Analytics Module | FIDIC/Consultancy Analytics | Decision on model reliability
5 | Issue early warning alerts for threshold breaches | Analyst/System | Validation Report | Alert Log | N | Continuous | Auto-escalate critical alerts | Analytics Module | FIDIC/Consultancy Risk Management
6 | Prepare dashboard visualizations for management review | BI Analyst | Alert Log | Dashboard Report | N | Daily/Weekly | Manager escalation if dashboard down >4 hrs | Analytics Module | FIDIC/Consultancy Reporting
7 | Distribute analytics insights to decision-makers | Coordinator | Dashboard Report | Distribution Log | N | Per schedule | Manager escalation if distribution fails | Analytics Module | FIDIC/Consultancy Communication

## PF-21
Step # | Action Description | Responsible Role | Input Document | Output Document | Decision Point (Y/N) | Time Limit | Escalation Rule | System Module | Contractual Basis (FIDIC/Consultancy clause) | Notes
1 | Identify communication need or trigger event | Any Role | Event/Requirement Notice | Communication Queue Entry | N | 1 BD | Manager escalation if not queued | Communication Module | FIDIC/Consultancy General
2 | Determine communication type, audience, and format | Coordinator/PM | Communication Queue Entry | Communication Plan | N | 2 BD | Manager escalation if audience unclear | Communication Module | FIDIC/Consultancy General
3 | Draft communication message with contract reference | Content Owner | Communication Plan | Draft Message | N | 3 BD | Manager escalation if message unclear | Communication Module | FIDIC/Consultancy General
4 | Review for accuracy, tone, and compliance | Manager/Legal | Draft Message | Review Feedback | Y | 2 BD | Escalate to Legal if content risk | Communication Module | FIDIC/Consultancy Compliance | Decision on approval
5 | Approve final communication for distribution | Authorized Approver | Review Feedback | Approved Message | N | 1 BD | Manager escalation if approval delayed | Communication Module | FIDIC/Consultancy Authority
6 | Distribute communication through appropriate channels | Coordinator | Approved Message | Distribution Log | N | 1 BD | Manager escalation if distribution fails | Communication Module | FIDIC/Consultancy General
7 | Track response and maintain communication archive | Coordinator | Distribution Log | Communication Archive Entry | N | Ongoing (per requirement) | Manager escalation if responses not tracked | Communication Module | FIDIC/Consultancy Compliance

## PF-22
Step # | Action Description | Responsible Role | Input Document | Output Document | Decision Point (Y/N) | Time Limit | Escalation Rule | System Module | Contractual Basis (FIDIC/Consultancy clause) | Notes
1 | Document generated and submitted for numbering | Any Role | New Document | Numbering Queue Entry | N | 1 BD | Auto-escalate if not queued >24 hrs | Doc Management Module | FIDIC/Consultancy Document Control
2 | Verify document type and assign number per scheme | Document Controller | Numbering Queue Entry | Assigned Document Number | N | 2 BD | Manager escalation if numbering error | Doc Management Module | FIDIC/Consultancy Document Control
3 | Register document with metadata (date, version, owner) | Document Controller | Assigned Document Number | Registry Entry | N | 1 BD | Manager escalation if metadata incomplete | Doc Management Module | FIDIC/Consultancy Document Control
4 | Apply version control and update document references | Document Controller | Registry Entry | Updated Document Reference Links | N | 1 BD | Manager escalation if references not updated | Doc Management Module | FIDIC/Consultancy Document Control
5 | Store document in repository with access controls | Document Controller | Updated Document Reference Links | Repository Storage Entry | N | 1 BD | Manager escalation if storage fails | Doc Management Module | FIDIC/Consultancy Document Control
6 | Notify stakeholders of document availability | Coordinator | Repository Storage Entry | Notification Log | N | 1 BD | Manager escalation if notification fails | Doc Management Module | FIDIC/Consultancy Communication
7 | Update document registry dashboard and audit trail | Document Controller | Notification Log | Audit Trail Entry | N | 1 BD | Manager escalation if audit incomplete | Doc Management Module | FIDIC/Consultancy Compliance

## PF-23
Step # | Action Description | Responsible Role | Input Document | Output Document | Decision Point (Y/N) | Time Limit | Escalation Rule | System Module | Contractual Basis (FIDIC/Consultancy clause) | Notes
1 | Meeting scheduled and invitations sent | Coordinator | Meeting Requirement | Meeting Register Entry | N | 5 BD | Manager escalation if not scheduled | Meeting Module | FIDIC/Consultancy General
2 | Prepare meeting agenda and supporting documents | Coordinator/PM | Meeting Register Entry | Agenda & Supporting Docs | N | 3 BD | Manager escalation if agenda incomplete | Meeting Module | FIDIC/Consultancy General
3 | Conduct meeting and document discussions | Meeting Chair | Agenda & Supporting Docs | Meeting Minutes Draft | N | 1 BD | Manager escalation if minutes not taken | Meeting Module | FIDIC/Consultancy General
4 | Extract action items and assign responsibilities | Coordinator | Meeting Minutes Draft | Action Items List | Y | 1 BD | Escalate if owners not identified | Meeting Module | FIDIC/Consultancy General | Decision on action assignment
5 | Approve minutes and distribute to attendees | Meeting Chair | Action Items List | Approved Minutes | N | 2 BD | Manager escalation if approval delayed | Meeting Module | FIDIC/Consultancy General
6 | Track action item completion and progress | Coordinator | Approved Minutes | Action Tracking Log | N | Ongoing (per action timeline) | Auto-escalate if overdue >1 BD | Meeting Module | FIDIC/Consultancy General
7 | Close completed actions and update action register | Coordinator | Action Tracking Log | Closed Action Log | N | 1 BD | Manager escalation if actions remain open | Meeting Module | FIDIC/Consultancy General

## PF-24
Step # | Action Description | Responsible Role | Input Document | Output Document | Decision Point (Y/N) | Time Limit | Escalation Rule | System Module | Contractual Basis (FIDIC/Consultancy clause) | Notes
1 | Mobilization plan prepared per contract terms | Project Manager | Contract requirements & Project scope | Mobilization Plan | N | 10 BD | Manager escalation if plan incomplete | Mobilization Module | FIDIC Red Book Sub-Clause 1.6 / Consultancy Article 2
2 | Verify resource deployment schedule and availability | HR/PM | Mobilization Plan | Resource Deployment Schedule | N | 5 BD | Manager escalation if resources unavailable | Mobilization Module | FIDIC Red Book Sub-Clause 1.6 / Consultancy Article 2 | Consultant: verify staff CVs and availability; Contractor: verify labour/equipment
3 | Establish site facilities and temporary works | Contractor/Consultant | Resource Deployment Schedule | Site Setup Evidence | N | [Completion Period] initial period | Manager escalation if site not ready on time | Mobilization Module | FIDIC Red Book Sub-Clause 1.6 | Construction specific: temporary offices, welfare, storage
4 | Conduct induction and safety compliance verification | Site Manager/HR | Site Setup Evidence | Induction & Safety Checklist | N | 2 BD post-arrival | Escalate if safety non-compliance found | Mobilization Module | FIDIC Red Book Sub-Clause 6 / Consultancy General
5 | Approve mobilization and issue commencement notice | Employer's Rep | Induction & Safety Checklist | Mobilization Approval | Y | 1 BD | Escalate if mobilization not approved | Mobilization Module | FIDIC Red Book Sub-Clause 1.6 / Consultancy Article 2 | Decision on contract commencement
6 | Record mobilization completion and update programme | Planner/Coordinator | Mobilization Approval | Updated Schedule & Mobilization Log | N | 1 BD | Manager escalation if records not updated | Mobilization Module | FIDIC Red Book Sub-Clause 1.6 / Consultancy Article 2
7 | Communicate mobilization completion to stakeholders | Coordinator | Updated Schedule & Mobilization Log | Stakeholder Notification Log | N | 1 BD | Manager escalation if communication fails | Mobilization Module | FIDIC Red Book Sub-Clause 1.6 / Consultancy Article 2

## PF-25
Step # | Action Description | Responsible Role | Input Document | Output Document | Decision Point (Y/N) | Time Limit | Escalation Rule | System Module | Contractual Basis (FIDIC/Consultancy clause) | Notes
1 | T&C schedule prepared with GSAS 4-star compliance requirements | Engineer | Contract requirements & GSAS standards | T&C Plan | N | 15 BD | Manager escalation if plan incomplete | T&C Module | FIDIC Red Book Sub-Clause 7.4 | Reference [Completion Period] for timeline
2 | Prepare test protocols and acceptance criteria per GSAS | Engineer | T&C Plan & GSAS Requirements | Test Protocols | N | 10 BD | Manager escalation if protocols unclear | T&C Module | FIDIC Red Book Sub-Clause 7.4 / GSAS V4
3 | Approve test protocols and mobilize testing team | Approver | Test Protocols | Approved T&C Schedule | Y | 2 BD | Escalate if testing resources unavailable | T&C Module | FIDIC Red Book Sub-Clause 7.4 | Decision on protocol approval
4 | Execute system tests and commission facilities | Site Engineer/Test Team | Approved T&C Schedule | Test Reports & Commissioning Records | N | Per T&C schedule | Manager escalation if test failures found | T&C Module | FIDIC Red Book Sub-Clause 7.4
5 | Conduct GSAS 4-star compliance verification and authority inspections | Third-party Certifier | Test Reports & Commissioning Records | GSAS Compliance Report & Inspection Records | Y | Per authority timeline | Escalate to Employer's Rep if non-compliance | T&C Module | GSAS V4 & Authority Requirements | Decision on GSAS certification
6 | Obtain GSAS rating certificate and authority approval | Legal/Compliance | GSAS Compliance Report & Inspection Records | Compliance Certificates | N | Per authority process | Manager escalation if certification delayed | T&C Module | GSAS V4 & Authority Approval
7 | Document T&C completion and update project records | Coordinator | Compliance Certificates | T&C Final Report & Archive | N | 2 BD | Manager escalation if records not complete | T&C Module | FIDIC Red Book Sub-Clause 7.4
8 | Issue final handover approval for GSAS-compliant facility | Employer's Rep | T&C Final Report & Archive | Handover Authorization | Y | 1 BD | Escalate if handover withheld | T&C Module | FIDIC Red Book Sub-Clause 10.1

## PF-26
Step # | Action Description | Responsible Role | Input Document | Output Document | Decision Point (Y/N) | Time Limit | Escalation Rule | System Module | Contractual Basis (FIDIC/Consultancy clause) | Notes
1 | End-user occupancy commences and support desk activated | Facility Manager | Handover Authorization | Occupancy Log & Support Desk Open | N | 1 BD | Manager escalation if support desk not operational | Facility Management Module | FIDIC Red Book Sub-Clause 11
2 | Capture and register end-user complaints and snagging items | Support Desk | End-user Reports | Complaints & Snagging Register | N | Ongoing (daily) | Auto-escalate if critical complaint unaddressed >24 hrs | Facility Management Module | FIDIC Red Book Sub-Clause 11
3 | Triage and prioritize complaints (critical/high/medium/low) | Facility Manager | Complaints & Snagging Register | Prioritized Work Order List | Y | 1 BD per batch | Escalate critical items to Manager | Facility Management Module | FIDIC Red Book Sub-Clause 11 | Decision on priority/escalation
4 | Process warranty claims and verification against defect liability period | Facility Manager/QS | Prioritized Work Order List | Warranty Claim Assessment | N | 5 BD | Manager escalation if claim validity unclear | Facility Management Module | FIDIC Red Book Sub-Clause 11 | Verify within DLP [Completion Period] scope
5 | Assign remedial work to contractor or third-party service provider | Facility Manager | Warranty Claim Assessment | Work Assignment & Service Order | N | 2 BD | Escalate if contractor non-responsive | Facility Management Module | FIDIC Red Book Sub-Clause 11
6 | Monitor remedial work execution and end-user satisfaction | Facility Manager | Work Assignment & Service Order | Completion & Feedback Record | N | Ongoing (per work timeline) | Manager escalation if satisfaction <80% | Facility Management Module | FIDIC Red Book Sub-Clause 11
7 | Close complaints and maintain warranty/service records | Facility Manager | Completion & Feedback Record | Closed Complaint Log & Facility Record | N | 1 BD post-resolution | Manager escalation if record incomplete | Facility Management Module | FIDIC Red Book Sub-Clause 11

## PF-27
Step # | Action Description | Responsible Role | Input Document | Output Document | Decision Point (Y/N) | Time Limit | Escalation Rule | System Module | Contractual Basis (FIDIC/Consultancy clause) | Notes
1 | Monthly consultant timesheet submitted with project allocation [15 WD] | Consultant | Project work evidence & timesheets | Timesheet Register Entry | N | 2 BD per 15 WD | Auto-escalate if unsubmitted >15 WD | Finance Module | Consultancy Article 15 (Payment) | 15 Working Day payment cycle
2 | Verify timesheet accuracy and project allocation compliance | HR/Finance | Timesheet Register Entry | Verification Report | Y | 3 BD | Escalate to Manager if allocation >100% or gaps found | Finance Module | Consultancy Article 15 (Payment) | Decision on timesheet acceptance
3 | Assess consultant KPI performance (deliverables, quality, responsiveness) | Project Manager | Project records & KPI criteria | Performance Score | N | 5 BD | Manager escalation if KPI issues identified | Finance Module | Consultancy Article 21 (Deductions) | Reference KPI scorecard per contract
4 | Calculate approved monthly fee and determine deductions per Article 21 | Finance | Verification Report & Performance Score | Payment Calculation | N | 3 BD | Manager escalation if [Contract Value] discrepancies | Finance Module | Consultancy Article 21 (Deductions) | Apply performance-based deductions if <80% KPI
5 | Approve payment and issue payment instruction | Approver | Payment Calculation | Payment Authorization | Y | 2 BD | Escalate to Employer's Rep if deductions >10% | Finance Module | Consultancy Article 15 (Payment) | Decision on final payment amount
6 | Process payment and issue payment confirmation | Finance | Payment Authorization | Payment Confirmation & Record | N | 1 BD | Manager escalation if payment delayed | Finance Module | Consultancy Article 15 (Payment)
7 | Update consultant payment records and notify of deductions | Finance/HR | Payment Confirmation & Record | Payment Register Update & Notification | N | 1 BD | Manager escalation if not recorded | Finance Module | Consultancy Article 21 (Deductions)

## PF-28
Step # | Action Description | Responsible Role | Input Document | Output Document | Decision Point | Time Limit | Escalation Rule | System Module | Contractual Basis | Notes
1 | Contractor submits application for TOC | Contractor | Application letter | Acknowledgment | Y | [14 CD] before intended date | L1 at D-5 | Handover | SC 10.1
2 | Engineer reviews contractor's application completeness | Resident Engineer | Application, Outstanding works list | Review report | Y | [5 CD] | L2 at D+0 | Handover | SC 10.1
3 | Pre-TOC inspection scheduled and conducted | QA/QC Manager | Inspection schedule, Checklists | Inspection report | Y | [7 CD] after application | L2 | Quality | SC 10.1
4 | Outstanding works / punch list compiled | QA/QC Manager + RE | Inspection report | Outstanding works register | N | [3 CD] after inspection | L1 | Quality | SC 10.1
5 | Engineer determines whether Works substantially complete | Project Director | Inspection report, Outstanding list | Decision memo | Y | [5 CD] | L3 at D+3 | Handover | SC 10.1
6 | TOC issued (or rejection with reasons) | Engineer (HAI) | Decision memo | Taking Over Certificate / Rejection letter | Y | Within [28 CD] of application | L4 if overdue | Handover | SC 10.1
7 | Outstanding works completion tracked | Resident Engineer | Outstanding register | Progress updates | N | Per agreed schedule | L2 | Quality | SC 11.1
8 | DLP period commences, defects notification period starts | Contract Admin | TOC | DLP tracker activation | N | Automatic on TOC date | — | Handover | SC 11.1

## PF-29
Step # | Action Description | Responsible Role | Input Document | Output Document | Decision Point | Time Limit | Escalation Rule | System Module | Contractual Basis | Notes
1 | Contractor submits draft final statement | Contractor | Draft final statement with supporting docs | Acknowledgment | N | Within [56 CD] after DLP expiry | L1 at D-14 | Cost | SC 14.11
2 | Engineer reviews and requests clarifications | QS/Cost Manager | Draft final statement | Review comments, RFI | Y | [28 CD] | L2 at D+0 | Cost | SC 14.11
3 | Contractor submits final statement (agreed or disagreed) | Contractor | Final statement | Acknowledgment | N | Within [28 CD] of disagreement | L2 | Cost | SC 14.11
4 | Engineer determines final contract value | QS/Cost Manager + Project Director | Final statement, all claims, VOs | Determination memo | Y | [28 CD] | L3 at D+7 | Cost | SC 14.13
5 | Final Payment Certificate issued | Engineer (HAI) | Determination memo | Final Payment Certificate | Y | Within [28 CD] of determination | L4 if overdue | Cost | SC 14.13
6 | Employer makes final payment | Employer | Final Payment Certificate | Payment confirmation | N | Within [56 CD] of FPC | L5 if overdue | Finance | SC 14.7
7 | Retention release (if not already released) | QS/Cost Manager | DLP expiry confirmation | Retention release certificate | Y | Per contract terms | L3 | Cost | SC 14.9
8 | Contract commercially closed, records archived | Document Controller | All certificates, correspondence | Archive confirmation | N | [30 CD] after final payment | L1 | Document Mgmt | General

## PF-30
Step # | Action Description | Responsible Role | Input Document | Output Document | Decision Point | Time Limit | Escalation Rule | System Module | Contractual Basis | Notes
1 | DLP expiry date tracked and alerted | Contract Admin | TOC, DLP duration | Alert notification | N | [30 CD] before DLP expiry | L1 at D-30 | Handover | SC 11.1
2 | Final defects inspection conducted | QA/QC Manager + RE | Defects register, Inspection plan | Final inspection report | Y | Within [14 CD] before DLP expiry | L2 | Quality | SC 11.1
3 | Outstanding defects status assessed | Resident Engineer | Defects register | Status report | Y | [7 CD] after inspection | L2 | Quality | SC 11.1
4 | Contractor completes remaining defects (if any) | Contractor | Defects list | Completion evidence | N | As directed by Engineer | L3 if overdue | Quality | SC 11.2
5 | Engineer confirms all obligations fulfilled | Project Director | Inspection report, Defects status | Confirmation memo | Y | [7 CD] | L3 | Handover | SC 11.9
6 | Performance Certificate issued | Engineer (HAI) | Confirmation memo | Performance Certificate | Y | Within [28 CD] of DLP expiry | L4 if overdue | Handover | SC 11.9
7 | Contract fully closed, all securities returned | Contract Admin | Performance Certificate | Security return confirmation | N | Within [21 CD] of PC | L3 | Finance | SC 4.2

## PF-31
Step # | Action Description | Responsible Role | Input Document | Output Document | Decision Point | Time Limit | Escalation Rule | System Module | Contractual Basis | Notes
1 | Snag identified during inspection | Site Engineer / QA/QC | Inspection checklist | Snag entry (photo, location, description, category, severity) | N | Same day as inspection | — | Quality | SC 7.2
2 | Snag logged in system with classification | QA/QC Manager | Snag entry | Snag register entry (Critical/Major/Minor) | Y | Within [1 CD] | L1 if Critical | Quality | SC 7.2
3 | Snag notification issued to Contractor | Document Controller | Snag register | NCR / Snag notice | N | Within [1 CD] of logging | Auto-notify | Correspondence | SC 7.2
4 | Contractor acknowledges and provides rectification plan | Contractor | Snag notice | Rectification plan with timeline | Y | Within [3 CD] of notice | L2 if no response | Quality | SC 7.2
5 | Rectification work carried out | Contractor | Rectification plan | Work completion notice | N | Per agreed timeline (Critical: [3 CD], Major: [7 CD], Minor: [14 CD]) | L3 if overdue | Quality | SC 11.2
6 | Re-inspection conducted | Site Engineer / QA/QC | Work completion notice | Re-inspection report | Y | Within [2 CD] of completion notice | L2 | Quality | SC 11.2
7 | Snag closed or re-issued | QA/QC Manager | Re-inspection report | Snag closure / Re-issue notice | Y | Within [1 CD] of re-inspection | L2 if re-issued repeatedly | Quality | SC 11.2
8 | Snag statistics compiled for performance scoring | QA/QC Manager | Snag register | Snag performance report (feed to PF-13) | N | Monthly | — | Reporting | Internal