## COVER SHEET
CONTRACTUAL DELIVERABLE
Level 4: Acceptance Checklists
Document Reference: | HAI-SS-ACL-2026-001-C
Classification: | CONFIDENTIAL — CONTRACTUAL
Document Type: | Contractual Deliverable
Creation Date: | 2026-02-28
PREAMBLE & BINDING TERMS:
This document defines the mandatory acceptance test scenarios for each implementation phase of the HAI SkyStruct Platform. The Service Provider (SkyStruct) must demonstrate each test scenario to HAI's satisfaction before the corresponding milestone payment is released per SOW Clause 7. PASS CRITERIA: All Critical tests must pass with full demonstration. A maximum of 2 High-priority tests may be deferred to the next phase ONLY with an agreed remediation plan, approved in writing by HAI's Representative, and verified at the next milestone gate. Each phase sign-off certifies completion of contractual obligations for that phase.
VERSION HISTORY
Version | Date | Author | Description
1.0 | 2026-02-28 | HAI Platform Team | Initial contractual release
DOCUMENT APPROVAL
HAI REPRESENTATIVE (Employer)
Name: | ________________________________________
Title: | ________________________________________
Signature: | ________________________________________
Date: | ________________________________________
SKYSTRUCT REPRESENTATIVE (Service Provider)
Name: | ________________________________________
Title: | ________________________________________
Signature: | ________________________________________
Date: | ________________________________________

## Phase 1 - Foundation
PHASE 1 ACCEPTANCE: Foundation (30% Payment Milestone)
Test ID | Category | Test Scenario | Expected Result | Steps to Execute | Evidence Required | Pass/Fail | Tester | Date | Notes | PF Reference | SOW Reference | Priority | Contractual Reference | Payment Gate | HAI Witness | Test Date | Result | Evidence Reference | Sign-off
P1-001 | Stage Gates | Configure Stage 0 entry/exit checklists | Stage 0 gate configured with entry and exit criteria | Navigate to Stage Configuration → Stage 0 → Entry Checklist | Screenshot of Stage 0 config panel | [5 empty] | HAI-SG-001 | Critical | SOW Clause 7.1 | Milestone 1 (30%)
P1-002 | Stage Gates | Configure all 10 stage gates (0-8) | All 10 gates configured and visible in system | Verify each gate 0,1,2,3,3.1,4,5,6,7,8 in config | Gate list report exported | [5 empty] | HAI-SG-002 | Critical | SOW Clause 7.1 | Milestone 1 (30%)
P1-003 | Stage Gates | Test stage progression blocking - incomplete gate | System blocks progression with incomplete items | Create project → Stage 0 → add incomplete item → attempt advance → verify block | Block message screenshot | [5 empty] | HAI-SG-003 | Critical | SOW Clause 7.1 | Milestone 1 (30%)
P1-004 | Stage Gates | Test stage progression with complete gate | System allows progression when all items complete | Complete all items in Stage 0 → attempt advance → verify success | Success message screenshot | [5 empty] | HAI-SG-004 | High | SOW Clause 7.1 | Milestone 1 (30%)
P1-005 | Freeze Types | Configure Hard Freeze exception workflow | Hard Freeze configured with exception escalation | Navigate to Freeze Config → Hard Freeze → Exception Workflow | Config screenshot | [5 empty] | HAI-FZ-001 | Critical | SOW Clause 7.1 | Milestone 1 (30%)
P1-006 | Freeze Types | Configure Soft Freeze exception workflow | Soft Freeze configured with exception escalation | Navigate to Freeze Config → Soft Freeze → Exception Workflow | Config screenshot | [5 empty] | HAI-FZ-002 | Critical | SOW Clause 7.1 | Milestone 1 (30%)
P1-007 | Freeze Types | Configure Read-Only Freeze exception workflow | Read-Only Freeze configured with exception escalation | Navigate to Freeze Config → Read-Only Freeze → Exception Workflow | Config screenshot | [5 empty] | HAI-FZ-003 | High | SOW Clause 7.1 | Milestone 1 (30%)
P1-008 | Freeze Types | Configure Data Lock Freeze exception workflow | Data Lock Freeze configured with exception escalation | Navigate to Freeze Config → Data Lock Freeze → Exception Workflow | Config screenshot | [5 empty] | HAI-FZ-004 | High | SOW Clause 7.1 | Milestone 1 (30%)
P1-009 | Approval Matrix | Configure approval matrix for Design stage - 7 workflow types | All 7 workflow types have approval matrix per stage | Navigate to Approval Matrix → Design Stage → verify 7 types | Matrix report with 7 types | [5 empty] | HAI-AM-001 | Critical | SOW Clause 7.1 | Milestone 1 (30%)
P1-010 | Approval Matrix | Configure approval matrix per stage for all 10 stages | 10 stages × 7 workflow types = 70 approval rules configured | Verify approval count in system | Total count report | [5 empty] | HAI-AM-002 | Critical | SOW Clause 7.1 | Milestone 1 (30%)
P1-011 | SLA Timers | Configure SLA D+3 escalation chain | SLA timer triggers at D+3 with escalation | Setup SLA → D+3 → add escalation chain | SLA config screenshot | [5 empty] | HAI-SLA-001 | Critical | SOW Clause 7.1 | Milestone 1 (30%)
P1-012 | SLA Timers | Configure SLA D+5 escalation chain | SLA timer triggers at D+5 with escalation | Setup SLA → D+5 → add escalation chain | SLA config screenshot | [5 empty] | HAI-SLA-002 | High | SOW Clause 7.1 | Milestone 1 (30%)
P1-013 | SLA Timers | Configure SLA D+7 escalation chain | SLA timer triggers at D+7 with escalation | Setup SLA → D+7 → add escalation chain | SLA config screenshot | [5 empty] | HAI-SLA-003 | High | SOW Clause 7.1 | Milestone 1 (30%)
P1-014 | SLA Escalation | Test SLA escalation triggering | Escalation notification sent at configured time | Create task → wait for D+3 → verify escalation triggered | Escalation log report | [5 empty] | HAI-SLA-004 | Critical | SOW Clause 7.1 | Milestone 1 (30%)
P1-015 | Digital Signature | Configure digital signature mechanism | Digital signature mechanism activated | Navigate to Security → Digital Signature → Enable | Config screenshot | [5 empty] | HAI-DS-001 | Critical | SOW Clause 7.1 | Milestone 1 (30%)
P1-016 | Digital Signature | Test document signature workflow | Document signature recorded with timestamp and user | Sign test document → verify signature metadata | Signed document with metadata | [5 empty] | HAI-DS-002 | High | SOW Clause 7.1 | Milestone 1 (30%)
P1-017 | EDMS | Configure structured document repository | Repository structure created with classification | Navigate to EDMS → Repository → Setup structure | Repository tree screenshot | [5 empty] | HAI-EDMS-001 | Critical | SOW Clause 7.1 | Milestone 1 (30%)
P1-018 | EDMS | Test version control mechanism | Previous versions retained and accessible | Upload v1 → modify → upload v2 → access v1 | Version list visible | [5 empty] | HAI-EDMS-002 | Critical | SOW Clause 7.1 | Milestone 1 (30%)
P1-019 | EDMS | Test auto-numbering functionality | Documents auto-numbered per configured pattern | Upload document → verify auto-numbering applied | Document with auto-number | [5 empty] | HAI-EDMS-003 | High | SOW Clause 7.1 | Milestone 1 (30%)
P1-020 | EDMS | Test cover page validation | Cover page template enforced and validated | Create document without cover page → upload → verify rejection | Validation error screenshot | [5 empty] | HAI-EDMS-004 | High | SOW Clause 7.1 | Milestone 1 (30%)
P1-021 | Document Workflow | Test 8-step document workflow - Submit stage | Document submitted to workflow | Upload document → click Submit → verify Step 1 | Workflow initiated screenshot | [5 empty] | HAI-DWF-001 | Critical | SOW Clause 7.1 | Milestone 1 (30%)
P1-022 | Document Workflow | Test 8-step workflow - Review stage | Document in Review status with reviewer assigned | Document submitted → assigned to reviewer → verify Step 2 | Review assignment screenshot | [5 empty] | HAI-DWF-002 | Critical | SOW Clause 7.1 | Milestone 1 (30%)
P1-023 | Document Workflow | Test 8-step workflow - Approval stage | Document in Approval stage with approver | Document reviewed → sent to approval → verify Step 3 | Approval status screenshot | [5 empty] | HAI-DWF-003 | High | SOW Clause 7.1 | Milestone 1 (30%)
P1-024 | Document Workflow | Test 8-step workflow - Issue resolution | Document issues documented and tracked | Document with issues → Issue stage → verify Step 4 | Issue tracking visible | [5 empty] | HAI-DWF-004 | High | SOW Clause 7.1 | Milestone 1 (30%)
P1-025 | Document Workflow | Test 8-step workflow - Rework stage | Document routed back for rework | Rejected document → Rework stage → verify Step 5 | Rework assignment screenshot | [5 empty] | HAI-DWF-005 | High | SOW Clause 7.1 | Milestone 1 (30%)
P1-026 | Document Workflow | Test 8-step workflow - Final review | Reworked document returned to review | Rework completed → Final Review stage → verify Step 6 | Final review status screenshot | [5 empty] | HAI-DWF-006 | High | SOW Clause 7.1 | Milestone 1 (30%)
P1-027 | Document Workflow | Test 8-step workflow - Sign-off | Document signed off by authorized user | Document approved → Sign-off stage → verify Step 7 | Sign-off metadata captured | [5 empty] | HAI-DWF-007 | High | SOW Clause 7.1 | Milestone 1 (30%)
P1-028 | Document Workflow | Test 8-step workflow - Release to repository | Document finalized and released to repository | Signed off → Release stage → verify Step 8 | Document in repository | [5 empty] | HAI-DWF-008 | Critical | SOW Clause 7.1 | Milestone 1 (30%)
P1-029 | Correspondence | Configure letter registry module | Letter registry template created and accessible | Navigate to Correspondence → Letter Registry → Create template | Template created screenshot | [5 empty] | HAI-CORR-001 | High | SOW Clause 7.1 | Milestone 1 (30%)
P1-030 | Correspondence | Test letter template functionality | Letter template auto-populates with project data | Select letter template → verify data population | Populated letter screenshot | [5 empty] | HAI-CORR-002 | High | SOW Clause 7.1 | Milestone 1 (30%)
P1-031 | Correspondence | Test letter search functionality | Letters searchable by date, recipient, type | Navigate to search → filter by recipient → verify results | Search results visible | [5 empty] | HAI-CORR-003 | Medium | SOW Clause 7.1 | Milestone 1 (30%)
P1-032 | Correspondence | Test correspondence archive | All correspondence logged and searchable | Send letter → verify in archive → search → retrieve | Letter in archive confirmed | [5 empty] | HAI-CORR-004 | High | SOW Clause 7.1 | Milestone 1 (30%)
P1-033 | UI Baseline | Verify UI design sign-off document | UI baseline approved and signed | Navigate to Document Control → UI Baseline → verify approval | Signed approval document | [5 empty] | HAI-UI-001 | Medium | SOW Clause 7.1 | Milestone 1 (30%)
P1-034 | Integration Test | Create new project end-to-end | Project created successfully in all systems | Dashboard → New Project → Complete setup → Verify creation | Project in system confirmed | [5 empty] | HAI-E2E-001 | Critical | SOW Clause 7.1 | Milestone 1 (30%)
P1-035 | Integration Test | Advance project Stage 0→1 | Project advances to Stage 1 | Project at Stage 0 → Complete checklist → Advance → Verify Stage 1 | Stage 1 confirmation | [5 empty] | HAI-E2E-002 | Critical | SOW Clause 7.1 | Milestone 1 (30%)
P1-036 | Integration Test | Advance project Stage 1→2 | Project advances to Stage 2 | Project at Stage 1 → Complete checklist → Advance → Verify Stage 2 | Stage 2 confirmation | [5 empty] | HAI-E2E-003 | High | SOW Clause 7.1 | Milestone 1 (30%)
P1-037 | Integration Test | Submit document through 8-step workflow | Document successfully completes all 8 workflow steps | Submit → Review → Approve → Issue → Rework → Review → Sign → Release | Document released to repository | [5 empty] | HAI-E2E-004 | Critical | SOW Clause 7.1 | Milestone 1 (30%)
P1-038 | Integration Test | Test SLA escalation in workflow | SLA escalation triggered during document workflow | Initiate workflow → monitor SLA timer → verify escalation at D+3/D+5/D+7 | Escalation log report | [5 empty] | HAI-E2E-005 | High | SOW Clause 7.1 | Milestone 1 (30%)
P1-039 | Integration Test | Test gate blocking scenario | Attempt to advance with incomplete mandatory items | Stage with incomplete items → Attempt advance → System blocks → Verify message | Block message and reason documented | [5 empty] | HAI-E2E-006 | Critical | SOW Clause 7.1 | Milestone 1 (30%)
P1-040 | System Verification | Verify Phase 1 acceptance criteria met | All 30% Phase 1 requirements verified and documented | Review all test results → Generate Phase 1 summary report | Sign-off document completed | [5 empty] | HAI-PHASE1-SIGN | Critical | SOW Clause 7.1 | Milestone 1 (30%)

## Phase 2 - Pilot
PHASE 2 ACCEPTANCE: Pilot (20% Payment Milestone)
Test ID | Category | Test Scenario | Expected Result | Steps to Execute | Evidence Required | Pass/Fail | Tester | Date | Notes | PF Reference | SOW Reference | Priority | Contractual Reference | Payment Gate | HAI Witness | Test Date | Result | Evidence Reference | Sign-off
P2-001 | Pilot Project | One real project fully operational | Real project running all features | Navigate to Projects → Select Pilot Project → Verify all modules active | Pilot project status dashboard | [5 empty] | HAI-PILOT-001 | Critical | SOW Clause 7.2 | Milestone 2 (20%)
P2-002 | Role-Based Dashboards | Configure PMO dashboard view | PMO role sees project overview, KPIs, risks | Login as PMO → Verify dashboard content | PMO dashboard screenshot | [5 empty] | HAI-DASH-001 | High | SOW Clause 7.2 | Milestone 2 (20%)
P2-003 | Role-Based Dashboards | Configure Finance dashboard view | Finance role sees budget, cost tracking, payment status | Login as Finance → Verify dashboard content | Finance dashboard screenshot | [5 empty] | HAI-DASH-002 | High | SOW Clause 7.2 | Milestone 2 (20%)
P2-004 | Role-Based Dashboards | Configure Contractor dashboard view | Contractor sees assigned tasks, approvals pending, work status | Login as Contractor → Verify dashboard content | Contractor dashboard screenshot | [5 empty] | HAI-DASH-003 | High | SOW Clause 7.2 | Milestone 2 (20%)
P2-005 | Role-Based Dashboards | Configure Quality dashboard view | Quality role sees inspections, NCRs, IR status | Login as Quality → Verify dashboard content | Quality dashboard screenshot | [5 empty] | HAI-DASH-004 | High | SOW Clause 7.2 | Milestone 2 (20%)
P2-006 | Role-Based Dashboards | Configure Design dashboard view | Design role sees documents, approvals, revisions | Login as Design → Verify dashboard content | Design dashboard screenshot | [5 empty] | HAI-DASH-005 | High | SOW Clause 7.2 | Milestone 2 (20%)
P2-007 | KPI Engine | Configure KPI 1: Project Progress % | KPI displays real-time project completion percentage | Configure KPI → Link to stages → Verify calculation | KPI configuration screenshot | [5 empty] | HAI-KPI-001 | Critical | SOW Clause 7.2 | Milestone 2 (20%)
P2-008 | KPI Engine | Configure KPI 2: Budget Variance % | KPI displays budget variance vs. baseline | Configure KPI → Link to cost data → Verify calculation | KPI configuration screenshot | [5 empty] | HAI-KPI-002 | Critical | SOW Clause 7.2 | Milestone 2 (20%)
P2-009 | KPI Engine | Configure KPI 3: Schedule Variance | KPI displays schedule variance in days | Configure KPI → Link to schedule → Verify calculation | KPI configuration screenshot | [5 empty] | HAI-KPI-003 | High | SOW Clause 7.2 | Milestone 2 (20%)
P2-010 | KPI Engine | Configure KPI 4: Quality Score | KPI displays defect/NCR-based quality score | Configure KPI → Link to quality module → Verify calculation | KPI configuration screenshot | [5 empty] | HAI-KPI-004 | High | SOW Clause 7.2 | Milestone 2 (20%)
P2-011 | KPI Engine | Configure KPI 5: Approval Cycle Time | KPI displays average document approval time | Configure KPI → Link to workflow metrics → Verify calculation | KPI configuration screenshot | [5 empty] | HAI-KPI-005 | High | SOW Clause 7.2 | Milestone 2 (20%)
P2-012 | KPI Engine | Configure KPI 6: Risk Status | KPI displays active risks and mitigation status | Configure KPI → Link to risk register → Verify calculation | KPI configuration screenshot | [5 empty] | HAI-KPI-006 | High | SOW Clause 7.2 | Milestone 2 (20%)
P2-013 | KPI Engine | Test live KPI updates | KPIs refresh in real-time with data changes | Make data change → Verify KPI updates within 5 minutes | KPI refresh log | [5 empty] | HAI-KPI-007 | High | SOW Clause 7.2 | Milestone 2 (20%)
P2-014 | Bottleneck Detection | Configure bottleneck detection engine | System identifies workflow bottlenecks | Navigate to Analytics → Bottleneck Detection → Verify enabled | Configuration screenshot | [5 empty] | HAI-BOTTLE-001 | High | SOW Clause 7.2 | Milestone 2 (20%)
P2-015 | Bottleneck Detection | Test bottleneck with stalled approval | System identifies stalled approval as bottleneck | Create approval stuck for 5+ days → Run bottleneck analysis → Verify detection | Bottleneck alert screenshot | [5 empty] | HAI-BOTTLE-002 | Critical | SOW Clause 7.2 | Milestone 2 (20%)
P2-016 | Procurement Module | Configure RFP creation workflow | RFP workflow from creation to issuance | Navigate to Procurement → Create RFP → Complete workflow | RFP in system confirmed | [5 empty] | HAI-PROC-001 | High | SOW Clause 7.2 | Milestone 2 (20%)
P2-017 | Procurement Module | Test RFP response collection | System accepts and tracks RFP responses | Send RFP → Receive responses → Verify tracking | RFP response register | [5 empty] | HAI-PROC-002 | High | SOW Clause 7.2 | Milestone 2 (20%)
P2-018 | Procurement Module | Test RFP evaluation framework | RFP responses evaluated and scored | Evaluate RFP responses → Verify scoring → Generate evaluation report | Evaluation report generated | [5 empty] | HAI-PROC-003 | High | SOW Clause 7.2 | Milestone 2 (20%)
P2-019 | Procurement Module | Test procurement recommendation | Recommendation generated with justification | Complete evaluation → Generate recommendation → Verify approval chain | Recommendation document signed | [5 empty] | HAI-PROC-004 | Critical | SOW Clause 7.2 | Milestone 2 (20%)
P2-020 | Quality Module | Configure Inspection Request (IR) form | IR form created with required fields | Navigate to Quality → Create IR template → Verify fields | IR template created screenshot | [5 empty] | HAI-QUAL-001 | High | SOW Clause 7.2 | Milestone 2 (20%)
P2-021 | Quality Module | Test IR workflow | IR submitted, reviewed, approved with findings | Submit IR → Assign inspector → Complete → Verify status flow | IR workflow completion | [5 empty] | HAI-QUAL-002 | High | SOW Clause 7.2 | Milestone 2 (20%)
P2-022 | Quality Module | Configure Non-Conformance Report (NCR) form | NCR form created with root cause, corrective action fields | Navigate to Quality → Create NCR template → Verify fields | NCR template created screenshot | [5 empty] | HAI-QUAL-003 | High | SOW Clause 7.2 | Milestone 2 (20%)
P2-023 | Quality Module | Test NCR tracking workflow | NCR raised, tracked through corrective action completion | Submit NCR → Assign corrective action → Complete → Verify closure | NCR closure documented | [5 empty] | HAI-QUAL-004 | High | SOW Clause 7.2 | Milestone 2 (20%)
P2-024 | Quality Module | Test site report with photo attachment | Site report created with embedded photos and observations | Create site report → Attach photos → Verify storage and display | Site report with photos visible | [5 empty] | HAI-QUAL-005 | High | SOW Clause 7.2 | Milestone 2 (20%)
P2-025 | Authority Tracker | Configure Authority Type 1: Design Authority | Design Authority tracking configured | Navigate to Authority Tracker → Add Design Authority → Verify config | Configuration screenshot | [5 empty] | HAI-AUTH-001 | High | SOW Clause 7.2 | Milestone 2 (20%)
P2-026 | Authority Tracker | Configure Authority Type 2: Payment Authority | Payment Authority tracking configured | Navigate to Authority Tracker → Add Payment Authority → Verify config | Configuration screenshot | [5 empty] | HAI-AUTH-002 | High | SOW Clause 7.2 | Milestone 2 (20%)
P2-027 | External Access | Configure Contractor access with permissions | Contractor login with limited permissions (assigned projects only) | Create contractor user → Grant project permissions → Login as contractor → Verify access | Contractor access verified | [5 empty] | HAI-EXT-001 | Critical | SOW Clause 7.2 | Milestone 2 (20%)
P2-028 | External Access | Configure Consultant access with permissions | Consultant login with read-only permissions on specific modules | Create consultant user → Grant read-only on docs → Login as consultant → Verify | Consultant access verified | [5 empty] | HAI-EXT-002 | High | SOW Clause 7.2 | Milestone 2 (20%)
P2-029 | Training | Verify training completion for HAI internal users | All HAI staff completed platform training | Navigate to Training Module → Verify completion records for all users | Training completion report | [5 empty] | HAI-TRAIN-001 | Medium | SOW Clause 7.2 | Milestone 2 (20%)
P2-030 | ERP Integration Design | Sign-off ERP integration design document | ERP integration design reviewed and approved | Review design → Get approvals → Signature collection → File in EDMS | Signed design document in repository | [5 empty] | HAI-ERP-DESIGN | Critical | SOW Clause 7.2 | Milestone 2 (20%)

## Phase 3 - ERP & Rollout
PHASE 3 ACCEPTANCE: ERP Integration & Rollout (20% Payment Milestone)
Test ID | Category | Test Scenario | Expected Result | Steps to Execute | Evidence Required | Pass/Fail | Tester | Date | Notes | PF Reference | SOW Reference | Priority | Contractual Reference | Payment Gate | HAI Witness | Test Date | Result | Evidence Reference | Sign-off
P3-001 | ERP Integration | Configure Contract Award to PO integration | Contract Award in SkyStruct creates/updates PO in ERP | Create Contract Award in SkyStruct → Verify PO created in ERP with matching data | PO in ERP system confirmed | [5 empty] | HAI-ERP-001 | Critical | SOW Clause 7.3 | Milestone 3 (20%)
P3-002 | ERP Integration | Test bi-directional Contract Award↔PO sync | Changes in either system sync to other system | Update PO in ERP → Verify Contract Award updates in SkyStruct | Sync log with timestamp | [5 empty] | HAI-ERP-002 | Critical | SOW Clause 7.3 | Milestone 3 (20%)
P3-003 | ERP Integration | Configure IPC to Payment integration | Invoice/Payment Certificate in SkyStruct triggers ERP payment | Submit IPC in SkyStruct → Verify payment transaction initiated in ERP | Payment transaction in ERP | [5 empty] | HAI-ERP-003 | Critical | SOW Clause 7.3 | Milestone 3 (20%)
P3-004 | ERP Integration | Test actuals to dashboard sync | Actual costs from ERP auto-populate dashboard KPIs | Record cost in ERP → Verify dashboard budget KPI updates within 5 min | KPI update log | [5 empty] | HAI-ERP-004 | High | SOW Clause 7.3 | Milestone 3 (20%)
P3-005 | ERP Integration | Test payment status in SkyStruct | Payment status from ERP visible in SkyStruct workflow | Process payment in ERP → Verify status visible in SkyStruct IPC | IPC payment status updated | [5 empty] | HAI-ERP-005 | High | SOW Clause 7.3 | Milestone 3 (20%)
P3-006 | Contractor Scoring | Configure contractor performance scoring | Scoring model configured with weighted criteria | Navigate to Contractor Module → Configure scoring → Set weights | Scoring model configuration | [5 empty] | HAI-SCORE-001 | High | SOW Clause 7.3 | Milestone 3 (20%)
P3-007 | Contractor Scoring | Test contractor score calculation | Score calculated based on quality, schedule, cost performance | Complete contractor task → Verify score updated with calculation detail | Scoring report with detail | [5 empty] | HAI-SCORE-002 | High | SOW Clause 7.3 | Milestone 3 (20%)
P3-008 | Contractor Scoring | Test contractor performance dashboard | Contractor ranked by overall performance score | Navigate to Contractor Performance → Verify ranking and scoring visible | Contractor ranking dashboard | [5 empty] | HAI-SCORE-003 | High | SOW Clause 7.3 | Milestone 3 (20%)
P3-009 | Handover/DLP Module | Configure handover checklist | Handover checklist items created and sequenced | Navigate to Handover → Create checklist → Add items → Verify sequence | Handover checklist visible | [5 empty] | HAI-HO-001 | High | SOW Clause 7.3 | Milestone 3 (20%)
P3-010 | Handover/DLP Module | Test handover workflow | Project handed over with all DLP items verified | Complete handover checklist → Obtain sign-offs → Finalize handover | Handover sign-off document | [5 empty] | HAI-HO-002 | Critical | SOW Clause 7.3 | Milestone 3 (20%)
P3-011 | Handover/DLP Module | Test DLP documentation requirements | All required documentation collected and filed for handover | Verify all DLP docs in repository → Generate DLP package | Complete DLP package in EDMS | [5 empty] | HAI-HO-003 | High | SOW Clause 7.3 | Milestone 3 (20%)
P3-012 | Full Rollout | Rollout to Building 1 | Building 1 project migrated to production SkyStruct | Migrate Building 1 data → Verify all information accessible → Begin operations | Building 1 operational in SkyStruct | [5 empty] | HAI-ROLL-001 | Critical | SOW Clause 7.3 | Milestone 3 (20%)
P3-013 | Full Rollout | Rollout to Building 2 | Building 2 project migrated to production SkyStruct | Migrate Building 2 data → Verify all information accessible → Begin operations | Building 2 operational in SkyStruct | [5 empty] | HAI-ROLL-002 | Critical | SOW Clause 7.3 | Milestone 3 (20%)
P3-014 | Full Rollout | Rollout to Building 3 | Building 3 project migrated to production SkyStruct | Migrate Building 3 data → Verify all information accessible → Begin operations | Building 3 operational in SkyStruct | [5 empty] | HAI-ROLL-003 | Critical | SOW Clause 7.3 | Milestone 3 (20%)
P3-015 | Full Rollout | Rollout to Minor Works project | Minor Works project migrated to production SkyStruct | Migrate Minor Works data → Verify all information accessible → Begin operations | Minor Works operational in SkyStruct | [5 empty] | HAI-ROLL-004 | High | SOW Clause 7.3 | Milestone 3 (20%)
P3-016 | System Stabilization | Verify zero critical defects post-rollout | No critical defects reported in first week post-rollout | Monitor all projects → Review defect log → Verify zero critical | Defect report - 0 critical | [5 empty] | HAI-STABIL-001 | Critical | SOW Clause 7.3 | Milestone 3 (20%)
P3-017 | System Stabilization | Monitor system performance metrics | System response time < 2 seconds for typical operations | Run load test → Monitor response times → Verify SLA compliance | Performance report - all green | [5 empty] | HAI-STABIL-002 | High | SOW Clause 7.3 | Milestone 3 (20%)
P3-018 | System Stabilization | Verify data integrity post-rollout | All migrated data verified accurate and complete | Run data validation scripts → Compare with source systems → Verify 100% match | Data validation report - 100% match | [5 empty] | HAI-STABIL-003 | Critical | SOW Clause 7.3 | Milestone 3 (20%)
P3-019 | Data Export | Configure governance report export to PDF | Governance report available in PDF format with formatting | Navigate to Reports → Governance Report → Export PDF → Verify format | PDF report generated | [5 empty] | HAI-EXPORT-001 | High | SOW Clause 7.3 | Milestone 3 (20%)
P3-020 | Data Export | Configure governance report export to Excel | Governance report available in Excel with sortable/filterable data | Navigate to Reports → Governance Report → Export Excel → Verify functionality | Excel report generated | [5 empty] | HAI-EXPORT-002 | High | SOW Clause 7.3 | Milestone 3 (20%)
P3-021 | Data Export | Test report data accuracy | Exported data matches system data exactly | Export report → Verify sample data points match system → Check calculations | Data accuracy verification | [5 empty] | HAI-EXPORT-003 | High | SOW Clause 7.3 | Milestone 3 (20%)
P3-022 | Data Export | Test scheduled report generation | Reports generated and distributed per schedule | Set report schedule → Verify execution at scheduled time → Check delivery | Scheduled report received | [5 empty] | HAI-EXPORT-004 | Medium | SOW Clause 7.3 | Milestone 3 (20%)
P3-023 | Integration Test | Test end-to-end workflow across all 4 projects | All projects operating seamlessly with ERP integration | Execute sample transaction across all projects → Verify completion | Transaction log across 4 projects | [5 empty] | HAI-E2E-P3-001 | Critical | SOW Clause 7.3 | Milestone 3 (20%)
P3-024 | Transition | Complete knowledge transfer to HAI operations team | HAI team capable of independent system operation | Conduct training sessions → Verify competency → Document handoff | Training completion and sign-off | [5 empty] | HAI-TRANS-001 | High | SOW Clause 7.3 | Milestone 3 (20%)
P3-025 | Phase 3 Sign-off | Verify Phase 3 acceptance criteria met | All Phase 3 requirements verified, documented, and approved | Review all test results → Generate Phase 3 summary → Obtain sign-offs | Phase 3 sign-off document | [5 empty] | HAI-PHASE3-SIGN | Critical | SOW Clause 7.3 | Milestone 3 (20%)

## Phase 4 - Optimization
PHASE 4 ACCEPTANCE: Optimization (30% Payment Milestone)
Test ID | Category | Test Scenario | Expected Result | Steps to Execute | Evidence Required | Pass/Fail | Tester | Date | Notes | PF Reference | SOW Reference | Priority | Contractual Reference | Payment Gate | HAI Witness | Test Date | Result | Evidence Reference | Sign-off
P4-001 | Predictive Analytics | Configure predictive model for project completion | ML model predicts project completion date with 80%+ accuracy | Setup model → Train on historical data → Test on current projects → Verify accuracy | Model accuracy report | [5 empty] | HAI-PRED-001 | High | SOW Clause 7.4 | Milestone 4 (30%)
P4-002 | Predictive Analytics | Test budget overrun prediction | Model predicts budget overrun risk early | Configure model → Test on historical overrun cases → Verify early warning | Prediction accuracy report | [5 empty] | HAI-PRED-002 | High | SOW Clause 7.4 | Milestone 4 (30%)
P4-003 | Predictive Analytics | Test schedule risk prediction | Model identifies schedule risk factors and predicts delays | Configure model → Analyze schedule trends → Verify prediction accuracy | Risk prediction report | [5 empty] | HAI-PRED-003 | Medium | SOW Clause 7.4 | Milestone 4 (30%)
P4-004 | Historical Analysis | Analyze historical project performance trends | Historical data summarized in trend analysis reports | Generate portfolio trend report → Verify data completeness → Review analytics | Trend analysis report | [5 empty] | HAI-HIST-001 | High | SOW Clause 7.4 | Milestone 4 (30%)
P4-005 | Historical Analysis | Test trend comparison across portfolio | Trends comparable across all 4 projects and historical baseline | Compare metrics across projects → Identify patterns → Generate comparison report | Comparative analysis report | [5 empty] | HAI-HIST-002 | High | SOW Clause 7.4 | Milestone 4 (30%)
P4-006 | Historical Analysis | Test cost performance index calculation | Historical CPI data available and trended over time | Calculate CPI for each project → Trend CPI over duration → Verify calculations | CPI trend report | [5 empty] | HAI-HIST-003 | Medium | SOW Clause 7.4 | Milestone 4 (30%)
P4-007 | Lessons Learned | Configure lessons learned module | Module captures lessons with categories and priority | Navigate to Lessons Learned → Create entry → Verify fields and search | LL module functional | [5 empty] | HAI-LL-001 | High | SOW Clause 7.4 | Milestone 4 (30%)
P4-008 | Lessons Learned | Test lessons learned capture process | Lessons documented with context, impact, recommended actions | Create LL entry → Add detail → Verify completeness → Archive | LL entry in repository | [5 empty] | HAI-LL-002 | High | SOW Clause 7.4 | Milestone 4 (30%)
P4-009 | Lessons Learned | Test preventive rule conversion | Lessons learned converted to preventive rules for future projects | Create LL → Convert to rule → Test application on new project → Verify enforcement | Rule application verification | [5 empty] | HAI-LL-003 | High | SOW Clause 7.4 | Milestone 4 (30%)
P4-010 | Audit Trail | Verify complete audit trail logging | All system actions logged with user, timestamp, change detail | Make change → Verify in audit trail → Check completeness of detail | Audit trail report | [5 empty] | HAI-AUDIT-001 | Critical | SOW Clause 7.4 | Milestone 4 (30%)
P4-011 | Audit Trail | Test audit trail searchability and filtering | Audit trail searchable by user, date range, action type | Search audit trail → Filter by various criteria → Verify results | Audit trail search results | [5 empty] | HAI-AUDIT-002 | High | SOW Clause 7.4 | Milestone 4 (30%)
P4-012 | Audit Trail | Test audit trail access controls | Audit trail accessible only to authorized users (Finance, PMO) | Login as different roles → Verify appropriate access/restrictions | Access control verification | [5 empty] | HAI-AUDIT-003 | Critical | SOW Clause 7.4 | Milestone 4 (30%)
P4-013 | Performance Benchmarks | Test system performance under normal load | System response time < 2 seconds for 95% of operations | Run normal load test → Measure response times → Generate performance report | Performance benchmark report | [5 empty] | HAI-PERF-001 | High | SOW Clause 7.4 | Milestone 4 (30%)
P4-014 | Performance Benchmarks | Test system performance under peak load | System response time < 5 seconds for 95% of operations under peak | Run peak load test → Measure response times → Verify SLA compliance | Peak load performance report | [5 empty] | HAI-PERF-002 | High | SOW Clause 7.4 | Milestone 4 (30%)
P4-015 | Performance Benchmarks | Test concurrent user limit | System supports 50 concurrent users without degradation | Simulate 50 concurrent users → Verify performance metrics → Check stability | Concurrent user test report | [5 empty] | HAI-PERF-003 | Medium | SOW Clause 7.4 | Milestone 4 (30%)
P4-016 | User Adoption | Measure user adoption metrics | 80%+ user adoption rate across HAI organization | Generate adoption report → Calculate active user percentage → Verify threshold | Adoption metrics report | [5 empty] | HAI-ADOPT-001 | High | SOW Clause 7.4 | Milestone 4 (30%)
P4-017 | User Adoption | Measure user engagement metrics | Average 3+ logins per user per week, avg session 20+ minutes | Generate engagement report → Calculate activity metrics → Verify targets | Engagement metrics report | [5 empty] | HAI-ADOPT-002 | High | SOW Clause 7.4 | Milestone 4 (30%)
P4-018 | User Adoption | Measure feature utilization | Core features utilized by 75%+ of active users | Analyze feature usage logs → Calculate utilization % → Verify baseline | Feature utilization report | [5 empty] | HAI-ADOPT-003 | Medium | SOW Clause 7.4 | Milestone 4 (30%)
P4-019 | Documentation | Verify system administrator guide completion | Admin guide covers all configuration, maintenance, troubleshooting tasks | Review admin guide → Verify completeness → Check accuracy vs. system | Admin guide document | [5 empty] | HAI-DOC-001 | High | SOW Clause 7.4 | Milestone 4 (30%)
P4-020 | Documentation | Verify end-user documentation completion | User guide covers daily tasks with screenshots and examples | Review user guide → Verify clarity and completeness → Test procedures | User guide document | [5 empty] | HAI-DOC-002 | High | SOW Clause 7.4 | Milestone 4 (30%)

## PHASE SIGN-OFF
PHASE-BY-PHASE ACCEPTANCE SIGN-OFF
Phase 1: Foundation SIGN-OFF
Payment Milestone: | Milestone 1 (30%)
SOW Reference: | SOW Clause 7.1
Conditions/Deferrals:
HAI REPRESENTATIVE
Name: | ________________________________________
Signature: | ________________________________________
Date: | ________________________________________
SKYSTRUCT REPRESENTATIVE
Name: | ________________________________________
Signature: | ________________________________________
Date: | ________________________________________
Phase 2: Pilot SIGN-OFF
Payment Milestone: | Milestone 2 (20%)
SOW Reference: | SOW Clause 7.2
Conditions/Deferrals:
HAI REPRESENTATIVE
Name: | ________________________________________
Signature: | ________________________________________
Date: | ________________________________________
SKYSTRUCT REPRESENTATIVE
Name: | ________________________________________
Signature: | ________________________________________
Date: | ________________________________________
Phase 3: ERP & Rollout SIGN-OFF
Payment Milestone: | Milestone 3 (20%)
SOW Reference: | SOW Clause 7.3
Conditions/Deferrals:
HAI REPRESENTATIVE
Name: | ________________________________________
Signature: | ________________________________________
Date: | ________________________________________
SKYSTRUCT REPRESENTATIVE
Name: | ________________________________________
Signature: | ________________________________________
Date: | ________________________________________
Phase 4: Optimization SIGN-OFF
Payment Milestone: | Milestone 4 (30%)
SOW Reference: | SOW Clause 7.4
Conditions/Deferrals:
HAI REPRESENTATIVE
Name: | ________________________________________
Signature: | ________________________________________
Date: | ________________________________________
SKYSTRUCT REPRESENTATIVE
Name: | ________________________________________
Signature: | ________________________________________
Date: | ________________________________________
FINAL PROJECT ACCEPTANCE (ALL PHASES COMPLETE)
Completion Date: | ________________________________________
HAI Representative: | ________________________________________
SkyStruct Representative: | ________________________________________
Date: | ________________________________________