## RACI by Process Flow
PF | Process Flow Name | Activity | R01 Prog Dir | R02 PM | R03 Contracts | R04 Technical Design Mgr | R05 Cost Mgr | R06 QA/QC | R07 Doc Ctrl | R08 Site Eng | R09 Planning | R10 Contr PM | R11 Contr DC | R12 Consult | R13 ER | R14 SysAdmin
PF-01 | Document Review | Submit document | [9 empty] | R | R
PF-01 | Document Review | QC check (compliance) | [6 empty] | R/A
PF-01 | Document Review | Technical review |  | A | C | R | C | C | C | C |  |  |  | C
PF-01 | Document Review | Issue response (A/B/C/D/E) | I | A | C | R | C | C | R |  |  | I | I | C | I
PF-01 | Document Review | ER endorsement | C | I | [10 empty] | R/A
PF-02 | Correspondence | Draft outgoing letter |  | R | C |  |  |  | C
PF-02 | Correspondence | Approve and send | A | R | C | [9 empty] | I
PF-02 | Correspondence | Log incoming correspondence |  | I | I |  |  |  | R
PF-02 | Correspondence | Track response deadline |  | A | R |  |  |  | C | [5 empty] | I
PF-03 | Variation Order | Identify variation need |  | C | C | C | C |  |  |  |  | R |  | C
PF-03 | Variation Order | Assess cost/time impact |  | C | R | C | R |  |  |  | C | C |  | C
PF-03 | Variation Order | Approve within authority | A | R | C |  | C | [7 empty] | I
PF-03 | Variation Order | Issue variation instruction | I | R/A | R | [6 empty] | I |  |  | I
PF-04 | Procurement | Prepare tender package |  | A | R | C | C
PF-04 | Procurement | Evaluate bids |  | A | R | C | R | [7 empty] | I
PF-04 | Procurement | Award recommendation | A | R | R |  | C | [7 empty] | I
PF-05 | Stage Gate | Complete gate checklist |  | R/A | C | C | C | C | C |  | C
PF-05 | Stage Gate | Review gate readiness | A | R | C | C | C | [7 empty] | I
PF-05 | Stage Gate | Approve gate passage | R | C | [10 empty] | A
PF-06 | Freeze Exception | Request exception |  | C | C | R | C |  |  |  |  | C
PF-06 | Freeze Exception | Assess impact |  | A | C | R | R
PF-06 | Freeze Exception | Approve/reject exception | R/A | C | [10 empty] | I
PF-07 | Authority Submissions | Prepare submission package |  | C |  | R |  |  | C |  |  | C
PF-07 | Authority Submissions | Submit to authority |  | R/A | C | C | [8 empty] | I
PF-07 | Authority Submissions | Track approval status |  | R |  | C |  |  | C | [5 empty] | I
PF-08 | IPC Processing | Submit payment application | [9 empty] | R
PF-08 | IPC Processing | Verify quantities/values |  | C | C |  | R/A | [6 empty] | C
PF-08 | IPC Processing | Certify IPC |  | R/A | C |  | C | [7 empty] | I
PF-09 | Approval Engine | Configure approval routes | [13 empty] | R/A
PF-09 | Approval Engine | Delegate authority | R | R | R | [10 empty] | C
PF-09 | Approval Engine | Process approval step |  | R | R | R | R | [7 empty] | A
PF-10 | Quality Supervision | Submit inspection request | [9 empty] | R
PF-10 | Quality Supervision | Conduct inspection | [5 empty] | R/A |  | R
PF-10 | Quality Supervision | Issue NCR |  | I |  |  |  | R/A |  | R |  | I
PF-11 | Spatial Coordination Cost | Prepare cost report |  | C | C |  | R/A
PF-11 | Spatial Coordination Cost | Review budget status | A | R |  |  | R | [7 empty] | I
PF-12 | Risk Register | Identify and log risk |  | R | C | C | C | C |  | C |  | C
PF-12 | Risk Register | Assess and score risk |  | R/A | C | C | C | C | [6 empty] | I
PF-12 | Risk Register | Assign mitigation owner | I | R/A | [10 empty] | I
PF-13 | Contractor Performance | Calculate monthly score |  | R/A | C |  | C | C
PF-13 | Contractor Performance | Issue score report | I | R | [7 empty] | I |  |  | I
PF-14 | Lessons Learned | Log lesson |  | R | C | C | C | C |  | C | C | C |  | C
PF-14 | Lessons Learned | Review and convert to action | A | R | [10 empty] | I
PF-15 | Handover DLP | Prepare handover package |  | A |  |  |  | C | C |  |  | R | R
PF-15 | Handover DLP | Verify completeness |  | R/A |  | C |  | R | [6 empty] | I
PF-15 | Handover DLP | Accept handover | I | R | [10 empty] | A
PF-16 | Meeting Tracking | Create meeting/minutes |  | R |  |  |  |  | C |  |  | C |  | C
PF-16 | Meeting Tracking | Track action items |  | R/A | C | C | C | C | C | C | C | C |  | C | I
PF-28 | TOC Management | Submit TOC application | [9 empty] | R
PF-28 | TOC Management | Conduct TOC inspection |  | R/A |  |  |  | R |  | R |  |  |  |  | I
PF-28 | TOC Management | Issue TOC | I | R/A | [10 empty] | A
PF-29 | Final Payment Certificate | Submit final account | [9 empty] | R
PF-29 | Final Payment Certificate | Verify final account |  | C | R |  | R/A | [7 empty] | I
PF-29 | Final Payment Certificate | Issue final payment cert | I | R/A | C |  | C | [7 empty] | A
PF-30 | Performance Certificate | Verify DLP completion |  | R/A |  |  |  | R |  | C |  |  |  |  | I
PF-30 | Performance Certificate | Issue performance certificate | I | R/A | [10 empty] | A
PF-31 | Snag List Resolution | Create snag list |  | C |  |  |  | R/A |  | R
PF-31 | Snag List Resolution | Rectify snags | [5 empty] | C |  |  |  | R | C
PF-31 | Snag List Resolution | Verify rectification |  | I |  |  |  | R/A |  | R

## Legend
Code | Meaning | Description
R | Responsible | Does the work. Can be multiple per activity.
A | Accountable | Final decision authority. ONE per activity.
C | Consulted | Provides input before decision.
I | Informed | Notified after decision.
R/A | Responsible & Accountable | Does the work AND owns the decision.