## Construction Contract Actions
Card ID | Scenario | FIDIC Clause | Time-bar (CD) | HAI Action Required | Responsible Role | Escalation Level | Document Template | Success Criteria | Risk if Missed
CC-001 | Contractor's Claims - Notice | SC 20.1 | [28 CD] | Receive, validate, and log claim notice with all required details | Document Controller | L2 | Claims Acknowledgement Form | Claim logged in register within [2 WD] | High
CC-002 | Contractor's Claims - Detailed Submission | SC 20.1 | [42 CD] | Review claim details, verify supporting documents, assess merit | RE/PM | L2 | Claims Assessment Report | Assessment completed within [14 CD] | High
CC-003 | Variation Order Issuance | SC 13.1 | As instructed | Issue formal Variation Instruction with clear scope, measurements, methodology | RE/PM | L2 | Variation Instruction Form | VO issued before work commencement | High
CC-004 | Variation Order Track A/B Assessment | SC 13.1 | [28 CD] | Determine valuation methodology (agreed rates, fair valuation, daywork) | RE/PM | L3 | VO Valuation Assessment | Track decision documented within [7 CD] | Medium
CC-005 | Interim Payment Certificate | SC 14.6 | [28 CD] | Inspect work, verify quantities, certify payment due within timeframe | RE/PM | L2 | IPC Certificate | IPC issued by deadline date | High
CC-006 | Taking Over Certificate | SC 10.1 | As works complete | Inspect works, verify completion, issue TOC or defects list | RE/PM | L2 | Taking Over Certificate | TOC issued or defects list within [14 CD] | High
CC-007 | Performance Security Validity | SC 4.2 | Continuous monitoring | Monitor performance security validity and notify of renewal requirement | Document Controller | L1 | Security Renewal Notice | Alert issued [30 CD] before expiry | Medium
CC-008 | Extension of Time Assessment | SC 8.4 | [42 CD] | Review EOT application, assess entitlement, calculate extension period | RE/PM | L3 | EOT Assessment Report | Decision issued within [28 CD] | High
CC-009 | Application of Delay Damages | SC 8.7 | Upon TOC | Apply liquidated damages at [Rate/Day] for delay period in IPC | RE/PM | L2 | Delay Damages Deduction Notice | Damages applied in next IPC certificate | High
CC-010 | Termination by Employer | SC 15.2 | [14 CD] notice | Prepare termination documentation, arrange demobilization, secure site | Project Director | L4 | Termination Notice | Termination executed as per contract | High
CC-011 | Retention Release | SC 14.9 | After TOC + DLP expiry | Release retention funds to contractor after all defects remedied | RE/PM | L2 | Retention Release Certificate | Release processed within [14 CD] of DLP expiry | Medium
CC-012 | Final Statement Preparation | SC 14.11 | [56 CD] after DLP | Prepare final account statement reconciling all claims and costs | RE/PM | L3 | Final Statement | Final statement issued by deadline date | High
CC-013 | Dispute - DAB Referral | SC 20.4 | [84 CD] | Prepare referral documentation, select DAB member, submit to adjudication | HAI Chief Governance Architect | L4 | DAB Referral Document | Referral filed within time-bar deadline | High
CC-014 | Notice of Dissatisfaction | SC 20.4 | [28 CD] | Review DAB decision, prepare dissatisfaction notice if required | HAI Chief Governance Architect | L4 | Dissatisfaction Notice | Notice submitted within deadline or right lost | High
CC-015 | Force Majeure Notification | SC 19.2 | [14 CD] | Assess event, document impacts, provide notice to contractor with evidence | Project Director | L3 | Force Majeure Notice | Notice delivered within time-bar period | Medium

## Consultancy Contract Actions
Card ID | Scenario | Contract Article | Time-bar | HAI Action Required | Responsible Role | Escalation Level | Document Template | Success Criteria | Risk if Missed
CS-001 | Monthly Payment Processing | Art. 11 | [15 WD] | Verify timesheets, validate deliverables, approve payment | Project Coordinator | L1 | Payment Approval Form | Payment approved within deadline | High
CS-002 | Performance Evaluation | Art. 14 | Monthly | Score consultant against KPIs, document performance metrics | Project Director | L2 | Monthly KPI Report | Report completed by [5th] of following month | Medium
CS-003 | Consultant Staff Replacement | Art. 9 | [14 CD] | Review replacement proposal, verify qualifications, approve/reject | Project Director | L2 | Staff Approval Form | Decision issued within timeframe | Medium
CS-004 | Scope Change - Additional Services | Art. 13 | Before commencement | Assess scope change, prepare amendment, negotiate fees | RE/PM | L3 | Scope Amendment Document | Amendment executed before service delivery | High
CS-005 | Stop Work Order | Art. 12 | Immediate | Issue stop work notice with justification and reinstatement conditions | Project Director | L4 | Stop Work Notice | Notice delivered immediately to consultant | High
CS-006 | Penalty Application | Art. 21 | Per monthly IPC | Deduct non-compliance penalties, document justification in certificate | RE/PM | L2 | Deduction Notice | Penalty deducted in next payment certificate | Medium
CS-007 | Mobilization Verification | Art. 8 | [30 CD] | Confirm resource deployment, verify team presence, validate mobilization | Project Coordinator | L1 | Mobilization Checklist | Verification completed within [30 CD] | High
CS-008 | Report Quality Review | Art. 15 | Per deliverable | Review daily/weekly/monthly reports for compliance and quality standards | RE/PM | L1 | Report Assessment Form | Review completed within [5 WD] | Medium
CS-009 | Contract Extension/Reduction | Art. 6 | [30 CD] before expiry | Assess performance, initiate extension or reduction discussions | Project Director | L3 | Contract Modification | Decision issued [30 CD] before expiry | High
CS-010 | Confidentiality Breach Response | Art. 18 | Immediate | Document breach, assess impact, issue corrective action notice | HAI Chief Governance Architect | L5 | Breach Report & Action Plan | Response issued within [2 WD] | High
CS-011 | Insurance Verification | Art. 10 | Annually | Verify insurance renewal, confirm coverage adequacy, obtain updated certificate | Document Controller | L1 | Insurance Certificate | Verification completed before expiry | Medium
CS-012 | Termination for Non-Compliance | Art. 16 | Per contract terms | Prepare termination notice, document non-compliance, execute termination | HAI Chief Governance Architect | L4 | Termination Notice | Termination executed per contract terms | High

## Time-bar Register
ID | Contract Type | Event | Clause Reference | Time-bar Period | Start Trigger | Consequence if Missed | Monitoring Frequency | Alert Schedule
TB-001 | Construction | Contractor Claims Notice | SC 20.1 | [28 CD] | Claim event occurrence | Claim forfeited | Per claim | L5: [20 CD], L4: [14 CD], L3: [7 CD]
TB-002 | Construction | Contractor Claims Details | SC 20.1 | [42 CD] | Claims notice received | Claim forfeited | Per claim | L5: [35 CD], L4: [28 CD], L3: [14 CD]
TB-003 | Construction | IPC Certification | SC 14.6 | [28 CD] | Application submission | Default interest accrual | Monthly | L4: [21 CD], L3: [14 CD], L2: [7 CD]
TB-004 | Construction | Taking Over Certificate | SC 10.1 | At completion | Work substantially complete | Retention period extended | Per milestone | L3: [10 CD], L2: [5 CD]
TB-005 | Construction | Extension of Time Decision | SC 8.4 | [42 CD] | EOT application received | Claim for EOT forfeited | Per application | L4: [35 CD], L3: [28 CD], L2: [14 CD]
TB-006 | Construction | Final Statement | SC 14.11 | [56 CD] | DLP expiration date | Dispute over final account | Once per contract | L5: [42 CD], L4: [28 CD], L3: [14 CD]
TB-007 | Construction | DAB Referral | SC 20.4 | [84 CD] | Dispute initiation | Right to arbitration lost | Per dispute | L5: [70 CD], L4: [56 CD], L3: [42 CD]
TB-008 | Construction | Notice of Dissatisfaction | SC 20.4 | [28 CD] | DAB decision received | Dispute settlement final | Per DAB decision | L4: [21 CD], L3: [14 CD], L2: [7 CD]
TB-009 | Construction | Force Majeure Notification | SC 19.2 | [14 CD] | Event occurrence | Claim for extension denied | Per event | L3: [10 CD], L2: [5 CD]
TB-010 | Construction | Retention Release | SC 14.9 | DLP expiry + [14 CD] | DLP expiration | Contractor claims | Per DLP | L2: [7 CD] before release
TB-011 | Construction | Performance Security Renewal | SC 4.2 | [30 CD] before expiry | Security expiration date | Loss of security coverage | Continuous | L4: [60 CD], L3: [30 CD], L2: [14 CD]
TB-012 | Consultancy | Monthly Payment Approval | Art. 11 | [15 WD] | Invoice submission | Payment default/interest | Monthly | L3: [10 WD], L2: [5 WD], L1: [2 WD]
TB-013 | Consultancy | Performance Evaluation | Art. 14 | Monthly | Month-end | Unrecorded performance | Monthly | L2: [25th], L1: [30th]
TB-014 | Consultancy | Staff Replacement Approval | Art. 9 | [14 CD] | Replacement request | Service continuity risk | Per request | L3: [10 CD], L2: [5 CD]
TB-015 | Consultancy | Mobilization Verification | Art. 8 | [30 CD] | Contract commencement | Performance delay | Once | L2: [21 CD], L1: [28 CD]
TB-016 | Consultancy | Contract Renewal Decision | Art. 6 | [30 CD] before expiry | Contract expiration date | Service gap | Annually | L3: [60 CD], L2: [30 CD]
TB-017 | Consultancy | Insurance Renewal | Art. 10 | [30 CD] before expiry | Insurance expiration date | Coverage gap | Annually | L1: [45 CD], L1: [30 CD]

## Escalation Matrix
Level | Trigger Timing | Decision Maker | Max Response Time | Communication Channel | Escalation Criteria
L1 | D-2 (2 days before deadline) | Document Controller | 24 hours | Email + Portal notification | Document submission, routine compliance items
L2 | D+0 (Due date) | RE/PM | 12 hours | Email + Phone + Portal | IPC processing, monthly payments, routine approvals
L3 | D+3 (3 days past due) | Project Director | 8 hours | Email + Phone + Meeting | Claims assessment, EOT evaluation, scope changes
L4 | D+7 (7 days past due) | HAI Chief Governance Architect | 4 hours | Email + Phone + Urgent meeting | Disputes, termination decisions, major contract changes
L5 | 48 hours before deadline | Board/Legal Committee | Immediate action | Emergency call + Email + Board alert | DAB disputes, legal claims, force majeure, termination

## Response Templates
Template ID | Scenario | Required Documents | Signatories | Distribution List | Deadline Formula
RT-001 | IPC Certificate | Measurement records, Cost analysis, Contractor invoice, Site inspection photos | RE, PM, Finance Manager | Contractor, Finance, RE, Employer | Within [28 CD] of application
RT-002 | Taking Over Certificate | Practical completion checklist, Defects list (if any), Performance security acknowledgement | RE, PM, Contractor | Contractor, Project Director, HAI | Within [14 CD] of substantial completion
RT-003 | Variation Instruction | Scope description, Measurement details, Cost estimate, Program impact | RE, PM, Employer | Contractor, RE, PM | Before work commencement
RT-004 | Extension of Time Assessment | EOT application, Delay analysis, Program impact, Supporting evidence | RE, PM, Project Director | Contractor, RE, PM | Within [28 CD] of decision
RT-005 | Claims Assessment Report | Claim documents, Supporting evidence, Cost analysis, Contract review | RE, Finance Manager, Project Director | Contractor, Employer, Project Director | Within [14 CD] of submission
RT-006 | Consultant Payment Certificate | Timesheet, Deliverable checklist, QA report, Invoice review | PM, Project Coordinator, Finance Manager | Consultant, Finance, PM | Within [15 WD] of submission
RT-007 | Performance Report | KPI scorecard, Deliverables summary, Issues log, Recommendations | RE/PM, Project Director | Employer, Consultant, Stakeholders | Within [5 WD] of period-end
RT-008 | Stop Work Order | Written justification, Cause documentation, Reinstatement conditions, Signatures | Project Director, HAI Chief GA | Contractor/Consultant, All stakeholders | Immediate upon issuance
RT-009 | Defects Certificate | Inspection records, Remedy requirements, Deadline notice, Sign-off protocol | RE, PM, Contractor | Contractor, RE, Project Director | Within [7 CD] of identification
RT-010 | Force Majeure Notice | Event documentation, Impact analysis, Timeline, Supporting evidence | Project Director, Employer | Contractor, Employer, Insurer | Within [14 CD] of event
RT-011 | Penalty Deduction Notice | Non-compliance details, Contract reference, Calculation basis, Deduction amount | RE/PM, Finance Manager | Contractor/Consultant, Finance | In payment certificate month
RT-012 | Final Statement | Cost reconciliation, All claims summary, Retention accounting, Payment summary | RE, Finance Manager, Employer | Contractor, Finance, Employer | Within [56 CD] after DLP

## Quick Reference
Action | Contract Type | Deadline | Clause | Risk Level
DAB Referral Filing | Construction | [84 CD] | SC 20.4 | High
Notice of Dissatisfaction | Construction | [28 CD] | SC 20.4 | High
Final Statement Preparation | Construction | [56 CD] | SC 14.11 | High
Contractor Claims Detail | Construction | [42 CD] | SC 20.1 | High
IPC Certification | Construction | [28 CD] | SC 14.6 | High
Extension of Time Decision | Construction | [42 CD] | SC 8.4 | High
Termination by Employer | Construction | [14 CD] | SC 15.2 | High
Taking Over Certificate | Construction | [14 CD] | SC 10.1 | High
Retention Release | Construction | [14 CD] | SC 14.9 | Medium
Contractor Claims Notice | Construction | [28 CD] | SC 20.1 | High
Force Majeure Notice | Construction | [14 CD] | SC 19.2 | Medium
Defects Notification | Construction | DLP period | SC 11.1 | Medium
Performance Security Renewal | Construction | [30 CD] | SC 4.2 | Medium
Monthly Payment Approval | Consultancy | [15 WD] | Art. 11 | High
Mobilization Verification | Consultancy | [30 CD] | Art. 8 | High
Staff Replacement Approval | Consultancy | [14 CD] | Art. 9 | Medium
Contract Renewal Decision | Consultancy | [30 CD] | Art. 6 | High
Performance Evaluation | Consultancy | Monthly | Art. 14 | Medium
Insurance Verification | Consultancy | [30 CD] | Art. 10 | Medium
Confidentiality Breach Response | Consultancy | [2 WD] | Art. 18 | High