## Duration Matrix
Ref | Sub-Clause | Activity / Obligation | Duration / Deadline | Time Unit | Party Responsible | Consequence of Breach | Platform Timer Config | Linked PF
CAT |  | COMMUNICATIONS (Sub-Clause 1.3)
DM-001 | 1.3 | Contractor response to Engineer's Notices | 3 | Calendar Days | Contractor | Delay caused by Contractor; no EOT | Auto-deadline D+3 from receipt | PF-02
DM-002 | 1.3 | Urgent Notices — response as stated by Engineer | As stated | Per Notice | Contractor | Non-compliance; potential default | Manual deadline entry by Engineer | PF-02
DM-003 | 1.3 | Electronic transmission deemed received | 1 | Day after transmission | System | If non-delivery notification received, not deemed delivered | Auto-receipt D+1 | PF-02
DM-004 | 1.3 | Fax followed by original document | 2 | Working Days | Sender | Fax not deemed received by Employer/Engineer | Reminder at D+1 | PF-02
DM-005 | 1.1.2.32 | Notice of Dissatisfaction (NOD) | 48 | Hours | Contractor | NOD considered null and void — TIME-BARRED | Auto-deadline 48h from determination | PF-02, PF-20
CAT |  | DOCUMENT REVIEW (Sub-Clauses 3.1, 4.28)
DM-006 | 3.1 / 4.28.1 | Engineer review of Contractor Documents | 15 | Working Days | Engineer | If no Notice → Contractor gives immediate notice → +7 days | Auto-deadline 15WD from receipt | PF-01
DM-007 | 4.28.1 | Extended review period (after Contractor notice) | 7 | Working Days | Engineer | If no Notice within 22WD total → document DEEMED REJECTED | Extension timer +7WD | PF-01
DM-008 | 4.28.1 | Total maximum review period | 22 | Working Days | Engineer | Document deemed rejected — Contractor must resubmit | Hard ceiling 22WD | PF-01
DM-009 | 3.1 / 4.28.1 | Contractor resubmission after rejection/comments | 3 | Working Days | Contractor | Delay caused by Contractor | Auto-deadline 3WD from rejection | PF-01
DM-010 | 3.1 | Further documents requested by Engineer | 48 | Hours | Contractor | Document may be rejected; submission considered rejected | Auto-deadline 48h from request | PF-01
DM-011 | 1.9 | Engineer response to Contractor Notices (general) | 15 | Working Days | Engineer | May extend to 21WD at Engineer's discretion | Default 15WD, extendable | PF-02
DM-012 | 1.9 | Engineer extended response (discretionary) | 21 | Working Days | Engineer | Maximum extension at Engineer's sole discretion | Max ceiling 21WD | PF-02
CAT |  | INSTRUCTIONS & VARIATIONS (Sub-Clause 3.3, 13)
DM-013 | 3.3 | Contractor notice that instruction is a Variation | 3 | Working Days | Contractor | No entitlement to additional time, cost, profit — TIME-BARRED | Auto-deadline 3WD from instruction | PF-16
DM-014 | 3.3 | Detailed Variation notice content (after initial notice) | Immediate | With notice | Contractor | Must identify instruction, cost impact, time impact | Checklist validation | PF-16
CAT |  | DETERMINATIONS (Sub-Clause 3.5)
DM-015 | 3.5.1 | Engineer's Notice of Determination | 28 | Calendar Days | Engineer | If no Notice → claim deemed REJECTED | Auto-deadline 28D from receipt | PF-20
DM-016 | 3.5.2 | Error identification in determination | 7 | Calendar Days | Either Party | After 7 days, determination is final | Window 7D from Notice | PF-20
DM-017 | 3.5.2 | Engineer correction after error found | 7 | Calendar Days | Engineer | Corrected determination replaces original | Auto-deadline 7D from error | PF-20
CAT |  | MEETINGS (Sub-Clause 3.6)
DM-018 | 3.6 | Contractor notice for non-urgent meetings | 48 | Hours | Contractor | Meeting may not be recognized | Minimum 48h advance scheduling | PF-02
DM-019 | 3.6 | Engineer meeting notice | 0 | No notice required | Engineer | Engineer sets meetings at discretion | No constraint | PF-02
CAT |  | PROGRAMME (Sub-Clause 8.3)
DM-020 | 8.3 | Initial programme submission | 14 | Calendar Days | Contractor | After signing Agreement | Auto-deadline 14D from signing | PF-07
DM-021 | 8.3 | Engineer review of initial programme | 15 | Calendar Days | Engineer | If no Notice → deemed REJECTED, resubmit in 3 days | Auto-deadline 15D | PF-07
DM-022 | 8.3 | Engineer review of revised programme | 10 | Calendar Days | Engineer | If no Notice → deemed REJECTED, resubmit in 3 days | Auto-deadline 10D | PF-07
DM-023 | 8.3 | Contractor resubmission of rejected programme | 3 | Calendar Days | Contractor | Delay caused by Contractor | Auto-deadline 3D from rejection | PF-07
CAT |  | PHYSICAL CONDITIONS (Sub-Clause 4.12)
DM-024 | 4.12.1 | Contractor notice of unforeseeable conditions | 24 | Hours | Contractor | No entitlement if late — TIME-BARRED | Auto-deadline 24h from discovery | PF-20
DM-025 | 4.12.1 | 3rd party report after notice | 3 | Calendar Days | Contractor | Required for Engineer inspection | Auto-deadline 3D from notice | PF-20
DM-026 | 4.12.2 | Engineer inspection after notice + report | 15 | Calendar Days | Engineer | After receiving satisfactory notice + report | Auto-deadline 15D | PF-20
CAT |  | CLAIMS (Sub-Clause 20.2)
DM-027 | 20.2.1 | Notice of Claim (general events) | 28 | Calendar Days | Claiming Party | Claim null and void — TIME-BARRED | Auto-deadline 28D from awareness | PF-20
DM-028 | 20.2.1 | Notice of Claim (instruction-related) | 7 | Calendar Days | Claiming Party | Claim null and void — TIME-BARRED | Auto-deadline 7D from instruction | PF-20
DM-029 | 20.2.2 | Engineer initial response to claim | 28 | Calendar Days | Engineer | If rejection → claim not processed; if no-objection → fully detailed claim required | Auto-deadline 28D from Notice | PF-20
DM-030 | 20.2.4 | Fully detailed claim submission | 7 | Calendar Days | Claiming Party | Notice of Claim deemed lapsed — TIME-BARRED | Auto-deadline 7D from awareness | PF-20
DM-031 | 20.2.4 | Fully detailed claim after Engineer no-objection | 48 | Hours | Contractor | Delayed submissions null and void — TIME-BARRED | Auto-deadline 48h from no-objection | PF-20
DM-032 | 20.2.5 | Engineer request for additional particulars | 28 | Calendar Days | Engineer | Promptly after receiving fully detailed claim | Auto-deadline 28D | PF-20
DM-033 | 20.2.5 | Contractor response to additional particulars request | 7 | Calendar Days | Contractor | Engineer proceeds on available information | Auto-deadline 7D from request | PF-20
DM-034 | 20.2 | Payment + EOT claims must be simultaneous | Simultaneous | With Notice | Contractor | Subsequent separate claim null and void | System enforces joint submission | PF-20
CAT |  | FORCE MAJEURE (Sub-Clause 19)
DM-035 | 19.2 | Force Majeure notice | 7 | Calendar Days | Affected Party | Reduced from FIDIC standard 14 days | Auto-deadline 7D from event | PF-20
CAT |  | PAYMENT (Sub-Clause 14)
DM-036 | 14.6.1 | Engineer certification of IPC | 28 | Calendar Days | Engineer | After receipt of satisfactory application + statement | Auto-deadline 28D from receipt | PF-10
DM-037 | 14.7 | Employer payment after certified invoice | 10 | Calendar Days | Employer | From date of certified invoice | Auto-deadline 10D from certification | PF-10
DM-038 | 14.9 | Retention withheld | 10% | Of gross value | Employer | 5% released at TOC, 5% at end of DLP | Auto-calculation | PF-10
DM-039 | 14.5 | Material on Site payment | 60% | Of BOQ amount | Engineer | Upon approved MIR | Auto-calculation on MIR approval | PF-10
CAT |  | DISPUTES (Sub-Clause 20.3–20.4)
DM-040 | 20.4(a)-(b) | Engineer + Contractor Rep resolution | 15 | Calendar Days | Both | After written notice of Dispute | Auto-deadline 15D | PF-20
DM-041 | 20.4(b)-(c) | Executive management resolution | 15 | Calendar Days | Both | From date of referral | Auto-deadline 15D from referral | PF-20
DM-042 | 20.4(c) | Court filing after failed resolution | 5 | Calendar Days | Claiming Party | From Final Date for Amicable Resolution — rights WAIVED if late | Auto-deadline 5D — CRITICAL | PF-20
CAT |  | KEY CONTRACT PARAMETERS
DM-043 | Art. 2 | Time for Completion | [Completion Period] | Calendar Days | Contractor | From Commencement Date | Master project timer | All
DM-044 | 11 | Defects Notification Period (DLP) | 400 | Calendar Days | Both | From date of Taking Over Certificate | DLP timer from TOC | PF-14
DM-045 | 8.7 | Delay damages | [Delay Damages Rate] | QAR/day | Contractor | Cap: 10% of Contract Price = QR 3,980,000 | Auto-calculation from TOC deadline | PF-07
DM-046 | 8.7 | Engineer's fee for delay | 4,000 | QAR/day | Contractor | No cap stated | Added to delay damages | PF-07
DM-047 | 4.2 | Performance Bond submission | 10 | Calendar Days | Contractor | From Commencement Date | Auto-deadline 10D | PF-09
DM-048 | 1.1.2.22 | Key Personnel change notice | 42 | Calendar Days | Contractor | Prior to change | Minimum 42D advance notice | PF-04
DM-049 | 4.21 | Monthly progress report late penalty trigger | 15 | Calendar Days | Contractor | 10% withholding of payments until compliant | Flag at D+15 from due date | PF-07
DM-050 | 4.28.2/3 | As-built records and O&M manuals review | No limit | Engineer discretion | Engineer | No time limit — TOC blocked until approved | No auto-deadline; manual tracking | PF-14

## Time-Bar Register
Ref | Sub-Clause | Obligation | Deadline | Party | Consequence | Risk Level
TB-001 | 1.1.2.32 | Notice of Dissatisfaction | 48 hours from determination | Contractor | NOD null and void | CRITICAL
TB-002 | 3.3 | Variation notice on instruction | 3 working days from instruction | Contractor | No entitlement to time/cost/profit | HIGH
TB-003 | 4.12.1 | Unforeseeable conditions notice | 24 hours from discovery | Contractor | No entitlement | HIGH
TB-004 | 20.2.1 | Notice of Claim (general) | 28 calendar days from awareness | Claiming Party | Claim null and void; other party discharged | CRITICAL
TB-005 | 20.2.1 | Notice of Claim (instruction) | 7 calendar days from instruction | Claiming Party | Claim null and void | CRITICAL
TB-006 | 20.2.4 | Fully detailed claim | 7 calendar days from awareness | Claiming Party | Notice of Claim deemed lapsed | CRITICAL
TB-007 | 20.2.4 | Fully detailed claim after no-objection | 48 hours from no-objection | Contractor | Delayed submission null and void | CRITICAL
TB-008 | 20.4(c) | Court filing after failed resolution | 5 calendar days from Final Date | Claiming Party | All rights waived permanently | CRITICAL
TB-009 | 19.2 | Force Majeure notice | 7 calendar days from event | Affected Party | Reduced from FIDIC 14 days | HIGH
TB-010 | 20.2 | Payment + EOT claims simultaneous | With Notice of Claim | Contractor | Subsequent separate claim null and void | CRITICAL

## Escalation Matrix
Level | Trigger | Timing | Escalation To | Action Required | Sub-Clause Ref
L1 — Reminder | SLA approaching deadline | D-2 (2 days before due) | Assigned reviewer/responder | Auto-reminder email + dashboard alert | 1.3, 4.28.1
L2 — Warning | SLA due today | D+0 (on deadline) | Assigned person + line manager | Warning notification + task flagged amber | 1.3, 4.28.1
L3 — Escalation | SLA breached | D+3 (3 days overdue) | Department Manager / Discipline Lead | Escalation email + task flagged red + dashboard KPI impact | 1.3, 3.6
L4 — Executive | SLA critically overdue | D+7 (7 days overdue) | HAI PM / Programme Director | Executive alert + formal letter + potential withholding trigger | 4.21, 4.23
L5 — Contractual | Time-bar approaching | 48h before expiry | HAI Contracts Manager + Legal | Critical alert — contractual rights at risk | 20.2, 3.3

## Platform Timer Config
Timer ID | Timer Name | Default Duration | Unit | Business Days? | Extendable? | Max Extension | Auto-Escalation? | Escalation Chain | Linked Sub-Clause
TMR-001 | Document Review | 15 | Working Days | Yes | Yes | 22 WD total | Yes | L1→L2→L3→L4 | 3.1, 4.28.1
TMR-002 | Resubmission | 3 | Working Days | Yes | No | N/A | Yes | L1→L2→L3 | 3.1, 4.28.1
TMR-003 | Further Documents | 48 | Hours | No | No | N/A | Yes | L2→L3→L4 | 3.1
TMR-004 | Notice Response | 3 | Calendar Days | No | No | N/A | Yes | L1→L2→L3→L4 | 1.3
TMR-005 | NOD Window | 48 | Hours | No | No | N/A | Yes | L5 (Critical) | 1.1.2.32
TMR-006 | Variation Notice | 3 | Working Days | Yes | No | N/A | Yes | L5 (Critical) | 3.3
TMR-007 | Claim Notice (General) | 28 | Calendar Days | No | No | N/A | Yes | L5 (Critical) | 20.2.1
TMR-008 | Claim Notice (Instruction) | 7 | Calendar Days | No | No | N/A | Yes | L5 (Critical) | 20.2.1
TMR-009 | Fully Detailed Claim | 7 | Calendar Days | No | No | N/A | Yes | L5 (Critical) | 20.2.4
TMR-010 | Fully Detailed Claim (post no-obj) | 48 | Hours | No | No | N/A | Yes | L5 (Critical) | 20.2.4
TMR-011 | Engineer Determination | 28 | Calendar Days | No | Yes | As deemed necessary | Yes | L3→L4 | 3.5.1
TMR-012 | Engineer Response (General) | 15 | Working Days | Yes | Yes | 21 WD | Yes | L1→L2→L3 | 1.9
TMR-013 | IPC Certification | 28 | Calendar Days | No | No | N/A | Yes | L3→L4 | 14.6.1
TMR-014 | Payment after IPC | 10 | Calendar Days | No | No | N/A | Yes | L3→L4 | 14.7
TMR-015 | Programme Review (Initial) | 15 | Calendar Days | No | No | N/A | Yes | L2→L3 | 8.3
TMR-016 | Programme Review (Revised) | 10 | Calendar Days | No | No | N/A | Yes | L2→L3 | 8.3
TMR-017 | Programme Resubmission | 3 | Calendar Days | No | No | N/A | Yes | L2→L3 | 8.3
TMR-018 | Physical Conditions Notice | 24 | Hours | No | No | N/A | Yes | L5 (Critical) | 4.12.1
TMR-019 | 3rd Party Report | 3 | Calendar Days | No | No | N/A | Yes | L3→L4 | 4.12.1
TMR-020 | Force Majeure Notice | 7 | Calendar Days | No | No | N/A | Yes | L5 (Critical) | 19.2
TMR-021 | Dispute Resolution L1 | 15 | Calendar Days | No | No | N/A | No | Manual | 20.4(b)
TMR-022 | Dispute Resolution L2 | 15 | Calendar Days | No | Yes | As agreed | No | Manual | 20.4(c)
TMR-023 | Court Filing Window | 5 | Calendar Days | No | No | N/A | Yes | L5 (Critical) | 20.4(c)
TMR-024 | Key Personnel Change | 42 | Calendar Days | No | No | N/A | Yes | L3→L4 | 1.1.2.22
TMR-025 | Meeting Notice (Contractor) | 48 | Hours | No | No | N/A | No | N/A | 3.6

## Contract vs FIDIC Default
Item | FIDIC 1999 Red Book Default | This Contract (Particular Conditions) | Variance | Risk to Contractor
Force Majeure notice | 14 days | 7 days | Halved | HIGH — shorter window to notify
NOD period | Not explicitly time-barred | 48 hours — null and void if late | New time-bar | CRITICAL — extremely short window
Claim notice (general) | 28 days | 28 days | Same | Standard
Claim notice (instruction) | 28 days | 7 days | Reduced to 7 days | HIGH — much shorter
Fully detailed claim | 42 days (FIDIC 2017) | 7 days from awareness | Drastically reduced | CRITICAL — near-impossible for complex claims
Fully detailed claim after no-obj | Not specified | 48 hours | New requirement | CRITICAL — extremely short
Payment + EOT simultaneous | Separate submissions allowed | Must be simultaneous or void | New restriction | CRITICAL — subsequent claims void
Document review period | 21 days | 15 WD (extendable to 22 WD) | Similar but deemed rejected if exceeded | MEDIUM — auto-rejection risk
Resubmission period | Not specified | 3 working days | New strict deadline | HIGH — very short turnaround
Further documents on request | Reasonable time | 48 hours | Very short | HIGH — rejection risk
Float ownership | Shared / debatable | Employer's asset explicitly | Contractor loses float | HIGH — no float protection
Contractor design errors | May claim variation | No variation or claim entitlement | Eliminated | HIGH — full risk on Contractor
Dispute resolution | DAB then arbitration | Negotiation → Executive → Qatari courts | No DAB, no arbitration | HIGH — no independent adjudication
Court filing deadline | Not time-barred | 5 days from Final Date or rights waived | New time-bar | CRITICAL — very short filing window
Engineer determination silence | Fair determination required | Deemed rejection of claim | Unfavorable deemed provision | HIGH — Engineer silence = rejection
Delay damages | Per Contract Data | QR 39,800/day + Engineer fee QR 4,000/day | Combined QR 43,800/day | HIGH — substantial daily exposure
Progress report penalty | No financial penalty | 10% withholding after 15 days late | New penalty | MEDIUM — cash flow impact
Housekeeping penalty | No financial penalty | 3% withholding after 24h non-compliance | New penalty | MEDIUM — cash flow impact