## L1 - Reminder (D-2 Days)
Step | Action | Detail | Channel | Recipient | Template | Auto or Manual | Notes
1 | System sends automated reminder | Email + In-App notification | Email + In-App | Task Owner | Task [X] is due in 2 days | Automatic | RED priority alert
2 | Task owner acknowledges receipt | Click acknowledgement button in app | In-App | Task Owner | N/A | Manual | If no response within 4 hours, send follow-up reminder
3 | Task owner reviews pending item | Check current status in system, identify blockers | System Dashboard | Task Owner | N/A | Manual | Review all blockers and dependencies
4 | Flag blockers if they exist | Complete blocker form with reason code | In-App Form | Task Owner | Blocker Form (Waiting for info, Resource unavailable, Technical issue, External dependency) | Manual | Must include specific reason category
5 | Confirm completion capability | Click 'Will complete on time' or flag blocker | In-App | Task Owner | N/A | Manual | No further action if confirmed; proceed to deadline
6 | Monitor for deadline miss | System monitors task completion | System | System | N/A | Automatic | If missed - triggers L2 Alert

## L2 - Alert (D+0 Days)
Step | Action | Detail | Channel | Recipient | Template | Auto or Manual | Notes
1 | System sends immediate alert | Deadline passed - RED priority notification | Email + SMS + In-App | Task Owner + Direct Supervisor | DEADLINE MISSED: [Task X] | Automatic | Immediate escalation within minutes of deadline pass
2 | Supervisor reviews delay reason | Dashboard check and call task owner for explanation | Phone + System | Supervisor | N/A | Manual | Document reason in system
3 | Evaluate reason validity | Assess if reason is legitimate and documented | System Review | Supervisor | N/A | Manual | Categorize: Valid, Invalid, or Partially Valid
4 | Extend deadline or instruct completion | If valid: extend max 24h; if invalid: order immediate completion | In-App + Email | Task Owner | Deadline Extension Form or Immediate Action Notice | Manual | Document justification for any extension
5 | Issue formal reminder if inter-party action needed | If waiting on Contractor: formal SLA reminder letter | Email + Formal Letter | Contractor | SLA Reminder Letter (cite relevant contractual clause) | Manual | Reference contract timeframe and SC clause
6 | Log delay in audit trail | Record timestamp, responsible party, and reason | System | System | N/A | Automatic | Non-repudiable audit entry
7 | Monitor 24-hour resolution window | Track if task resolves within 24 hours | System | System | N/A | Automatic | If unresolved - triggers L3 Manager Escalation

## L3 - Manager Escalation (D+3 Days)
Step | Action | Detail | Channel | Recipient | Template | Auto or Manual | Notes
1 | System escalates to Department Manager | Task 3 days overdue - HIGH priority escalation | Email + SMS | Department Manager | ESCALATION NOTICE L3 | Automatic | Include full escalation chain history
2 | Manager reviews full history | Review original task, L1 reminder, L2 alert, delay reasons documented | System Dashboard | Department Manager | N/A | Manual | Print or export full audit trail
3 | Conduct root cause analysis | Interview task owner, review system logs, identify true blocker | Interview + System | Department Manager | Root Cause Analysis Form | Manual | Document findings in writing
4 | Assign recovery action with deadline | Issue new deadline (max 48 hours) with clear recovery steps | Email + In-App | Task Owner | Recovery Action Notice | Manual | Specify exactly what must be done
5 | Contact counterpart if cross-departmental blocker | If issue involves other department, Manager initiates contact | Phone + Email | Counterpart Manager | Escalation Letter or Formal Request | Manual | Document all communications
6 | Issue formal contractual letter if Contractor-caused | If Contractor caused delay, cite contractual breach and SLA | Formal Letter + Email | Contractor + Legal | Breach of Obligation Letter (cite SC clause) | Manual | Copy Legal and Contracts department
7 | Require daily status updates | Task owner must report progress daily until resolved | Email Report | Department Manager | Daily Status Update Template | Manual | Set automated daily reporting
8 | Monitor 48-hour resolution window | Track resolution completion | System | System | N/A | Automatic | If unresolved - triggers L4 Executive Escalation

## L4 - Executive Escalation (D+7 Days)
Step | Action | Detail | Channel | Recipient | Template | Auto or Manual | Notes
1 | System escalates to HAI Director | Task 7 days overdue - RED priority emergency alert | Email + SMS + Calendar Invite | HAI Director or Programme Director | CRITICAL ESCALATION L4 | Automatic | Calendar invite for emergency review meeting
2 | Executive reviews full escalation chain | Review all actions, reasons, L1-L3 escalations, all communications | Escalation Dossier | HAI Director | N/A | Manual | May require 30-60 min review time
3 | Convene emergency review meeting | Schedule and hold within 24 hours with all involved parties | Video Conference or In-Person | All Parties (Owner, Supervisor, Manager, Contractor, Legal) | Meeting Invite + Agenda | Manual | Document attendance and outcomes
4 | Determine executive actions needed | Decide: additional resources, contractual action, formal notice, risk update | Executive Decision Form | HAI Director | N/A | Manual | Four options: Resources, Contractual, Notice, Risk Register
5 | Issue formal contractual notice if needed | If Contractor non-compliance confirmed, issue formal notice | Formal Legal Notice | Contractor + Legal Counsel | Formal Notice (cite specific SC clause) | Manual | Legal counsel must review before issue
6 | Reassign responsibility if internal failure | If internal failure, reassign task owner and modify workflow | Email + System | New Task Owner or Manager | Reassignment Notice | Manual | Document reasons for reassignment
7 | Update risk register and escalation log | Document executive decision, actions, and risk implications | Risk Register + Log | Risk Manager or HAI Director | N/A | Manual | Include meeting minutes as attachment
8 | Monitor for time-bar impact | Check if resolution impacts any contractual time-bars | System Check | Contracts Manager | N/A | Manual | If time-bar at risk - IMMEDIATE L5 trigger

## L5 - Critical Legal (48h time-bar)
Step | Action | Detail | Channel | Recipient | Template | Auto or Manual | Notes
1 | CRITICAL ALERT: 48h before time-bar expiry | FLASH RED alert - 48 hours until contractual time-bar expires | ALL CHANNELS (Email + SMS + Phone + In-App FLASH) | HAI Contracts Manager + Legal Counsel + HAI Director | CRITICAL TIME-BAR ALERT | Automatic | Triggered automatically when time-bar deadline minus 48h reached
2 | Immediate notification to Contracts Manager and Legal | Drop everything - immediate escalation to both parties | Phone Call + Email + SMS | Contracts Manager + Legal | N/A | Automatic | Bypass normal notification hierarchy
3 | Assess protective action within 2 hours | Contracts Manager determines if protective action is legally required | Urgent Assessment | Contracts Manager | Assessment Form | Manual | 2-hour window is HARD DEADLINE
4 | Draft protective notice IMMEDIATELY if needed | Do NOT wait for full assessment - draft notice immediately | Email Draft + Legal Review | Legal Counsel | Draft Protective Notice Template | Manual | Speed is critical - draft first, assess second
5 | Issue protective notice to preserve rights | Send notice immediately - even if full assessment still pending | Formal Notice + Email | Contractor or Relevant Party | Protective Notice (NOD or Time-bar confirmation or Variation notice) | Manual | Must be issued before 48h window closes
6 | Cite relevant FIDIC SC clauses | Examples: SC 1.1.2.32 (NOD - 48h), SC 20.2.1 (Time-bar on claim), SC 3.3 (Variation notice) | Formal Notice | Contractor | Clause-specific notice template | Manual | Ensure correct SC clause cited for legal validity
7 | Parallel legal review and further advice | Legal reviews position and advises on additional actions needed | Urgent Legal Opinion | Legal Counsel + HAI Director | Legal Opinion Memo | Manual | May identify additional protective actions required
8 | Document all actions with exact timestamps | Record every action, time, person, and outcome in audit trail | Escalation Log + System | System | N/A | Automatic | Timestamped entries non-repudiable
9 | Update risk register and escalation log | Record resolution, actions taken, and lessons learned | Risk Register + Escalation Log | Risk Manager | N/A | Manual | Include all protective notices as attachments
10 | Post-event review: lessons learned | After resolution, conduct debrief on what could prevent recurrence | Review Meeting | All involved parties | Lessons Learned Report | Manual | Feed insights into process improvement

## Escalation Log
Escalation ID | Date Triggered | Original Task | PF Reference | Current Level (L1-L5) | Days Overdue | Task Owner | Escalated To | Actions Taken | Resolution | Resolution Date | Days to Resolve | Lessons Learned
ESC-2026-001 | 2026-02-15 | Submit Contract Amendment | [Project Reference]-VAR-001 | L3 | 3 | Ahmed Al-Kaabi | Dept Manager | Root cause: waiting on Contractor comments. Manager contacted Contractor directly. | Amendment received and approved | 2026-02-19 | 4 | Establish automatic 48h follow-up for Contractor submissions
ESC-2026-002 | 2026-02-18 | Obtain Safety Inspection Certificate | [Project Reference]-HSE-045 | L2 | 1 | Fatima Al-Mohannadi | Direct Supervisor | Blocker: Health authority office closed on national holiday. Supervisor rescheduled for next working day. | Certificate received | 2026-02-20 | 2 | Add national holiday calendar to project schedule
ESC-2026-003 | 2026-02-22 | Issue Variation Order | [Project Reference]-VAR-003 | L4 | 7 | Mohammed Al-Raisi | HAI Director | Contractor delay impacting critical path. Executive decision: escalate to Program Director, issue formal breach notice. | Variation issued after Contractor provided info | 2026-02-28 | 6 | Implement stricter Variation approval SLA (5 days max)
ESC-2026-004 | 2026-02-25 | File Notice of Delay Claim | [Project Reference]-CLM-015 | L5 | 0 | Khalid Al-Mansouri | Contracts Manager + Legal | Time-bar: 48h before claim deadline. Legal drafted protective notice immediately. Notice filed within 30h window. | Protective notice filed successfully | 2026-02-26 | 1 | Implement automated time-bar tracking 60 days prior
ESC-2026-005 | 2026-03-01 | Complete Handover Documentation | [Project Reference]-HO-089 | L1 | 0 | Layla Al-Qahtani | Task Owner (reminder only) | Preventive reminder sent 2 days before deadline. Task owner acknowledged and confirmed on-time delivery. | Documentation submitted on schedule | 2026-03-03 | 2 | Preventive approach prevented escalation

## Quick Reference
Level | Time Offset | Primary Channel | Recipients | Max Resolution Time | Auto-Escalate To Next | Key Principle
L1 | D-2 (2 days before) | Email + In-App | Task Owner | 2 days | Yes to L2 | Prevention: catch issues before deadline
L2 | D+0 (deadline day) | Email + SMS + In-App | Owner + Supervisor | 24 hours | Yes to L3 | Immediate response: escalate management
L3 | D+3 (3 days late) | Email + SMS | Department Manager | 48 hours | Yes to L4 | Root cause analysis and recovery planning
L4 | D+7 (7 days late) | All channels (Email + SMS + Calendar) | HAI Director or Programme Director | 24 hours | Yes if time-bar to L5 | Executive intervention and contractual action
L5 | 48h before time-bar | ALL CHANNELS FLASH (Red alert) | Contracts Manager + Legal + Director | 2h assessment then immediate action | N/A (final level) | Rights preservation: protective notice filing