## Summary
Gate | Gate Name | Total Items | Completed | Pending | Pass Rate % | Gate Status | Approved By | Date
Gate 0 | Strategic Definition | 30 | 0 | 30
Gate 1 | Preparation & Briefing | 20 | 0 | 20
Gate 2 | Concept Design | 15 | 0 | 15
Gate 3 | Spatial Coordination | 15 | 0 | 15
Gate 3.1 | Developed Technical Design | 15 | 0 | 15
Gate 4 | Technical Design | 15 | 0 | 15
Gate 5 | Manufacturing & Construction | 25 | 0 | 25
Gate 6 | Handover | 20 | 0 | 20
Gate 7 | In Use & DLP | 15 | 0 | 15
Gate 8 | Post-Completion | 10 | 0 | 10

## Gate 0 - Pre-Inception
Item # | Category | Checklist Item | Required Evidence | Responsible | Target Date | Completion Date | Status | Notes
1 | PLATFORM SETUP | Create project in SkyStruct | Project Code [Project Reference] confirmation | SkyStruct Admin |  |  | Open
2 | PLATFORM SETUP | Set base currency | QAR selected in system settings | SkyStruct Admin |  |  | Open
3 | PLATFORM SETUP | Set contract value | QAR [Contract Value] entered | SkyStruct Admin |  |  | Open
4 | PLATFORM SETUP | Set contract type | FIDIC 1999 Red Book Lump Sum | SkyStruct Admin |  |  | Open
5 | PLATFORM SETUP | Set completion date | [Completion Period] from commencement | SkyStruct Admin |  |  | Open
6 | PLATFORM SETUP | Set DLP period | 400 days configured | SkyStruct Admin |  |  | Open
7 | USER MANAGEMENT | Create user accounts | HAI_User_Roles_Permissions_Matrix.xlsx | IT Manager |  |  | Open
8 | USER MANAGEMENT | Assign roles per Matrix | Role assignments verified | IT Manager |  |  | Open
9 | USER MANAGEMENT | Configure approval thresholds | Thresholds per contract | IT Manager |  |  | Open
10 | USER MANAGEMENT | Test login for all users | All users can access system | IT Manager |  |  | Open
11 | USER MANAGEMENT | Verify role-based access | Access restrictions working | IT Manager |  |  | Open
12 | DOCUMENT NUMBERING | Configure Pattern 1 (Drawings) | [Project Reference]-[CNT]-[DISC]-[TYPE]-[SEQ]-[SUB]-R[n].[m] | Doc Manager |  |  | Open
13 | DOCUMENT NUMBERING | Configure Pattern 2 (Others) | [Project Reference]-[CNT]-[DISC]-[TYPE]-[SEQ]-R[n].[m] | Doc Manager |  |  | Open
14 | DOCUMENT NUMBERING | Configure status codes | A/B/C/D codes active | Doc Manager |  |  | Open
15 | DOCUMENT NUMBERING | Test document upload | Numbering validation working | Doc Manager |  |  | Open
16 | WORKFLOW CONFIGURATION | Configure 23 workflows | HAI_Workflow_Engine_Rules.xlsx | Workflow Admin |  |  | Open
17 | WORKFLOW CONFIGURATION | Set SLA timers - Technical Design | 5 days for Doc Review Technical Design | Workflow Admin |  |  | Open
18 | WORKFLOW CONFIGURATION | Set SLA timers - Shop Dwgs | 3 days for Shop Drawings | Workflow Admin |  |  | Open
19 | WORKFLOW CONFIGURATION | Set SLA timers - Correspondence | 14 days for Correspondence | Workflow Admin |  |  | Open
20 | WORKFLOW CONFIGURATION | Set SLA timers - IPC | 28 days for IPC Certificates | Workflow Admin |  |  | Open
21 | WORKFLOW CONFIGURATION | Set SLA timers - Claims | 28 CD / 7 CD per SC 20.2 | Workflow Admin |  |  | Open
22 | WORKFLOW CONFIGURATION | Configure escalation rules | 5-level escalation active | Workflow Admin |  |  | Open
23 | WORKFLOW CONFIGURATION | Test workflow execution | End-to-end testing complete | Workflow Admin |  |  | Open
24 | NOTIFICATION SETUP | Configure notification rules | HAI_Notification_Alert_Rules.xlsx | Comms Admin |  |  | Open
25 | NOTIFICATION SETUP | Configure email templates | All templates configured | Comms Admin |  |  | Open
26 | NOTIFICATION SETUP | Test email delivery | Email + in-app notifications working | Comms Admin |  |  | Open
27 | NOTIFICATION SETUP | Verify escalation triggers | Escalations functioning | Comms Admin |  |  | Open
28 | INTEGRATION | Configure ERP integration | HAI_Integration_Specification.xlsx | Integration Lead |  |  | Open
29 | INTEGRATION | Configure SMTP email server | Email server active | Integration Lead |  |  | Open
30 | INTEGRATION | Configure document storage | Storage system linked | Integration Lead |  |  | Open

## Gate 1 - Inception
Item # | Category | Checklist Item | Required Evidence | Responsible | Target Date | Completion Date | Status | Notes
1 | REQUIREMENTS | Employer Requirements confirmed | PF-01 uploaded to system | HAI |  |  | Open
2 | REQUIREMENTS | Appointment of key personnel | Personnel list documented | HAI |  |  | Open
3 | KICK-OFF | Kick-off meeting conducted | PF-16 minutes recorded | HAI |  |  | Open
4 | KICK-OFF | Initial risk register populated | PF-12 uploaded | HAI |  |  | Open
5 | KICK-OFF | Communication plan distributed | HAI_A068_Communication_Plan.xlsx issued | HAI |  |  | Open
6 | KICK-OFF | Document numbering system communicated | All parties briefed | HAI |  |  | Open
7 | SUBMISSIONS | Contractor submission schedule received | Schedule date confirmed | Contractor |  |  | Open
8 | CORRESPONDENCE | Initial correspondence log established | PF-02 active | HAI |  |  | Open
9 | PROGRAMME | Programme baseline received and loaded | PF-05 in system | Contractor |  |  | Open
10 | CONTRACTS | Contract execution confirmed | Signed contract filed | Legal |  |  | Open
11 | BONDS | Performance bond received | Bond copy in system | Contractor |  |  | Open
12 | INSURANCE | Insurance certificates received | Policies per contract | Contractor |  |  | Open
13 | MOBILISATION | Site mobilisation plan received | Plan reviewed and approved | Contractor |  |  | Open
14 | QUALITY | Quality assurance plan submitted | QAP per specification | Contractor |  |  | Open
15 | SAFETY | Safety & H&E plan submitted | SHEP per regulation | Contractor |  |  | Open
16 | ENVIRONMENTAL | Environmental management plan | EMP submitted and reviewed | Contractor |  |  | Open
17 | STAKEHOLDERS | Stakeholder register established | Key contacts identified | HAI |  |  | Open
18 | FINANCE | Financial procedures agreed | Payment terms confirmed | Finance |  |  | Open
19 | CLAIMS | Claims procedure briefing | All parties aware of SC 20 | HAI |  |  | Open
20 | VARIATIONS | Variation procedure briefing | All parties aware of SC 13 | HAI |  |  | Open
21 | CONSULTANT | PF-27 Consultant contract parameters configured | Consultant contract setup document | HAI

## Gate 2 - Brief
Item # | Category | Checklist Item | Required Evidence | Responsible | Target Date | Completion Date | Status | Notes
1 | BRIEF | Detailed project brief approved | Concept Design document signed | HAI |  |  | Open
2 | CONSULTANT | Consultant scope confirmed | Scope of work agreed | Consultant |  |  | Open
3 | PROCUREMENT | Procurement strategy for design consultants | PF-04 approved | Procurement |  |  | Open
4 | BUDGET | Spatial Coordination framework established | PF-11 baseline set | Finance |  |  | Open
5 | DESIGN | Technical Design brief issued to Contractor | Concept Design distributed | HAI |  |  | Open
6 | STANDARDS | Quality standards defined | Standards document issued | HAI |  |  | Open
7 | SUBMISSIONS | Submission requirements matrix issued | Matrix per contract requirements | HAI |  |  | Open
8 | AUTHORITIES | Authority submission requirements identified | List of authorities compiled | HAI |  |  | Open
9 | TIMELINES | Technical Design timelines established | Schedule agreed with Contractor | Contractor |  |  | Open
10 | COORDINATION | Coordination protocol established | Meeting schedule set | HAI |  |  | Open
11 | INSPECTIONS | Inspection & testing plan agreed | Plan per specification | HAI |  |  | Open
12 | INTERFACES | Interface management procedure | Procedure documented | HAI |  |  | Open
13 | APPROVALS | Approval authority identified | HAI sign-off process defined | HAI |  |  | Open
14 | RISKS | Technical Design-phase risks reviewed | PF-12 updated | Risk Manager |  |  | Open
15 | COMMUNICATION | Technical Design communication channels confirmed | Contact list updated | Comms |  |  | Open

## Gate 3 - Budget
Item # | Category | Checklist Item | Required Evidence | Responsible | Target Date | Completion Date | Status | Notes
1 | COST PLAN | Cost Plan L1-L2 approved | PF-11 approved and signed | HAI |  |  | Open
2 | BUDGET | Spatial Coordination loaded into system | Spatial Coordination in SkyStruct | Finance |  |  | Open
3 | IPC SCHEDULE | IPC schedule agreed with Contractor | PF-08 payment schedule | HAI/Contractor |  |  | Open
4 | RETENTION | Retention terms confirmed | 10%-50% rates documented | Finance |  |  | Open
5 | RETENTION | Retention release terms | 5% after completion set | Finance |  |  | Open
6 | ADVANCE | Advance payment terms set | Terms per contract | Finance |  |  | Open
7 | WORK PACKAGES | Spatial Coordination allocation per work package | WP breakdown in system | Finance |  |  | Open
8 | FINANCIAL | Financial reporting template agreed | Template established | Finance |  |  | Open
9 | CONTINGENCY | Contingency allocation approved | Contingency amount set | Finance |  |  | Open
10 | CASHFLOW | Cashflow projection established | Monthly projection set | Finance |  |  | Open
11 | INVOICING | Invoicing procedure briefed | All parties understand process | Finance |  |  | Open
12 | CLAIMS | Claims assessment budget | Spatial Coordination for claims evaluated | Finance |  |  | Open
13 | VARIATIONS | Variation budget headroom | Allowance for variations set | Finance |  |  | Open
14 | REPORTING | Monthly financial reporting schedule | Reporting dates set | Finance |  |  | Open
15 | AUDIT | Finance audit protocol | Audit procedure documented | Finance |  |  | Open

## Gate 3.1 - Design Development
Item # | Category | Checklist Item | Required Evidence | Responsible | Target Date | Completion Date | Status | Notes
1 | DESIGN | Concept design approved | Technical Design baseline locked | HAI |  |  | Open
2 | SUBMISSIONS | Technical Design development submissions tracked | PF-01 submissions active | HAI |  |  | Open
3 | DESIGN FREEZE | Technical Design freeze baseline established | PF-06 baseline set | HAI |  |  | Open
4 | VALUE ENG | Value engineering options recorded | Options evaluated and documented | Contractor |  |  | Open
5 | COORDINATION | Technical Design coordination meetings scheduled | PF-16 meeting schedule | HAI |  |  | Open
6 | COST PLAN | Cost Plan L3 updated | PF-11 updated to L3 | Finance |  |  | Open
7 | AUTHORITIES | Authority submissions identified | PF-07 submissions planned | HAI |  |  | Open
8 | REGULATORY | Regulatory compliance review | Compliance verified | HAI |  |  | Open
9 | MATERIALS | Material specifications defined | Specs approved by Contractor | HAI |  |  | Open
10 | PERFORMANCE | Performance specifications confirmed | Perf specs locked | HAI |  |  | Open
11 | INTERFACES | Interface coordination complete | All disciplines coordinated | Contractor |  |  | Open
12 | COMMENTS | Technical Design review comments resolved | All comments addressed | HAI |  |  | Open
13 | DRAWING | Drawing production schedule | Schedule for final drawings | Contractor |  |  | Open
14 | TENDER | Tender document structure | Tender doc outline approved | HAI |  |  | Open
15 | RISK | Technical Design risk assessment | PF-12 design risks reviewed | Risk Manager |  |  | Open

## Gate 4 - Design
Item # | Category | Checklist Item | Required Evidence | Responsible | Target Date | Completion Date | Status | Notes
1 | DESIGN | Technical design approved (Architecture) | Technical Design approved by HAI | HAI |  |  | Open
2 | DESIGN | Technical design approved (M&E) | M&E design approved | HAI |  |  | Open
3 | DESIGN | Technical design approved (Civil) | Civil design approved | HAI |  |  | Open
4 | DESIGN FREEZE | Technical Design freeze locked | PF-06 final freeze | HAI |  |  | Open
5 | TENDER | Tender documents prepared | Complete tender package ready | HAI |  |  | Open
6 | TENDER | Tender drawings complete | All drawings included | Contractor |  |  | Open
7 | TENDER | Tender specifications complete | All specs included | Contractor |  |  | Open
8 | COST PLAN | Cost Plan L4 finalized | PF-11 final cost plan | Finance |  |  | Open
9 | SPECIFICATIONS | Specification compliance verified | All specs meet requirements | HAI |  |  | Open
10 | AUTHORITIES | Authority approvals obtained | PF-07 approvals received | HAI |  |  | Open
11 | CONTRACTOR | Contractor tender evaluation plan | Evaluation criteria set | HAI |  |  | Open
12 | CONTRACTOR | Contractor tender evaluation complete | PF-04 evaluation done | HAI |  |  | Open
13 | TENDER ISSUE | Tender documents issued | Tender released to market | HAI |  |  | Open
14 | PROGRAMME | Technical Design completion programme | Schedule locked | Contractor |  |  | Open
15 | HANDOVER | Technical Design handover to construction | Technical Design package complete | HAI |  |  | Open

## Gate 5 - Implementation
Item # | Category | Checklist Item | Required Evidence | Responsible | Target Date | Completion Date | Status | Notes
1 | COMMENCEMENT | Commencement date recorded | Start date in system | HAI |  |  | Open
2 | MOBILISATION | All 23 PFs activated | All processes live | HAI |  |  | Open
3 | SITE TEAM | Site supervision team mobilized | PF-10 team on site | HAI |  |  | Open
4 | QUALITY | Quality inspection schedule established | Inspection plan active | HAI |  |  | Open
5 | PAYMENTS | IPC monthly submissions active | PF-08 submissions tracking | Contractor |  |  | Open
6 | VARIATIONS | Variation register active | PF-03 tracking SC 13.1 | HAI |  |  | Open
7 | CLAIMS | Claims monitoring active | SC 20.2.1 (28 CD notice) | HAI |  |  | Open
8 | CLAIMS | Claims detail process active | SC 20.2.4 (7 CD detail) | HAI |  |  | Open
9 | RISK | Risk register reviewed monthly | PF-12 monthly updates | Risk Manager |  |  | Open
10 | PERFORMANCE | Contractor performance scoring active | PF-13 scoring underway | HAI |  |  | Open
11 | MEETINGS | Weekly site meetings established | PF-16 weekly schedule | HAI |  |  | Open
12 | MEETINGS | Monthly progress meetings | Monthly schedule set | HAI |  |  | Open
13 | STAKEHOLDERS | External stakeholder portal active | PF-17 portal live | IT |  |  | Open
14 | DASHBOARD | Dashboard operational | PF-21 monitoring live | IT |  |  | Open
15 | PROGRAMME | Programme updates submitted per schedule | PF-05 updates tracking | Contractor |  |  | Open
16 | DOCUMENTATION | Daily site records collected | Site diary active | HAI |  |  | Open
17 | PHOTOS | Photo documentation schedule | Photo records collected | HAI |  |  | Open
18 | TESTING | Testing & commissioning plan active | T&C schedule established | Contractor |  |  | Open
19 | SAFETY | Site safety inspections weekly | Safety log maintained | HAI |  |  | Open
20 | ENVIRONMENTAL | Environmental monitoring active | Env checks per plan | HAI |  |  | Open
21 | DELIVERY | Material delivery schedule tracked | Delivery log active | Contractor |  |  | Open
22 | PROGRESS | Progress milestone tracking | Milestones vs schedule | HAI |  |  | Open
23 | FORECAST | Schedule forecast updates | Monthly forecasts issued | Contractor |  |  | Open
24 | BUDGET | Spatial Coordination tracking active | Cost tracking underway | Finance |  |  | Open
25 | CONTINGENCY | Contingency budget tracking | Contingency drawdown tracked | Finance |  |  | Open
26 | MOBILISATION | PF-24 Mobilization plan approved | Mobilization checklist signed off | HAI
27 | SNAGGING | PF-31 Snag tracking system configured | Snag management system live | HAI
28 | CONSULTANT | PF-27 Consultant KPIs baselined | KPI baseline document signed | HAI

## Gate 6 - Handover
Item # | Category | Checklist Item | Required Evidence | Responsible | Target Date | Completion Date | Status | Notes
1 | COMPLETION | Works substantially complete | SC 8 substantial completion | HAI |  |  | Open
2 | SNAGGING | Snagging list issued | Defects list documented | HAI |  |  | Open
3 | OUTSTANDING | Outstanding works list agreed | Remaining works schedule | HAI/Contractor |  |  | Open
4 | AS-BUILT | As-built drawings received | PF-01 as-built package | Contractor |  |  | Open
5 | OPERATIONS | O&M manuals received | Manuals per specification | Contractor |  |  | Open
6 | HANDOVER CERT | Handover certificates prepared | Handover docs ready | HAI |  |  | Open
7 | PERFORMANCE | Final contractor performance score | PF-13 final score | HAI |  |  | Open
8 | LESSONS | Lessons learned captured | PF-14 lessons documented | HAI |  |  | Open
9 | PARTIAL CERT | Partial completion certificates issued | Where applicable per contract | HAI |  |  | Open
10 | RETENTION 50% | Retention release 50% assessed | 50% release calculated | Finance |  |  | Open
11 | WARRANTY | Warranty information provided | Warranty docs received | Contractor |  |  | Open
12 | COMMISSIONING | Commissioning completed | T&C sign-off obtained | Contractor |  |  | Open
13 | TRAINING | Training & handover completed | User training done | Contractor |  |  | Open
14 | KEYS | Keys and access provided | Handover to Employer | Contractor |  |  | Open
15 | FINAL ACCOUNT | Final account submitted (Stage 1) | Initial final account | Contractor |  |  | Open
16 | DEFECTS PLAN | Defects rectification plan | Plan for DLP works | Contractor |  |  | Open
17 | INSURANCE | Insurance transferred | Insurance documents updated | HAI |  |  | Open
18 | UTILITIES | Utilities transferred | Services transferred to Employer | Contractor |  |  | Open
19 | DOCUMENTATION | Complete project documentation | All records handed over | HAI |  |  | Open
20 | CLOSURE PREP | Gate 7 closure preparation | DLP planning begins | HAI |  |  | Open
21 | COMMISSIONING | PF-25 T&C plan complete | T&C schedule with all items completed | HAI
22 | COMMISSIONING | PF-25 GSAS pre-assessment done | GSAS pre-assessment report | Consultant
23 | TOC | PF-28 TOC checklist prepared | Pre-TOC inspection checklist signed | HAI
24 | SNAGGING | PF-31 Pre-handover snag list complete | Snag list with contractor sign-off | HAI

## Gate 7 - DLP Closure
Item # | Category | Checklist Item | Required Evidence | Responsible | Target Date | Completion Date | Status | Notes
1 | DLP | Defects liability period monitored | PF-15 400-day monitoring | HAI |  |  | Open
2 | DEFECTS | All defects rectified and signed off | Defects register cleared | HAI |  |  | Open
3 | FINAL IPC | Final IPC prepared | PF-08 final payment cert | HAI |  |  | Open
4 | FINAL ACCOUNT | Final account agreed | PF-11 final account settled | HAI |  |  | Open
5 | VARIATIONS | Outstanding variation claims resolved | PF-03 final claims closed | HAI |  |  | Open
6 | RETENTION | Release of retention balance | Final 50% retention released | Finance |  |  | Open
7 | BONDS | Performance bond release assessed | Bond release approved | HAI |  |  | Open
8 | BONDS | Performance bond released | Bond returned to Contractor | Finance |  |  | Open
9 | FINAL CERTS | Final certificates issued | Practical completion cert issued | HAI |  |  | Open
10 | COMPLETION CERT | Completion certificate issued | SC 8.8 certificate | HAI |  |  | Open
11 | INSURANCE | Insurance liability transferred | Employer assumes risk | HAI |  |  | Open
12 | WARRANTY | Warranty period confirmed | Warranty start date locked | HAI |  |  | Open
13 | CLAIMS | All claims settled | No outstanding claims | HAI |  |  | Open
14 | DISPUTES | All disputes resolved | No outstanding disputes | HAI |  |  | Open
15 | ARCHIVING | Project documents archived | All records archived | HAI |  |  | Open
16 | FINAL ACCOUNT | PF-29 Draft Final Statement reviewed | Final Statement document approved | HAI
17 | DLP CLOSURE | PF-30 DLP defects inspection complete | DLP inspection report | HAI
18 | SNAGGING | PF-31 All snags resolved or accepted | Snag closure report signed | HAI/Contractor

## Gate 8 - Post-Completion
Item # | Category | Checklist Item | Required Evidence | Responsible | Target Date | Completion Date | Status | Notes
1 | WARRANTY PERIOD | Warranty period monitored | Ongoing warranty management | HAI |  |  | Open
2 | DEFECTS | Warranty defects tracked and rectified | PF-15 warranty tracking | HAI |  |  | Open
3 | LESSONS | Lessons learned report finalized | PF-14 final report | HAI |  |  | Open
4 | ARCHIVING | All documents archived with audit trail | Complete archive with logs | IT |  |  | Open
5 | FINAL REPORT | Final project report generated | PF-18 final report | HAI |  |  | Open
6 | AUDIT | System audit completed | PF-23 audit finished | IT |  |  | Open
7 | CLOSURE | Project closure report signed off | Closure documentation complete | HAI |  |  | Open
8 | DATABASE | Database archived for reference | Archive backup created | IT |  |  | Open
9 | STAKEHOLDER | Stakeholder feedback collected | Post-project feedback | HAI |  |  | Open
10 | COMPLIANCE | Compliance audit completed | All requirements verified | Compliance |  |  | Open
11 | POST-OCCUPANCY | PF-26 Post-occupancy plan active | Post-occupancy service schedule | HAI
12 | FINAL ACCOUNT | PF-29 Final Payment Certificate issued | Final Payment Certificate signed | Finance
13 | PERFORMANCE | PF-30 Performance Certificate issued | Performance Certificate by HAI | HAI