## Convention
HAI PROJECT [Project Reference] — DOCUMENT NUMBERING CONVENTION
PATTERN 1 — DRAWINGS (DWG, SHD, ABD)
[Project Reference]-[CNT]-[DISC]-[TYPE]-[SEQ]-[SUB]-R[n].[m]
Component | Code | Description | Length | Example | Mandatory | Notes
Project Code | [Project Reference] | Artan Holding project identifier | 4 chars | [Project Reference] | Yes | Fixed per project
Contract No. | [CNT] | Contract number | 3 digits | 001 | Yes | See Contracts sheet
Discipline | [DISC] | Discipline code | 2-3 chars | AR | Yes | See Disciplines sheet
Document Type | [TYPE] | Drawing type code | 3 chars | DWG | Yes | DWG, SHD, or ABD only
Sequential No. | [SEQ] | Drawing set number | 4 digits | 0001 | Yes | Sequential within DISC+TYPE
Sub-Sequence | [SUB] | Sheet number within set | 2 digits | 01 | Yes | Sheet/page within drawing set
Revision | R[n].[m] | QC rev . QA sub-rev | Variable | R0.0 | Yes | See Revision Rules sheet
PATTERN 2 — ALL OTHER DOCUMENTS
[Project Reference]-[CNT]-[DISC]-[TYPE]-[SEQ]-R[n].[m]
Component | Code | Description | Length | Example | Mandatory | Notes
Project Code | [Project Reference] | Artan Holding project identifier | 4 chars | [Project Reference] | Yes | Fixed per project
Contract No. | [CNT] | Contract number | 3 digits | 001 | Yes | See Contracts sheet
Discipline | [DISC] | Discipline code | 2-3 chars | AR | Yes | See Disciplines sheet
Document Type | [TYPE] | Document type code | 3 chars | CAL | Yes | See Doc Types sheet
Sequential No. | [SEQ] | Sequential number | 4 digits | 0001 | Yes | Sequential within DISC+TYPE
Revision | R[n].[m] | QC rev . QA sub-rev | Variable | R0.0 | Yes | See Revision Rules sheet
DOCUMENT TYPES BY PATTERN
Pattern | Types Included | Notes
Pattern 1 (with SUB) | DWG, SHD, ABD | Drawings only — SUB field is sheet number within a drawing set
Pattern 2 (no SUB) | CAL, RPT, RFI, TQ, MAT, MSS, SAM, SPC, SCH, MOD, MRP, FFC, STR, COR, NOT, RSP, DET, CVI, SI, EoT, CLM, VO, VON, IPC, BOQ, BUD, VLN, NCR, WIR, MIR, ITP, ITR, SNL, QAP, MTL, MOC, MOM, AGN, TRN, HSP, RAR, INC, PTW, OAM, HND, WAR, CER, TRG, NOC, PER, APS, PRG, DLY, INS, BND, POA | All non-drawing documents
EXAMPLES
Full Number | Pattern | Meaning
[Project Reference]-001-AR-DWG-0001-01-R0.0 | 1 | Contract 001, Architecture Drawing set #1, sheet 01, first issue
[Project Reference]-001-AR-DWG-0001-02-R0.0 | 1 | Same drawing set, sheet 02
[Project Reference]-001-ST-SHD-0003-01-R2.1 | 1 | Contract 001, Structural Shop Drawing set #3, sheet 01, QC rev 2, QA sub-rev 1
[Project Reference]-001-ME-ABD-0012-01-R0.0 | 1 | Contract 001, Mechanical As-Built Drawing set #12, sheet 01
[Project Reference]-001-ST-CAL-0003-R2.1 | 2 | Contract 001, Structural Calculation #3, QC rev 2, QA sub 1
[Project Reference]-001-FE-RPT-0001-R0.0 | 2 | Contract 001, Fire Engineering Report #1, first issue
[Project Reference]-001-PM-COR-0045-R0.0 | 2 | Contract 001, PM Correspondence #45
[Project Reference]-002-EL-NCR-0002-R0.0 | 2 | Contract 002, Electrical NCR #2
[Project Reference]-001-CT-VO-0008-R1.0 | 2 | Contract 001, Variation Order #8, QC rev 1
[Project Reference]-001-QA-WIR-0019-R0.0 | 2 | Contract 001, Work Inspection Request #19
[Project Reference]-001-QA-MIR-0007-R0.0 | 2 | Contract 001, Material Inspection Request #7
[Project Reference]-001-PM-MRP-0006-R0.0 | 2 | Contract 001, Monthly Report #6
[Project Reference]-001-AC-RPT-0003-R0.2 | 2 | Contract 001, Acoustics Report #3, QA failed twice in current cycle
[Project Reference]-001-QS-IPC-0004-R0.0 | 2 | Contract 001, Interim Payment Certificate #4
[Project Reference]-001-CO-DWG-0001-01-R0.0 | 1 | Contract 001, Coordination Drawing set #1, sheet 01

## Disciplines
DISCIPLINE CODES — ALIGNED TO QCS 2014 SECTIONS
Code | Discipline | QCS 2014 Section | Category | Notes
GN | General | S01 — General | General | General project-wide provisions, terms and definitions
QA | Quality Assurance & Control | S02 — QA/QC | Management | Submittals, inspections, NCRs, quality plans, audits
GE | Geotechnical | S03 — Ground Investigation | Specialist | Boreholes, soil sampling, in-situ testing, lab testing
FD | Foundations | S04 — Foundations & Retaining Structures | Design | Piling, shallow/deep foundations, retaining structures
CN | Concrete | S05 — Concrete | Design | Concrete works, reinforcement, formwork, pre-cast, pre-stressed
RD | Roadworks | S06 — Roadworks | Design | Asphalt, pavements, kerbs, road drainage, traffic signs, lighting
SU | Sustainability / Green Building | S07 — Green Constructions | Specialist | GSAS, green building, energy efficiency, sustainable design
DR | Drainage (Infrastructure) | S08 — Drainage Works | Design | Sewerage networks, manholes, pumping stations
ME | Mechanical & Electrical Equipment | S09 — Mechanical & Electrical Equipment | Design | Pumps, generators, actuators, lifting equipment, odour control
IC | Instrumentation & Control | S10 — Instrumentation Control & Automation | Specialist | SCADA, BMS, control panels, instrumentation
HS | Health & Safety | S11 — Health and Safety | Management | HSE plans, risk assessments, working at heights, SAMAS
EW | Earthworks | S12 — Earthworks Related to Buildings | Design | Excavation, filling, compaction, dewatering for buildings
MS | Masonry | S13 — Masonry | Design | Blockwork, brickwork, stone cladding, mortar
RF | Roofing | S14 — Roofing | Design | Membrane, metal/plastic roofing, roof insulation
TI | Thermal Insulation | S15 — Thermal Insulation of Buildings | Design | Building envelope insulation, thermal performance
SS | Structural Steelwork | S16 — Structural Steelworks | Design | Steel structures, connections, fabrication, erection
MW | Metalwork | S17 — Metalwork | Design | Metal doors/windows, architectural metalwork, cladding support
CJ | Carpentry, Joinery & Ironmongery | S18 — Carpentry, Joinery & Ironmongery | Design | Timber, joinery, ironmongery, wood treatment
PL | Plumbing | S19 — Plumbing Work | Design | Water supply, distribution, hot/cold water storage, gas
BD | Building Drainage | S20 — Drainage Works for Buildings | Design | Internal drainage, soil/waste/rainwater within buildings
EL | Electrical | S21 — Electrical Works | Design | Power distribution, cabling, lighting, earthing, generators, UPS
AC | HVAC / Air Conditioning | S22 — AC, Refrigeration & Ventilation | Design | HVAC systems, chillers, AHUs, ductwork, refrigeration, ventilation
FF | Fire Fighting & Fire Alarm | S23 — Fire Fighting & Fire Alarm Systems | Design | Sprinklers, suppression, detection, alarm systems
FN | Finishes | S24 — Finishes to Buildings | Design | Plastering, tiling, flooring, ceilings, wall finishes
GL | Glass & Glazing | S25 — Glass and Glazing | Design | Glass types, curtain walling, structural glazing
PT | Painting & Decorating | S26 — Painting and Decorating | Design | Surface preparation, paint systems, coatings
XW | External Works | S27 — External Works | Design | Paving, fencing, site furniture, fountains, shade structures
LS | Landscaping | S28 — Landscaping | Design | Soft/hard landscaping, irrigation, planting
RW | Railways | S29 — Railways | Specialist | Rail infrastructure (where applicable)
AR | Architecture | Cross-section (S13,S17,S18,S24,S25,S26) | Design | Overall architectural design — references multiple QCS sections
ST | Structural | Cross-section (S04,S05,S12,S16) | Design | Structural engineering — foundations, concrete, steel, earthworks
ID | Interior Design | Cross-section (S18,S24,S25,S26) | Design | Fit-out, finishes, FF&E — references joinery, finishes, glass, paint
LT | Lighting | Within S21 — Electrical Works | Design | Lighting design — subset of electrical works
FE | Fire Engineering | Cross-section (S23, CDD) | Specialist | Fire strategy, life safety — references QCS S23 + Civil Defence
ELV | Extra Low Voltage / ICT | Within S21 — Electrical Works | Specialist | Data, telecom, CCTV, structured cabling — subset of S21
VT | Vertical Transportation | Within S09 — Mech & Elec Equipment | Specialist | Lifts, escalators — subset of mechanical equipment
WP | Waterproofing | Cross-section (S14,S15) | Specialist | Below-grade, wet area waterproofing
ACS | Acoustics | Specialist (no dedicated QCS section) | Specialist | Acoustic design and reports — no standalone QCS section
EN | Environmental | Specialist (no dedicated QCS section) | Specialist | EIA, environmental compliance — regulatory
KI | Kitchen | Specialist (no dedicated QCS section) | Specialist | Commercial kitchen design — specialist
AV | Audio Visual | Within S21 — Electrical Works | Specialist | AV systems — subset of electrical works
SE | Security | Within S21 — Electrical Works | Specialist | Access control, surveillance — subset of electrical works
SV | Survey | Related to S03 | Specialist | Topographic, measured building survey
TR | Traffic | Within S06 — Roadworks | Specialist | Traffic impact, parking studies — subset of roadworks
WI | Wind Engineering | Specialist (no dedicated QCS section) | Specialist | Wind analysis, cladding pressure — specialist
PM | Project Management | N/A — Management | Management | PM office, coordination, reporting, correspondence
QS | Quantity Surveying | N/A — Commercial | Commercial | Cost management, BOQ, valuations, payment certification
CT | Contracts | N/A — Commercial | Commercial | Contractual documents, FIDIC notices, claims, variations
FI | Finance | N/A — Commercial | Commercial | Budget, payment, financial reporting
PG | Planning / Programming | N/A — Management | Management | Master programme, schedules, delay analysis
IF | Information Management | N/A — Management | Management | BIM, document control, information protocols
CO | Coordination | Cross-section (multiple) | Multi | Multi-discipline coordination drawings
MU | Multi-discipline | Cross-section (multiple) | Multi | Documents spanning multiple disciplines

## Doc Types
DOCUMENT TYPE CODES
Code | Document Type | Category | Pattern | Typical Originator | Definition
DWG | Drawing | Design | 1 | Consultant | Design, detail, layout, GA, section, elevation drawings produced during the design process
SHD | Shop Drawing | Design | 1 | Contractor | Fabrication and installation drawings produced by the contractor or sub-contractor for manufacturing/construction
ABD | As-Built Drawing | Design | 1 | Contractor | Record drawings reflecting the actual constructed condition, updated post-construction
SPC | Specification | Design | 2 | Consultant | Technical specifications defining material, workmanship, and performance requirements
CAL | Calculation | Design | 2 | Consultant | Structural, MEP, or specialist engineering calculations supporting the design
SCH | Schedule (Design) | Design | 2 | Consultant | Design schedules such as door schedule, finish schedule, equipment schedule
MOD | 3D Model / BIM | Design | 2 | Consultant | BIM models, clash detection reports, federated model deliverables
RPT | Report (General) | Report | 2 | Various | Technical, specialist, or advisory reports not covered by other specific types
MRP | Monthly Report | Report | 2 | PM | Monthly project progress report covering programme, cost, quality, HSE, and risk
FFC | Forecast Final Cost | Report | 2 | QS | Monthly updated forecast of the project's final cost at completion
STR | Stage Report | Report | 2 | PM | RIBA stage completion report summarising deliverables and sign-off status
COR | Correspondence (General) | Contractual | 2 | Various | General letters, written communications between project parties
NOT | Notice (FIDIC) | Contractual | 2 | Various | Formal contractual notice issued under FIDIC contract conditions
RSP | Response (FIDIC) | Contractual | 2 | Various | Formal response to a contractual notice, within stipulated timeframes
DET | Determination | Contractual | 2 | HAI/Employer | Engineer's or Employer's determination under FIDIC clause provisions
CVI | Confirmation of Verbal Instruction | Contractual | 2 | HAI | Written confirmation of a verbal instruction issued on site
SI | Site Instruction | Contractual | 2 | HAI | Formal written instruction issued to the contractor on site
EoT | Extension of Time | Contractual | 2 | Contractor | Claim or application for extension of the contract completion date
CLM | Claim | Contractual | 2 | Contractor | Contractual claim submission for additional time or cost under FIDIC
VO | Variation Order | Commercial | 2 | Various | Approved instruction to vary the works, with cost and time implications
VON | Variation Order Notice | Commercial | 2 | Contractor | Notice of intent to claim a variation, prior to formal VO approval
IPC | Interim Payment Certificate | Commercial | 2 | Contractor/QS | Monthly payment application and certified valuation of works done
BOQ | Bill of Quantities | Commercial | 2 | QS | Priced bill of quantities forming part of the contract
BUD | Budget Report | Commercial | 2 | QS/Finance | Budget status report including amendments, contingency, and drawdown
VLN | Valuation | Commercial | 2 | QS | Interim valuation of works for payment certification purposes
NCR | Non-Conformance Report | Quality | 2 | HAI QA | Report documenting a quality deficiency or non-compliance with specifications
WIR | Work Inspection Request | Quality | 2 | Contractor | Request submitted by contractor for HAI/consultant to inspect completed work
MIR | Material Inspection Request | Quality | 2 | Contractor | Request submitted by contractor for HAI/consultant to inspect materials on site
ITP | Inspection & Test Plan | Quality | 2 | Contractor | Document defining inspection and testing activities, hold/witness points
ITR | Inspection & Test Record | Quality | 2 | Contractor | Completed record of an inspection or test as per the ITP
SNL | Snag List | Quality | 2 | HAI | List of deficiencies identified during inspection prior to handover
QAP | Quality Assurance Plan | Quality | 2 | Contractor | Project-level QA/QC plan defining quality management procedures
MTL | Material Submittal | Submittal | 2 | Contractor | Submittal of proposed materials, products, or equipment for approval
MSS | Method Statement | Submittal | 2 | Contractor | Detailed description of the methodology for executing specific works
SAM | Sample Submittal | Submittal | 2 | Contractor | Physical or digital sample submitted for approval prior to procurement
MOC | Mockup | Submittal | 2 | Contractor | Full-scale or representative mockup submitted for design/quality approval
MOM | Minutes of Meeting | Meeting | 2 | PM | Formal record of discussions, decisions, and actions from a project meeting
AGN | Agenda | Meeting | 2 | PM | Pre-meeting document listing topics, attendees, and time allocations
RFI | Request for Information | Communication | 2 | Various | Formal request for clarification on design, specification, or contractual matters
TQ | Technical Query | Communication | 2 | Various | Technical question raised during design or construction requiring resolution
TRN | Transmittal | Communication | 2 | Various | Cover document accompanying the formal transmission of documents between parties
HSP | Health & Safety Plan | HSE | 2 | Contractor | Project health and safety management plan per local regulations
RAR | Risk Assessment | HSE | 2 | Various | Activity-specific risk assessment identifying hazards and mitigation measures
INC | Incident Report | HSE | 2 | Contractor/HAI | Report documenting an HSE incident, near-miss, or dangerous occurrence on site
PTW | Permit to Work | HSE | 2 | Contractor | Formal permit authorising specific high-risk work activities
OAM | Operation & Maintenance Manual | Handover | 2 | Contractor | Documentation for building systems operation and maintenance post-handover
HND | Handover Document | Handover | 2 | Contractor | Document forming part of the project handover and close-out package
WAR | Warranty Certificate | Handover | 2 | Contractor | Certificate confirming warranty terms for materials, equipment, or works
CER | Completion Certificate | Handover | 2 | HAI | Taking-over certificate or practical/substantial completion certificate
TRG | Training Record | Handover | 2 | Contractor | Record of operator/end-user training on building systems and equipment
NOC | No Objection Certificate | Authority | 2 | Authority | Certificate of no objection from a regulatory or statutory authority
PER | Permit | Authority | 2 | Authority | Building permit, construction permit, or other regulatory approval
APS | Authority Submission | Authority | 2 | Consultant | Design or compliance submission to QCDD, Civil Defence, Kahramaa, Ashghal, etc.
PRG | Programme / Schedule | Programme | 2 | Contractor/PM | Master programme, baseline schedule, look-ahead schedule, recovery programme
DLY | Delay Analysis | Programme | 2 | PM/Contractor | Forensic or prospective delay analysis of a time-related event
INS | Insurance Certificate | Legal | 2 | Contractor | Certificate of insurance coverage as required by the contract
BND | Bond / Guarantee | Legal | 2 | Contractor | Performance bond, advance payment guarantee, or retention guarantee
POA | Power of Attorney | Legal | 2 | Various | Legal instrument delegating authority to act on behalf of a party

## Revision Rules
REVISION CONVENTION — R[n].[m]
Component | Symbol | Trigger | Action
Main Revision | n | QC rejection (Status C or D from Consultant or HAI Engineer) | n increments by 1, m resets to 0
Sub-Revision | m | QA rejection (Consultant DC fails QA check) | m increments by 1, n unchanged
Initial | R0.0 | First submission | All documents start at R0.0
Approved | R[n].[m] | HAI endorses Status A or B | Revision freezes at approval point
STATUS CODE DEFINITIONS
Code | Status | Meaning | Revision Impact
A | Approved | Proceed to execution. No comments issued. | Document closed at current R[n].[m]
B | Approved with Comments | Execute, but comply with all comments — no compromise. No further comments will be issued. | Document closed at current R[n].[m]. Comments tracked as compliance obligations.
C | Revise & Resubmit | Do NOT execute. Revise per comments and resubmit. Further comments may be issued. | Main revision increments: R[n].[m] -> R[(n+1)].0
D | Rejected | Complete redo. Do NOT execute. | Main revision increments: R[n].[m] -> R[(n+1)].0
LIFECYCLE EXAMPLE — How R3.2 happens
Revision | Event | Who | Result
R0.0 | First submission | Originator | Enters system
R0.0 | QA Pass | Consultant DC | Forwards to Consultant Engineer
R0.0 | QC: Status C (revise) | Consultant Engineer | Main revision increments
R1.0 | Resubmission | Originator | n=1, m reset to 0
R1.0 | QA Pass | Consultant DC | Forwards to Consultant Engineer
R1.0 | QC: Status C (revise) | Consultant Engineer | Main revision increments
R2.0 | Resubmission | Originator | n=2, m reset to 0
R2.0 | QA Pass | Consultant DC | Forwards to Consultant Engineer
R2.0 | QC: Status C (revise) | Consultant Engineer | Main revision increments
R3.0 | Resubmission | Originator | n=3, m reset to 0
R3.0 | QA Fail | Consultant DC | Sub-revision increments
R3.1 | Resubmission (QA fix) | Originator | m increments, n stays
R3.1 | QA Fail again | Consultant DC | Sub-revision increments
R3.2 | Resubmission (QA fix) | Originator | We are now at R3.2
R3.2 | QA Pass | Consultant DC | Forwards to Consultant Engineer
R3.2 | QC: Status A | Consultant Engineer | Forwards to HAI
R3.2 | HAI Endorses A | HAI Engineer | APPROVED at R3.2

## Acronyms & Definitions
ACRONYMS, ABBREVIATIONS & DEFINITIONS
Reference guide for all codes and terminology used in the HAI [Project Reference] Document Numbering System
1. NUMBERING SYSTEM COMPONENTS
Abbreviation | Stands For | Type | Explanation
[Project Reference] | Project Code | Fixed | Artan Holding project identifier assigned by HAI
CNT | Contract Number | Variable | 3-digit number identifying the specific contract package (e.g., 001 = Main Contractor, 002 = MEP Subcontractor)
DISC | Discipline | Variable | 2-3 character code identifying the engineering or management discipline (see Disciplines sheet)
TYPE | Document Type | Variable | 3-character code identifying the kind of document (see Doc Types sheet)
SEQ | Sequential Number | Variable | 4-digit auto-incrementing number within each DISC+TYPE combination
SUB | Sub-Sequence | Variable | 2-digit sheet/page number within a drawing set (Pattern 1 only)
R[n].[m] | Revision | Variable | Two-tier revision: n = QC revision (main), m = QA sub-revision
n | QC Revision Number | Counter | Increments when Consultant or HAI Engineer issues Status C or D
m | QA Sub-Revision Number | Counter | Increments when Consultant DC rejects at QA stage; resets to 0 when n increments
2. REVIEW STATUS CODES
Code | Status | Action Required | Detailed Definition
A | Approved | Proceed to execution | Document is approved without comments. The originator may proceed with fabrication, procurement, or construction based on this document.
B | Approved with Comments | Execute + comply with comments | Document is approved for execution. However, all comments must be incorporated without compromise. No new comments will be issued. Compliance is tracked.
C | Revise & Resubmit | Do NOT execute | Document is not approved. The originator must revise the document in accordance with the comments provided and resubmit. Further comments may be issued on resubmission.
D | Rejected | Do NOT execute | Document is rejected outright. The originator must redo the document and resubmit. This typically indicates fundamental deficiencies.
3. WORKFLOW ROLES & ABBREVIATIONS
Abbreviation | Full Title | Stage | Role in Document Review
DC | Document Controller | QA / Admin | Reviews document completeness, formatting, and compliance with submission requirements before forwarding
QA | Quality Assurance | Check | Consultant DC performs QA check — verifies document meets submission standards and format requirements
QC | Quality Control | Review | Consultant Designated Engineer performs QC review — technical review of content, issues Status A/B/C/D
HAI | House of Architecture & Interiors | Endorsement | Employer's Representative. HAI Designated Engineer endorses or revises the Consultant's status decision
ER | Employer's Representative | Authority | HAI acts as ER for Artan Holding. Has override authority at any review stage
PM | Project Manager / Management | Management | Project management office responsible for coordination, reporting, and correspondence
QS | Quantity Surveyor / Surveying | Commercial | Cost management, valuations, payment certification, variation assessment
FIDIC | Federation Internationale des Ingenieurs-Conseils | Contract | International standard form of construction contract used as the contractual framework
RIBA | Royal Institute of British Architects | Framework | RIBA Plan of Work defines design stages (0-7) used as project milestones
GSAS | Global Sustainability Assessment System | Certification | Qatar's green building rating system for sustainability compliance
QCDD | Qatar Civil Defence Department | Authority | Regulatory authority for fire and life safety approvals
BIM | Building Information Modelling | Technology | Digital representation of physical and functional characteristics of a facility
FF&E | Furniture, Fixtures & Equipment | Scope | Movable items not permanently attached to the building structure
MEP | Mechanical, Electrical & Plumbing | Discipline Group | Collective term for building services engineering disciplines
HSE | Health, Safety & Environment | Management | Health, safety, and environmental management function on the project
O&M | Operation & Maintenance | Handover | Post-construction documentation for building systems operation and maintenance
GA | General Arrangement | Drawing Type | Overall layout drawing showing spatial arrangement of building elements
IFC | Issued for Construction | Status | Document status indicating the document is approved and released for construction use
4. DOCUMENT TYPE ACRONYMS (ALPHABETICAL)
Code | Full Name | Category | Definition
ABD | As-Built Drawing | Design | Record drawings reflecting the actual constructed condition, updated post-construction
AGN | Agenda | Meeting | Pre-meeting document listing topics, attendees, and time allocations
APS | Authority Submission | Authority | Design or compliance submission to QCDD, Civil Defence, Kahramaa, Ashghal, etc.
BND | Bond / Guarantee | Legal | Performance bond, advance payment guarantee, or retention guarantee
BOQ | Bill of Quantities | Commercial | Priced bill of quantities forming part of the contract
BUD | Budget Report | Commercial | Budget status report including amendments, contingency, and drawdown
CAL | Calculation | Design | Structural, MEP, or specialist engineering calculations supporting the design
CER | Completion Certificate | Handover | Taking-over certificate or practical/substantial completion certificate
CLM | Claim | Contractual | Contractual claim submission for additional time or cost under FIDIC
COR | Correspondence (General) | Contractual | General letters, written communications between project parties
CVI | Confirmation of Verbal Instruction | Contractual | Written confirmation of a verbal instruction issued on site
DET | Determination | Contractual | Engineer's or Employer's determination under FIDIC clause provisions
DLY | Delay Analysis | Programme | Forensic or prospective delay analysis of a time-related event
DWG | Drawing | Design | Design, detail, layout, GA, section, elevation drawings produced during the design process
EoT | Extension of Time | Contractual | Claim or application for extension of the contract completion date
FFC | Forecast Final Cost | Report | Monthly updated forecast of the project's final cost at completion
HND | Handover Document | Handover | Document forming part of the project handover and close-out package
HSP | Health & Safety Plan | HSE | Project health and safety management plan per local regulations
INC | Incident Report | HSE | Report documenting an HSE incident, near-miss, or dangerous occurrence on site
INS | Insurance Certificate | Legal | Certificate of insurance coverage as required by the contract
IPC | Interim Payment Certificate | Commercial | Monthly payment application and certified valuation of works done
ITP | Inspection & Test Plan | Quality | Document defining inspection and testing activities, hold/witness points
ITR | Inspection & Test Record | Quality | Completed record of an inspection or test as per the ITP
MIR | Material Inspection Request | Quality | Request submitted by contractor for HAI/consultant to inspect materials on site
MOC | Mockup | Submittal | Full-scale or representative mockup submitted for design/quality approval
MOD | 3D Model / BIM | Design | BIM models, clash detection reports, federated model deliverables
MOM | Minutes of Meeting | Meeting | Formal record of discussions, decisions, and actions from a project meeting
MRP | Monthly Report | Report | Monthly project progress report covering programme, cost, quality, HSE, and risk
MSS | Method Statement | Submittal | Detailed description of the methodology for executing specific works
MTL | Material Submittal | Submittal | Submittal of proposed materials, products, or equipment for approval
NCR | Non-Conformance Report | Quality | Report documenting a quality deficiency or non-compliance with specifications
NOC | No Objection Certificate | Authority | Certificate of no objection from a regulatory or statutory authority
NOT | Notice (FIDIC) | Contractual | Formal contractual notice issued under FIDIC contract conditions
OAM | Operation & Maintenance Manual | Handover | Documentation for building systems operation and maintenance post-handover
PER | Permit | Authority | Building permit, construction permit, or other regulatory approval
POA | Power of Attorney | Legal | Legal instrument delegating authority to act on behalf of a party
PRG | Programme / Schedule | Programme | Master programme, baseline schedule, look-ahead schedule, recovery programme
PTW | Permit to Work | HSE | Formal permit authorising specific high-risk work activities
QAP | Quality Assurance Plan | Quality | Project-level QA/QC plan defining quality management procedures
RAR | Risk Assessment | HSE | Activity-specific risk assessment identifying hazards and mitigation measures
RFI | Request for Information | Communication | Formal request for clarification on design, specification, or contractual matters
RPT | Report (General) | Report | Technical, specialist, or advisory reports not covered by other specific types
RSP | Response (FIDIC) | Contractual | Formal response to a contractual notice, within stipulated timeframes
SAM | Sample Submittal | Submittal | Physical or digital sample submitted for approval prior to procurement
SCH | Schedule (Design) | Design | Design schedules such as door schedule, finish schedule, equipment schedule
SHD | Shop Drawing | Design | Fabrication and installation drawings produced by the contractor or sub-contractor for manufacturing/construction
SI | Site Instruction | Contractual | Formal written instruction issued to the contractor on site
SNL | Snag List | Quality | List of deficiencies identified during inspection prior to handover
SPC | Specification | Design | Technical specifications defining material, workmanship, and performance requirements
STR | Stage Report | Report | RIBA stage completion report summarising deliverables and sign-off status
TQ | Technical Query | Communication | Technical question raised during design or construction requiring resolution
TRG | Training Record | Handover | Record of operator/end-user training on building systems and equipment
TRN | Transmittal | Communication | Cover document accompanying the formal transmission of documents between parties
VLN | Valuation | Commercial | Interim valuation of works for payment certification purposes
VO | Variation Order | Commercial | Approved instruction to vary the works, with cost and time implications
VON | Variation Order Notice | Commercial | Notice of intent to claim a variation, prior to formal VO approval
WAR | Warranty Certificate | Handover | Certificate confirming warranty terms for materials, equipment, or works
WIR | Work Inspection Request | Quality | Request submitted by contractor for HAI/consultant to inspect completed work

## Sample Register
[Project Reference] DOCUMENT REGISTER — SAMPLE ENTRIES
Doc Number | Title | Contract | Discipline | Type | Originator | Current Rev | Status | Date Submitted | Date Approved | Remarks
[Project Reference]-001-AR-DWG-0001-01-R0.0 | Ground Floor Plan | 001 | AR | DWG | Design Consultant | R0.0 | A | 2026-03-01 | 2026-03-15 | Approved first issue
[Project Reference]-001-AR-DWG-0001-02-R0.0 | Ground Floor Plan - Sheet 2 | 001 | AR | DWG | Design Consultant | R0.0 | A | 2026-03-01 | 2026-03-15 | Second sheet of same set
[Project Reference]-001-ST-CAL-0001-R1.0 | Foundation Design Calculation | 001 | ST | CAL | Structural Consultant | R1.0 | B | 2026-03-05 | 2026-03-20 | Approved w/ comments
[Project Reference]-001-ME-SHD-0001-01-R2.1 | AHU Installation Shop Drawing | 001 | ME | SHD | MEP Contractor | R2.1 | C | 2026-03-10 |  | Under revision
[Project Reference]-001-FE-RPT-0001-R0.0 | Fire Strategy Report | 001 | FE | RPT | Fire Engineer | R0.0 | B | 2026-03-01 | 2026-03-18 | Comply with egress comments
[Project Reference]-001-AC-RPT-0001-R0.0 | Acoustic Assessment Report | 001 | AC | RPT | Acoustic Consultant | R0.0 | A | 2026-03-02 | 2026-03-16
[Project Reference]-001-PM-COR-0001-R0.0 | Progress Meeting Notification | 001 | PM | COR | HAI PM | R0.0 | — | 2026-03-01 | — | Correspondence
[Project Reference]-001-CT-NOT-0001-R0.0 | Notice of Delay - Piling | 001 | CT | NOT | Contractor | R0.0 | — | 2026-03-12 | — | FIDIC notice
[Project Reference]-001-CT-VO-0001-R0.0 | VO: Additional Piling Zone B | 001 | CT | VO | Contractor | R0.0 | — | 2026-03-15 | — | Under QS assessment
[Project Reference]-001-QS-IPC-0001-R0.0 | IPC #1 - March 2026 | 001 | QS | IPC | Contractor | R0.0 | — | 2026-04-01 | — | Under verification
[Project Reference]-001-QA-NCR-0001-R0.0 | NCR: Rebar spacing non-compliant | 001 | QA | NCR | HAI Inspector | R0.0 | — | 2026-03-20 | — | Rectification pending
[Project Reference]-001-QA-WIR-0001-R0.0 | WIR: Raft Foundation Pour Zone A | 001 | QA | WIR | Contractor | R0.0 | — | 2026-03-18 | — | Inspected, approved
[Project Reference]-001-QA-MIR-0001-R0.0 | MIR: Steel Grade S355 | 001 | QA | MIR | Contractor | R0.0 | — | 2026-03-19 | — | Sample approved
[Project Reference]-002-EL-DWG-0003-01-R0.0 | Lighting Layout Level 2 | 002 | EL | DWG | Electrical Consultant | R0.0 | A | 2026-03-08 | 2026-03-22 | Contract 002
[Project Reference]-001-PL-DWG-0002-01-R3.2 | Drainage Layout Basement | 001 | PL | DWG | MEP Consultant | R3.2 | A | 2026-03-28 | 2026-04-10 | Approved at R3.2
[Project Reference]-001-CO-DWG-0001-01-R0.0 | MEP Coordination Section AA | 001 | CO | DWG | BIM Coordinator | R0.0 | B | 2026-03-22 | 2026-04-05 | Multi-discipline
[Project Reference]-001-PM-MRP-0006-R0.0 | Monthly Report - March 2026 | 001 | PM | MRP | HAI PM | R0.0 | — | 2026-04-05 | —
[Project Reference]-001-HS-RAR-0001-R0.0 | Risk Assessment: Crane Ops | 001 | HS | RAR | Contractor | R0.0 | — | 2026-03-15 | — | HSE review
[Project Reference]-001-CT-CLM-0001-R0.0 | Claim: Unforeseen Ground | 001 | CT | CLM | Contractor | R0.0 | — | 2026-04-01 | — | Under assessment
[Project Reference]-001-PG-PRG-0001-R1.0 | Master Programme Rev 1 | 001 | PG | PRG | Contractor | R1.0 | B | 2026-03-15 | 2026-04-02 | Baseline accepted