## Stakeholder Register
HAI [Project Reference] — STAKEHOLDER REGISTER
Per PMI Construction Extension to PMBOK — Section 10: Communications Management
ID | Stakeholder | Organisation | Role / Title | Category | Interest Level | Influence Level | Engagement Strategy | Key Concerns | Primary Contact
SH-01 | Artan Holding | Artan Holding | Employer / Owner | Internal | High | High | Manage Closely | ROI, programme, quality, brand reputation | Board Representative
SH-02 | HAI — Programme Director | HAI | Employer's Representative — Programme Lead | Internal | High | High | Manage Closely | Governance, compliance, risk, cost control | Hasan Mollamahmutoglu
SH-03 | HAI — Project Manager | HAI | ER — Day-to-day Project Management | Internal | High | High | Manage Closely | Programme, quality, coordination, reporting | TBN
SH-04 | HAI — Cost Manager / QS | HAI | ER — Commercial Management | Internal | High | Medium | Keep Satisfied | Cost, valuations, variations, claims | TBN
SH-05 | HAI — Design Manager | HAI | ER — Design Oversight | Internal | High | Medium | Keep Satisfied | Design compliance, review cycle, stage gates | TBN
SH-06 | HAI — Site Supervision | HAI | ER — Quality & Site Supervision | Internal | High | Medium | Keep Satisfied | Workmanship, QCS 2014 compliance, safety | TBN
SH-07 | Lead Design Consultant | TBN Consultant | Engineer / Lead Designer | External — Consultant | High | High | Manage Closely | Design integrity, programme, coordination, liability | TBN
SH-08 | Specialist Subconsultants | Various | Fire, Acoustics, GSAS, VT, etc. | External — Consultant | Medium | Medium | Keep Informed | Specialist scope compliance, timely input | Various
SH-09 | Main Contractor | TBN Contractor | Contractor — Works Execution | External — Contractor | High | High | Manage Closely | Programme, payment, variations, site access, resources | TBN
SH-10 | MEP Subcontractor | TBN Subcontractor | Nominated/Domestic MEP Sub | External — Contractor | High | Medium | Keep Satisfied | Coordination, shop drawings, testing, handover | TBN
SH-11 | Specialist Subcontractors | Various | Facade, Piling, Lifts, Kitchen, etc. | External — Contractor | Medium | Low | Monitor | Scope clarity, programme, payment flow, approvals | Various
SH-12 | Qatar Civil Defence (QCDD) | Government | Fire & Life Safety Authority | External — Authority | Low | High | Keep Satisfied | Fire strategy compliance, NOC approvals | Assigned Officer
SH-13 | Ashghal (PWA) | Government | Public Works Authority | External — Authority | Low | High | Keep Satisfied | Infrastructure connections, road permits, drainage | Assigned Officer
SH-14 | Kahramaa | Government | Electricity & Water Authority | External — Authority | Low | High | Keep Satisfied | Power/water supply connections, meter installation | Assigned Officer
SH-15 | Municipality (Baladiya) | Government | Planning & Building Permit Authority | External — Authority | Low | High | Keep Satisfied | Building permit, planning compliance, inspections | Assigned Officer
SH-16 | GORD (GSAS Assessor) | GORD | Green Building Certification Body | External — Authority | Low | Medium | Keep Informed | GSAS certification compliance, documentation | Assigned Assessor
SH-17 | End Users / Tenants | Artan Holding | Future Occupants / Operators | External — End User | Medium | Low | Keep Informed | Functionality, MEP systems, O&M, finishes quality | Via Artan Holding
SH-18 | Neighbours / Community | Adjacent Properties | Affected Parties | External — Community | Low | Low | Monitor | Noise, dust, traffic disruption, crane oversail | Via Contractor HSE
SH-19 | Insurance / Surety Provider | TBN Insurer | CAR / PI / Bond Provider | External — Financial | Low | Medium | Keep Informed | Risk exposure, claims notifications, compliance | Broker

## Communication Matrix
HAI [Project Reference] — COMMUNICATION MATRIX
PMI Construction Extension — 10.1 Plan Communications Management ¦ FIDIC 2017 Clause References
Comm ID | Communication Item | Purpose / Objective | From (Sender) | To (Receiver) | Method / Channel | Frequency | Format / Deliverable | Contract Ref | Response Time | Escalation Path | FIDIC / Contract Ref | RIBA Stage | Remarks
GOVERNANCE & REPORTING
CM-01 | Monthly Progress Report | Report project status across all KPIs (programme, cost, quality, HSE, risk) | HAI PM | Artan Holding + HAI Programme Director | Email + Hard Copy | Monthly | Word/PDF report with dashboard (MRP) | English | N/A | HAI PM -> Programme Director -> Artan Board | GCC 4.21 / FIDIC 4.21 | All stages | Issued by 5th of following month
CM-02 | Weekly Progress Report | Track weekly site activities, look-ahead, issues log | Main Contractor | HAI PM + Consultant | Email | Weekly (Thursday) | PDF report + photo log | English | N/A | Contractor PM -> HAI PM | FIDIC 4.21 | Stage 5 (Construction) | Due every Thursday by 14:00
CM-03 | Forecast Final Cost (FFC) | Monthly updated project cost forecast | HAI QS | Artan Holding + HAI Programme Director | Email + Presentation | Monthly | Excel model + PDF summary (FFC) | English | N/A | HAI QS -> Programme Director -> Artan Board | FIDIC 14.3 | All stages | Issued with Monthly Report
CM-04 | Executive Dashboard | High-level KPI summary for Owner decision-making | HAI PM | Artan Holding Board | Presentation (in person) | Monthly / As needed | PowerPoint + 1-page PDF | English | N/A | HAI PM -> Programme Director | N/A | All stages | Board meeting format
CM-05 | Stage Gate Report | RIBA stage completion sign-off and readiness assessment | HAI PM + Design Manager | Artan Holding + HAI Programme Director | Meeting + Report | Per RIBA stage | Word/PDF report (STR) | English | 14 days review | HAI PM -> Programme Director -> Artan Board | N/A | End of each RIBA stage | Requires Owner sign-off to proceed
MEETINGS
CM-06 | Project Progress Meeting | Review programme, issues, actions, risks, coordination | HAI PM (Chair) | All project parties | In person + MS Teams | Weekly | Agenda (AGN) + Minutes (MOM) | SC 3.6 | Action items per MOM deadline | HAI PM -> Programme Director | FIDIC 4.21 | All stages | Fixed day/time, mandatory attendance
CM-07 | Design Coordination Meeting | Resolve design interfaces, clashes, RFIs, TQs | HAI Design Manager (Chair) | Consultant + Specialist Subconsultants | In person + MS Teams | Weekly / Bi-weekly | Agenda + MOM | SC 3.6 | Per MOM | HAI DM -> HAI PM | N/A | Stages 2-4 | BIM coordination review included
CM-08 | Commercial Meeting | Review valuations, variations, claims, cost status | HAI QS (Chair) | Contractor QS + Consultant QS | In person | Bi-weekly / Monthly | Agenda + MOM | English | Per MOM | HAI QS -> HAI PM -> Programme Director | FIDIC 14.3 / 20.1 | Stages 4-6 | Confidential — restricted distribution
CM-09 | HSE Meeting | Review safety performance, incidents, permits, inspections | HAI Site Supervisor / HSE | Contractor HSE + all site parties | In person (site) | Weekly | Agenda + MOM | English | Immediate for incidents | HAI HSE -> HAI PM -> Programme Director | FIDIC 4.8 / QCS S11 | Stage 5 | Mandatory for all site staff
CM-10 | Authority Coordination Meeting | Track NOC submissions, permit status, authority requirements | HAI PM | Consultant + Authorities (as needed) | In person / Authority office | As required | Agenda + MOM + Tracker | English / Arabic | Per authority SLA | HAI PM -> Programme Director | N/A | Stages 3-5 | Arabic for authority correspondence
CM-11 | Handover & Close-out Meeting | Track snagging, O&M, as-builts, testing, commissioning | HAI PM (Chair) | Contractor + Consultant + End User rep | In person | Weekly (during handover) | Agenda + MOM + Snag Tracker | English | Per MOM | HAI PM -> Programme Director -> Artan | FIDIC 10.1 / 11.1 | Stage 6 | Begins 3 months before PC
DOCUMENT SUBMITTALS & REVIEWS
CM-12 | Design Document Submittal | Submit design drawings, specs, calculations for review | Consultant / Contractor | HAI (via Document Control) | EDMS (SkyStruct) | Per programme | Per Doc Numbering System | SC 3.1, 4.28.1 | 14 calendar days (design) / 21 days (shop drawings) | Originator DC -> Consultant DC -> Consultant Eng -> HAI Eng | FIDIC 5.2 / 1.8 | Stages 2-5 | Status A/B/C/D per PF-01
CM-13 | Material Submittal (MTL) | Submit proposed materials/products for approval | Contractor | HAI (via Consultant) | EDMS + physical sample | Per procurement schedule | Submittal form + data sheets + sample | SC 3.1, 4.28.1 | 10 calendar days | Consultant -> HAI Design Manager | FIDIC 7.2 / QCS S02 | Stages 4-5 | Sample board for finishes
CM-14 | Method Statement (MSS) | Describe execution methodology for approval | Contractor | HAI (via Consultant) | EDMS | Per activity start | Word/PDF document | SC 3.1, 4.28.1 | 14 calendar days | Consultant -> HAI Site Supervisor | FIDIC 4.1 / QCS S02 | Stage 5 | Required before work commencement
CM-15 | RFI / Technical Query | Seek clarification on design, specification, or contract | Any party | Addressed party (usually Consultant) | EDMS | As arising | RFI / TQ form | SC 1.3, 1.9 | 7 calendar days (RFI) / 14 days (TQ) | Originator -> Addressed -> HAI if unresolved | FIDIC 1.8 | All stages | Log maintained in EDMS
CONTRACTUAL COMMUNICATIONS
CM-16 | FIDIC Notices | Formal contractual notices (delay, claim, variation, etc.) | Any party | Addressed party (per contract) | Registered letter + Email + EDMS | 3 calendar days (CD) response to Notices; as per Engineer for Urgent; Electronic deemed received D+1; Fax + original 2 working days | Formal letter (NOT) | SC 1.3 | Per FIDIC clause (typically 28 days) | Per FIDIC dispute resolution ladder | FIDIC 1.3 / 20.2 | All stages | Time-bar critical — logged with timestamp
CM-17 | Site Instruction (SI) | Formal instruction to contractor on site | HAI (ER) | Contractor | EDMS + hard copy | As arising | SI form | English | Immediate acknowledgement, comply per SI | HAI Site -> HAI PM -> Programme Director | FIDIC 3.5 | Stage 5 | May trigger variation assessment
CM-18 | Variation Order (VO) | Instruct variation with cost/time implications | HAI (ER) | Contractor | EDMS + hard copy | As arising | VO form + assessment | English | 28 days for Contractor quotation | HAI QS -> HAI PM -> Programme Director -> Artan | FIDIC 13.1 / 13.3 | Stages 4-6 | Requires Owner approval above threshold
CM-19 | Extension of Time Claim (EoT) | Claim for time extension under contract | Contractor | HAI (ER) | Registered letter + EDMS | 28 CD notice of claim (TIME-BARRED); 7 CD fully detailed claim (TIME-BARRED); 48h post no-objection (TIME-BARRED) | Formal claim + contemporaneous records | SC 20.2 | 42 days for Engineer determination | HAI PM -> Programme Director -> Artan (if >threshold) | FIDIC 8.5 / 20.2 | Stages 4-6 | Time-bar: 28 days from awareness
CM-20 | Interim Payment Certificate (IPC) | Monthly payment application and certification | Contractor (application) -> HAI QS (certification) | HAI -> Artan Holding (for payment) | EDMS + hard copy | Monthly (28 CD) | IPC form + supporting docs | SC 14 | 28 days certification / 56 days payment | Contractor -> HAI QS -> HAI PM -> Artan Finance | FIDIC 14.3 / 14.6 / 14.7 | Stages 5-6 | Payment timeline per FIDIC
QUALITY & INSPECTION
CM-21 | Work Inspection Request (WIR) | Request inspection of completed work before cover-up | Contractor | HAI Site Supervisor + Consultant | EDMS | 48 hours before required inspection | WIR form + ITP reference | English | 24 hours for inspection | Contractor QA -> HAI Site -> Consultant | FIDIC 7.3 / QCS S02 | Stage 5 | No cover-up without approved WIR
CM-22 | Material Inspection Request (MIR) | Request inspection of delivered materials | Contractor | HAI Site Supervisor + Consultant | EDMS | Upon material delivery | MIR form + test certificates | English | 24 hours for inspection | Contractor QA -> HAI Site -> Consultant | FIDIC 7.2 / QCS S02 | Stage 5 | Materials quarantined until approved
CM-23 | Non-Conformance Report (NCR) | Document quality deficiency and require rectification | HAI QA / Site Supervisor | Contractor | EDMS + hard copy | As arising | NCR form | English | 7 days for rectification plan, per NCR for completion | HAI QA -> HAI PM (if unresolved) | FIDIC 7.5 / 7.6 / QCS S02 | Stage 5 | Tracked in NCR register
HSE COMMUNICATIONS
CM-24 | Incident / Accident Report | Report and investigate HSE incidents | Contractor / HAI HSE | HAI PM + Programme Director + Authorities (if LTI) | Email (immediate) + formal report | Immediate (within 1 hour for serious) | Incident report form | English / Arabic | Immediate notification, formal report within 24 hours | Contractor HSE -> HAI HSE -> HAI PM -> Programme Director -> Artan | FIDIC 4.8 / QCS S11 | Stage 5 | Reported to MoL if fatality/LTI
CM-25 | Permit to Work (PTW) | Authorise high-risk work activities | Contractor | HAI Site Supervisor (approval) | Hard copy (site) | Per activity | PTW form | English | 24 hours in advance | Contractor HSE -> HAI Site | QCS S11 | Stage 5 | Hot work, confined space, working at height, etc.
AUTHORITY & CERTIFICATION
CM-26 | Authority Submission (NOC/Permit) | Submit design/compliance documents to authorities | Consultant (prepared by) + HAI (submitted by) | QCDD / Ashghal / Kahramaa / Municipality | Authority portal + hard copy | Per authority requirements | Authority submission package (APS) | English / Arabic | Per authority SLA (typically 21-45 days) | Consultant -> HAI PM -> Authority liaison | N/A | Stages 3-5 | Arabic translations as required
CM-27 | GSAS Submission | Submit sustainability documentation for GSAS certification | GSAS Consultant | GORD | GORD portal | Per GSAS scheme stages | GSAS template package | English | Per GORD review timeline | GSAS Consultant -> HAI DM -> GORD | N/A | Stages 2-6 | Tied to RIBA stage gates
HANDOVER & CLOSE-OUT
CM-28 | O&M Manuals | Deliver operation and maintenance documentation | Contractor | HAI -> Artan Holding / FM Team | EDMS + hard copy (3 sets) | Pre-handover | O&M manual set (OAM) | English | Reviewed within 28 days | Contractor -> Consultant review -> HAI -> Artan | FIDIC 5.6 | Stage 6 | Required before Taking-Over Certificate
CM-29 | As-Built Drawings | Deliver record drawings of actual construction | Contractor | HAI -> Artan Holding | EDMS + hard copy (3 sets) | Pre-handover | As-built drawing set (ABD) | English | Reviewed within 14 days | Contractor -> Consultant review -> HAI | FIDIC 5.6 | Stage 6 | Mandatory before final payment
CM-30 | Training & Handover Records | Document operator training and system handover | Contractor | HAI -> Artan Holding / FM Team | In person + EDMS | Pre-handover | Training records (TRG) + certificates | English | Completed before Taking-Over | Contractor -> HAI -> Artan FM | FIDIC 5.6 / 10.1 | Stage 6 | Covers all building systems

## Escalation Matrix
HAI [Project Reference] — ESCALATION MATRIX
Level | Trigger / Condition | Escalated By | Escalated To | Response Time | Authority | Action Required | De-escalation
Level 1 — Operational | Day-to-day coordination issues, minor delays, routine queries | Site Engineer / Inspector | HAI Site Supervisor / Consultant Team Leader | Same day | Instruct, adjust site activities | Resolve at site level, log in daily report | Issue resolved, logged in weekly report
Level 2 — Project | Recurring issues, programme slippage <2 weeks, cost impact <1% of contract, unresolved RFIs >14 days | HAI Site Supervisor / Consultant | HAI Project Manager | 48 hours | Issue formal instructions, convene ad-hoc meeting | Formal meeting, action plan with deadlines, warning letter if pattern | SC 3.6 (Meetings)
Level 3 — Programme | Programme slippage >2 weeks, cost impact 1-5%, NCR patterns, contractual notice received, claim >$100k | HAI Project Manager | HAI Programme Director | 5 working days | Issue contractual notices, approve recovery plan, engage legal if needed | Programme Director intervention, recovery programme required, notice to Contractor | Recovery plan accepted, programme on track, claim resolved
Level 4 — Executive | Programme slippage >4 weeks, cost impact >5%, safety incident (LTI), termination consideration, dispute | HAI Programme Director | Artan Holding Board / Owner | Immediate briefing, formal report within 48 hours | Contract termination, dispute referral (FIDIC 21), budget reallocation, strategic decisions | Board decision, legal action if required, contractor default notice if applicable | Board resolution documented, corrective strategy approved

## Meeting Schedule
HAI [Project Reference] — MEETING SCHEDULE & PROTOCOLS
Meeting ID | Meeting | Chair | Mandatory Attendees | Optional Attendees | Frequency | Day / Time | Location | Agenda Issued | MOM Issued | Contract Ref
MTG-01 | Project Progress Meeting | HAI PM | HAI PM, HAI DM, HAI QS, HAI Site, Consultant PM, Contractor PM | Specialist consultants, subcontractors (by invite) | Weekly | Sunday 10:00 | HAI Site Office / MS Teams | Thursday prior | Within 48 hours (Tuesday) | SC 3.6
MTG-02 | Design Coordination Meeting | HAI Design Manager | HAI DM, Consultant Lead, BIM Coordinator | Specialist subconsultants (by discipline) | Weekly (design) / Bi-weekly (construction) | Monday 10:00 | HAI Office / MS Teams | Thursday prior | Within 48 hours (Wednesday) | SC 3.6
MTG-03 | Commercial Review Meeting | HAI QS | HAI QS, Contractor QS, Consultant QS | HAI PM (as needed) | Monthly | First Tuesday of month | HAI Office (confidential) | 3 days prior | Within 5 working days | Restricted distribution — commercially sensitive
MTG-04 | HSE Meeting | HAI Site Supervisor | HAI Site, Contractor HSE Manager, all subcontractor HSE reps | Consultant (as needed) | Weekly | Sunday 08:00 | Site — Toolbox area | N/A (standing agenda) | Within 24 hours (Monday) | Toolbox talk + safety walk included
MTG-05 | Authority Coordination Meeting | HAI PM | HAI PM, Consultant Lead, Authority liaison | Contractor (for infrastructure) | As required | Per authority schedule | Authority office / HAI Office | 5 days prior | Within 48 hours | Arabic interpreter if required
MTG-06 | Risk Review Meeting | HAI PM | HAI PM, HAI QS, Consultant PM | Contractor PM | Monthly | Second Wednesday of month | HAI Office | 3 days prior | Within 5 working days | Risk register update mandatory
MTG-07 | Stage Gate Review Meeting | HAI Programme Director | HAI Programme Director, HAI PM, HAI DM, HAI QS, Consultant Lead | Artan Holding representative | Per RIBA stage completion | As scheduled | HAI Office | 7 days prior | Within 5 working days | Go/No-Go decision required
MTG-08 | Owner Briefing / Board Presentation | HAI Programme Director | HAI Programme Director, HAI PM | HAI QS, HAI DM (by invite) | Monthly / As needed | Per Artan schedule | Artan Holding HQ | 5 days prior | Within 48 hours | PowerPoint format, max 30 minutes
MTG-09 | Handover Coordination Meeting | HAI PM | HAI PM, HAI Site, Consultant, Contractor, Artan FM | End user representative | Weekly (during handover phase) | Wednesday 10:00 | Site / HAI Office | Thursday prior | Within 48 hours | Begins 3 months before targeted PC date

## Distribution Matrix
HAI [Project Reference] — DISTRIBUTION MATRIX (RACI)
R = Responsible (does the work) ¦ A = Accountable (approves) ¦ C = Consulted ¦ I = Informed
Communication Item | Artan Holding | HAI Prog Dir | HAI PM | HAI QS | HAI DM | HAI Site | Consultant | Contractor | Subcontractors | Authorities | End User / FM
Monthly Progress Report | I | A | R | C | C | C | C | C | — | — | —
Weekly Progress Report | — | I | I | — | — | I | I | R | C | — | —
Forecast Final Cost | I | A | C | R | — | — | C | C | — | — | —
Executive Dashboard | I | A | R | C | C | — | — | — | — | — | —
Stage Gate Report | A | R | R | C | C | C | C | I | — | — | I
Progress Meeting MOM | — | I | R | C | C | C | C | C | I | — | —
Design Coord MOM | — | — | I | — | R | — | C | C | — | — | —
Commercial Meeting MOM | — | I | I | R | — | — | C | C | — | — | —
Document Submittal Review | — | — | I | — | A | — | C | R | C | — | —
Material Submittal | — | — | I | — | A | C | C | R | C | — | —
Method Statement | — | — | I | — | — | A | C | R | C | — | —
RFI / TQ | — | — | I | — | C | C | R | C | C | — | —
FIDIC Notices | I | A | R | C | — | — | C | C | — | — | —
Site Instruction | — | I | A | C | — | R | C | I | I | — | —
Variation Order | A | R | C | R | C | — | C | I | I | — | —
IPC / Payment | A | I | C | R | — | — | C | R | — | — | —
WIR / MIR | — | — | — | — | — | A | C | R | C | — | —
NCR | — | I | I | — | — | R | C | I | I | — | —
Incident Report | I | A | R | — | — | C | I | R | C | I | —
Authority Submission | — | I | A | — | C | — | R | C | — | I | —
O&M / As-Builts / Training | I | I | A | — | C | C | C | R | C | — | I

## Technology & Tools
HAI [Project Reference] — COMMUNICATION TECHNOLOGY & TOOLS
Tool / System | Purpose | Owner / Admin | Users | Access Level | Backup / Redundancy
SkyStruct Platform (EDMS) | Document management, submittal workflows, approvals, register, reporting | HAI Information Manager | All project parties | Role-based (Admin/Reviewer/Submitter/Viewer) | Cloud-hosted, daily backup, 99.9% SLA
Microsoft Teams | Video conferencing, chat, screen sharing for remote meetings | HAI IT | All project parties | Per team channels (restricted for commercial) | Microsoft 365 cloud infrastructure
Microsoft Outlook / Email | Formal correspondence, transmittals, notifications | Each organisation | All project parties | Individual accounts | Organisation email servers
BIM 360 / ACC | BIM model hosting, clash detection, design coordination | HAI BIM Coordinator / Consultant | Design team + Contractor (view) | Model-level permissions | Autodesk cloud, version history
Primavera P6 / MS Project | Programme management, scheduling, critical path analysis | Contractor (P6) / HAI (review) | HAI PM, Contractor Planner | Read-only for HAI, edit for Contractor | Contractor server + HAI backup copy
Cost Management System | Budget tracking, FFC, variation register, payment certification | HAI QS | HAI QS team, Programme Director (view) | Restricted — commercial sensitivity | HAI cloud server, encrypted
Site Diary / Daily Report App | Daily site activities, weather, labour, plant, progress photos | Contractor | Contractor Site Team, HAI Site Supervisor (view) | Contractor edit, HAI view | Cloud-synced daily
Power BI / Dashboard | Executive reporting, KPI visualisation, automated dashboards | HAI PM / Data Analyst | HAI Programme Director, Artan Board (view) | View-only for stakeholders | Linked to SkyStruct data feeds