## FIDIC Clause Mapping
FIDIC Clause | Clause Title | Obligation Type | Initiator | Time Bar (CD) | System Workflow (PF) | Template(s) | SLA Reference | Auto-Action | Escalation Level | Stage Applicability | Risk if Missed
1.3 | Communications | Notice | Any party | As specified | PF-02 | Submittal_Transmittal_Letter.docx | SLA-003 | Auto-log + timestamp | L2 at 5 CD | All stages | Invalid notice → deemed not given
1.8 | Care and Supply of Documents | Document | Contractor | As instructed | PF-01 | DES-A00, Drawing_Register.xlsx | SLA-001 | Track versions | L1 at warning | Stage 2-6 | Non-compliance → instruction to comply
2.1 | Right of Access to Site | Obligation | Employer | Per programme | PF-05 | N/A | N/A | Gate prerequisite check | L3 immediately | Stage 5 | EOT entitlement per 8.4
4.1 | Contractor General Obligations | Obligation | Contractor | Ongoing | PF-01, PF-10 | QA-D01_Project_Quality_Plan.docx | N/A | Compliance checklist | L2 on NCR | Stage 5-6 | Non-compliance → instruction + cost recovery
4.4 | Subcontractors | Approval | Contractor | 28 CD before work | PF-04 | CON-G08_Subcontractor_Approval.xlsx | SLA-005 | Approval workflow | L2 at deadline | Stage 5 | Unapproved sub → instruction to remove
8.1 | Commencement of Works | Milestone | Contractor | Per Appendix | PF-05 | PRG-F01_Mobilisation_Plan.docx | SLA-011 | Gate 5 prerequisite | L3 if delayed | Stage 5 | Default → termination risk per 15.2
8.3 | Programme | Submission | Contractor | 28 CD from commencement | PF-01, PF-09 | PRG-F03_Recovery_Programme.docx | SLA-001 | Review workflow + baseline lock | L2 on delay | Stage 5 | FIDIC 8.3 → Engineer may withhold IPC
8.4 | Extension of Time | Claim | Contractor | 28 CD from awareness | PF-03 | CON-G04_EOT_Application.docx | SLA-008 | Auto-flag deadline + assessment workflow | L3 at 21 CD | Stage 5-7 | Time-barred if notice late per 20.1
10.1 | Taking Over | Certificate | Contractor/Engineer | 14 CD from application | PF-28 | HOV-H00_Handover_Cover.docx | SLA-014 | Inspection schedule + snag list auto-gen | L3 at 10 CD | Stage 6 | Deemed TOC if Engineer fails to respond
11.1 | Completion of Outstanding Work | Obligation | Contractor | Per TOC notice | PF-31 | QA-D12_Snag_List.xlsx | SLA-013 | Track snag closure | L2 at SLA | Stage 6-7 | Employer may employ others per 11.4
11.9 | Performance Certificate | Certificate | Engineer | 28 CD after DLP | PF-30 | N/A (system generated) | SLA-015 | Auto-generate if DLP items closed | L4 at deadline | Stage 7-8 | Deemed issued per FIDIC 11.9
13.1 | Right to Vary | Instruction | Engineer | Any time | PF-03 | CON-G02_Variation_Proposal.docx | SLA-005 | VO workflow + cost/time assessment | L2 at 14 CD | Stage 5 | Disputed variation → 20.1 claim
14.3 | Application for IPC | Submission | Contractor | Monthly per Appendix | PF-08 | CON-G01_Payment_Application.docx | SLA-006 | IPC receipt + verification workflow | L2 at 7 CD | Stage 5-7 | Interest per 14.8 if late certification
14.6 | Issue of IPC | Certificate | Engineer | 28 CD from application | PF-08 | N/A (system calculated) | SLA-006 | Auto-calculate + route for approval | L3 at 21 CD | Stage 5-7 | Interest per 14.8 + dispute per 20.1
14.7 | Payment | Payment | Employer | 56 CD from application | PF-08, PF-20 | N/A (ERP integration) | N/A | Push certified amount to ERP | L4 at 42 CD | Stage 5-7 | Interest per 14.8 + suspension per 16.1
14.11 | Final Payment Certificate | Certificate | Engineer | 28 CD after final statement agreed | PF-29 | CON-G12_Final_Account.xlsx | SLA-015 | Final account workflow | L4 at 21 CD | Stage 7 | Dispute per 20.1 if not issued
15.2 | Termination by Employer | Notice | Employer | 14 CD notice | PF-02 | CON-G11_Contractual_Notice.docx | N/A | Formal notice workflow + lock contractor access | L5 immediate | Any | Wrongful termination → 16.4 claim
16.1 | Suspension by Contractor | Notice | Contractor | 21 CD notice | PF-02 | CON-G05_Notice_of_Delay.docx | N/A | Alert chain to ER + Employer | L5 immediate | Any | Non-payment > 42 CD → suspension right
20.1 | Contractor Claims | Claim | Contractor | 28 CD notice + 42 CD particulars | PF-03 | CON-G03_Claim_Submission.docx | SLA-007 | Claim workflow + time-bar tracking | L4 at 21 CD | Stage 5-7 | Time-barred if late notice
20.4 | Obtaining DAB Decision | Dispute | Any party | 84 CD for decision | PF-02 | CON-G12_Dispute_Notice.docx | N/A | Dispute tracking + DAB referral | L5 immediate | Any | Arbitration per 20.6 if no DAB decision