## QCS Compliance Matrix
QCS Section | QCS Title | Key Requirement | System Module / PF | Template(s) | Verification Method | Frequency | Responsible Role | Evidence Required | Stage Applicability
Part 1 §1.1 | General | Comply with all QCS requirements | PF-10, PF-01 | QA-D01_Project_Quality_Plan.docx | Quality plan review | At mobilisation | R06 | Approved QA Plan | Stage 5
Part 1 §1.4 | Quality Assurance | QA/QC plan submittal and approval | PF-01, PF-09 | QA-D01_Project_Quality_Plan.docx | Submittal review | At mobilisation + updates | R06 | Approved QA Plan Rev X | Stage 5
Part 1 §1.5 | Health and Safety | HSE plan and implementation | PF-01, PF-10 | HSE-E01_Project_HSE_Plan.docx | Site audit | Monthly | R06 | HSE audit report | Stage 5-6
Part 1 §1.6 | Document Control | Document management system | PF-01 | Drawing_Register.xlsx, Document_Transmittal_Log.xlsx | System audit | Quarterly | R07 | Document register export | Stage 1-7
Part 1 §1.7 | Quality Records | Maintain quality records throughout | PF-10, PF-23 | QA-D02_ITP_Template.xlsx | Records audit | Monthly | R06 | ITP completion records | Stage 5-6
Part 2 §2 | Site Investigation | Geotechnical and survey requirements | PF-01 | QA-D11_Survey_Report.xlsx | Report review | At design stage | R04 | Approved survey reports | Stage 3-4
Part 4 §4 | Concrete | Mix design approval and testing | PF-01, PF-10 | MAT-B11_Concrete_Mix_Technical Design.xlsx, QA-D04_Concrete_Test.xlsx | Test result review | Per batch/pour | R06 | Approved mix design + cube results | Stage 5
Part 5 §5 | Steel and Metals | Material certification and welding QC | PF-01, PF-10 | QA-D05_Welding_Inspection.xlsx, QA-D08_WPS.xlsx | Inspection | Per delivery/weld | R06 | Mill certs + WPS + inspection reports | Stage 5
Part 8 §8 | Mechanical Works | MEP installation and testing | PF-01, PF-10 | MS-C06_MEP_Installation.docx, QA-D06_Pressure_Test.xlsx | Witness test | Per system | R06 | Test certificates | Stage 5-6
Part 9 §9 | Electrical Works | Electrical installation and testing | PF-01, PF-10 | MS-C06_MEP_Installation.docx | Witness test | Per system | R06 | Test certificates + Kahramaa approval | Stage 5-6
Part 10 §10 | Instrumentation | Calibration and commissioning | PF-10 | QA-D10_Calibration_Register.xlsx, QA-D07_Commissioning_Procedure.xlsx | Commissioning witness | Per system | R06 | Calibration certs + commissioning reports | Stage 6
Part 14 §14 | Roads and Drainage | Road construction and drainage works | PF-01, PF-10 | MS-C08_Road_Infrastructure.docx | Inspection + testing | Per layer/section | R06 | Compaction test results + Ashghal NOC | Stage 5
Part 16 §16 | Landscaping | Landscape works and irrigation | PF-01, PF-10 | N/A | Inspection | Per zone | R06 | Inspection reports | Stage 5-6
Part 17 §17 | Fire Protection | Fire safety systems | PF-01, PF-07 | N/A | Civil Defence inspection | Per system | R06 | Civil Defence approval | Stage 6

## Authority Approvals
Authority | Approval Type | Required Stage | Submission Via | PF Reference | Template | Typical Duration | Prerequisite
Ashghal | Road Opening Permit | Stage 5 | PF-07 | PF-07 | REG-J03_Ashghal_NOC.xlsx | 14-28 CD | Approved traffic management plan
Ashghal | Infrastructure NOC | Stage 4-5 | PF-07 | PF-07 | REG-J03_Ashghal_NOC.xlsx | 28-42 CD | Technical Design approval
QCDD (Civil Defence) | Fire Safety Approval | Stage 4 | PF-07 | PF-07 | REG-J01_Civil_Defence.xlsx | 28-56 CD | Fire strategy report
QCDD (Civil Defence) | Building Permit | Stage 4 | PF-07 | PF-07 | REG-J01_Civil_Defence.xlsx | 28-42 CD | Structural + MEP drawings
Municipality (Baladiya) | Planning Permission | Stage 3 | PF-07 | PF-07 | REG-J04_Municipality.xlsx | 42-84 CD | Town planning submission
Municipality (Baladiya) | Completion Certificate | Stage 6 | PF-07, PF-28 | PF-07 | REG-J04_Municipality.xlsx | 28-42 CD | All inspections passed
Kahramaa | Electrical Connection | Stage 5-6 | PF-07 | PF-07 | REG-J05_Kahramaa.xlsx | 28-56 CD | Electrical design approval
Kahramaa | Water Connection | Stage 5-6 | PF-07 | PF-07 | REG-J05_Kahramaa.xlsx | 28-56 CD | Plumbing design approval
GSAS Trust | GSAS Certification | Stage 0-8 | PF-11 | PF-11 | REG-J07_GSAS.xlsx | Per milestone | Sustainability documentation