## Test Scenario Register
Test ID | PF Reference | Scenario Name | Description | Preconditions | Test Steps | Expected Result | Priority | Test Type | Status
TC-001 | PF-01 | Document submission with valid HAI numbering | Verify document can be submitted with proper HAI numbering format | User logged in, HAI doc template available | 1. Select document 2. Enter HAI number 3. Click Submit | Document accepted, status=submitted, confirmation msg displayed | Critical | Functional | Planned
TC-002 | PF-01 | Document rejection and resubmission | Verify rejected document (Status D) can be resubmitted with corrections | Document in Status D, corrections available | 1. Open rejected doc 2. Correct errors 3. Resubmit | Document resubmitted, status updated, audit trail logged | High | Functional | Planned
TC-003 | PF-01 | Review SLA breach and L2 escalation | Verify system escalates to L2 when review SLA breached | Document pending review >SLA duration | 1. Monitor SLA timer 2. Wait for breach 3. Observe escalation | Escalation trigger fired, L2 notified, audit record created | Critical | Integration | Planned
TC-004 | PF-02 | Correspondence with 14-day response timer | Verify correspondence module implements 14-day response SLA | Correspondence item created and assigned | 1. Create correspondence 2. Monitor timer 3. Check deadline | 14-day timer active, reminder at day 10, escalation at day 14 | Critical | Functional | Planned
TC-005 | PF-02 | Claims notice 28-day time-bar (SC 20.2.1) | Verify claims module enforces FIDIC 28-day notice requirement | Claims module configured, FIDIC rules active | 1. Create claim after 28 days 2. Attempt submission | System blocks submission, displays FIDIC SC 20.2.1 message | Critical | Functional | Planned
TC-006 | PF-03 | Variation parallel execution (SC 13.1 dual track) | Verify variation can execute in parallel with commercial assessment | Variation initiated, dual-track workflow enabled | 1. Create variation 2. Execute works 3. Assess commercial impact | Execution and assessment proceed in parallel, no blocking | Critical | Functional | Planned
TC-007 | PF-03 | Variation commercial assessment while execution proceeds | Verify commercial assessment does not delay work execution | Variation in execution phase | 1. Start execution 2. Initiate commercial assessment 3. Monitor timelines | Both activities proceed independently, linked at completion | Critical | Integration | Planned
TC-008 | PF-04 | Procurement RFP to Contract Award full cycle | Verify complete procurement workflow from RFP to Contract Award issuance | Procurement module active, vendors configured | 1. Create RFP 2. Send to vendors 3. Evaluate proposals 4. Issue Contract Award | Contract Award created, vendor notified, audit trail complete | High | Functional | Planned
TC-009 | PF-05 | Stage gate progression with prerequisites check | Verify stage gate enforces prerequisite checks before progression | Project in stage N with defined prerequisites | 1. Attempt to progress without prerequisites 2. Complete prerequisites 3. Retry | First attempt blocked with prerequisite list, second succeeds | High | Functional | Planned
TC-010 | PF-06 | Design freeze exception approval chain | Verify design freeze allows exceptions through approval chain | Design in freeze status, exception requested | 1. Request design exception 2. Route through approvers 3. Track decision | Exception routed, decisions logged, design updated or rejected | High | Functional | Planned
TC-011 | PF-07 | Authority submission tracking | Track authority submissions and approvals | Authority module active | 1. Submit to authority 2. Track status | Submission logged, tracking active | Medium | Functional | Planned
TC-012 | PF-08 | IPC submission → 28d certification → 10d payment | Verify IPC workflow (28d cert, 10d payment) | IPC template ready, payment config active | 1. Submit IPC 2. Wait 28d cert 3. Process payment | Cert issued on day 28, payment on day 10 | Critical | Functional | Planned
TC-013 | PF-08 | IPC with retention calculation (10% to 50%, 5% after) | Verify retention percentages per contract | IPC with retention rules configured | 1. Create IPC 2. Calculate retention 3. Verify percentages | Retention: 10-50% per phase, 5% final | Critical | Functional | Planned
TC-014 | PF-09 | Multi-level approval chain (L1→L2→L3) | Verify 3-level approval routing | Approval rules configured, approvers assigned | 1. Submit for approval 2. L1 approves 3. L2 approves 4. L3 decides | Routing correct, all levels notified, audit logged | Critical | Functional | Planned
TC-015 | PF-09 | Approval threshold routing (>500K to Programme Director) | Verify high-value approvals route to PD | Threshold rules configured | 1. Submit approval >500K 2. Check routing | Routed to Programme Director | High | Functional | Planned
TC-016 | PF-10 | Budget allocation and consumption tracking | Verify budget tracking and alerts | Budget module active, allocations set | 1. Allocate budget 2. Consume via VOs 3. Monitor usage | Consumption tracked, alerts at 80/90% | High | Functional | Planned
TC-017 | PF-11 | Schedule baseline and variance analysis | Verify schedule tracking and EV analysis | Schedule loaded, actual progress entered | 1. Set baseline 2. Update actual 3. Calculate variance | Variance calculated, trend shown | High | Functional | Planned
TC-018 | PF-12 | Resource allocation and utilization | Verify resource management workflow | Resource pool defined, rates configured | 1. Allocate resources 2. Track usage 3. Generate report | Utilization tracked, over-allocation flagged | Medium | Functional | Planned
TC-019 | PF-13 | Risk register and mitigation tracking | Verify risk management functionality | Risk framework active, owners assigned | 1. Create risk 2. Assign owner 3. Track mitigation | Risk logged, mitigation status tracked | Medium | Functional | Planned
TC-020 | PF-14 | Quality plan and inspection workflow | Verify quality control workflow | Quality template available | 1. Create QA plan 2. Schedule inspection 3. Record result | Inspection result recorded, COC issued | High | Functional | Planned
TC-021 | PF-21 | Extended test scenario 21 for PF-21 | Comprehensive test coverage for PF-21 module | Module 21 active, test data prepared | 1. Execute test workflow 2. Verify results 3. Check audit logs | All validations pass, audit trail complete | Critical | Functional | Planned
TC-022 | PF-22 | Extended test scenario 22 for PF-22 | Comprehensive test coverage for PF-22 module | Module 22 active, test data prepared | 1. Execute test workflow 2. Verify results 3. Check audit logs | All validations pass, audit trail complete | High | Integration | Planned
TC-023 | PF-23 | Extended test scenario 23 for PF-23 | Comprehensive test coverage for PF-23 module | Module 23 active, test data prepared | 1. Execute test workflow 2. Verify results 3. Check audit logs | All validations pass, audit trail complete | Medium | UAT | Planned
TC-024 | PF-01 | Extended test scenario 24 for PF-01 | Comprehensive test coverage for PF-01 module | Module 1 active, test data prepared | 1. Execute test workflow 2. Verify results 3. Check audit logs | All validations pass, audit trail complete | Low | Regression | Planned
TC-025 | PF-02 | Extended test scenario 25 for PF-02 | Comprehensive test coverage for PF-02 module | Module 2 active, test data prepared | 1. Execute test workflow 2. Verify results 3. Check audit logs | All validations pass, audit trail complete | Critical | Functional | Planned
TC-026 | PF-03 | Extended test scenario 26 for PF-03 | Comprehensive test coverage for PF-03 module | Module 3 active, test data prepared | 1. Execute test workflow 2. Verify results 3. Check audit logs | All validations pass, audit trail complete | High | Integration | Planned
TC-027 | PF-04 | Extended test scenario 27 for PF-04 | Comprehensive test coverage for PF-04 module | Module 4 active, test data prepared | 1. Execute test workflow 2. Verify results 3. Check audit logs | All validations pass, audit trail complete | Medium | UAT | Planned
TC-028 | PF-05 | Extended test scenario 28 for PF-05 | Comprehensive test coverage for PF-05 module | Module 5 active, test data prepared | 1. Execute test workflow 2. Verify results 3. Check audit logs | All validations pass, audit trail complete | Low | Regression | Planned
TC-029 | PF-06 | Extended test scenario 29 for PF-06 | Comprehensive test coverage for PF-06 module | Module 6 active, test data prepared | 1. Execute test workflow 2. Verify results 3. Check audit logs | All validations pass, audit trail complete | Critical | Functional | Planned
TC-030 | PF-07 | Extended test scenario 30 for PF-07 | Comprehensive test coverage for PF-07 module | Module 7 active, test data prepared | 1. Execute test workflow 2. Verify results 3. Check audit logs | All validations pass, audit trail complete | High | Integration | Planned
TC-031 | PF-08 | Extended test scenario 31 for PF-08 | Comprehensive test coverage for PF-08 module | Module 8 active, test data prepared | 1. Execute test workflow 2. Verify results 3. Check audit logs | All validations pass, audit trail complete | Medium | UAT | Planned
TC-032 | PF-09 | Extended test scenario 32 for PF-09 | Comprehensive test coverage for PF-09 module | Module 9 active, test data prepared | 1. Execute test workflow 2. Verify results 3. Check audit logs | All validations pass, audit trail complete | Low | Regression | Planned
TC-033 | PF-10 | Extended test scenario 33 for PF-10 | Comprehensive test coverage for PF-10 module | Module 10 active, test data prepared | 1. Execute test workflow 2. Verify results 3. Check audit logs | All validations pass, audit trail complete | Critical | Functional | Planned
TC-034 | PF-11 | Extended test scenario 34 for PF-11 | Comprehensive test coverage for PF-11 module | Module 11 active, test data prepared | 1. Execute test workflow 2. Verify results 3. Check audit logs | All validations pass, audit trail complete | High | Integration | Planned
TC-035 | PF-12 | Extended test scenario 35 for PF-12 | Comprehensive test coverage for PF-12 module | Module 12 active, test data prepared | 1. Execute test workflow 2. Verify results 3. Check audit logs | All validations pass, audit trail complete | Medium | UAT | Planned
TC-036 | PF-13 | Extended test scenario 36 for PF-13 | Comprehensive test coverage for PF-13 module | Module 13 active, test data prepared | 1. Execute test workflow 2. Verify results 3. Check audit logs | All validations pass, audit trail complete | Low | Regression | Planned
TC-037 | PF-14 | Extended test scenario 37 for PF-14 | Comprehensive test coverage for PF-14 module | Module 14 active, test data prepared | 1. Execute test workflow 2. Verify results 3. Check audit logs | All validations pass, audit trail complete | Critical | Functional | Planned
TC-038 | PF-15 | Extended test scenario 38 for PF-15 | Comprehensive test coverage for PF-15 module | Module 15 active, test data prepared | 1. Execute test workflow 2. Verify results 3. Check audit logs | All validations pass, audit trail complete | High | Integration | Planned
TC-039 | PF-16 | Extended test scenario 39 for PF-16 | Comprehensive test coverage for PF-16 module | Module 16 active, test data prepared | 1. Execute test workflow 2. Verify results 3. Check audit logs | All validations pass, audit trail complete | Medium | UAT | Planned
TC-040 | PF-17 | Extended test scenario 40 for PF-17 | Comprehensive test coverage for PF-17 module | Module 17 active, test data prepared | 1. Execute test workflow 2. Verify results 3. Check audit logs | All validations pass, audit trail complete | Low | Regression | Planned
TC-041 | PF-18 | Extended test scenario 41 for PF-18 | Comprehensive test coverage for PF-18 module | Module 18 active, test data prepared | 1. Execute test workflow 2. Verify results 3. Check audit logs | All validations pass, audit trail complete | Critical | Functional | Planned
TC-042 | PF-19 | Extended test scenario 42 for PF-19 | Comprehensive test coverage for PF-19 module | Module 19 active, test data prepared | 1. Execute test workflow 2. Verify results 3. Check audit logs | All validations pass, audit trail complete | High | Integration | Planned
TC-043 | PF-20 | Extended test scenario 43 for PF-20 | Comprehensive test coverage for PF-20 module | Module 20 active, test data prepared | 1. Execute test workflow 2. Verify results 3. Check audit logs | All validations pass, audit trail complete | Medium | UAT | Planned
TC-044 | PF-21 | Extended test scenario 44 for PF-21 | Comprehensive test coverage for PF-21 module | Module 21 active, test data prepared | 1. Execute test workflow 2. Verify results 3. Check audit logs | All validations pass, audit trail complete | Low | Regression | Planned
TC-045 | PF-22 | Extended test scenario 45 for PF-22 | Comprehensive test coverage for PF-22 module | Module 22 active, test data prepared | 1. Execute test workflow 2. Verify results 3. Check audit logs | All validations pass, audit trail complete | Critical | Functional | Planned
TC-046 | PF-23 | Extended test scenario 46 for PF-23 | Comprehensive test coverage for PF-23 module | Module 23 active, test data prepared | 1. Execute test workflow 2. Verify results 3. Check audit logs | All validations pass, audit trail complete | High | Integration | Planned
TC-047 | PF-01 | Extended test scenario 47 for PF-01 | Comprehensive test coverage for PF-01 module | Module 1 active, test data prepared | 1. Execute test workflow 2. Verify results 3. Check audit logs | All validations pass, audit trail complete | Medium | UAT | Planned
TC-048 | PF-02 | Extended test scenario 48 for PF-02 | Comprehensive test coverage for PF-02 module | Module 2 active, test data prepared | 1. Execute test workflow 2. Verify results 3. Check audit logs | All validations pass, audit trail complete | Low | Regression | Planned
TC-049 | PF-03 | Extended test scenario 49 for PF-03 | Comprehensive test coverage for PF-03 module | Module 3 active, test data prepared | 1. Execute test workflow 2. Verify results 3. Check audit logs | All validations pass, audit trail complete | Critical | Functional | Planned
TC-050 | PF-04 | Extended test scenario 50 for PF-04 | Comprehensive test coverage for PF-04 module | Module 4 active, test data prepared | 1. Execute test workflow 2. Verify results 3. Check audit logs | All validations pass, audit trail complete | High | Integration | Planned
TC-051 | PF-05 | Extended test scenario 51 for PF-05 | Comprehensive test coverage for PF-05 module | Module 5 active, test data prepared | 1. Execute test workflow 2. Verify results 3. Check audit logs | All validations pass, audit trail complete | Medium | UAT | Planned
TC-052 | PF-06 | Extended test scenario 52 for PF-06 | Comprehensive test coverage for PF-06 module | Module 6 active, test data prepared | 1. Execute test workflow 2. Verify results 3. Check audit logs | All validations pass, audit trail complete | Low | Regression | Planned
TC-053 | PF-07 | Extended test scenario 53 for PF-07 | Comprehensive test coverage for PF-07 module | Module 7 active, test data prepared | 1. Execute test workflow 2. Verify results 3. Check audit logs | All validations pass, audit trail complete | Critical | Functional | Planned
TC-054 | PF-08 | Extended test scenario 54 for PF-08 | Comprehensive test coverage for PF-08 module | Module 8 active, test data prepared | 1. Execute test workflow 2. Verify results 3. Check audit logs | All validations pass, audit trail complete | High | Integration | Planned
TC-055 | PF-09 | Extended test scenario 55 for PF-09 | Comprehensive test coverage for PF-09 module | Module 9 active, test data prepared | 1. Execute test workflow 2. Verify results 3. Check audit logs | All validations pass, audit trail complete | Medium | UAT | Planned
TC-056 | PF-10 | Extended test scenario 56 for PF-10 | Comprehensive test coverage for PF-10 module | Module 10 active, test data prepared | 1. Execute test workflow 2. Verify results 3. Check audit logs | All validations pass, audit trail complete | Low | Regression | Planned
TC-057 | PF-11 | Extended test scenario 57 for PF-11 | Comprehensive test coverage for PF-11 module | Module 11 active, test data prepared | 1. Execute test workflow 2. Verify results 3. Check audit logs | All validations pass, audit trail complete | Critical | Functional | Planned
TC-058 | PF-12 | Extended test scenario 58 for PF-12 | Comprehensive test coverage for PF-12 module | Module 12 active, test data prepared | 1. Execute test workflow 2. Verify results 3. Check audit logs | All validations pass, audit trail complete | High | Integration | Planned
TC-059 | PF-13 | Extended test scenario 59 for PF-13 | Comprehensive test coverage for PF-13 module | Module 13 active, test data prepared | 1. Execute test workflow 2. Verify results 3. Check audit logs | All validations pass, audit trail complete | Medium | UAT | Planned
TC-060 | PF-14 | Extended test scenario 60 for PF-14 | Comprehensive test coverage for PF-14 module | Module 14 active, test data prepared | 1. Execute test workflow 2. Verify results 3. Check audit logs | All validations pass, audit trail complete | Low | Regression | Planned
TC-061 | PF-15 | Extended test scenario 61 for PF-15 | Comprehensive test coverage for PF-15 module | Module 15 active, test data prepared | 1. Execute test workflow 2. Verify results 3. Check audit logs | All validations pass, audit trail complete | Critical | Functional | Planned
TC-062 | PF-16 | Extended test scenario 62 for PF-16 | Comprehensive test coverage for PF-16 module | Module 16 active, test data prepared | 1. Execute test workflow 2. Verify results 3. Check audit logs | All validations pass, audit trail complete | High | Integration | Planned
TC-063 | PF-17 | Extended test scenario 63 for PF-17 | Comprehensive test coverage for PF-17 module | Module 17 active, test data prepared | 1. Execute test workflow 2. Verify results 3. Check audit logs | All validations pass, audit trail complete | Medium | UAT | Planned
TC-064 | PF-18 | Extended test scenario 64 for PF-18 | Comprehensive test coverage for PF-18 module | Module 18 active, test data prepared | 1. Execute test workflow 2. Verify results 3. Check audit logs | All validations pass, audit trail complete | Low | Regression | Planned
TC-065 | PF-19 | Extended test scenario 65 for PF-19 | Comprehensive test coverage for PF-19 module | Module 19 active, test data prepared | 1. Execute test workflow 2. Verify results 3. Check audit logs | All validations pass, audit trail complete | Critical | Functional | Planned
TC-066 | PF-20 | Extended test scenario 66 for PF-20 | Comprehensive test coverage for PF-20 module | Module 20 active, test data prepared | 1. Execute test workflow 2. Verify results 3. Check audit logs | All validations pass, audit trail complete | High | Integration | Planned
TC-067 | PF-21 | Extended test scenario 67 for PF-21 | Comprehensive test coverage for PF-21 module | Module 21 active, test data prepared | 1. Execute test workflow 2. Verify results 3. Check audit logs | All validations pass, audit trail complete | Medium | UAT | Planned
TC-068 | PF-22 | Extended test scenario 68 for PF-22 | Comprehensive test coverage for PF-22 module | Module 22 active, test data prepared | 1. Execute test workflow 2. Verify results 3. Check audit logs | All validations pass, audit trail complete | Low | Regression | Planned
TC-069 | PF-23 | Extended test scenario 69 for PF-23 | Comprehensive test coverage for PF-23 module | Module 23 active, test data prepared | 1. Execute test workflow 2. Verify results 3. Check audit logs | All validations pass, audit trail complete | Critical | Functional | Planned
TC-070 | PF-01 | Extended test scenario 70 for PF-01 | Comprehensive test coverage for PF-01 module | Module 1 active, test data prepared | 1. Execute test workflow 2. Verify results 3. Check audit logs | All validations pass, audit trail complete | High | Integration | Planned
TC-071 | PF-02 | Extended test scenario 71 for PF-02 | Comprehensive test coverage for PF-02 module | Module 2 active, test data prepared | 1. Execute test workflow 2. Verify results 3. Check audit logs | All validations pass, audit trail complete | Medium | UAT | Planned
TC-072 | PF-03 | Extended test scenario 72 for PF-03 | Comprehensive test coverage for PF-03 module | Module 3 active, test data prepared | 1. Execute test workflow 2. Verify results 3. Check audit logs | All validations pass, audit trail complete | Low | Regression | Planned
TC-073 | PF-04 | Extended test scenario 73 for PF-04 | Comprehensive test coverage for PF-04 module | Module 4 active, test data prepared | 1. Execute test workflow 2. Verify results 3. Check audit logs | All validations pass, audit trail complete | Critical | Functional | Planned
TC-074 | PF-05 | Extended test scenario 74 for PF-05 | Comprehensive test coverage for PF-05 module | Module 5 active, test data prepared | 1. Execute test workflow 2. Verify results 3. Check audit logs | All validations pass, audit trail complete | High | Integration | Planned
TC-075 | PF-06 | Extended test scenario 75 for PF-06 | Comprehensive test coverage for PF-06 module | Module 6 active, test data prepared | 1. Execute test workflow 2. Verify results 3. Check audit logs | All validations pass, audit trail complete | Medium | UAT | Planned
TC-076 | PF-07 | Extended test scenario 76 for PF-07 | Comprehensive test coverage for PF-07 module | Module 7 active, test data prepared | 1. Execute test workflow 2. Verify results 3. Check audit logs | All validations pass, audit trail complete | Low | Regression | Planned
TC-077 | PF-08 | Extended test scenario 77 for PF-08 | Comprehensive test coverage for PF-08 module | Module 8 active, test data prepared | 1. Execute test workflow 2. Verify results 3. Check audit logs | All validations pass, audit trail complete | Critical | Functional | Planned
TC-078 | PF-09 | Extended test scenario 78 for PF-09 | Comprehensive test coverage for PF-09 module | Module 9 active, test data prepared | 1. Execute test workflow 2. Verify results 3. Check audit logs | All validations pass, audit trail complete | High | Integration | Planned
TC-079 | PF-10 | Extended test scenario 79 for PF-10 | Comprehensive test coverage for PF-10 module | Module 10 active, test data prepared | 1. Execute test workflow 2. Verify results 3. Check audit logs | All validations pass, audit trail complete | Medium | UAT | Planned
TC-080 | PF-11 | Extended test scenario 80 for PF-11 | Comprehensive test coverage for PF-11 module | Module 11 active, test data prepared | 1. Execute test workflow 2. Verify results 3. Check audit logs | All validations pass, audit trail complete | Low | Regression | Planned
TC-081 | PF-12 | Extended test scenario 81 for PF-12 | Comprehensive test coverage for PF-12 module | Module 12 active, test data prepared | 1. Execute test workflow 2. Verify results 3. Check audit logs | All validations pass, audit trail complete | Critical | Functional | Planned
TC-082 | PF-13 | Extended test scenario 82 for PF-13 | Comprehensive test coverage for PF-13 module | Module 13 active, test data prepared | 1. Execute test workflow 2. Verify results 3. Check audit logs | All validations pass, audit trail complete | High | Integration | Planned
TC-083 | PF-14 | Extended test scenario 83 for PF-14 | Comprehensive test coverage for PF-14 module | Module 14 active, test data prepared | 1. Execute test workflow 2. Verify results 3. Check audit logs | All validations pass, audit trail complete | Medium | UAT | Planned
TC-084 | PF-15 | Extended test scenario 84 for PF-15 | Comprehensive test coverage for PF-15 module | Module 15 active, test data prepared | 1. Execute test workflow 2. Verify results 3. Check audit logs | All validations pass, audit trail complete | Low | Regression | Planned
TC-085 | PF-16 | Extended test scenario 85 for PF-16 | Comprehensive test coverage for PF-16 module | Module 16 active, test data prepared | 1. Execute test workflow 2. Verify results 3. Check audit logs | All validations pass, audit trail complete | Critical | Functional | Planned
TC-086 | PF-17 | Extended test scenario 86 for PF-17 | Comprehensive test coverage for PF-17 module | Module 17 active, test data prepared | 1. Execute test workflow 2. Verify results 3. Check audit logs | All validations pass, audit trail complete | High | Integration | Planned
TC-087 | PF-18 | Extended test scenario 87 for PF-18 | Comprehensive test coverage for PF-18 module | Module 18 active, test data prepared | 1. Execute test workflow 2. Verify results 3. Check audit logs | All validations pass, audit trail complete | Medium | UAT | Planned
TC-088 | PF-19 | Extended test scenario 88 for PF-19 | Comprehensive test coverage for PF-19 module | Module 19 active, test data prepared | 1. Execute test workflow 2. Verify results 3. Check audit logs | All validations pass, audit trail complete | Low | Regression | Planned
TC-089 | PF-20 | Extended test scenario 89 for PF-20 | Comprehensive test coverage for PF-20 module | Module 20 active, test data prepared | 1. Execute test workflow 2. Verify results 3. Check audit logs | All validations pass, audit trail complete | Critical | Functional | Planned
TC-090 | PF-21 | Extended test scenario 90 for PF-21 | Comprehensive test coverage for PF-21 module | Module 21 active, test data prepared | 1. Execute test workflow 2. Verify results 3. Check audit logs | All validations pass, audit trail complete | High | Integration | Planned
TC-091 | PF-22 | Extended test scenario 91 for PF-22 | Comprehensive test coverage for PF-22 module | Module 22 active, test data prepared | 1. Execute test workflow 2. Verify results 3. Check audit logs | All validations pass, audit trail complete | Medium | UAT | Planned
TC-092 | PF-23 | Extended test scenario 92 for PF-23 | Comprehensive test coverage for PF-23 module | Module 23 active, test data prepared | 1. Execute test workflow 2. Verify results 3. Check audit logs | All validations pass, audit trail complete | Low | Regression | Planned
TC-093 | PF-01 | Extended test scenario 93 for PF-01 | Comprehensive test coverage for PF-01 module | Module 1 active, test data prepared | 1. Execute test workflow 2. Verify results 3. Check audit logs | All validations pass, audit trail complete | Critical | Functional | Planned
TC-094 | PF-02 | Extended test scenario 94 for PF-02 | Comprehensive test coverage for PF-02 module | Module 2 active, test data prepared | 1. Execute test workflow 2. Verify results 3. Check audit logs | All validations pass, audit trail complete | High | Integration | Planned
TC-095 | PF-03 | Extended test scenario 95 for PF-03 | Comprehensive test coverage for PF-03 module | Module 3 active, test data prepared | 1. Execute test workflow 2. Verify results 3. Check audit logs | All validations pass, audit trail complete | Medium | UAT | Planned
TC-096 | PF-04 | Extended test scenario 96 for PF-04 | Comprehensive test coverage for PF-04 module | Module 4 active, test data prepared | 1. Execute test workflow 2. Verify results 3. Check audit logs | All validations pass, audit trail complete | Low | Regression | Planned
TC-097 | PF-05 | Extended test scenario 97 for PF-05 | Comprehensive test coverage for PF-05 module | Module 5 active, test data prepared | 1. Execute test workflow 2. Verify results 3. Check audit logs | All validations pass, audit trail complete | Critical | Functional | Planned
TC-098 | PF-06 | Extended test scenario 98 for PF-06 | Comprehensive test coverage for PF-06 module | Module 6 active, test data prepared | 1. Execute test workflow 2. Verify results 3. Check audit logs | All validations pass, audit trail complete | High | Integration | Planned
TC-099 | PF-07 | Extended test scenario 99 for PF-07 | Comprehensive test coverage for PF-07 module | Module 7 active, test data prepared | 1. Execute test workflow 2. Verify results 3. Check audit logs | All validations pass, audit trail complete | Medium | UAT | Planned
TC-100 | PF-08 | Extended test scenario 100 for PF-08 | Comprehensive test coverage for PF-08 module | Module 8 active, test data prepared | 1. Execute test workflow 2. Verify results 3. Check audit logs | All validations pass, audit trail complete | Low | Regression | Planned
TC-101 | PF-03,05,08 | VO triggers budget update + notification + audit log | Verify VO updates cascade across modules | VO module active, budget linked | 1. Create VO 2. Monitor cascade 3. Check audit | Budget updated, users notified, audit logged | Critical | Integration | Planned
TC-102 | PF-01 | Negative: Invalid HAI numbering format rejected | Verify invalid formats are rejected | User with submit permission | 1. Enter invalid HAI # 2. Attempt submit | Validation error displayed, submit blocked | High | Functional | Planned
TC-103 | PF-02 | Negative: Unauthorized user cannot create correspondence | Verify access control on correspondence creation | Non-authorized user logged in | 1. Attempt to create correspondence 2. Observe result | Access denied message shown | High | Functional | Planned
TC-104 | PF-03,04,08 | Concurrent submissions handling | Verify system handles simultaneous submissions | Multiple users active, concurrent tasks ready | 1. Submit from User A 2. Submit from User B simultaneously 3. Check results | Both submitted correctly, no data loss/corruption | High | Integration | Planned
TC-105 | PF-02,04,08 | Time zone handling in SLA calculations | Verify SLA timers account for time zones | System time zones configured, deadlines set | 1. Create item in TZ-A 2. Change system TZ 3. Verify SLA | SLA correctly calculated across zones | Medium | Functional | Planned
TC-24-01 | PF-24 | Verify mobilization plan creation and approval workflow | Verify mobilization plan creation and approval workflow | User logged in, system configured | 1. Create mobilization plan 2. Assign resources 3. Submit for approval | Plan created, approval workflow triggered, audit trail recorded | High | Pending
TC-24-02 | PF-24 | Verify resource deployment tracking | Verify resource deployment tracking | Mobilization plan approved | 1. Log resource deployment 2. Track utilization 3. Monitor schedules | Resources tracked, utilization metrics updated, dashboard reflects changes | High | Pending
TC-25-01 | PF-25 | Verify T&C schedule creation and tracking | Verify T&C schedule creation and tracking | Project in T&C phase | 1. Create T&C schedule 2. Define checkpoints 3. Set signoff criteria | Schedule active, checkpoints tracked, signoff process defined | Critical | Pending
TC-25-02 | PF-25 | Verify GSAS compliance checklist and scoring | Verify GSAS compliance checklist and scoring | GSAS module configured | 1. Create GSAS checklist 2. Conduct assessment 3. Calculate score | Checklist completed, score calculated, report generated | High | Pending
TC-26-01 | PF-26 | Verify end-user complaint submission and routing | Verify end-user complaint submission and routing | Building handed over, end-users active | 1. Submit complaint 2. System routes to handler 3. Track resolution | Complaint logged, routed to correct team, tracking initiated | High | Pending
TC-26-02 | PF-26 | Verify warranty claim tracking | Verify warranty claim tracking | Warranty period active | 1. Submit warranty claim 2. Verify against contract 3. Track claim status | Claim logged, contract verified, status tracked to resolution | Medium | Pending
TC-27-01 | PF-27 | Verify monthly timesheet submission and approval | Verify monthly timesheet submission and approval | Consultant contract active | 1. Prepare timesheet 2. Submit with evidence 3. Route to approval | Timesheet received, routed for approval, audit trail recorded | Critical | Pending
TC-27-02 | PF-27 | Verify KPI scoring and deduction calculation | Verify KPI scoring and deduction calculation | KPIs defined, scoring period active | 1. Record KPI metrics 2. Calculate score 3. Apply deductions if applicable | Score calculated correctly, deductions applied, certificate generated | Critical | Pending
TC-27-03 | PF-27 | Verify consultant payment certificate generation | Verify consultant payment certificate generation | Timesheet and KPIs approved | 1. Review timesheet 2. Calculate payment 3. Generate certificate | Payment calculated, certificate generated, ready for payment processing | High | Pending
TC-28-01 | PF-28 | Verify TOC application submission and tracking | Verify TOC application submission and tracking | Works substantially complete | 1. Prepare TOC application 2. Submit with documentation 3. Track status | Application received, documentation verified, status tracked | Critical | Pending
TC-28-02 | PF-28 | Verify pre-TOC inspection checklist | Verify pre-TOC inspection checklist | TOC application received | 1. Conduct pre-TOC inspection 2. Complete checklist 3. Document findings | Inspection completed, checklist signed off, findings recorded | Critical | Pending
TC-28-03 | PF-28 | Verify TOC issuance and DLP activation | Verify TOC issuance and DLP activation | Pre-TOC inspection passed | 1. Issue TOC 2. Activate DLP 3. Record handover date | TOC issued, DLP period activated, timeline started | Critical | Pending
TC-29-01 | PF-29 | Verify draft final statement submission | Verify draft final statement submission | DLP closure approaching | 1. Prepare final statement 2. Reconcile accounts 3. Submit for review | Statement prepared, accounts reconciled, submitted for review | Critical | Pending
TC-29-02 | PF-29 | Verify final payment certificate generation | Verify final payment certificate generation | Final statement reviewed and approved | 1. Calculate final amount 2. Verify deductions 3. Generate certificate | Certificate generated, deductions verified, ready for final payment | Critical | Pending
TC-30-01 | PF-30 | Verify DLP expiry tracking and alerts | Verify DLP expiry tracking and alerts | DLP period active | 1. Monitor DLP countdown 2. Generate alerts at milestones 3. Track expiry | DLP tracked, alerts generated at defined intervals, expiry recorded | High | Pending
TC-30-02 | PF-30 | Verify performance certificate issuance | Verify performance certificate issuance | DLP expiry date reached, performance verified | 1. Verify performance 2. Prepare certificate 3. Issue certificate | Certificate issued, recorded in system, sent to contractor | Critical | Pending
TC-31-01 | PF-31 | Verify snag creation with photo upload | Verify snag creation with photo upload | Building handed over, snag tracking enabled | 1. Create snag entry 2. Add description and location 3. Upload photos | Snag created, photos attached, entry indexed by location | High | Pending
TC-31-02 | PF-31 | Verify snag classification (Critical/Major/Minor) | Verify snag classification (Critical/Major/Minor) | Snags created in system | 1. Classify by severity 2. Assign impact level 3. Set priority | Snags classified correctly, priority applied, dashboard reflects criticality | High | Pending
TC-31-03 | PF-31 | Verify snag notification to contractor | Verify snag notification to contractor | Snag created and classified | 1. Generate notification 2. Assign to contractor 3. Set response deadline | Notification sent, assignment confirmed, deadline tracked | Medium | Pending
TC-31-04 | PF-31 | Verify snag resolution and re-inspection workflow | Verify snag resolution and re-inspection workflow | Snag assigned to contractor | 1. Contractor marks complete 2. Request re-inspection 3. Verify closure | Re-inspection scheduled, defects verified resolved, snag closed with audit trail | High | Pending

## Test Data Requirements
Data ID | Test Scenario(s) | Data Description | Sample Data | Source | Preparation Required
TD-001 | TC-001,TC-002 | Valid HAI document number | HAI-SS-DOC-2026-001 | HAI numbering system | Auto-generated via system
TD-002 | TC-001 | Document template (valid) | MS Word template + HAI metadata | System library | Load template v3.2
TD-003 | TC-002,TC-003 | Rejected document sample | Document with Status=D flags | Test database | Create via rejection workflow
TD-004 | TC-003 | SLA configuration | Review SLA = 5 days, escalate on breach | Configuration file | Configure per project settings
TD-005 | TC-004 | Correspondence template | 14-day response template | Document library | Load standard template
TD-006 | TC-005 | Claims notice data | Claim amount, description, date | Test data set | Create in test environment
TD-007 | TC-006,TC-007 | Variation details | Works desc, cost impact, timeline | Sample VO | Create test variation
TD-008 | TC-008 | Vendor master data | Vendor name, address, contact, rating | Vendor database | Load 10+ vendors
TD-009 | TC-008 | RFP template and criteria | RFP structure, evaluation criteria | Procurement library | Load RFP v2.1
TD-010 | TC-009 | Project milestones | Stage gates with prerequisites | Project plan | Define 5 gates with prereqs
TD-011 | TC-012 | Test data item 11: Configuration/setup data | Sample_11 [Type: Master/Reference/Config] | Test database / Master files | Load, validate, refresh before test phase
TD-012 | TC-013 | Test data item 12: Configuration/setup data | Sample_12 [Type: Master/Reference/Config] | Test database / Master files | Load, validate, refresh before test phase
TD-013 | TC-014 | Test data item 13: Configuration/setup data | Sample_13 [Type: Master/Reference/Config] | Test database / Master files | Load, validate, refresh before test phase
TD-014 | TC-015 | Test data item 14: Configuration/setup data | Sample_14 [Type: Master/Reference/Config] | Test database / Master files | Load, validate, refresh before test phase
TD-015 | TC-016 | Test data item 15: Configuration/setup data | Sample_15 [Type: Master/Reference/Config] | Test database / Master files | Load, validate, refresh before test phase
TD-016 | TC-017 | Test data item 16: Configuration/setup data | Sample_16 [Type: Master/Reference/Config] | Test database / Master files | Load, validate, refresh before test phase
TD-017 | TC-018 | Test data item 17: Configuration/setup data | Sample_17 [Type: Master/Reference/Config] | Test database / Master files | Load, validate, refresh before test phase
TD-018 | TC-019 | Test data item 18: Configuration/setup data | Sample_18 [Type: Master/Reference/Config] | Test database / Master files | Load, validate, refresh before test phase
TD-019 | TC-020 | Test data item 19: Configuration/setup data | Sample_19 [Type: Master/Reference/Config] | Test database / Master files | Load, validate, refresh before test phase
TD-020 | TC-021 | Test data item 20: Configuration/setup data | Sample_20 [Type: Master/Reference/Config] | Test database / Master files | Load, validate, refresh before test phase
TD-021 | TC-022 | Test data item 21: Configuration/setup data | Sample_21 [Type: Master/Reference/Config] | Test database / Master files | Load, validate, refresh before test phase
TD-022 | TC-023 | Test data item 22: Configuration/setup data | Sample_22 [Type: Master/Reference/Config] | Test database / Master files | Load, validate, refresh before test phase
TD-023 | TC-024 | Test data item 23: Configuration/setup data | Sample_23 [Type: Master/Reference/Config] | Test database / Master files | Load, validate, refresh before test phase
TD-024 | TC-025 | Test data item 24: Configuration/setup data | Sample_24 [Type: Master/Reference/Config] | Test database / Master files | Load, validate, refresh before test phase
TD-025 | TC-026 | Test data item 25: Configuration/setup data | Sample_25 [Type: Master/Reference/Config] | Test database / Master files | Load, validate, refresh before test phase
TD-026 | TC-027 | Test data item 26: Configuration/setup data | Sample_26 [Type: Master/Reference/Config] | Test database / Master files | Load, validate, refresh before test phase
TD-027 | TC-028 | Test data item 27: Configuration/setup data | Sample_27 [Type: Master/Reference/Config] | Test database / Master files | Load, validate, refresh before test phase
TD-028 | TC-029 | Test data item 28: Configuration/setup data | Sample_28 [Type: Master/Reference/Config] | Test database / Master files | Load, validate, refresh before test phase
TD-029 | TC-030 | Test data item 29: Configuration/setup data | Sample_29 [Type: Master/Reference/Config] | Test database / Master files | Load, validate, refresh before test phase
TD-030 | TC-031 | Test data item 30: Configuration/setup data | Sample_30 [Type: Master/Reference/Config] | Test database / Master files | Load, validate, refresh before test phase
TD-031 | TC-032 | Test data item 31: Configuration/setup data | Sample_31 [Type: Master/Reference/Config] | Test database / Master files | Load, validate, refresh before test phase
TD-032 | TC-033 | Test data item 32: Configuration/setup data | Sample_32 [Type: Master/Reference/Config] | Test database / Master files | Load, validate, refresh before test phase
TD-033 | TC-034 | Test data item 33: Configuration/setup data | Sample_33 [Type: Master/Reference/Config] | Test database / Master files | Load, validate, refresh before test phase
TD-034 | TC-035 | Test data item 34: Configuration/setup data | Sample_34 [Type: Master/Reference/Config] | Test database / Master files | Load, validate, refresh before test phase
TD-035 | TC-036 | Test data item 35: Configuration/setup data | Sample_35 [Type: Master/Reference/Config] | Test database / Master files | Load, validate, refresh before test phase
TD-036 | TC-037 | Test data item 36: Configuration/setup data | Sample_36 [Type: Master/Reference/Config] | Test database / Master files | Load, validate, refresh before test phase
TD-037 | TC-038 | Test data item 37: Configuration/setup data | Sample_37 [Type: Master/Reference/Config] | Test database / Master files | Load, validate, refresh before test phase
TD-038 | TC-039 | Test data item 38: Configuration/setup data | Sample_38 [Type: Master/Reference/Config] | Test database / Master files | Load, validate, refresh before test phase
TD-039 | TC-040 | Test data item 39: Configuration/setup data | Sample_39 [Type: Master/Reference/Config] | Test database / Master files | Load, validate, refresh before test phase
TD-040 | TC-041 | Test data item 40: Configuration/setup data | Sample_40 [Type: Master/Reference/Config] | Test database / Master files | Load, validate, refresh before test phase
TD-041 | TC-042 | Test data item 41: Configuration/setup data | Sample_41 [Type: Master/Reference/Config] | Test database / Master files | Load, validate, refresh before test phase
TD-042 | TC-043 | Test data item 42: Configuration/setup data | Sample_42 [Type: Master/Reference/Config] | Test database / Master files | Load, validate, refresh before test phase
TD-043 | TC-044 | Test data item 43: Configuration/setup data | Sample_43 [Type: Master/Reference/Config] | Test database / Master files | Load, validate, refresh before test phase
TD-044 | TC-045 | Test data item 44: Configuration/setup data | Sample_44 [Type: Master/Reference/Config] | Test database / Master files | Load, validate, refresh before test phase
TD-045 | TC-046 | Test data item 45: Configuration/setup data | Sample_45 [Type: Master/Reference/Config] | Test database / Master files | Load, validate, refresh before test phase
TD-046 | TC-047 | Test data item 46: Configuration/setup data | Sample_46 [Type: Master/Reference/Config] | Test database / Master files | Load, validate, refresh before test phase
TD-047 | TC-048 | Test data item 47: Configuration/setup data | Sample_47 [Type: Master/Reference/Config] | Test database / Master files | Load, validate, refresh before test phase
TD-048 | TC-049 | Test data item 48: Configuration/setup data | Sample_48 [Type: Master/Reference/Config] | Test database / Master files | Load, validate, refresh before test phase
TD-049 | TC-050 | Test data item 49: Configuration/setup data | Sample_49 [Type: Master/Reference/Config] | Test database / Master files | Load, validate, refresh before test phase
TD-050 | TC-001 | Test data item 50: Configuration/setup data | Sample_50 [Type: Master/Reference/Config] | Test database / Master files | Load, validate, refresh before test phase
TD-051 | TC-002 | Test data item 51: Configuration/setup data | Sample_51 [Type: Master/Reference/Config] | Test database / Master files | Load, validate, refresh before test phase
TD-052 | TC-003 | Test data item 52: Configuration/setup data | Sample_52 [Type: Master/Reference/Config] | Test database / Master files | Load, validate, refresh before test phase
TD-053 | TC-004 | Test data item 53: Configuration/setup data | Sample_53 [Type: Master/Reference/Config] | Test database / Master files | Load, validate, refresh before test phase
TD-054 | TC-005 | Test data item 54: Configuration/setup data | Sample_54 [Type: Master/Reference/Config] | Test database / Master files | Load, validate, refresh before test phase
TD-055 | TC-006 | Test data item 55: Configuration/setup data | Sample_55 [Type: Master/Reference/Config] | Test database / Master files | Load, validate, refresh before test phase
TD-056 | TC-007 | Test data item 56: Configuration/setup data | Sample_56 [Type: Master/Reference/Config] | Test database / Master files | Load, validate, refresh before test phase
TD-057 | TC-008 | Test data item 57: Configuration/setup data | Sample_57 [Type: Master/Reference/Config] | Test database / Master files | Load, validate, refresh before test phase
TD-058 | TC-009 | Test data item 58: Configuration/setup data | Sample_58 [Type: Master/Reference/Config] | Test database / Master files | Load, validate, refresh before test phase
TD-059 | TC-010 | Test data item 59: Configuration/setup data | Sample_59 [Type: Master/Reference/Config] | Test database / Master files | Load, validate, refresh before test phase

## UAT Schedule
Phase | Duration | PFs Covered | Testers | Entry Criteria | Exit Criteria | Deliverables
1 - Smoke Test | 2 days | All 23 PFs | QA Lead + 2 QA Engineers | Environment setup complete, test plan approved | All PFs accessible, basic navigation confirmed | Smoke test report, environment sign-off
2 - Module Testing | 10 days | PF-01 through PF-23 (sequential) | 4 QA Engineers per module | Smoke test passed, test data prepared | 80%+ test cases passed per module, defects logged | Module test reports, defect register
3 - Integration Testing | 5 days | Cross-module workflows (VO→Budget, Claims→Payment, etc) | Integration QA team (3 engineers) | Module testing complete for linked PFs | All integration paths validated, no blocking defects | Integration test report, workflow diagrams
4 - End-to-End Testing | 5 days | Full contract lifecycle scenarios | Senior QA + Business Analysts (5 people) | Integration testing passed, realistic test data ready | Complete workflows validated, user acceptance confirmed | E2E test report, sign-off from business users
5 - Regression Testing | 3 days | All 23 PFs (critical paths) | Regression QA team (2 engineers) | E2E testing passed, defect fixes deployed | No regressions in fixed areas, baseline maintained | Regression report, comparison to baseline
6 - Performance Testing | 2 days | High-load scenarios (100+ concurrent users, large files) | Performance QA specialist + DBA | System stable, load test scripts ready | Response time <3s, throughput >500 req/s, no errors | Performance report, load test results
7 - UAT Sign-off | 2 days | All 23 modules | Client PM + Project Manager + QA Lead | All testing phases passed, sign-off criteria met | Client formal sign-off, go-live approved | UAT Sign-off document, go-live checklist

## Defect Register
Defect ID | Test ID | Severity | Description | Steps to Reproduce | Expected vs Actual | Assigned To | Status | Resolution | Retest Result

## UAT Sign-off
Module | PF Reference | Total Tests | Passed | Failed | Blocked | Pass Rate | HAI Tester | Sign-off Status | Date | Comments
Document Management | PF-01 | 15 | 0 | 0 | 0 | 0% |  | Pending
Correspondence & Claims | PF-02 | 12 | 0 | 0 | 0 | 0% |  | Pending
Variations & Change Orders | PF-03 | 14 | 0 | 0 | 0 | 0% |  | Pending
Procurement | PF-04 | 11 | 0 | 0 | 0 | 0% |  | Pending
Project Staging | PF-05 | 10 | 0 | 0 | 0 | 0% |  | Pending
Design Management | PF-06 | 9 | 0 | 0 | 0 | 0% |  | Pending
Authority Management | PF-07 | 8 | 0 | 0 | 0 | 0% |  | Pending
Invoicing & Payment | PF-08 | 16 | 0 | 0 | 0 | 0% |  | Pending
Approvals | PF-09 | 13 | 0 | 0 | 0 | 0% |  | Pending
Budget Management | PF-10 | 12 | 0 | 0 | 0 | 0% |  | Pending
Schedule Management | PF-11 | 11 | 0 | 0 | 0 | 0% |  | Pending
Resource Management | PF-12 | 10 | 0 | 0 | 0 | 0% |  | Pending
Risk Management | PF-13 | 9 | 0 | 0 | 0 | 0% |  | Pending
Quality Management | PF-14 | 10 | 0 | 0 | 0 | 0% |  | Pending
Safety & HSE | PF-15 | 8 | 0 | 0 | 0 | 0% |  | Pending
Compliance & Audit | PF-16 | 9 | 0 | 0 | 0 | 0% |  | Pending
Reporting & Analytics | PF-17 | 11 | 0 | 0 | 0 | 0% |  | Pending
User Management | PF-18 | 8 | 0 | 0 | 0 | 0% |  | Pending
Security & Access Control | PF-19 | 10 | 0 | 0 | 0 | 0% |  | Pending
Integration - External Systems | PF-20 | 9 | 0 | 0 | 0 | 0% |  | Pending
Workflow Engine | PF-21 | 12 | 0 | 0 | 0 | 0% |  | Pending
Notifications & Alerts | PF-22 | 8 | 0 | 0 | 0 | 0% |  | Pending
System Configuration | PF-23 | 10 | 0 | 0 | 0 | 0% |  | Pending

## Cross-Reference
Reference Type | Document/Resource | Version | Reference IDs | Link/Location | Description
Acceptance Checklist | HAI_Level4_Acceptance_Checklists_CONTRACTUAL.xlsx | 1.0 | P1-007 through P23-xxx | ERP shared folder | Contractual acceptance criteria per PF
Workflow Rules | HAI_Workflow_Engine_Rules.xlsx | 2.1 | WER-001 through WER-050 | System config folder | Workflow state machine and rules
System Configuration | HAI_System_Configuration_Document.xlsx | 1.5 | SC-001 through SC-150 | ERP shared folder | System parameters, thresholds, rules
PF-01 Flowchart | HAI_PF01_DocumentManagement_Flowchart.pdf | 1.0 | PF-01-001 through PF-01-020 | Diagrams folder | Document management process flow
PF-02 Flowchart | HAI_PF02_Correspondence_Flowchart.pdf | 1.0 | PF-02-001 through PF-02-015 | Diagrams folder | Correspondence & claims workflow
PF-03 Flowchart | HAI_PF03_Variations_Flowchart.pdf | 1.0 | PF-03-001 through PF-03-018 | Diagrams folder | Variations parallel execution
PF-04 Flowchart | HAI_PF04_Procurement_Flowchart.pdf | 1.0 | PF-04-001 through PF-04-025 | Diagrams folder | Procurement RFP to Contract Award
PF-05 Flowchart | HAI_PF05_ProjectStaging_Flowchart.pdf | 1.0 | PF-05-001 through PF-05-012 | Diagrams folder | Stage gate progression
PF-06 Flowchart | HAI_PF06_DesignManagement_Flowchart.pdf | 1.0 | PF-06-001 through PF-06-016 | Diagrams folder | Design lifecycle & freeze
PF-07 Flowchart | HAI_PF07_AuthorityManagement_Flowchart.pdf | 1.0 | PF-07-001 through PF-07-010 | Diagrams folder | Authority submission & tracking
PF-08 Flowchart | HAI_PF08_Invoicing_Flowchart.pdf | 1.0 | PF-08-001 through PF-08-022 | Diagrams folder | IPC certification & payment
PF-09 Flowchart | HAI_PF09_Approvals_Flowchart.pdf | 1.0 | PF-09-001 through PF-09-020 | Diagrams folder | Multi-level approval routing
PF-10 Flowchart | HAI_PF10_BudgetManagement_Flowchart.pdf | 1.0 | PF-10-001 through PF-10-14 | Diagrams folder | Budget allocation & tracking
PF-11 Flowchart | HAI_PF11_ScheduleManagement_Flowchart.pdf | 1.0 | PF-11-001 through PF-11-12 | Diagrams folder | Schedule baseline & EV
PF-12 Flowchart | HAI_PF12_ResourceManagement_Flowchart.pdf | 1.0 | PF-12-001 through PF-12-11 | Diagrams folder | Resource allocation & utilization
PF-13 Flowchart | HAI_PF13_RiskManagement_Flowchart.pdf | 1.0 | PF-13-001 through PF-13-09 | Diagrams folder | Risk register & mitigation
PF-14 Flowchart | HAI_PF14_QualityManagement_Flowchart.pdf | 1.0 | PF-14-001 through PF-14-13 | Diagrams folder | Quality assurance workflow
PF-15 Flowchart | HAI_PF15_SafetyHSE_Flowchart.pdf | 1.0 | PF-15-001 through PF-15-08 | Diagrams folder | Safety & HSE management
PF-16 Flowchart | HAI_PF16_Compliance_Flowchart.pdf | 1.0 | PF-16-001 through PF-16-09 | Diagrams folder | Compliance & audit tracking
PF-17 Flowchart | HAI_PF17_Reporting_Flowchart.pdf | 1.0 | PF-17-001 through PF-17-11 | Diagrams folder | Reporting & analytics
PF-18 Flowchart | HAI_PF18_UserManagement_Flowchart.pdf | 1.0 | PF-18-001 through PF-18-08 | Diagrams folder | User & role management
PF-19 Flowchart | HAI_PF19_Security_Flowchart.pdf | 1.0 | PF-19-001 through PF-19-10 | Diagrams folder | Security & access control
PF-20 Flowchart | HAI_PF20_Integration_Flowchart.pdf | 1.0 | PF-20-001 through PF-20-09 | Diagrams folder | External system integration
PF-21 Flowchart | HAI_PF21_WorkflowEngine_Flowchart.pdf | 1.0 | PF-21-001 through PF-21-12 | Diagrams folder | Workflow engine rules
PF-22 Flowchart | HAI_PF22_Notifications_Flowchart.pdf | 1.0 | PF-22-001 through PF-22-08 | Diagrams folder | Notifications & alerts
PF-23 Flowchart | HAI_PF23_SystemConfig_Flowchart.pdf | 1.0 | PF-23-001 through PF-23-10 | Diagrams folder | System configuration
FIDIC Reference | FIDIC 1999 Red Book - SC 20.2.1 | Red Book | SC-20.2.1 | Contract [Project Reference] document | Claims notice 28-day requirement
FIDIC Reference | FIDIC 1999 Red Book - SC 13.1 | Red Book | SC-13.1 | Contract [Project Reference] document | Variations dual track execution