## Migration Scope
HAI SkyStruct Platform - Migration Specification ¦ Document ID: HAI-SS-MIG-2026-001
Migration ID | Data Category | Source System | Volume Estimate | Priority | Target Module | PF Reference | Status
MIG-01 | Existing Project Documents | File server/SharePoint | ~5000 docs | Critical | EDMS | PF-01 | Ready
MIG-02 | Correspondence History | Email/existing system | ~2000 letters | High | Correspondence | PF-02 | Ready
MIG-03 | Variation Orders | Excel/manual | ~50 VOs | Critical | Variations | PF-03 | Ready
MIG-04 | IPC History | Excel | ~12 IPCs | Critical | IPC | PF-08 | Ready
MIG-05 | Budget Data | ERP/Excel | Full budget | Critical | Budget | PF-11 | Ready
MIG-06 | Risk Register | Excel | ~100 risks | High | Risk | PF-12 | Ready
MIG-07 | Meeting Minutes | Word/PDF | ~200 records | Medium | Meetings | PF-16 | Ready
MIG-08 | Contractor Submissions | Various | ~3000 items | High | EDMS | PF-01 | Ready
MIG-09 | Drawing Register | Excel | ~2000 drawings | Critical | EDMS | PF-01 | Ready
MIG-10 | Claims Register | Excel | ~20 claims | Critical | Correspondence | PF-02 | Ready
MIG-11 | User Accounts | AD/Manual | ~50 users | Critical | User Mgmt | PF-19 | Ready
MIG-12 | Authority Submissions | Manual | ~30 submissions | High | Authority | PF-07 | Ready
MIG-13 | Quality Records | Various | ~500 records | High | Quality | PF-10 | Ready
MIG-14 | Programme/Schedule | P6/MS Project | Full programme | Critical | Stage Gates | PF-05 | Ready
MIG-15 | Lessons Learned | Manual | ~20 entries | Low | Lessons | PF-14 | Ready

## Migration Plan
Phase | Phase Name | Description | Start | Duration | Dependencies | Deliverables | Owner | Status
1 | Assessment | Initial data audit and requirements analysis | 2026-04-01 | 2 weeks | Project approval | Assessment Report | Migration Lead | Not Started
2 | Data Cleansing | Source data validation and cleansing | 2026-04-15 | 3 weeks | Phase 1 complete | Cleansed Data Sets | Data Team | Not Started
3 | Mapping & Transform | Field mapping and transformation rules definition | 2026-05-06 | 2 weeks | Phase 2 complete | Mapping Document | Technical Team | Not Started
4 | Trial Migration | Test migration with sample data | 2026-05-20 | 2 weeks | Phase 3 complete | Trial Report | QA Team | Not Started
5 | Validation | Comprehensive data validation | 2026-06-03 | 2 weeks | Phase 4 complete | Validation Report | QA Lead | Not Started
6 | Production Migration | Full production data migration | 2026-06-17 | 1 week | Phase 5 signed off | Migration Logs | Migration Lead | Not Started
7 | Post-Migration Verification | Production verification and closeout | 2026-06-24 | 1 week | Phase 6 complete | Closeout Report | Project Manager | Not Started

## Data Mapping
Source Field | Source Format | Target Field | Target Format | Transformation Rule | Validation | Notes
Document_ID | Text (Legacy) | DOC_ID | UUID | Generate UUID from legacy ID | Non-null, unique | EDMS standard
Document_Title | Text | TITLE | Text (max 500) | Trim whitespace | Non-null
Document_Date | Date (DD/MM/YYYY) | CREATED_DATE | ISO 8601 | Convert format | Valid date
Document_Type | Dropdown (legacy) | DOC_TYPE | Lookup table | Map using lookup | In DOC_TYPE table | EDMS classification
Document_Source | Free text | SOURCE_SYSTEM | Text | Standardize values | In allowed list
Letter_ID | Text | CORR_ID | UUID | Generate UUID | Non-null, unique
Letter_Date | Date | CORR_DATE | ISO 8601 | Convert format | Valid date
Letter_From | Text | FROM_PARTY | Foreign Key | Match contact DB | Valid contact | Verify existence
Letter_To | Text | TO_PARTY | Foreign Key | Match contact DB | Valid contact | Verify existence
Letter_Subject | Text | SUBJECT | Text (max 255) | Trim | Non-null
VO_Number | Text | VAR_ID | Sequence | From master list | Unique, sequential | FIDIC 1999
VO_Date | Date | VAR_DATE | ISO 8601 | Convert | Valid date
VO_Amount | Currency | VAR_AMOUNT | Decimal(15,2) | Convert to QAR | Numeric, positive | Include exchange rate
VO_Status | Text | VAR_STATUS | Lookup | Map status codes | In status table
IPC_Number | Text | IPC_ID | Sequence | From master | Unique, sequential
IPC_Date | Date | IPC_DATE | ISO 8601 | Convert | Valid date
IPC_Amount | Currency | IPC_AMOUNT | Decimal(15,2) | Convert to QAR | Numeric, positive
IPC_Status | Text | IPC_STATUS | Lookup | Map codes | In status table
Budget_Code | Text | COST_CODE | Text | Standardize format | Non-null, unique | WBS aligned
Budget_Description | Text | COST_DESC | Text (max 500) | Trim | Non-null
Budget_Amount | Currency | COST_AMOUNT | Decimal(15,2) | Convert to QAR | Numeric, positive
Risk_ID | Text | RISK_ID | UUID | Generate UUID | Non-null, unique
Risk_Description | Text | RISK_DESC | Text (max 1000) | Trim | Non-null
Risk_Probability | Percentage | RISK_PROB | Decimal(3,2) | Convert %, validate 0-1 | 0-1 range
Risk_Impact | Text/Number | RISK_IMPACT | Lookup | Map to scale | In impact table
Meeting_Date | Date | MEET_DATE | ISO 8601 | Convert | Valid date
Meeting_Type | Text | MEET_TYPE | Lookup | Map types | In type table
Meeting_Attendees | Text (comma-sep) | ATTENDEES | JSON array | Parse and normalize | Valid contacts
Submission_ID | Text | SUBM_ID | UUID | Generate UUID | Non-null, unique
Submission_Date | Date | SUBM_DATE | ISO 8601 | Convert | Valid date
Drawing_Number | Text | DWG_NUMBER | Text | Standardize format | Non-null, unique | Standard format
Drawing_Title | Text | DWG_TITLE | Text (max 500) | Trim | Non-null
Drawing_Revision | Text | DWG_REV | Text | Standardize | Format A-Z
Drawing_Date | Date | DWG_DATE | ISO 8601 | Convert | Valid date
Claim_ID | Text | CLAIM_ID | Sequence | From master | Unique, sequential
Claim_Date | Date | CLAIM_DATE | ISO 8601 | Convert | Valid date
Claim_Amount | Currency | CLAIM_AMOUNT | Decimal(15,2) | Convert to QAR | Numeric, positive
Claim_Status | Text | CLAIM_STATUS | Lookup | Map codes | In status table
Username | Text | USER_ID | Text | Standardize | Alphanumeric, unique | AD format
User_Email | Email | EMAIL | Email | Validate format | Valid email
User_Role | Text | ROLE | Lookup | Map to roles | In role table
User_Department | Text | DEPT | Lookup | Map departments | In dept table
Authority_Submission_ID | Text | AUTH_SUBM_ID | UUID | Generate UUID | Non-null, unique
Quality_Record_ID | Text | QA_REC_ID | UUID | Generate UUID | Non-null, unique
QA_Category | Text | QA_CAT | Lookup | Map categories | In category table
Schedule_Activity_ID | Text | TASK_ID | UUID | Generate UUID | Non-null, unique | P6/MSP
Activity_Duration | Days | DURATION | Integer | Convert to days | Numeric, positive
Activity_Status | Text | TASK_STATUS | Lookup | Map status codes | In status table
Lesson_ID | Text | LESSON_ID | UUID | Generate UUID | Non-null, unique
Lesson_Description | Text | LESSON_DESC | Text (max 2000) | Trim | Non-null

## Validation Checklist
Check ID | Data Category | Validation Rule | Expected Result | Actual Result | Pass/Fail | Notes
VAL-01 | Documents | All records have unique IDs | 100% unique IDs
VAL-02 | Documents | No null values in required fields | 0 nulls in TITLE
VAL-03 | Documents | Document count matches source | 5000 documents
VAL-04 | Documents | File references valid | All paths resolve
VAL-05 | Correspondence | All letters have dates | 100% date coverage
VAL-06 | Correspondence | From/To parties exist in contacts | 100% valid contacts
VAL-07 | Correspondence | Record count matches source | 2000 letters
VAL-08 | Variations | All VOs have sequential IDs | No gaps in sequence
VAL-09 | Variations | VO amounts are valid QAR | All positive decimals
VAL-10 | Variations | VO status values standardized | 4 valid statuses only
VAL-11 | IPC | All IPCs have dates | 100% date coverage |  |  | FIDIC 1999
VAL-12 | IPC | IPC amounts are positive | No negative amounts
VAL-13 | IPC | Record count matches source | 12 IPCs
VAL-14 | Budget | All cost codes standardized | Consistent format |  |  | WBS aligned
VAL-15 | Budget | No duplicate cost codes | All unique
VAL-16 | Budget | Budget totals match | Variance < 0.01%
VAL-17 | Risk | Risk probabilities in 0-1 range | All valid
VAL-18 | Risk | Risk impacts from lookup table | 100% valid values
VAL-19 | Risk | Record count matches source | 100 risks
VAL-20 | Meetings | All meeting dates valid | No future dates
VAL-21 | Meetings | Attendee contacts verified | 100% valid contacts
VAL-22 | Submissions | All submissions have dates | 100% coverage
VAL-23 | Drawings | Drawing numbers standardized | Consistent format
VAL-24 | Drawings | Revisions follow A-Z format | All valid revisions
VAL-25 | Drawings | Record count matches source | 2000 drawings
VAL-26 | Claims | All claims have sequence IDs | Unique, sequential
VAL-27 | Claims | Claim amounts are positive QAR | No negative values
VAL-28 | Users | User IDs follow AD format | Consistent format
VAL-29 | Users | Email addresses valid | Valid email format
VAL-30 | Users | User roles in valid list | 100% valid roles

## Rollback Plan
Scenario | Trigger | Rollback Steps | Recovery Time | Owner | Dependencies
Phase 1 Failure | Assessment not approved | 1. Halt assessment 2. Review findings 3. Restart with new scope | 3 days | Migration Lead | Project approval
Phase 2 Failure | Data quality < 95% | 1. Identify corrupt records 2. Restart cleansing 3. Revalidate | 5 days | Data Team | Phase 1 complete
Phase 3 Failure | Mapping issues > 10% | 1. Review failed mappings 2. Update rules 3. Retransform data | 4 days | Technical Team | Phase 2 complete
Phase 4 Failure | Trial data missing > 5% | 1. Restore from backup 2. Identify issues 3. Re-run trial | 3 days | QA Team | Phase 3 complete
Phase 5 Failure | Validation fails > 10 items | 1. Flag failed items 2. Correct source data 3. Retransform & revalidate | 5 days | QA Lead | Phase 4 complete
Phase 6 Critical Issue | Production data integrity < 99% | 1. Stop migration 2. Restore from backup 3. Investigate & restart | 2 hours | Migration Lead | Phase 5 approved
Data Loss | Unplanned data loss during migration | 1. Activate disaster recovery 2. Restore from latest backup 3. Restart from last checkpoint | 1 hour | Database Admin | Backup systems
Performance Failure | Migration performance < SLA | 1. Optimize queries 2. Increase resources 3. Restart migration | 4 hours | Technical Team | Infrastructure

## Cross-Reference
Reference ID | Document Title | Version | Status | Purpose
PF-01 | EDMS (Document Management) | 1.0 | Active | Document and file storage
PF-02 | Correspondence Management | 1.0 | Active | Letter and communication tracking
PF-03 | Variations Management | 1.0 | Active | Variation order processing
PF-04 | Quality Management | 1.0 | Active | Quality assurance records
PF-05 | Stage Gates (Programme) | 1.0 | Active | Schedule and programme management
PF-06 | Baseline & Change Control | 1.0 | Active | Configuration management
PF-07 | Authority Management | 1.0 | Active | Authority submissions tracking
PF-08 | IPC Processing | 1.0 | Active | Invoice and payment processing
PF-09 | Performance Tracking | 1.0 | Active | KPI and metrics tracking
PF-10 | Quality Records | 1.0 | Active | QA documentation
PF-11 | Budget Management | 1.0 | Active | Financial and budget tracking
PF-12 | Risk Management | 1.0 | Active | Risk register and mitigation
PF-13 | Resource Planning | 1.0 | Active | Resource allocation
PF-14 | Lessons Learned | 1.0 | Active | Knowledge management
PF-15 | Stakeholder Management | 1.0 | Active | Stakeholder communication
PF-16 | Meetings Management | 1.0 | Active | Meeting minutes and actions
PF-17 | Safety Records | 1.0 | Active | Safety documentation
PF-18 | Handover/Closeout | 1.0 | Active | Project closeout
PF-19 | User Management | 1.0 | Active | User accounts and access
PF-20 | Integration Hub | 1.0 | Active | System integration
PF-21 | Reporting & Analytics | 1.0 | Active | Reports and dashboards
PF-22 | Data Archive | 1.0 | Active | Historical data storage
PF-23 | Audit Trail | 1.0 | Active | System audit logs
DOC-01 | HAI_System_Configuration_Document.xlsx | 2.1 | Active | System configuration details
DOC-02 | HAI_Integration_Specification.xlsx | 1.8 | Active | Integration points and APIs
DOC-03 | HAI_Level3_Data_Model_CONTRACTUAL.xlsx | 3.0 | Active | Detailed data model for contract data
DOC-04 | HAI-SS-MIG-2026-001 | 1.0 | Active | This migration specification document