HAI SkyStruct Platform

Manufacturing & Construction Roadmap

Software Configurator Roadmap — Stage 0 to Stage 8

Version 3.0
March 2026

Prepared by: Hasan Mollamahmutoglu

# Chapter 1: Purpose & Scope

This Manufacturing & Construction Roadmap provides the software configurator with the exact sequence of work, timeline, and dependencies required to successfully implement the SkyStruct Platform across all 9 project stages (Stage 0 through Stage 8). The roadmap outlines:

• Project phases and timelines

• Stage-by-stage configuration requirements

• Process flows to activate at each stage

• Templates to load and configure

• Dashboard and reporting enablement

• Integration points with ERP and other systems

• Gate exit criteria for stage progression

• Workshop schedule and deliverables

• Risk mitigation strategies

# Chapter 2: Manufacturing & Construction Phases & Timeline

The implementation is divided into 6 phases spanning 16 weeks:

| Phase | Timeline | Key Activities |
| --- | --- | --- |
| Phase 0: Foundation | Weeks 1-2 | Project setup, parameters, roles, numbering system |
| Phase 1: Core Workflows | Weeks 3-4 | Document management, correspondence, approval engine |
| Phase 2: Financial & Governance | Weeks 5-8 | IPC, VO, claims, stage-gate, freeze mechanisms |
| Phase 3: Quality, HSE & Site | Weeks 9-12 | QA/QC, HSE, inspection, reporting |
| Phase 4: Advanced Features | Weeks 13-14 | Analytics, dashboards, ERP integration, predictive |
| Phase 5: UAT, Training & Go-Live | Weeks 15-16 | User acceptance testing, training, production launch |

# Chapter 3: Stage-by-Stage Configuration Roadmap

Detailed configuration requirements for each stage:

| Stage 0 |  |
| --- | --- |
| Module | Project Setup |
| Process Flows | PF-05, PF-19 |
| Templates | None |
| Dashboards | Basic Project Dashboard |
| Integration | Enterprise Data Link |
| Exit Criteria | Project parameters defined, roles assigned, numbering active |

| Stage 1 |  |
| --- | --- |
| Module | Document Management, Correspondence |
| Process Flows | PF-01, PF-02, PF-09, PF-25 |
| Templates | A-Design, General |
| Dashboards | Document Tracker |
| Integration | Document Repository Link |
| Exit Criteria | 107 documents uploaded, correspondence active |

| Stage 2 |  |
| --- | --- |
| Module | Technical Design Review, RFI, Risk |
| Process Flows | PF-01, PF-12, PF-16 |
| Templates | General (RFI, MOM, Drawing Register) |
| Dashboards | Technical Design Review Dashboard |
| Integration | Risk Register Link |
| Exit Criteria | RFIs processed, risk log active |

| Stage 3 |  |
| --- | --- |
| Module | Freeze, Submittals, Spatial Coordination |
| Process Flows | PF-06, PF-11 |
| Templates | B-Material, C-Method Statements |
| Dashboards | Spatial Coordination Tracker |
| Integration | Spatial Coordination Control |
| Exit Criteria | Freeze implemented, submittals tracked |

| Stage 4 |  |
| --- | --- |
| Module | Procurement, Authority |
| Process Flows | PF-04, PF-07 |
| Templates | J-Specialist, G-Contractual (subset) |
| Dashboards | Procurement Dashboard |
| Integration | Supplier Database |
| Exit Criteria | Tenders issued, submissions tracked |

| Stage 5 |  |
| --- | --- |
| Module | Execution & Monitoring |
| Process Flows | All 22 PFs active |
| Templates | All 108 templates loaded |
| Dashboards | Full suite (20+ dashboards) |
| Integration | Full ERP integration |
| Exit Criteria | All modules operational, live tracking |

| Stage 6 |  |
| --- | --- |
| Module | Handover & Closeout |
| Process Flows | PF-15, PF-28, PF-31 |
| Templates | H-Handover |
| Dashboards | Handover Progress |
| Integration | Asset Management |
| Exit Criteria | Snagging complete, TOC issued |

| Stage 7 |  |
| --- | --- |
| Module | Post-Delivery |
| Process Flows | PF-15, PF-30, PF-14, PF-27 |
| Templates | DLP, Lessons Learned |
| Dashboards | Warranty Dashboard |
| Integration | Performance Tracking |
| Exit Criteria | DLP satisfied, retention released |

| Stage 8 |  |
| --- | --- |
| Module | Final Closure |
| Process Flows | PF-26, PF-29, PF-24, PF-27 |
| Templates | Final Account, Archive |
| Dashboards | Project Summary |
| Integration | Archive System |
| Exit Criteria | Final account settled, project archived |

# Chapter 4: Workshop Plan

14 structured workshops across the 16-week implementation period:

| Workshop # | Topic | Week | HAI Attendees | Deliverables |
| --- | --- | --- | --- | --- |
| W1 | Kickoff & Architecture Overview | 1 | Lead Architect, Config Manager | Project Charter |
| W2 | Data Model & Entity Setup | 2 | Data Architect, Admin | Entity Definitions |
| W3 | Process Flow Configuration | 3 | Workflow Manager, SMEs | PF-01 to PF-10 Specs |
| W4 | Template Loading & Customization | 4 | Content Manager | 108 Templates Loaded |
| W5 | Document Management Deep Dive | 5 | Records Manager | Doc Routing Rules |
| W6 | Financial & Spatial Coordination Configuration | 6 | Finance Lead | Spatial Coordination Controls Active |
| W7 | IPC & VO Workflows | 7 | Finance, Contracts | IPC Process Defined |
| W8 | Approval Engine & Stage Gates | 8 | Process Owner | Gate Criteria Defined |
| W9 | QA/QC Module Configuration | 9 | Quality Lead | QA Workflows Active |
| W10 | HSE & Compliance Setup | 10 | HSE Manager | Compliance Checks |
| W11 | Dashboard & Analytics | 12 | BI Lead | 20+ Dashboards Live |
| W12 | ERP Integration Testing | 13 | Integration Team | ERP Links Verified |
| W13 | UAT Preparation | 14 | QA Lead | Test Scripts Ready |
| W14 | Go-Live Readiness Review | 16 | Project Manager | Go-Live Approval |

# Chapter 5: Process Flow Catalog with Stage Mapping

All 31 Process Flows mapped to stages and modules:

| PF# | Name | GOV Ref | Active Stages | Module |
| --- | --- | --- | --- | --- |
| PF-01 | Document Registration | GOV-015 | 0-8 | Document Management |
| PF-02 | Correspondence Log | GOV-016 | 1-8 | Correspondence |
| PF-04 | RFQ & Tender | GOV-020 | 4-5 | Procurement |
| PF-05 | Project Setup | GOV-006 | 0 | Foundation |
| PF-06 | Material Submittal | GOV-025 | 3-5 | Submittals |
| PF-07 | Authority Submission | GOV-022 | 4-5 | Approvals |
| PF-09 | Consultant Mobilization | GOV-018 | 1 | HR/Resource |
| PF-11 | Spatial Coordination Control | GOV-019 | 3-5 | Finance |
| PF-12 | RFI Management | GOV-021 | 2-3 | Technical Design |
| PF-14 | Lessons Learned | GOV-050 | 7-8 | Knowledge |
| PF-15 | Handover Workflow | GOV-035 | 6-7 | Closeout |
| PF-16 | Risk Register | GOV-023 | 2-5 | Risk |
| PF-19 | Numbering & Coding | GOV-007 | 0 | Foundation |
| PF-24 | Final Account | GOV-045 | 8 | Finance |
| PF-25 | Meeting Minutes | GOV-017 | 1-2 | Meetings |
| PF-26 | Claims Management | GOV-040 | 8 | Claims |
| PF-27 | Variation Order | GOV-030 | 3-8 | Changes |
| PF-28 | Snagging | GOV-036 | 6 | QA |
| PF-29 | Final Payment | GOV-046 | 8 | Finance |
| PF-30 | DLP Management | GOV-042 | 7 | Warranty |
| PF-31 | TOC & Handover | GOV-037 | 6 | Closeout |
| PF-32 | Performance Report | GOV-051 | 7 | Reporting |
| PF-33 | Time Tracking | GOV-052 | 5-8 | Project Control |
| PF-34 | Resource Planning | GOV-053 | 1-5 | HR |
| PF-35 | Change Log | GOV-054 | 3-8 | Changes |
| PF-36 | Status Dashboard | GOV-055 | 5-8 | Reporting |
| PF-37 | Archive Management | GOV-056 | 8 | Records |
| PF-38 | Compliance Tracker | GOV-057 | 3-8 | Governance |
| PF-39 | Equipment Register | GOV-058 | 5-6 | Assets |
| PF-40 | Inspection Report | GOV-059 | 6-7 | QA |
| PF-41 | Safety Log | GOV-060 | 1-8 | HSE |

# Chapter 6: Data Model Overview

15 core entities in the SkyStruct Platform data model:

| Entity | Description | Key Attributes |
| --- | --- | --- |
| Project | Master project record | Name, Client, Spatial Coordination, Timeline, Manager |
| Stage Instance | Project stage execution | Stage, Status, Dates, Gate Status |
| Document | All project documents | Type, Version, Status, Author, Date |
| Approval | Document/submittal approvals | Status, Approver, Comments, Date |
| Variation | Change orders & variations | Description, Cost, Schedule Impact |
| IPC | Invoice payment certificates | Amount, Status, Due Date |
| Contract | Contractor agreements | Scope, Terms, Price, Duration |
| Authority Submission | Regulatory/authority approvals | Type, Status, Submission Date |
| User/Role | System users and roles | Name, Role, Permissions, Department |
| Contractor | Contractor master data | Name, License, Insurance, Contact |
| Lesson Learned | Project knowledge capture | Category, Description, Owner, Impact |
| Freeze | Stage freeze records | Stage, Freeze Date, Reason, Released |
| Snag Item | Defect/snagging log | Description, Priority, Status, Owner |
| Final Account | Project financial closure | Total Cost, Variance, Settlement |
| Performance Certificate | Post-completion assessment | Rating, Date, Assessor |

# Chapter 7: Acceptance Criteria by Phase

Phase-gated acceptance criteria for implementation sign-off:

## Phase 0: Foundation

✓ Project parameters defined in system

✓ User roles and permissions configured

✓ Numbering systems active and tested

✓ Enterprise link established

✓ Backup/recovery procedures documented

## Phase 1: Core Workflows

✓ 107 documents uploaded and indexed

✓ Document routing rules tested

✓ Correspondence workflow live

✓ Approval chain configured (3-party)

✓ Search functionality validated

## Phase 2: Financial & Governance

✓ IPC workflow operational

✓ VO process live with tracking

✓ Claims submission active

✓ Stage gates enforced

✓ Financial reports generated

## Phase 3: Quality, HSE & Site

✓ QA/QC module configured

✓ HSE checks integrated

✓ Inspection templates loaded

✓ Reporting dashboards live

✓ Compliance audit trail enabled

## Phase 4: Advanced Features

✓ Analytics engine operational

✓ 20+ dashboards live

✓ Predictive models configured

✓ ERP integration tested

✓ Performance metrics tracked

## Phase 5: UAT & Go-Live

✓ 100% of UAT test cases passed

✓ End-user training completed

✓ Data migration validated

✓ Cutover plan executed

✓ Go-live sign-off obtained

# Chapter 8: Risk Register

Key implementation risks and mitigation strategies:

| Risk | Likelihood | Impact | Mitigation | Owner |
| --- | --- | --- | --- | --- |
| Delayed data migration | Medium | High | Pre-migration testing, parallel runs | IT Lead |
| User resistance to change | Medium | High | Early training, change champions | HR Lead |
| Integration issues with ERP | High | High | Early testing, dedicated team | Integration Lead |
| Scope creep | High | Medium | Strict change control, gate reviews | PM |
| Key person unavailability | Medium | Medium | Cross-training, documentation | PM |
| Performance under load | Low | High | Load testing, optimization | Tech Lead |
| Third-party tool delays | Medium | High | Vendor SLAs, backup vendors | Procurement |

# Appendix: HAI-GOV Document Reference

Complete catalog of HAI-GOV documents (GOV-000 through GOV-083):

| GOV # | Document Title | Format |
| --- | --- | --- |
| GOV-001 | SkyStruct Platform — Master Specification | DOCX |
| GOV-006 | Project Setup & Configuration | DOCX |
| GOV-007 | Manufacturing & Construction Roadmap | DOCX |
| GOV-015 | Document Management | DOCX |
| GOV-016 | Correspondence Management | DOCX |
| GOV-017 | Meeting Management | DOCX |
| GOV-018 | Consultant Mobilization | DOCX |
| GOV-019 | Spatial Coordination Control & Tracking | DOCX |
| GOV-020 | RFQ & Tender Management | DOCX |
| GOV-021 | RFI Management | DOCX |
| GOV-022 | Authority Submissions | DOCX |
| GOV-023 | Risk Register | DOCX |
| GOV-025 | Material Submittal Process | DOCX |
| GOV-030 | Variation Order Management | DOCX |
| GOV-035 | Handover Procedures | DOCX |
| GOV-036 | Snagging & Defect Log | DOCX |
| GOV-037 | TOC & Handover Certificate | DOCX |
| GOV-040 | Claims Management | DOCX |
| GOV-042 | DLP & Warranty | DOCX |
| GOV-045 | Final Account Process | DOCX |
| GOV-046 | Final Payment | DOCX |
| GOV-050 | Lessons Learned Capture | DOCX |
| GOV-051 | Performance Reporting | DOCX |
| GOV-052 | Time Tracking | DOCX |
| GOV-053 | Resource Planning | DOCX |
| GOV-054 | Change Log | DOCX |
| GOV-055 | Status Dashboard | DOCX |
| GOV-056 | Archive Management | DOCX |
| GOV-057 | Compliance Tracking | DOCX |
| GOV-060 | Safety & HSE Log | DOCX |

# Approval Chain

This document requires approval from the following parties:

| Role | Name | Signature / Date |
| --- | --- | --- |
| Contractor Representative |  |  |
| Lead Consultant |  |  |
| ER/HAI |  |  |