FRAMEWORK AGREEMENT

AND

SCOPE OF WORK NO. 1

Integrated Governance Platform

Customization, Implementation, Integration & Support

RIBA Plan of Work 2020 | RICS PM Standards | Qatar Authority Gates | GSAS Sustainability

BETWEEN

House of Architecture & Interiors (HAI)

— The Client —

AND

SkyStruct Technologies

— The Service Provider —

HAI-SS-FWA-2026-001  |  [______] March 2026

DRAFT — Version 3.0 — For Review and Acceptance

Confidential

PART A — FRAMEWORK AGREEMENT

## 1. DEFINITIONS AND INTERPRETATION

- “Client” means House of Architecture & Interiors (HAI).

- “Service Provider” means SkyStruct Technologies.

- “Platform” means the SkyStruct cloud-based project governance software.

- “Scope of Work” / “SOW” means a scope of work issued under this Framework Agreement.

- “Customization” means any configuration, workflow design, feature development, integration, or enhancement for HAI.

- “Acceptance” means written confirmation by HAI’s authorized representative that a deliverable meets acceptance criteria.

- “Governance Engine” means the integrated system of lifecycle stages, approval workflows, freeze gateways, EDMS, dashboards, analytics, and reporting.

- “ERP” means Artan Holding’s enterprise resource planning system.

- “SLA” means Service Level Agreement as defined in Schedule D.

- “Data” means all information, documents, records, and metadata created or processed within the Platform by or on behalf of the Client.

- “EDMS” means Electronic Document Management System.

- “RIBA” means the Royal Institute of British Architects Plan of Work 2020.

- “RICS” means the Royal Institution of Chartered Surveyors professional standards and guidance.

- “GSAS” means the Global Sustainability Assessment System administered by GORD.

- “Stage Gate” means the set of mandatory entry criteria, exit criteria, and freeze rules that must be satisfied before a project advances from one HAI Stage to the next within the Platform.

## 2. TERM AND RENEWAL

Initial term: three (3) years from Effective Date. Auto-renewal for successive three-year periods unless 180 days’ written notice. 15-year partnership trajectory with step-down subscription pricing per Schedule C.

## 3. GOVERNING LAW AND DISPUTE RESOLUTION

Qatar Civil Law. QICCA arbitration (Doha, English). Sole arbitrator unless >QAR 5M, then three.

## 4. INTELLECTUAL PROPERTY

- Platform IP: Service Provider retains core platform rights.

- Customization IP: Joint ownership. HAI gets perpetual, irrevocable, royalty-free license surviving termination.

- Client Data: Exclusively owned by HAI.

## 5. DATA PROTECTION, SECURITY, AND RESIDENCY

- Residency: Location confirmed by HAI IT/Compliance prior to go-live. [TBD]

- Security: ISO 27001 equivalent. Evidence on request.

- Export: All Data exportable at any time (CSV, JSON, XML, PDF). 90 days post-termination.

- Destruction: 30 days post-termination with written certification.

## 6. SOURCE CODE ESCROW AND BUSINESS CONTINUITY

- Escrow deposit within 60 days. Updated per major release. Costs shared 50/50.

- Release triggers: insolvency, 60-day support failure, unassumed acquisition.

- BCP/DR: RTO ≤4 hours, RPO ≤1 hour. Documented within 30 days. Annual test.

## 7. LIABILITY

- Cap: 1x annual subscription value. Excludes: confidentiality breach, data breach, IP infringement, fraud, indemnification.

- No consequential damages except gross negligence/fraud.

- Service Provider indemnifies HAI against third-party IP/data/negligence claims.

## 8. TERMINATION

- Convenience: 180 days’ notice. Client pays for accepted work + pro-rated subscription.

- Cause — Minor: 14-day cure. Critical: immediate. 3+ failures in 6 months: immediate.

- Post-termination: 90-day transition, full data export, perpetual license, escrow assessment, refund of undelivered milestone payments within 30 days.

## 9. CONFIDENTIALITY

Strict confidentiality. Survives 5 years post-termination. Standard exceptions.

## 10. CHANGE CONTROL

- Written CR required. No execution without dual sign-off.

- Technological changes within existing platform: no additional cost (per Addendum 26 Feb 2026).

- New-concept technologies: separate commercial negotiation.

## 11. GENERAL PROVISIONS

Entire Agreement, Amendment (written only), Assignment (HAI may assign to group entities), Force Majeure, Notices (email + read receipt), Severability, Waiver, Counterparts.

PART A — EXECUTION

IN WITNESS WHEREOF, the parties have executed this Framework Agreement.

Name:

Title: Authorized Representative

Entity: House of Architecture & Interiors (HAI)

Date: ___________________

Signature: ___________________

Name:

Title: Authorized Representative

Entity: SkyStruct Technologies

Date: ___________________

Signature: ___________________

PART B — SCOPE OF WORK NO. 1

Integrated Governance Platform — Implementation

## 1. BACKGROUND AND OBJECTIVES

HAI functions as the Employer’s Representative and Construction Project Management Company, overseeing multi-disciplinary projects from early design through operations, coordinating among internal stakeholders (Procurement, Finance, Legal, FM) and external parties (Consultants, Contractors, Authorities: QCDD, Kahramaa, Ashghal, Civil Defense).

HAI requires a single-platform Governance Engine built on SkyStruct that enforces a stage-gated project lifecycle aligned with RIBA Plan of Work 2020 core tasks, RICS project management deliverables, Qatar authority approval gates, and GSAS sustainability checkpoints.

The Platform shall replace all manual integration, email-based coordination, physical signature loops, and fragmented approval chains. The only external system is Artan Holding’s ERP.

The stage gate model is non-negotiable: the system must enforce mandatory entry criteria, exit criteria, and freeze rules at every stage boundary. No project shall advance to the next stage unless all gate conditions are met or a formal exception is approved through the designated workflow.

## 2. HAI LIFECYCLE MODEL — STAGE GATE DEFINITIONS

The following defines each HAI Stage (0–8) with its RIBA equivalent, core tasks, RICS PM deliverables, Qatar authority requirements, GSAS sustainability checkpoints, HAI-specific SkyStruct actions, mandatory entry criteria, mandatory exit criteria, and freeze rules.

The Service Provider shall configure the Platform to enforce these gates. The exit criteria checklist for each stage shall be implemented as a mandatory system checklist — items must be marked complete (with evidence where specified) before the system allows stage progression.

Color coding: Blue = RIBA | Green = RICS | Amber = Qatar Authority | Teal = GSAS | Purple = HAI/SkyStruct | Gray = Entry | Yellow = Exit | Red = Freeze

HAI STAGE 0 — LAND & CLIENT INTENT

RIBA Equivalent: Stage 0 — Strategic Definition

Stage Outcome: The best means of achieving the Client Requirements confirmed.

| RIBA Core Tasks | 1. Prepare Client Requirements 2. Develop Business Case for feasible options including review of Project Risks and Project Budget 3. Ratify option that best delivers Client Requirements 4. Review Feedback from previous projects (Lessons Learned) 5. Undertake Site Appraisals 6. Prepare Project Strategies (Cost, Fire Safety, H&S, Inclusive Design, Planning, Procurement, Sustainability) 7. Define Sustainability Outcomes at project level |
| --- | --- |
| RICS PM Deliverables | 1. Project Initiation Document (PID) preparation 2. Feasibility study and options appraisal 3. Initial cost benchmarking and order-of-magnitude estimate 4. Risk register establishment (initial) 5. Stakeholder identification and mapping 6. Client brief facilitation and documentation 7. Appointment of client advisers (no design team yet at Stage 0) |
| Qatar Authority Requirements | 1. Land use verification with Municipality / Planning Authority 2. Preliminary zoning compliance check 3. Environmental screening (if applicable) 4. Initial coordination with Ashghal for infrastructure requirements (if greenfield) |
| GSAS Sustainability Checkpoints | 1. GSAS Registration (if targeting certification) 2. Establish high-level Sustainability Outcomes aligned with GSAS categories 3. Define GSAS target rating (stars / class) 4. Urban Connectivity pre-assessment (site selection sustainability criteria) 5. Initial energy and water baseline expectations |
| HAI-Specific Actions (SkyStruct) | 1. Job Request Form initiated 2. Project folder and numbering structure created in SkyStruct 3. HAI Project Manager assigned 4. Initial coordination with Artan Holding stakeholders |
| ENTRY CRITERIA (mandatory) | ☐ Land ownership / lease confirmed or under negotiation ☐ Client intent documented (formal or informal brief) ☐ Budget authority confirmed (who approves project initiation) |
| EXIT CRITERIA (gate release) | ☐ Business Case approved by Client / Employer ☐ Project Budget (Order of Cost Estimate / RICS Cost Plan Level 0) signed off ☐ Site Appraisal report complete ☐ Project Risk Register (initial) established ☐ Lessons Learned from previous projects reviewed and documented ☐ Client Requirements document signed off ☐ Project Strategies (high-level) documented ☐ GSAS target rating confirmed (if applicable) ☐ Decision to proceed to Stage 1 formally recorded |
| FREEZE RULES | No freeze at this stage. Strategic definition only. |

HAI STAGE 1 — CONCEPT DESIGN

RIBA Equivalent: Stage 1 — Preparation and Briefing

Stage Outcome: Project Brief approved by the client and confirmed that it can be accommodated on the site.

| RIBA Core Tasks | 1. Prepare Project Brief including Project Outcomes, Sustainability Outcomes, Quality Aspirations, and Spatial Requirements 2. Prepare Feasibility Studies 3. Agree Project Budget (RICS Cost Plan Level 1) 4. Source pre-application planning advice 5. Agree Responsibility Matrix and Information Requirements 6. Prepare Project Execution Plan (PEP) 7. Appoint Design Team |
| --- | --- |
| RICS PM Deliverables | 1. Project Execution Plan (PEP) preparation 2. Responsibility Matrix finalized 3. RICS Cost Plan Level 1 (Order of Cost Estimate refined) 4. Procurement Strategy recommendation 5. Programme / Master Schedule (Level 1) preparation 6. Design team appointment and fee negotiation 7. Consultant scope of services definition 8. Risk register update with design and planning risks 9. Stakeholder communication plan |
| Qatar Authority Requirements | 1. Pre-application consultation with QCDD (Qatar Civil Defense Department) if required 2. Preliminary Ashghal coordination for roads/infrastructure 3. Kahramaa preliminary load assessment application (electricity and water) |
| GSAS Sustainability Checkpoints | 1. GSAS Concept Assessment submission preparation 2. Site category assessment (urban connectivity, transport access) 3. Energy strategy alignment with GSAS energy criteria 4. Water strategy alignment with GSAS water criteria 5. Material selection strategy (GSAS materials category) |
| HAI-Specific Actions (SkyStruct) | 1. Concept design coordination between Employer, HAI, and Architect/Consultant 2. Initial DMS structure confirmed in SkyStruct 3. Design management lead assigned 4. Coordination with Artan Holding Procurement for consultant appointments |
| ENTRY CRITERIA (mandatory) | ☐ Stage 0 exit criteria fully met ☐ Business Case approved ☐ Client Requirements document signed off ☐ Budget authority for Stage 1 confirmed |
| EXIT CRITERIA (gate release) | ☐ Project Brief signed off by Client / Employer ☐ Feasibility Studies complete ☐ RICS Cost Plan Level 1 approved ☐ Responsibility Matrix and Information Requirements agreed ☐ Design Team appointed with signed agreements ☐ PEP issued ☐ Master Programme (Level 1) issued ☐ Procurement Strategy approved ☐ GSAS Concept Assessment submitted (if applicable) ☐ Decision to proceed to Stage 2 formally recorded |
| FREEZE RULES | Client Requirements freeze recommended at end of Stage 1. Changes after this point managed via Change Control. |

HAI STAGE 2 — SCHEMATIC DESIGN

RIBA Equivalent: Stage 2 — Concept Design

Stage Outcome: Architectural Concept approved by the client and aligned to the Project Brief.

| RIBA Core Tasks | 1. Prepare Architectural Concept incorporating Project Strategies 2. Agree Architectural Concept with Client 3. Prepare Cost Plan (RICS Cost Plan Level 2) 4. Undertake Design Reviews 5. Develop Project Strategies to align with Architectural Concept 6. Review and update Project Brief (brief remains live during Stage 2) 7. Prepare initial Sustainability Strategy including measurable targets |
| --- | --- |
| RICS PM Deliverables | 1. RICS Cost Plan Level 2 (Formal Cost Plan based on concept) 2. Cost Plan reconciliation with Project Budget 3. Value Engineering workshops (if cost exceeds budget) 4. Programme update (Level 2) with design milestones 5. Design Review management and sign-off coordination 6. Risk register update with design development risks 7. Change Control Procedures established 8. Consultant performance monitoring initiated |
| Qatar Authority Requirements | 1. DC1 — Authority Concept Approval application (QCDD/Municipality) 2. Kahramaa formal load application (if not done in Stage 1) 3. Ashghal infrastructure design coordination 4. Civil Defense preliminary fire strategy review |
| GSAS Sustainability Checkpoints | 1. GSAS Design Assessment — address Part 1 criteria 2. Energy modeling initiated (GSAS Energy category) 3. Water efficiency measures defined (GSAS Water category) 4. Indoor/outdoor environment quality targets set 5. Material sustainability specifications initiated |
| HAI-Specific Actions (SkyStruct) | 1. HAI design review comments documented in SkyStruct 2. Concept design submission/approval workflow via EDMS 3. Coordination with consultants via SkyStruct transmittals 4. Authority submission tracking initiated in SkyStruct |
| ENTRY CRITERIA (mandatory) | ☐ Stage 1 exit criteria fully met ☐ Project Brief signed off ☐ Design Team appointed and mobilized ☐ RICS Cost Plan Level 1 approved |
| EXIT CRITERIA (gate release) | ☐ Architectural Concept approved by Client (formal sign-off) ☐ RICS Cost Plan Level 2 approved ☐ DC1 application submitted (or approved) ☐ Project Strategies aligned with Concept and documented ☐ Sustainability Strategy with measurable targets issued ☐ Design Review records documented ☐ GSAS Design Assessment — Part 1 criteria addressed ☐ Change Control Procedures in place ☐ Decision to proceed to Stage 3 formally recorded |
| FREEZE RULES | DESIGN FREEZE recommended at end of Stage 2. Architectural Concept locked. Changes after this point require formal Change Control with cost/programme impact assessment. |

HAI STAGE 3 — DEVELOPED DESIGN

RIBA Equivalent: Stage 3 — Spatial Coordination

Stage Outcome: Architectural and engineering information Spatially Coordinated.

| RIBA Core Tasks | 1. Prepare Spatially Coordinated design (architectural + engineering) 2. Undertake Design Studies and detailed engineering analysis 3. Cost Plan update (RICS Cost Plan Level 3) 4. Add detail to Project Strategies 5. Prepare Planning Application (typically submitted at end of Stage 3) 6. Use Change Control Procedures for any functional changes to Brief or Concept 7. Coordinate specialist subcontractor design requirements for Stage 4 |
| --- | --- |
| RICS PM Deliverables | 1. RICS Cost Plan Level 3 (Detailed Cost Plan based on spatial coordination) 2. Value Engineering review (if cost/budget misalignment) 3. Programme update with planning submission timeline 4. Buildability review with potential contractors 5. Risk register update — planning risk, regulatory risk, coordination risk 6. Consultant deliverable tracking and compliance monitoring 7. Pre-tender documentation review |
| Qatar Authority Requirements | 1. DC2 — Authority Detailed Approval application (QCDD/Municipality) 2. Ashghal detailed infrastructure design approval 3. Kahramaa detailed design coordination 4. Civil Defense detailed fire strategy and life safety submission 5. Planning Application submission (if separate from DC2) |
| GSAS Sustainability Checkpoints | 1. GSAS Design Assessment — address Part 2 criteria 2. Detailed energy simulation results submitted 3. Water balance calculations completed 4. Material specifications assessed against GSAS criteria 5. Indoor environment quality (IEQ) simulation or assessment 6. GSAS Letter of Conformance (LoC) application preparation |
| HAI-Specific Actions (SkyStruct) | 1. HAI engineering review and coordination tracked in SkyStruct 2. Authority submission tracker updated in SkyStruct 3. Design change log maintained in SkyStruct 4. Comparison sheet preparation for Stage 4 procurement begins 5. Variation register initiated |
| ENTRY CRITERIA (mandatory) | ☐ Stage 2 exit criteria fully met ☐ Architectural Concept signed off and frozen ☐ RICS Cost Plan Level 2 approved ☐ DC1 submitted or approved |
| EXIT CRITERIA (gate release) | ☐ Spatially Coordinated design complete and signed off ☐ RICS Cost Plan Level 3 approved ☐ DC2 submitted (or approved) ☐ Civil Defense fire strategy approved ☐ Kahramaa/Ashghal coordination complete ☐ Planning Application submitted (if applicable) ☐ GSAS LoC issued or application submitted ☐ Pre-tender cost estimate prepared ☐ Decision to proceed to Stage 4 formally recorded |
| FREEZE RULES | SCOPE FREEZE at end of Stage 3. Spatial coordination locked. No further changes to building footprint, floor areas, structural grid, or core layouts without formal variation process. BUDGET FREEZE initiated — Cost Plan Level 3 becomes the control baseline. |

HAI STAGE 3.1 — AUTHORITY DETAILED (DC2)

RIBA Equivalent: Stage 3 Extended — Regulatory Freeze Layer (no direct RIBA equivalent; hybrid gate)

Stage Outcome: All regulatory approvals obtained. Design frozen for authority compliance.

| RIBA Core Tasks | 1. Obtain DC2 approval from QCDD/Municipality 2. Resolve all authority comments and conditions 3. Incorporate authority requirements into design documents 4. Confirm regulatory compliance across all disciplines |
| --- | --- |
| RICS PM Deliverables | 1. Authority response tracking and compliance log 2. Cost impact assessment of any authority-mandated changes 3. Programme impact assessment of authority timelines 4. Risk register update — regulatory compliance risk closed or mitigated |
| Qatar Authority Requirements | 1. DC2 approved with all conditions cleared 2. Civil Defense approval confirmed 3. Kahramaa approval for electrical/water design 4. Ashghal road/infrastructure NOC 5. Environmental compliance confirmation (if applicable) |
| GSAS Sustainability Checkpoints | 1. GSAS design criteria fully addressed — ready for LoC 2. GSAS Letter of Conformance (LoC) obtained or in final review |
| HAI-Specific Actions (SkyStruct) | 1. Authority tracker in SkyStruct shows all submissions at APPROVED status 2. Compliance checklist completed and signed off by HAI Design Manager |
| ENTRY CRITERIA (mandatory) | ☐ Stage 3 exit criteria met (except authority approvals pending) ☐ DC2 application submitted ☐ All authority submissions complete |
| EXIT CRITERIA (gate release) | ☐ DC2 approved — no outstanding conditions ☐ Civil Defense approval letter received ☐ Kahramaa approval letter received ☐ Ashghal NOC received ☐ GSAS LoC issued ☐ All authority conditions incorporated into design ☐ Regulatory compliance checklist 100% complete ☐ Decision to proceed to Stage 4 formally recorded |
| FREEZE RULES | REGULATORY FREEZE. No design changes that affect authority approvals without re-submission. Any change triggering re-approval requires formal CR with full cost/programme/authority impact assessment. |

HAI STAGE 4 — TENDER / RFP

RIBA Equivalent: Stage 4 — Technical Design

Stage Outcome: All design information required to manufacture and construct the project completed.

| RIBA Core Tasks | 1. Prepare Technical Design (all information for manufacture and construction) 2. Prepare and issue Tender Documentation (RFP, BOQ, specifications) 3. Allocate specialist subcontractor design work 4. Finalize all specifications and scope of works 5. Prepare Employer's Requirements (if D&B) or full production information (Traditional) 6. Complete pre-tender health and safety information |
| --- | --- |
| RICS PM Deliverables | 1. Pre-tender estimate / RICS Cost Plan Level 4 2. Tender documentation preparation and review 3. RFP issuance and bid management 4. Bid evaluation report and recommendation 5. Contract/Contract Award preparation 6. Programme update with construction timeline 7. Buildability and programme review with tenderers 8. Risk allocation review in contract conditions 9. Procurement evaluation matrix and scoring |
| Qatar Authority Requirements | 1. Building Permit application (if not already obtained via DC2) 2. Final utility connection applications (Kahramaa, Ashghal) 3. Pre-construction notifications |
| GSAS Sustainability Checkpoints | 1. GSAS Construction Management Plan preparation 2. GSAS criteria embedded in tender/specification documents 3. Sustainability requirements included in contractor scope |
| HAI-Specific Actions (SkyStruct) | 1. Comparison sheets processed through SkyStruct approval workflow 2. Tender evaluation logged in SkyStruct procurement module 3. Contract Award/Contract issued via SkyStruct with ERP sync 4. Baseline programme uploaded to SkyStruct 5. Contractor onboarded to SkyStruct (external user access) |
| ENTRY CRITERIA (mandatory) | ☐ Stage 3/3.1 exit criteria fully met ☐ All authority approvals obtained ☐ RICS Cost Plan Level 3 approved and frozen as baseline ☐ Scope Freeze and Budget Freeze confirmed |
| EXIT CRITERIA (gate release) | ☐ Technical Design complete — all production information issued ☐ Tender Documentation issued to market ☐ Bids received and evaluated ☐ Recommendation report approved by Client/Employer ☐ Contract/Contract Award awarded and signed ☐ Construction programme (baseline) agreed with Contractor ☐ Pre-construction H&S plan reviewed ☐ Building Permit obtained (or confirmed) ☐ GSAS Construction Management Plan issued to Contractor ☐ Contractor mobilization plan received ☐ Decision to proceed to Stage 5 formally recorded |
| FREEZE RULES | ALL FREEZES ACTIVE. Design, Scope, and Budget frozen. Contract value becomes the cost baseline. Any change from this point is a formal Variation with cost/time impact assessment, approval workflow, and freeze exception process. |

HAI STAGE 5 — CONSTRUCTION

RIBA Equivalent: Stage 5 — Manufacturing and Construction

Stage Outcome: Manufacturing, construction and Commissioning completed.

| RIBA Core Tasks | 1. Administer Building Contract 2. Inspect construction and monitor progress 3. Resolve Site Queries (no new design work except SQ resolution) 4. Review Contractor's design submissions (if D&B elements) 5. Issue instructions, certify payments (IPCs) 6. Monitor variations, delays, and claims 7. Undertake commissioning activities |
| --- | --- |
| RICS PM Deliverables | 1. Contract administration per contract conditions (FIDIC/JCT/NEC) 2. Monthly progress reports and dashboard updates 3. Cost reporting: actual vs. baseline, forecast at completion, variation log 4. Programme monitoring: planned vs. actual, critical path, float analysis 5. Quality management: inspection regime, NCR tracking, IR processing 6. Variation management: assessment, approval workflow, cost/time impact 7. IPC certification and payment recommendation 8. Claims management (contractor and employer) 9. Risk register: active monitoring and mitigation 10. Stakeholder communication and reporting 11. Health and Safety monitoring |
| Qatar Authority Requirements | 1. Periodic authority inspections (QCDD, Civil Defense) 2. Kahramaa connection and testing coordination 3. Ashghal road completion and handover 4. Civil Defense fire system testing and inspection |
| GSAS Sustainability Checkpoints | 1. GSAS Construction Management audits (routine and random inspections by GSAS Trust) 2. Conformance to Design audit — verify built matches design intent 3. Site construction practices audit (waste management, energy use on site, water conservation) 4. Construction environmental management monitoring |
| HAI-Specific Actions (SkyStruct) | 1. Daily site reports submitted via SkyStruct 2. IRs and NCRs processed through SkyStruct quality module 3. Weekly coordination meeting minutes logged in SkyStruct 4. Progress photos uploaded to SkyStruct 5. Correspondence (all letters, instructions) via SkyStruct EDMS 6. IPC certification workflow through SkyStruct with ERP sync 7. Variation register maintained in SkyStruct with cost/time tracking |
| ENTRY CRITERIA (mandatory) | ☐ Stage 4 exit criteria fully met ☐ Contract signed and mobilization complete ☐ Baseline programme agreed ☐ All authority permits obtained ☐ Contractor onboarded to SkyStruct |
| EXIT CRITERIA (gate release) | ☐ Construction substantially complete (Practical Completion) ☐ All commissioning complete and documented ☐ Final IPC certified ☐ All NCRs closed or with agreed resolution path ☐ Variation account agreed or under determination ☐ As-built drawings received ☐ O&M manuals received ☐ Test reports received and verified ☐ GSAS Construction Management assessment complete ☐ Authority final inspections passed ☐ Snag list prepared ☐ Decision to proceed to Stage 6 formally recorded |
| FREEZE RULES | All freezes remain active. Variations processed through formal workflow only. No expenditure beyond frozen budget without approved variation. |

HAI STAGE 6 — BCC / AUTHORITY COMPLETION

RIBA Equivalent: Stage 5→6 Hybrid Completion Gate / Stage 6 — Handover

Stage Outcome: Building handed over, Aftercare initiated, Building Contract concluded.

| RIBA Core Tasks | 1. Hand over building to Client 2. Conclude Building Contract 3. Compile and issue Handover Package (Building Owner's Manual, H&S File) 4. Review project performance (Lessons Learned) 5. Initiate Aftercare period 6. Discharge any remaining planning conditions 7. Rectify defects (snagging) |
| --- | --- |
| RICS PM Deliverables | 1. Practical Completion assessment and certification 2. Final Account preparation and agreement 3. Defects list (snag list) preparation and management 4. Handover documentation completeness review 5. Post-project review and Lessons Learned workshop 6. Financial close-out: final cost report, retention release schedule 7. Contract close-out: all claims resolved, final certificate issued 8. DLP commencement confirmation and defect process established |
| Qatar Authority Requirements | 1. BCC (Building Completion Certificate) application to QCDD/Municipality 2. Civil Defense final NOC (fire safety completion) 3. Kahramaa permanent connection confirmation 4. Ashghal final infrastructure NOC 5. All authority NOCs obtained 6. BCC issued |
| GSAS Sustainability Checkpoints | 1. GSAS Final Review — resubmit criteria to verify as-built matches design 2. GSAS Final Certificate application 3. GSAS plaque of recognition (if certified) |
| HAI-Specific Actions (SkyStruct) | 1. Digital Handover Package assembled in SkyStruct 2. BCC and NOC tracking complete in authority module 3. Defect list managed through SkyStruct 4. Lessons Learned entered into SkyStruct database 5. Final cost report generated from SkyStruct/ERP data 6. Closure report generated |
| ENTRY CRITERIA (mandatory) | ☐ Stage 5 exit criteria met ☐ Practical Completion achieved ☐ All commissioning complete ☐ Snag list prepared |
| EXIT CRITERIA (gate release) | ☐ BCC obtained from QCDD/Municipality ☐ All authority NOCs received ☐ Handover Package complete and delivered to Client ☐ Building Owner's Manual issued ☐ H&S File issued ☐ Final Account agreed (or in determination) ☐ Retention schedule confirmed ☐ DLP period commenced ☐ GSAS Final Certificate obtained (if applicable) ☐ Lessons Learned report completed and uploaded to SkyStruct ☐ Post-project review conducted ☐ FM team notified (MIPC FM transition initiated) ☐ Decision to proceed to Stage 7 formally recorded |
| FREEZE RULES | Contract close-out. No further variations unless defect-related. Budget reconciliation vs. frozen baseline completed. |

HAI STAGE 7 — DLP & IN USE

RIBA Equivalent: Stage 7 — Use (concurrent with Stage 6)

Stage Outcome: Building used, operated and maintained efficiently.

| RIBA Core Tasks | 1. Stage 7.1 — DLP Period (400 days from Taking Over Certificate / Practical Completion) 2. Stage 7.2 — Beyond DLP: ongoing operation 3. Undertake light-touch Post Occupancy Evaluation (POE) 4. Verify building performance against Sustainability Outcomes 5. Monitor operational costs (CAPEX, OPEX, maintenance, replacement) 6. Manage Aftercare program |
| --- | --- |
| RICS PM Deliverables | 1. DLP defect management and tracking 2. Retention release management (typically 50% at PC, 50% at end of DLP) 3. Final Certificate issuance at end of DLP 4. Post Occupancy Evaluation (POE) coordination 5. Operational cost monitoring: energy, water, consumables, staffing 6. Maintenance and repair tracking: preventive, corrective, spare parts 7. Life cycle cost tracking (CAPEX vs. OPEX analysis) 8. Building performance benchmarking |
| Qatar Authority Requirements | 1. Ongoing compliance with authority conditions 2. Periodic authority inspections (if required) 3. Utility billing and consumption monitoring |
| GSAS Sustainability Checkpoints | 1. GSAS Operations certification (if targeting operational rating) 2. Post-occupancy energy and water performance verification 3. Indoor environment quality monitoring 4. Operational management assessment against GSAS criteria |
| HAI-Specific Actions (SkyStruct) | 1. DLP defect tracking in SkyStruct 2. Warranty expiry alerts from SkyStruct 3. O&M database searchable in SkyStruct 4. FM transition to MIPC FM documented 5. Maintenance KPI monitoring via SkyStruct dashboards 6. Retention release tracked in SkyStruct/ERP |
| ENTRY CRITERIA (mandatory) | ☐ Stage 6 exit criteria met ☐ BCC obtained ☐ Building occupied / in use ☐ DLP period active |
| EXIT CRITERIA (gate release) | ☐ All DLP defects rectified and closed ☐ Final Certificate issued (end of DLP) ☐ Retention fully released ☐ Post Occupancy Evaluation completed ☐ Building performance data collected and benchmarked ☐ FM team fully operational (MIPC FM) ☐ Warranty tracking active in SkyStruct ☐ GSAS Operations assessment complete (if applicable) ☐ Transition to Stage 8 monitoring (long-term) |
| FREEZE RULES | No freeze applicable. Operational monitoring phase. |

HAI STAGE 8 — END OF LIFE

RIBA Equivalent: No direct RIBA equivalent — HAI extension (EOL management)

Stage Outcome: End-of-life costs managed: decommissioning, demolition, disposal, residual/salvage value.

| RIBA Core Tasks | 1. Assess building condition and remaining useful life 2. Determine end-of-life strategy: refurbish, repurpose, or demolish 3. Prepare decommissioning plan 4. Manage demolition/disposal if applicable 5. Calculate residual/salvage value 6. Environmental impact assessment for demolition/disposal 7. Archive all project records |
| --- | --- |
| RICS PM Deliverables | 1. Condition survey and remaining life assessment 2. Cost-benefit analysis: refurbishment vs. demolition vs. repurposing 3. Decommissioning budget and programme 4. Salvage value assessment 5. Environmental compliance for demolition 6. Final project archive and knowledge management |
| Qatar Authority Requirements | 1. Demolition permit application (if applicable) 2. Environmental clearance for demolition/disposal 3. Utility disconnection coordination (Kahramaa, Ashghal) 4. Municipality approval for site redevelopment (if applicable) |
| GSAS Sustainability Checkpoints | 1. Circular economy assessment: reuse, recycle, recover potential 2. Waste management plan for demolition materials 3. Environmental impact of disposal assessed against GSAS criteria |
| HAI-Specific Actions (SkyStruct) | 1. Project marked as EOL in SkyStruct 2. Archived project moved to read-only status 3. Full project lifecycle data available for analytics and benchmarking 4. Feeds into Stage 0 of any replacement project (lessons learned, cost data, performance data) |
| ENTRY CRITERIA (mandatory) | ☐ Building has reached end of useful life or strategic decision to decommission ☐ Stage 7 monitoring data reviewed ☐ Client decision to initiate EOL process formally recorded |
| EXIT CRITERIA (gate release) | ☐ EOL strategy approved by Client ☐ Decommissioning/demolition complete (if applicable) ☐ Site cleared and handed over (if applicable) ☐ All project records archived in SkyStruct ☐ Salvage value realized ☐ Environmental compliance confirmed ☐ Project record closed in SkyStruct ☐ Lessons Learned (lifecycle) captured |
| FREEZE RULES | Project record freeze. All data archived and locked for audit/reference purposes. No modification to historical records. |

## 3. HAI DEPARTMENTAL FRAMEWORK

| Department | Core Responsibilities |
| --- | --- |
| Project Management (Civil/MEP/Fit-out) | Site management, progress tracking, QA/QC, coordination with consultants and contractors |
| Design Management | Concept, tender, and IFC design coordination; authority compliance; design change control |
| Contracts & Procurement | Tendering, evaluation, Contract Award/contract issuance, variation analysis, cost control |
| Document Control & Admin | Centralized correspondence, drawings, submittals, approvals, letter management |
| Finance & Commercial | IPC verification, cost reporting, retention management, payment tracking |
| FM Transition (MIPC FM) | Post-handover maintenance, O&M review, snag and DLP management |
| HSE | Health, safety, environmental compliance, incident reporting, audit tracking |

## 4. DOCUMENT SUBMISSION & REVIEW WORKFLOW

The Platform shall automate the full 8-step closed-loop document cycle:

- Step 1 — Contractor Preparation: Standardized cover page with mandatory fields enforced by system.

- Step 2 — Contractor DC QC Check: Numbering, revision, completeness, attachments, stamps. Non-compliant = returned with logged comments.

- Step 3 — HAI-DC QC Check: Transmittal verification, numbering, referencing, completeness. Discrepancies = Rejection for Resubmission. Compliant = HAI Master Document Register entry with unique HAI Reference (HAI-[ProjectCode]-[Discipline]-[Type]-[No]-[Rev]).

- Step 4 — Distribution to Reviewer: Auto-assignment by discipline field. Task notification with review deadline (SLA: 3–5 days).

- Step 5 — Engineering Review: Status codes: Approved / Approved with Comments / Rejected-Resubmit / For Information Only. PDF markup within Platform.

- Step 6 — Multi-Discipline Consolidation: Merged comments, PM validation, official HAI Response Document with electronic stamp.

- Step 7 — Issuance to Contractor: Outgoing transmittal logged with HAI Ref, title, discipline, revision, status, reviewer, date.

- Step 8 — Contractor Implementation: Receipt logged. Resubmission generates new revision with cross-reference.

Review SLA Timers: D+3 reminder, D+5 manager escalation, D+7 PM escalation with dashboard flag.

## 5. PLATFORM MODULES

The Service Provider shall deliver the following modules:

- Module 1: EDMS — Structured repository, version control, automated numbering, cover page validation, document taxonomy, transmittal registers, PDF markup, searchable archive.

- Module 2: Document Workflow — 8-step cycle as defined in Section 4.

- Module 3: Correspondence — Letter registry, HAI templates, FIDIC sequence (Notice → Response → Determination), email capture.

- Module 4: Governance Gateways — Budget/Design/Scope Freeze with audit trail, exception workflows. Hard-enforced stage-gate progression per Section 2 definitions.

- Module 5: Approval Matrix — Single accountable approver, 7 workflow types, SLA timers, delegation rules, digital signatures.

- Module 6: Procurement — Supplier database, RFP workflow, Contract Award/contract register, variation tracking.

- Module 7: Quality & Site — IR/NCR forms, daily/weekly reports, photo upload, auto-notifications, S-curve progress tracking.

- Module 8: Authority Coordination — QCDD/Kahramaa/Ashghal/Civil Defense tracker with status board.

- Module 9: Handover & DLP — Digital Handover Package, BCC/NOC tracking, defect lists, warranty database.

- Module 10: KPI Dashboards — Role-based, departmental. KPIs: approval turnaround, stage compliance, cost deviation, variation trend, IPC time, submittal metrics, rejection rates.

- Module 11: Bottleneck Detection — Stalled approvals, overloaded managers, recurring delay nodes.

- Module 12: Contractor Scoring — Timeliness, variation rate, defect rate, claims, response time.

- Module 13: Lessons Learned — Categorized by root cause, linked to stage, convertible to preventive rules.

- Module 14: Analytics (Phase 4) — Predictive cost alerts, delay forecasting, variation patterns, compliance anomaly detection, manager performance.

- Module 15: ERP Integration — Bi-directional with Artan Holding’s ERP (Budget, Procurement, Finance, HR, IT). Rule: SkyStruct governs the decision; ERP executes the transaction.

- Module 16: External Access — Controlled permissions for contractors, consultants, authorities.

- Module 17: Meeting & Calendar — Milestone sync, meeting minutes, MS Outlook integration.

## 6. DELIVERY MODEL

Hybrid: fixed milestones, agile execution within phases. Two-week sprints, bi-weekly demos. Workshops: min 2/week, 4 hours, face-to-face Qatar through Phase 2. Onsite: discovery, UAT, go-live. Remote: config, build, integration, testing.

## 7. MILESTONE SCHEDULE

| Phase | Milestone | Date | Key Deliverables | Class |
| --- | --- | --- | --- | --- |
| 1 | Foundation | 25 Mar 2026 | Lifecycle 0-8 with RIBA/RICS/Qatar/GSAS gate enforcement, 3 freeze gateways, approval matrix, SLA timers, delegation, digital signatures, full EDMS with 8-step workflow, correspondence module, document naming, UI backlog baseline, UAT build | CRITICAL |
| 2 | Pilot + Ops | 25 May 2026 | Pilot live (all modules), dashboards, KPI engine, bottleneck detection, lessons learned, procurement, quality/site, authority tracker, external access, ERP design sign-off, training | CRITICAL |
| 3 | ERP + Rollout | 20 Jun 2026 | ERP bi-directional live, contractor scoring, handover/DLP, data export, calendar/email integration, full rollout, stabilization | CRITICAL |
| 4 | Analytics | Q3/Q4 2026 | Predictive analytics, delay forecasting, variation patterns, compliance anomaly, manager performance, enhanced lessons learned, multi-jurisdiction readiness | MINOR |

## 8. PAYMENT TERMS

| Milestone | % Total | Trigger | Target |
| --- | --- | --- | --- |
| Mobilization | 30% | Contract execution + workshop calendar locked | 2 Mar 2026 |
| Phase 1 Complete | 20% | Written UAT sign-off on Foundation | 25 Mar 2026 |
| Phase 2 Complete | 20% | Written pilot acceptance | 25 May 2026 |
| Phase 3 Complete | 30% | Written ERP + rollout acceptance | 20 Jun 2026 |

- No payment without written Acceptance.

- Subscription from month after Phase 2.

- Phase 4 payments per separate amendment.

## 9. ACCEPTANCE AND QUALITY

- 10 business days to accept/reject. No deemed acceptance (silence ≠ acceptance).

- Defects: Critical ≤48h, Major ≤5 days, Minor ≤10 days or backlog.

## 10. RESPONSIBILITIES

### 10.1 Client

- Nominate pilot + stakeholders within 5 days. Named approvers per stage. ERP owner + docs by Week 2. Timely sign-offs. Workshop availability. Data residency confirmation within 15 days.

### 10.2 Service Provider

- Deliver all modules per this SOW. WBS within 5 days. Test cases and documentation for all gates. Onsite for discovery/UAT/go-live. Dedicated PM. Training. Escrow within 60 days. BCP within 30 days.

## 11. ASSUMPTIONS AND EXCLUSIONS

- Assumptions: HAI provides timely access; workshops from kickoff; ERP scope confirmed early; SkyStruct confirms full capability (disclose limitations in writing before execution).

- Exclusions: Additional lifecycle models beyond 0–8; legacy data re-engineering; UI beyond signed backlog; third-party integrations beyond ERP; institutional website; SharePoint (unless in ERP scope).

SCHEDULE B — REQUIREMENTS REGISTER

Service Provider confirms acceptance of all requirements by executing this Agreement.

STAGE GATE ENFORCEMENT

| Ref | Module | Requirement | Acceptance Criteria | Phase | Priority |
| --- | --- | --- | --- | --- | --- |
| SG.1 | Gate | RIBA-aligned entry/exit criteria per stage | Every HAI Stage (0-8) has configurable checklist; items enforced at system level | Ph1 | Critical |
| SG.2 | Gate | Stage-gate progression blocking | System blocks advancement if mandatory checklist items incomplete | Ph1 | Critical |
| SG.3 | Gate | RICS Cost Plan checkpoints per stage | Cost plan level (0-4) tracked; budget sign-off mandatory at designated stages | Ph1 | Critical |
| SG.4 | Gate | Qatar authority gate tracking | DC1, DC2, BCC, Kahramaa, Ashghal, Civil Defense status tracked per stage | Ph1 | Critical |
| SG.5 | Gate | GSAS checkpoint integration | GSAS milestones (registration, design assessment, LoC, construction audit, final cert) tracked | Ph2 | High |
| SG.6 | Gate | Freeze enforcement (Budget/Design/Scope/Regulatory) | 4 freeze types configurable; exception workflow required to bypass; full audit trail | Ph1 | Critical |
| SG.7 | Gate | Gate exception workflow | Formal exception with cost/time impact, approver sign-off, audit trail | Ph1 | Critical |

EDMS & DOCUMENT WORKFLOW

| Ref | Module | Requirement | Acceptance Criteria | Phase | Priority |
| --- | --- | --- | --- | --- | --- |
| D.1 | EDMS | Structured repository by project/discipline/type | Matches HAI org structure; searchable; access-controlled | Ph1 | Critical |
| D.2 | EDMS | Automated version control | Every revision tracked with unique ID and change history | Ph1 | Critical |
| D.3 | EDMS | Automated document numbering (HAI convention) | HAI-[ProjectCode]-[Discipline]-[Type]-[No]-[Rev] | Ph1 | Critical |
| D.4 | EDMS | Cover page validation | Submission blocked if mandatory fields missing | Ph1 | Critical |
| D.5 | Workflow | 8-step document submission/review cycle | Full cycle automated per Section 4 | Ph1 | Critical |
| D.6 | Workflow | Review SLA timers (D+3/D+5/D+7) | Configurable; auto-escalation chain | Ph1 | Critical |
| D.7 | Workflow | Review status codes | APP/APP-COM/REJ/INFO per review | Ph1 | Critical |
| D.8 | EDMS | Transmittal register (in/out) | Auto-logged with full metadata | Ph1 | Critical |
| D.9 | EDMS | PDF markup | In-platform markup on PDF docs | Ph1 | High |

GOVERNANCE & APPROVALS

| Ref | Module | Requirement | Acceptance Criteria | Phase | Priority |
| --- | --- | --- | --- | --- | --- |
| G.1 | Freeze | Budget Freeze gateway | Lock enforced; exception workflow; ERP sync; audit trail | Ph1 | Critical |
| G.2 | Freeze | Design Freeze gateway | Revision control after lock; exception handling | Ph1 | Critical |
| G.3 | Freeze | Scope Freeze gateway | No scope changes without variation + freeze exception | Ph1 | Critical |
| G.4 | Freeze | Regulatory Freeze gateway | No changes affecting authority approvals without re-submission | Ph1 | Critical |
| G.5 | Approval | Single accountable approver per stage/process | Approve-once mechanism; no circular routing | Ph1 | Critical |
| G.6 | Approval | 7 configurable workflow types | Budget, comparison, Contract Award, advance, IPC, variation, design/gateway | Ph1 | Critical |
| G.7 | Approval | SLA timers + escalation | Per approval type; breach triggers auto-escalation | Ph1 | Critical |
| G.8 | Approval | Authority delegation | Named substitute, defined period, audit trail | Ph1 | High |
| G.9 | Approval | Digital signatures | Electronic stamp with actor ID, timestamp, legal defensibility | Ph1 | High |
| G.10 | Audit | Full audit trail for every action | Exportable audit report | Ph1 | Critical |

CORRESPONDENCE, PROCUREMENT, QUALITY, AUTHORITY, HANDOVER

| Ref | Module | Requirement | Acceptance Criteria | Phase | Priority |
| --- | --- | --- | --- | --- | --- |
| C.1 | Corr. | Letter registry linked to projects | Logged with ref, project, stakeholder | Ph1 | Critical |
| C.2 | Corr. | FIDIC correspondence sequence | Notice → Response → Determination with SLA | Ph2 | High |
| P.1 | Procure | Supplier/contractor database | Searchable; linked to scorecard | Ph2 | High |
| P.2 | Procure | RFP, evaluation, recommendation workflow | End-to-end in Platform | Ph2 | High |
| P.3 | Procure | Contract Award/contract register with alerts | Expiry/renewal alerts; variation linked | Ph2 | High |
| Q.1 | Quality | IR/NCR digital forms | Mandatory fields; linked to project/trade | Ph2 | Critical |
| Q.2 | Quality | Daily/weekly site reports with photos | Templates + photo upload | Ph2 | High |
| Q.3 | Quality | S-curve progress tracking | % complete, earned value, visualization | Ph2 | High |
| A.1 | Authority | QCDD/Kahramaa/Ashghal/CD tracker | Status board with date tracking | Ph2 | High |
| H.1 | Handover | Digital Handover Package | Docs, warranties, O&M, as-builts | Ph3 | High |
| H.2 | DLP | Defect list with assignment/closure | Creation, assignment, status, close | Ph3 | High |
| H.3 | DLP | Warranty/O&M database | Searchable by system/equipment; alerts | Ph3 | High |

KPI, ANALYTICS & ERP

| Ref | Module | Requirement | Acceptance Criteria | Phase | Priority |
| --- | --- | --- | --- | --- | --- |
| K.1 | KPI | Approval turnaround per department | Real-time; RAG status | Ph2 | Critical |
| K.2 | KPI | Cost deviation from baseline | Real-time vs frozen; project/portfolio | Ph2 | Critical |
| K.3 | KPI | IPC processing time | Submission → cert → payment; bottleneck ID | Ph2 | Critical |
| K.4 | KPI | Bottleneck flagging | Stalled, overloaded, recurring delays | Ph2 | Critical |
| K.5 | Score | Contractor scorecard | Timeliness, variation, defects, claims, response | Ph3 | High |
| K.6 | Lessons | Lessons learned database | Categorized; linked to stage; convertible to rules | Ph2 | High |
| K.7 | Analytics | Predictive cost deviation | Rule-based Ph2; ML Ph4 | Ph2/4 | High |
| K.8 | Analytics | Compliance anomaly detection | Bypass flagging, unsigned deliverables | Ph4 | High |
| E.1 | ERP | Bi-directional ERP integration | Budget/PO/IPC synced; validated E2E | Ph3 | Critical |
| E.2 | ERP | Financial lock via ERP | Budget freeze enforced in both systems | Ph3 | Critical |
| E.3 | Access | External user access | Controlled per party/project | Ph2 | High |
| E.4 | Calendar | Meeting/calendar + Outlook | Milestone sync; email capture | Ph3 | Medium |

TOTAL REQUIREMENTS: 53 functional + 7 stage gate = 60

SCHEDULE C — COMMERCIAL TERMS

[SkyStruct to provide revised quotation aligned to expanded scope.]

Payment: 30/20/20/30. Subscription from Phase 2 Acceptance. 15-year step-down: Y1-3 base; Y4-7 [X]%; Y8-11 [X]%; Y12-15 [X]%. [SkyStruct to propose.]

SCHEDULE D — SLA

| Category | Target | Measure | Remedy |
| --- | --- | --- | --- |
| Availability | 99.5% monthly | Excl. maint (4h/mo, 48h notice) | 5% credit per 0.5% below |
| Critical Bug | ≤4h resp; ≤24h fix | Ticket → resolution | CTO escalation >24h |
| Major Bug | ≤8h resp; ≤5d fix | Ticket → resolution | Escalation >5d |
| Backup | Daily; RPO≤1h | Logs on request | Immediate investigation |
| DR | RTO≤4h | Annual test | Credit if exceeded |
| Support | Biz:≤2h; After:≤8h | Ticket → 1st response | Escalation matrix |

SCHEDULE E — KEY CONTACTS

| Role | HAI | SkyStruct |
| --- | --- | --- |
| Contract Owner | [Name / Title] | [Name / Title] |
| Project Manager | [Name / Title] | [Name / Title] |
| Technical Lead | [Name / Title] | [Name / Title] |
| ERP Owner | [Name / Title] | [Name / Title] |
| Escalation | [Name / Title] | [Name / Title] |
| Notices | [Address + Email] | [Address + Email] |

SCOPE OF WORK NO. 1 — EXECUTION

By executing this Scope of Work, the Service Provider confirms that:

- (a) It has reviewed all 60 requirements in Schedule B including the 7 Stage Gate enforcement requirements.

- (b) It has reviewed the Stage Gate Definitions in Section 2 (HAI Stages 0–8) including all RIBA core tasks, RICS PM deliverables, Qatar authority requirements, and GSAS sustainability checkpoints.

- (c) Its Platform is capable of delivering all specified features within the phased timeline.

- (d) Any limitation or inability to deliver must be disclosed in writing prior to execution.

Name:

Title: Authorized Representative

Entity: House of Architecture & Interiors (HAI)

Date: ___________________

Signature: ___________________

Name:

Title: Authorized Representative

Entity: SkyStruct Technologies

Date: ___________________

Signature: ___________________

— END OF DOCUMENT —