CONTRACTUAL DELIVERABLE

SOW No. 1 / Schedule B

Level 1: Process Flow Diagrams

SkyStruct Platform Customization

House of Architecture & Interiors (HAI)

Prepared for SkyStruct Technologies

HAI-SS-PFD-2026-001-C

28 February 2026 | Version 1.0

CONFIDENTIAL — CONTRACTUAL

# Document Control

| Document Reference | HAI-SS-PFD-2026-001-C |
| --- | --- |
| Version | 1.0 — CONTRACTUAL |
| Date | 28 February 2026 |
| Prepared by | HAI PMO — Project Governance Division |
| Reviewed by | [___________________________] |
| Approved by | [___________________________] |
| Classification | CONFIDENTIAL — CONTRACTUAL |
| Total Process Flows | 23 (PF-01 through PF-23) |

# Contractual Preamble

## 1. Scope & Applicability

This document defines the mandatory process flow specifications for the SkyStruct Platform. The Service Provider shall configure all workflows exactly as specified herein. Each process flow defines the actors, steps, system behaviors, SLAs, decision points, freeze interactions, ERP integration points, and KPIs that the Platform must support.

## 2. Compliance Prerequisite

Process flow compliance is a prerequisite for Phase 1 and Phase 2 acceptance per Section 7.1 and 7.2 of the Manufacturing & Construction Roadmap (HAI-SS-IMP-ROADMAP-2026-001). The Service Provider shall not claim milestone payment for any phase until all process flows assigned to that phase have been demonstrated and accepted by HAI.

## 3. Change Management

Deviations from any process flow require a written Change Request per Framework Agreement Clause 10. No verbal or informal modifications are valid. The Service Provider shall document any technical limitation that prevents exact implementation of a specified workflow and propose an alternative that meets the same functional outcome.

# SOW Traceability Matrix

The following matrix maps all 23 process flows to their SOW module and requirement references:

| PF-ID | Process Flow | Module | SOW Refs | RIBA Stages |
| --- | --- | --- | --- | --- |
| PF-01 | Document Submission & Review (8-Step Cycle) | EDMS | D.1-D.4, D.7 | All |
| PF-02 | Correspondence Management (FIDIC-Aligned) | Correspondence | D.8-D.9 | All |
| PF-03 | Variation Order Workflow | Variations | G.7-G.10, SG.5 | Stages 4-5 |
| PF-04 | Procurement (RFP to Contract Award) | Procurement | P.1-P.3, SG.3 | Stage 3 |
| PF-05 | Stage-Gate Progression | Stage Gate | SG.1-SG.7 | All transitions |
| PF-06 | Freeze Exception Workflow | Governance | SG.4, SG.5 | Post-freeze stages |
| PF-07 | Authority Submission Tracking | Authority | A.1 | Stages 2-5 |
| PF-08 | IPC Processing (Certification & Payment) | IPC | C.1-C.2 | Stages 4-6 |
| PF-09 | Approval Workflow Engine (7 Types) | Approvals | G.1-G.6 | All |
| PF-10 | Quality & Site Supervision | Quality | Q.1-Q.3 | Stages 4-5 |
| PF-11 | Spatial Coordination & Cost Management | Financial Control | G.7-G.10, SG.3 | Stages 1-6 |
| PF-12 | Risk Register Management | Governance | SG.2, SG.7 | Stages 1-6 |
| PF-13 | Contractor Performance Scoring | KPI & Analytics | K.1-K.8 | Stages 4-6 |
| PF-14 | Lessons Learned Capture | Quality | Q.3, H.3 | All (captured), Stages 5-6 (formal review) |
| PF-15 | Handover & DLP Management | Handover & DLP | H.1-H.3 | Stages 5-7 |
| PF-16 | Meeting & Action Tracking | Integration | E.4 | All |
| PF-17 | External Stakeholder Access (Contractor/Consultant Portal) | Integration & Access | E.1-E.3 | Stages 3-6 |
| PF-18 | Report Generation & Export | KPI & Analytics | K.4-K.8 | All |
| PF-19 | User & Role Management | Integration & Access | E.1-E.2 | N/A (system admin) |
| PF-20 | ERP Bi-Directional Integration | Integration | E.1-E.4 | Stages 3-6 |
| PF-21 | Dashboard & Analytics Engine | KPI & Analytics | K.1-K.8 | All |
| PF-22 | Notification & Escalation Engine | Governance | G.4-G.6 | All |
| PF-23 | Predictive Analytics & Trend Analysis | KPI & Analytics | K.5-K.8 | All (data from Stage 2+) |

# PF-01: Document Review (8-Step Cycle)

Module: EDMS | SOW References: D.1-D.4, D.7 | RIBA Stages: All

## Purpose

Manage submission, review, and approval of all project documents with automated tracking, version control, and audit compliance. Ensures HAI numbering standards, mandatory field completion, and discipline-based review routing.

## Actors & Responsibilities

| Actor | Role | Department |
| --- | --- | --- |
| Originator | Submits documents | Consultant/Contractor |
| HAI Doc Controller | Validates completeness | HAI Administration |
| HAI Reviewer | Technical review | Discipline Lead |
| HAI PM | Oversight | Project Management |

## Step-by-Step Process

| Step | Actor | Action | System Behavior | SLA | Exception |
| --- | --- | --- | --- | --- | --- |
| 1 | Originator | Upload document with cover page | System validates HAI numbering, mandatory fields | — | — |
| 2 | Doc Controller | Receive and check completeness | Log submission date, flag incomplete items | 2 days | Missing info → return to originator |
| 3 | Doc Controller | Assign reviewer per discipline matrix | Route to appropriate reviewer | 1 day | No reviewer available → escalate |
| 4 | Reviewer | Review with markup tools | Track mark-up timeline | 5d (design), 3d (shop drawings) | Urgent request → expedited review |
| 5 | Reviewer | Mark status code (A/B/C/D) | Log review outcome | — | — |
| 6 | Originator | Resubmit if B/C status | System tracks revision chain | 10 days | Multiple rejections → escalate |
| 7 | Doc Controller | If A: update register, issue transmittal | Auto-generate transmittal | 1 day | — |
| 8 | System | Archive with full audit trail | Index and store document | — | — |

## Decision Points

- Status code assignment (A/B/C/D) based on review outcome

- Resubmission required (B/C status vs. A status)

- Design Freeze: blocks new design submissions unless exception approved

## Freeze Interaction

Design Freeze blocks new design submissions unless exception approved

## ERP Integration Points

Document metadata synced to ERP for audit compliance

## KPIs Captured

- Review cycle time (days from submission to final status)

- First-time approval rate (%)

- SLA compliance % (reviews completed on time)

## Boundary & Exclusions

Covers original submissions through final approval. Excludes internal HAI drafts prior to originator submission. Does not include post-approval document changes (use Variation Order process).

## SOW Requirement References

This process flow is mandated by SOW Schedule B requirements: D.1-D.4, D.7. Module: EDMS.

## Acceptance Test References

The following Level 4 Acceptance Tests verify this process flow: P1-007, P1-008, P1-009, P1-010

## Configuration Obligations

The Service Provider SHALL configure HAI document numbering rules (HAI-[ProjectCode]-[Discipline]-[Type]-[No]-[Rev]), discipline-based review matrix routing, 8-step document workflow with status codes A/B/C/D, and cover page mandatory field validation.

## Compliance Verification

The Service Provider shall demonstrate this process flow through: (1) End-to-end walkthrough with HAI project data, (2) User acceptance testing per Level 4 test scenarios, (3) Audit trail verification showing all steps logged with timestamps.

# PF-02: Correspondence (FIDIC-Aligned)

Module: Correspondence | SOW References: D.8-D.9 | RIBA Stages: All

## Purpose

Track all contractual and administrative correspondence with FIDIC-aligned timelines. Enforces response deadlines, escalation triggers, and audit trail for claims and disputes.

## Actors & Responsibilities

| Actor | Role | Department |
| --- | --- | --- |
| HAI PM | Initiates correspondence | Project Management |
| HAI Contracts Manager | Reviews high-value letters | Contracts |
| Contractor PM | Receives and responds | Contractor |
| Employer | Receives notifications | Client Representative |

## Step-by-Step Process

| Step | Actor | Action | System Behavior | SLA | Exception |
| --- | --- | --- | --- | --- | --- |
| 1 | Sender | Draft letter using template | System enforces HAI ref numbering | — | — |
| 2 | Contracts/PM | Review if required | Add comments or require revisions | 1 day | — |
| 3 | Sender | Issue letter with tracking number | Request delivery confirmation | — | — |
| 4 | Recipient | Log receipt date | System records receipt timestamp | — | — |
| 5 | System | Track response deadline per letter type | Auto-calculate deadline (Notice 7d, Response 14d, etc.) | — | — |
| 6 | System | SLA escalation chain | D+3 reminder, D+5 manager escalation, D+7 PM escalation | 3/5/7 days | Override if formal extension issued |
| 7 | Recipient | Response logged and linked | System links to original correspondence | — | Late response flagged |

## Decision Points

- Letter type classification (Notice/Response/Determination/General)

- Escalation trigger on overdue responses

## Freeze Interaction

N/A

## ERP Integration Points

Correspondence log available in ERP for claims and disputes tracking

## KPIs Captured

- Response time (days from issuance to receipt of response)

- Overdue correspondence count

- Correspondence volume per project phase

## Boundary & Exclusions

Covers all formal correspondence (letters, notices, determinations). Excludes internal emails and informal communications.

## SOW Requirement References

This process flow is mandated by SOW Schedule B requirements: D.8-D.9. Module: Correspondence.

## Acceptance Test References

The following Level 4 Acceptance Tests verify this process flow: P1-011, P1-012

## Configuration Obligations

The Service Provider SHALL configure correspondence templates per letter type (Notice/Response/Determination/General), HAI reference numbering, FIDIC-aligned response deadlines, and D+3/D+5/D+7 SLA escalation chain.

## Compliance Verification

The Service Provider shall demonstrate this process flow through: (1) End-to-end walkthrough with HAI project data, (2) User acceptance testing per Level 4 test scenarios, (3) Audit trail verification showing all steps logged with timestamps.

# PF-03: Variation Order

Module: Variations | SOW References: G.7-G.10, SG.5 | RIBA Stages: Stages 4-5

## Purpose

Process variation order claims from contract to approval, including entitlement validation, quantum assessment, budget impact analysis, and approval routing per delegation matrix.

## Actors & Responsibilities

| Actor | Role | Department |
| --- | --- | --- |
| Contractor | Submits VO claim | Contractor |
| HAI PM | Validates entitlement | Project Management |
| HAI QS | Assesses quantum | Quantity Surveying |
| HAI Finance | Reviews budget impact | Finance |
| Approval Authority | Approves per matrix | CEO |

## Step-by-Step Process

| Step | Actor | Action | System Behavior | SLA | Exception |
| --- | --- | --- | --- | --- | --- |
| 1 | Contractor | Submit VO claim | System validates required fields (cost, justification, time impact) | — | Incomplete → return to contractor |
| 2 | HAI PM | Validate entitlement | PM assessment: valid/not valid per contract | 5 days | Entitlement disputed → escalate |
| 3 | HAI QS | Assess quantum | Independent valuation, cost breakdown verification | 7 days | Quantum disputed → mediation |
| 4 | HAI Finance | Review budget impact | Current budget, approved VOs, this VO, projected total | 3 days | Spatial Coordination breach → freeze exception |
| 5 | Approval Authority | Approve per delegation matrix | Route to CEO or delegated authority | 5 days | — |
| 6 | System | Update all registers and sync ERP | Approved VO updates budget baseline, contractor notified | 1 day | — |

## Decision Points

- Entitlement validation (valid/invalid per contract)

- Quantum assessment (agreed/disputed/mediation)

- Value threshold routing per delegation matrix

## Freeze Interaction

Budget Freeze: VO cannot proceed without freeze exception if budget is frozen

## ERP Integration Points

Approved VO updates budget baseline in ERP, contractor notified with payment schedule

## KPIs Captured

- Variation % trend (total VOs / original contract value)

- Assessment turnaround (days from submission to approval)

- Approval cycle time by authority level

## Boundary & Exclusions

Covers contractor-initiated variation claims. Excludes HAI-directed changes (use separate Admin Changes process). Includes both time and cost impacts.

## SOW Requirement References

This process flow is mandated by SOW Schedule B requirements: G.7-G.10, SG.5. Module: Variations.

## Acceptance Test References

The following Level 4 Acceptance Tests verify this process flow: P2-008, P2-009, P2-010

## Configuration Obligations

The Service Provider SHALL configure variation order submission form with mandatory fields, entitlement validation workflow, quantum assessment steps, delegation matrix-based approval routing, and automatic budget baseline update on approval.

## Compliance Verification

The Service Provider shall demonstrate this process flow through: (1) End-to-end walkthrough with HAI project data, (2) User acceptance testing per Level 4 test scenarios, (3) Audit trail verification showing all steps logged with timestamps.

# PF-04: Procurement (RFP to Contract Award)

Module: Procurement | SOW References: P.1-P.3, SG.3 | RIBA Stages: Stage 3

## Purpose

Execute procurement process from request through Contract issuance with competitive bidding, evaluation, approval routing, and ERP PO creation.

## Actors & Responsibilities

| Actor | Role | Department |
| --- | --- | --- |
| HAI PM | Initiates request | Project Management |
| HAI Procurement | Manages RFP process | Procurement |
| HAI Contracts | Prepares recommendation | Contracts |
| Approval Authority | Approves award | CEO |

## Step-by-Step Process

| Step | Actor | Action | System Behavior | SLA | Exception |
| --- | --- | --- | --- | --- | --- |
| 1 | HAI PM | Initiate procurement request | System creates request with scope, budget ref, estimated value | — | — |
| 2 | HAI Procurement | Prepare RFP package | Compile specs, terms, bid schedule | 3 days | — |
| 3 | System | Issue RFP to suppliers | Log RFP, enforce response deadline | — | — |
| 4 | HAI Procurement & PM | Evaluate bids with comparison sheet | Technical & commercial evaluation, compliance check | 5 days | Non-compliant bids → exclude |
| 5 | HAI Contracts | Prepare recommendation memo | Award recommendation with justification | 2 days | — |
| 6 | Approval Authority | Approve per matrix | Route based on Contract Award value threshold | 3 days | — |
| 7 | HAI Contracts | Issue Contract Award/Contract | Generate contract, obtain signatures | 2 days | — |
| 8 | System | Push to ERP for PO creation | Auto-create ERP PO, return PO number | 1 day | Integration failure → manual fallback |

## Decision Points

- Bid compliance check (compliant/non-compliant)

- Recommendation approval (award/re-tender)

- Award decision by approval authority

## Freeze Interaction

Budget Freeze must be approved (Gate 3) before procurement module unlocks

## ERP Integration Points

Approved Contract Award → ERP PO creation, PO number returned to SkyStruct

## KPIs Captured

- Procurement cycle time (RFP to Contract Award)

- Bid evaluation turnaround

- PO creation lag (Contract Award issued → ERP PO available)

## Boundary & Exclusions

Covers RFP through Contract Award issuance. Excludes expedited purchases (handled separately). Post-award order changes use Variation Order process.

## SOW Requirement References

This process flow is mandated by SOW Schedule B requirements: P.1-P.3, SG.3. Module: Procurement.

## Acceptance Test References

The following Level 4 Acceptance Tests verify this process flow: P2-011, P2-012, P2-013

## Configuration Obligations

The Service Provider SHALL configure procurement request form, RFP template auto-population, bid comparison sheet generation, evaluation criteria weighting, delegation matrix-based approval, Contract Award/contract template generation, and ERP PO creation API integration.

## Compliance Verification

The Service Provider shall demonstrate this process flow through: (1) End-to-end walkthrough with HAI project data, (2) User acceptance testing per Level 4 test scenarios, (3) Audit trail verification showing all steps logged with timestamps.

# PF-05: Stage Gate-Gate Progression

Module: Stage Gate | SOW References: SG.1-SG.7 | RIBA Stages: All transitions

## Purpose

Manage stage advancement with mandatory exit criteria validation, freeze rule activation, and digital approval by gate authority. Gates: 1 (Preparation & Briefing), 2 (Concept Design), 3 (Spatial Coordination), 4 (Technical Design), 5 (Manufacturing & Construction), 6 (Handover), 7 (In Use & DLP).

## Actors & Responsibilities

| Actor | Role | Department |
| --- | --- | --- |
| HAI PM | Requests stage advancement | Project Management |
| Gate Approver(s) | Reviews and approves | Authority per matrix |
| System | Validates and routes | Governance |

## Step-by-Step Process

| Step | Actor | Action | System Behavior | SLA | Exception |
| --- | --- | --- | --- | --- | --- |
| 1 | HAI PM | Request stage advancement | System opens gate package checklist | — | — |
| 2 | System | Validate ALL exit criteria | Check RIBA, RICS, Qatar, GSAS, HAI-specific standards | — | Incomplete → block, show missing items |
| 3 | System | If complete: route to Gate Approver(s) | Create approval task per matrix | — | — |
| 4 | Gate Approver | Review gate package | Assess checklist, evidence, deliverables | 5 days | — |
| 5 | Gate Approver | Approve/Reject with digital signature | Log approval decision | — | Rejection → return to PM for remediation |
| 6 | System | Advance stage, activate freeze rules | Stage status updated, freeze rules engaged | 1 day | — |
| 7 | System | Create next stage checklist | Auto-populate stage tasks and deliverables | — | — |

## Decision Points

- Exit criteria validation (all-or-nothing: all must pass)

- Gate approval decision (Approve/Reject)

## Freeze Interaction

Stage advancement activates applicable freezes: Design Freeze @ Gate 4, Budget Freeze @ Gate 3

## ERP Integration Points

Stage status synced to ERP project record

## KPIs Captured

- Stage cycle duration (days from start to gate approval)

- Gate approval turnaround

- Checklist completion rate at gate

## Boundary & Exclusions

Covers stage transitions only. Excludes within-stage activities. Gates are all-or-nothing (cannot proceed with partial exit criteria).

## SOW Requirement References

This process flow is mandated by SOW Schedule B requirements: SG.1-SG.7. Module: Stage Gate.

## Acceptance Test References

The following Level 4 Acceptance Tests verify this process flow: P1-001, P1-002, P1-003, P1-004, P1-005

## Configuration Obligations

The Service Provider SHALL configure all 10 stage gates (0,1,2,3,3.1,4,5,6,7,8) with entry/exit checklists per SOW Section 2, RIBA/RICS/Qatar/GSAS criteria per stage, mandatory blocking on incomplete criteria, freeze rule activation per gate, and digital signature mechanism.

## Compliance Verification

The Service Provider shall demonstrate this process flow through: (1) End-to-end walkthrough with HAI project data, (2) User acceptance testing per Level 4 test scenarios, (3) Audit trail verification showing all steps logged with timestamps.

# PF-06: Freeze Exception

Module: Governance | SOW References: SG.4, SG.5 | RIBA Stages: Post-freeze stages

## Purpose

Process requests to lift freeze rules (Technical Design, Spatial Coordination, Regulatory) on a per-item basis with impact assessment and senior authority approval.

## Actors & Responsibilities

| Actor | Role | Department |
| --- | --- | --- |
| Requester | Submits exception request | Any PM/Reviewer |
| HAI PM | Technical assessment | Project Management |
| HAI Finance | Financial impact assessment | Finance |
| Senior Authority | Approves/rejects | CEO/Executive |

## Step-by-Step Process

| Step | Actor | Action | System Behavior | SLA | Exception |
| --- | --- | --- | --- | --- | --- |
| 1 | Requester | Submit exception request | System captures: which freeze, what change, justification, cost/time impact | — | — |
| 2 | HAI PM | Technical assessment | PM evaluates impact and recommends (recommended/not recommended) | 2 days | — |
| 3 | HAI Finance | Financial impact confirmation | Finance validates cost/budget impact | 2 days | — |
| 4 | Senior Authority | Approve/reject | Senior decision with notes | 3 days | — |
| 5 | System | Lift freeze for specific scope only | Update freeze status, record audit trail with decision rationale | 1 day | Rejection → archive as rejected |

## Decision Points

- PM recommendation (recommended/not recommended)

- Finance confirmation (within budget/requires amendment)

- Authority approval (approve/reject)

## Freeze Interaction

This IS the freeze exception process; per-item exceptions only, not blanket lifts

## ERP Integration Points

If budget impact, ERP baseline updated with freeze exception amendment

## KPIs Captured

- Exception frequency per project (trend)

- Approval rate (approved / total submitted)

- Spatial Coordination impact of exceptions (total exception value)

## Boundary & Exclusions

Handles exceptions to active freeze rules only. Excludes blanket freeze lifting (CEO decision only). Each exception is audited and versioned.

## SOW Requirement References

This process flow is mandated by SOW Schedule B requirements: SG.4, SG.5. Module: Governance.

## Acceptance Test References

The following Level 4 Acceptance Tests verify this process flow: P1-005, P1-006

## Configuration Obligations

The Service Provider SHALL configure all 4 freeze types (Spatial Coordination/Technical Design/Scope/Regulatory), per-item exception request form with mandatory impact fields, sequential PM→Finance→Authority approval routing, and audit trail with scope-limited freeze lifting.

## Compliance Verification

The Service Provider shall demonstrate this process flow through: (1) End-to-end walkthrough with HAI project data, (2) User acceptance testing per Level 4 test scenarios, (3) Audit trail verification showing all steps logged with timestamps.

# PF-07: Authority Submissions

Module: Authority | SOW References: A.1 | RIBA Stages: Stages 2-5

## Purpose

Track submissions to external authorities (QCDD, Kahramaa, Ashghal, Civil Defense) with status milestones, comment resolution, and stage gate integration.

## Actors & Responsibilities

| Actor | Role | Department |
| --- | --- | --- |
| HAI Technical Design Manager | Prepares submission | Technical Design |
| HAI PM | Reviews and authorizes | Project Management |
| External Authorities | Reviews and approves | Government Agencies |

## Step-by-Step Process

| Step | Actor | Action | System Behavior | SLA | Exception |
| --- | --- | --- | --- | --- | --- |
| 1 | Technical Design Manager | Prepare submission package | Compile per authority checklist (DC1, DC2, BCC, etc.) | — | — |
| 2 | HAI PM | Review and authorize submission | PM approval with comments | 1 day | — |
| 3 | Technical Design Manager | Submit externally | Log submission date, reference number | — | — |
| 4 | System | Track authority status | Monitor: Submitted/Review/Comments/Approved/Rejected | 30-60d typical | — |
| 5 | Technical Design Manager | Process authority comments | If comments: address and resubmit | Per authority | Rejection → PM/Authority escalation |
| 6 | System | Update stage gate checklist | Mark completion: DC1→Stage 2, DC2→Stage 3.1, BCC→Stage 6 | — | — |

## Decision Points

- Package completeness check (complete/incomplete)

- Authority decision (approved/comments/rejected)

## Freeze Interaction

Regulatory Freeze: authority resubmission requires freeze exception if in frozen stage

## ERP Integration Points

Authority approval milestones synced to ERP for stage gate scheduling

## KPIs Captured

- Authority cycle duration per type (days from submit to approval)

- Conditions closure rate (authority conditions met)

- Resubmission count per authority

## Boundary & Exclusions

Covers external authority submissions only. Excludes internal HAI design review (use Document Submission process). Authorities: QCDD, Kahramaa, Ashghal, Civil Defense.

## SOW Requirement References

This process flow is mandated by SOW Schedule B requirements: A.1. Module: Authority.

## Acceptance Test References

The following Level 4 Acceptance Tests verify this process flow: P2-016, P2-017

## Configuration Obligations

The Service Provider SHALL configure authority type register (QCDD/Kahramaa/Ashghal/Civil Defense), submission type checklists (DC1/DC2/BCC/NOC), status tracking board, SLA monitoring, condition tracking with closure workflow, and automatic stage gate checklist update on authority approval.

## Compliance Verification

The Service Provider shall demonstrate this process flow through: (1) End-to-end walkthrough with HAI project data, (2) User acceptance testing per Level 4 test scenarios, (3) Audit trail verification showing all steps logged with timestamps.

# PF-08: IPC Processing (Certification & Payment)

Module: IPC | SOW References: C.1-C.2 | RIBA Stages: Stages 4-6

## Purpose

Process Interim Payment Certificates with quantity verification, retention deduction, certification approval, and payment instruction routing to ERP.

## Actors & Responsibilities

| Actor | Role | Department |
| --- | --- | --- |
| Contractor | Submits IPC | Contractor |
| HAI QS | Verifies quantities | Quantity Surveying |
| HAI PM | Recommends certification | Project Management |
| Approval Authority | Certifies | Authority per matrix |
| HAI Finance | Processes payment | Finance |

## Step-by-Step Process

| Step | Actor | Action | System Behavior | SLA | Exception |
| --- | --- | --- | --- | --- | --- |
| 1 | Contractor | Submit IPC with BOQ breakdown | System validates completeness and format | — | Incomplete → return to contractor |
| 2 | HAI QS | Verify quantities on-site | Physical measurement, deduction calculation (retentions, defects) | 5 days | Disputed qty → contractor re-measure |
| 3 | HAI PM | Review and recommend certification | PM assessment with scope completion check | 2 days | — |
| 4 | Approval Authority | Certify | Authority issues certificate with certified amount | 3 days | — |
| 5 | HAI Finance | Process payment instruction | Prepare payment from budget, apply retentions | 2 days | — |
| 6 | System | Push certified IPC to ERP | Auto-create payment instruction, actuals updated | 1 day | Integration failure → manual fallback |

## Decision Points

- Quantity verification (quantity accepted / disputed)

- Deduction disputes (retain / release)

- Certification approval (approve / reject)

## Freeze Interaction

Budget Freeze: IPC against frozen budget requires exception if exceeds baseline

## ERP Integration Points

Certified IPC → ERP payment instruction, actuals updated in project financials

## KPIs Captured

- IPC processing time (submission → certification → payment)

- Certification accuracy (certified vs. claimed amount ratio)

- Payment cycle (certification → bank payment)

## Boundary & Exclusions

Covers monthly/interim payment certificates. Excludes final accounts (separate process). Includes retentions and provisional sums per contract.

## SOW Requirement References

This process flow is mandated by SOW Schedule B requirements: C.1-C.2. Module: IPC.

## Acceptance Test References

The following Level 4 Acceptance Tests verify this process flow: P2-014, P2-015

## Configuration Obligations

The Service Provider SHALL configure IPC submission form with BOQ breakdown, quantity verification workflow, retention calculation engine, certification approval routing per delegation matrix, payment instruction generation, and ERP payment API integration.

## Compliance Verification

The Service Provider shall demonstrate this process flow through: (1) End-to-end walkthrough with HAI project data, (2) User acceptance testing per Level 4 test scenarios, (3) Audit trail verification showing all steps logged with timestamps.

# PF-09: Approval Engine (7 Types)

Module: Approvals | SOW References: G.1-G.6 | RIBA Stages: All

## Purpose

Centralized approval engine for 7 approval types: Gate, Document, Variation, Procurement, Spatial Coordination, IPC, Freeze Exception. Includes notification, escalation, delegation, and audit logging.

## Actors & Responsibilities

| Actor | Role | Department |
| --- | --- | --- |
| Requester | Submits for approval | Various |
| Approver(s) | Reviews and decides | Authority per matrix |
| Delegate | Acts with authority | Technical Designated substitute |
| System | Routes and tracks | Governance |

## Step-by-Step Process

| Step | Actor | Action | System Behavior | SLA | Exception |
| --- | --- | --- | --- | --- | --- |
| 1 | System | Route approval per type and matrix | Select approver(s) based on value, type, project | — | — |
| 2 | System | Notify approver | Email, in-app, mobile push per preferences | — | — |
| 3 | Approver | Review with full context | View all supporting details, previous comments | — | — |
| 4 | Approver | Decide and add notes | Approve / Reject / Return with rationale | 3/5/7 day SLA per type | Escalation if overdue |
| 5 | System | Check delegation | If delegated: route to delegate with full authority | — | — |
| 6 | System | Log decision | Timestamp, digital signature (if required), audit trail | — | — |
| 7 | System | SLA escalation chain | D+3 reminder, D+5 manager, D+7 PM | — | — |

## Decision Points

- Approval type classification (7 types)

- Authority matrix routing

- Approval decision (Approve/Reject/Return)

- Delegation active yes/no

## Freeze Interaction

N/A (approval engine serves all freezes)

## ERP Integration Points

Approval decisions synced to ERP audit log for compliance

## KPIs Captured

- Approval turnaround by type (days to decision)

- SLA compliance % (approvals completed on time)

- Delegation frequency (% of approvals delegated)

## Boundary & Exclusions

Covers all 7 approval types. Excludes ad-hoc approvals outside formal matrix. Approvals are immutable once logged (no post-decision modification).

## SOW Requirement References

This process flow is mandated by SOW Schedule B requirements: G.1-G.6. Module: Approvals.

## Acceptance Test References

The following Level 4 Acceptance Tests verify this process flow: P1-013, P1-014, P1-015, P1-016

## Configuration Obligations

The Service Provider SHALL configure all 7 approval workflow types (Gate/Document/Variation/Procurement/Spatial Coordination/IPC/Freeze Exception), delegation mechanism with substitute authority, D+3/D+5/D+7 SLA escalation chain, digital signature, and immutable audit logging.

## Compliance Verification

The Service Provider shall demonstrate this process flow through: (1) End-to-end walkthrough with HAI project data, (2) User acceptance testing per Level 4 test scenarios, (3) Audit trail verification showing all steps logged with timestamps.

# PF-10: Quality Supervision

Module: Quality | SOW References: Q.1-Q.3 | RIBA Stages: Stages 4-5

## Purpose

Conduct on-site inspections, raise non-conformance reports (NCRs), track rectification, and maintain contractor quality scorecard.

## Actors & Responsibilities

| Actor | Role | Department |
| --- | --- | --- |
| HAI Site Inspector | Conducts inspections | Quality Assurance |
| HAI QA Manager | Manages NCRs | Quality Assurance |
| Contractor QC | Rectifies defects | Contractor |
| HAI PM | Oversight | Project Management |

## Step-by-Step Process

| Step | Actor | Action | System Behavior | SLA | Exception |
| --- | --- | --- | --- | --- | --- |
| 1 | Inspector | Create inspection report | Mobile app: photos, location, checklist items | — | — |
| 2 | Inspector | If non-conformance: raise NCR | Severity classification (Critical/Major/Minor) | — | — |
| 3 | System | Generate NCR notification | Contractor receives auto-notification with details | — | — |
| 4 | Contractor | Submit rectification proposal | Root cause analysis, corrective action plan | 5 days | Late submission → escalate |
| 5 | Inspector | Verify rectification on-site | Inspect completed work against NCR requirement | 5 days | Rectification failed → re-raise NCR |
| 6 | QA Manager | Close NCR or escalate | Approve closure or return for re-work | 2 days | — |
| 7 | System | Link to contractor scorecard | Update contractor quality metrics | — | — |

## Decision Points

- NCR severity classification (Critical/Major/Minor)

- Rectification acceptance (acceptable/failed)

- Closure decision (close/escalate)

## Freeze Interaction

N/A

## ERP Integration Points

Quality metrics feed contractor evaluation in ERP

## KPIs Captured

- NCR count per contractor

- Rectification turnaround (days from NCR to closure)

- Open NCR aging (days open)

## Boundary & Exclusions

Covers on-site quality inspections and NCR management. Excludes design quality reviews (Document Submission process). Contractor scorecard based on NCR data.

## SOW Requirement References

This process flow is mandated by SOW Schedule B requirements: Q.1-Q.3. Module: Quality.

## Acceptance Test References

The following Level 4 Acceptance Tests verify this process flow: P2-018, P2-019

## Configuration Obligations

The Service Provider SHALL configure mobile inspection form with photo capture, NCR severity classification (Critical/Major/Minor), rectification workflow with SLA, contractor notification engine, NCR closure approval, and contractor scorecard data feed.

## Compliance Verification

The Service Provider shall demonstrate this process flow through: (1) End-to-end walkthrough with HAI project data, (2) User acceptance testing per Level 4 test scenarios, (3) Audit trail verification showing all steps logged with timestamps.

# PF-11: Spatial Coordination Cost

Module: Financial Control | SOW References: G.7-G.10, SG.3 | RIBA Stages: Stages 1-6

## Purpose

Maintain progressive cost plan from RICS Level 0 to Level 4, track monthly Forecast Final Cost (FFC), manage budget baselines, and escalate variance breaches.

## Actors & Responsibilities

| Actor | Role | Department |
| --- | --- | --- |
| HAI QS | Maintains cost plan | Quantity Surveying |
| HAI Finance | Spatial Coordination administration | Finance |
| HAI PM | Cost oversight | Project Management |
| CEO | Approves amendments | Executive |

## Step-by-Step Process

| Step | Actor | Action | System Behavior | SLA | Exception |
| --- | --- | --- | --- | --- | --- |
| 1 | HAI QS | Prepare cost plan per RICS levels | Progressive detail: L0 (order of magnitude) → L4 (detailed) | — | — |
| 2 | System | Maintain versioned budget baseline | Create baseline at Gate 3, version on approval | — | — |
| 3 | HAI QS | Monthly FFC update | Forecast Final Cost based on current trajectory | — | — |
| 4 | System | Auto-compare FFC vs baseline | Flag variance thresholds: 5%, 10%, 15% | — | — |
| 5 | System | Generate variance report | Breakdown by package, category, timeline | — | — |
| 6 | System | Escalation if threshold breached | Escalate to PM then CEO per threshold | 1 day | — |
| 7 | CEO | Approve budget amendment | Approve or reject amendment request | 3 days | — |
| 8 | System | Update baseline (versioned) | New baseline locked, audit trail recorded | 1 day | — |

## Decision Points

- Variance threshold breach (5% / 10% / 15%)

- Spatial Coordination amendment approval

## Freeze Interaction

Budget Freeze: no amendments without CEO + freeze exception

## ERP Integration Points

Spatial Coordination baseline synced bi-directionally with ERP, FFC→ERP actuals comparison

## KPIs Captured

- Cost deviation % (FFC variance from baseline)

- FFC accuracy (final vs. forecast at project end)

- Spatial Coordination amendment frequency per project

## Boundary & Exclusions

Covers budget maintenance from Stage 1 onward. Excludes procurement pricing (use Procurement process). Includes only FFC and baseline management.

## SOW Requirement References

This process flow is mandated by SOW Schedule B requirements: G.7-G.10, SG.3. Module: Financial Control.

## Acceptance Test References

The following Level 4 Acceptance Tests verify this process flow: P2-006, P2-007

## Configuration Obligations

The Service Provider SHALL configure RICS cost plan levels (L0-L4), budget baseline versioning at Gate 3, monthly FFC update workflow, variance threshold alerts (5%/10%/15%), CEO budget amendment approval, and ERP bi-directional budget sync.

## Compliance Verification

The Service Provider shall demonstrate this process flow through: (1) End-to-end walkthrough with HAI project data, (2) User acceptance testing per Level 4 test scenarios, (3) Audit trail verification showing all steps logged with timestamps.

# PF-12: Risk Register

Module: Governance | SOW References: SG.2, SG.7 | RIBA Stages: Stages 1-6

## Purpose

Create, maintain, and review project risk register at each stage gate. Track risk burn-down, version control, and risk-based stage gate decisions.

## Actors & Responsibilities

| Actor | Role | Department |
| --- | --- | --- |
| HAI PM | Creates and updates register | Project Management |
| Risk Owner | Manages mitigation | Various |
| Gate Approver | Accepts risks at gate | Authority |

## Step-by-Step Process

| Step | Actor | Action | System Behavior | SLA | Exception |
| --- | --- | --- | --- | --- | --- |
| 1 | HAI PM | Create risk register at Stage 1 | Version 1: initial risk identification | — | — |
| 2 | HAI PM & Team | Define each risk | Description, category, probability (H/M/L), impact (H/M/L), mitigation, owner, residual risk | — | — |
| 3 | System | Version register at each gate | Gate 1/2/3 etc.: lock version, archive | — | — |
| 4 | HAI PM | Add new risks through lifecycle | Monthly update cycle, new risks logged with version | — | — |
| 5 | System | Track risk burn-down monthly | Residual risk trend analysis | — | — |
| 6 | Gate Approver | Review at gate (mandatory) | Gate checklist includes risk register review | — | — |
| 7 | System | Feed status into stage gate | Risk register version locked at gate | — | — |

## Decision Points

- Risk severity classification (probability x impact)

- Mitigation adequacy assessment

- Gate-level risk acceptance decision

## Freeze Interaction

Risk register locked at each gate (versioned, immutable)

## ERP Integration Points

Risk exposure feeds project dashboard in ERP

## KPIs Captured

- Risk count by severity (H/M/L)

- Burn-down rate (residual risk trend)

- Overdue mitigations (actions not closed)

## Boundary & Exclusions

Covers project risk management from Stage 1. Excludes corporate/portfolio risks. Register versioning tied to stage gates (immutable snapshots).

## SOW Requirement References

This process flow is mandated by SOW Schedule B requirements: SG.2, SG.7. Module: Governance.

## Acceptance Test References

The following Level 4 Acceptance Tests verify this process flow: P2-020, P2-021

## Configuration Obligations

The Service Provider SHALL configure risk register with probability/impact matrix (H/M/L), version control locked at each gate, risk burn-down tracking, monthly update workflow, gate-level risk review as mandatory checklist item, and risk dashboard.

## Compliance Verification

The Service Provider shall demonstrate this process flow through: (1) End-to-end walkthrough with HAI project data, (2) User acceptance testing per Level 4 test scenarios, (3) Audit trail verification showing all steps logged with timestamps.

# PF-13: Contractor Performance

Module: KPI & Analytics | SOW References: K.1-K.8 | RIBA Stages: Stages 4-6

## Purpose

Aggregate contractor performance metrics from Quality (NCRs), Variations, IPCs, and Correspondence into monthly scorecard with watch-list and blacklist thresholds.

## Actors & Responsibilities

| Actor | Role | Department |
| --- | --- | --- |
| HAI PM | Oversees scoring | Project Management |
| HAI QS | Provides cost data | Quantity Surveying |
| HAI QA Manager | Provides quality data | Quality Assurance |
| System | Aggregates and calculates | Analytics |

## Step-by-Step Process

| Step | Actor | Action | System Behavior | SLA | Exception |
| --- | --- | --- | --- | --- | --- |
| 1 | System | Collect data from modules | NCRs (Quality), VOs (Variations), IPCs (IPC), correspondence response times | Monthly | — |
| 2 | System | Apply scoring algorithm | Timeliness 20%, Variation rate 25%, Defect rate 25%, Claims 15%, Response time 15% | — | — |
| 3 | System | Generate monthly scorecard | Per-contractor score (0-100), trend vs. previous month | — | — |
| 4 | System | Publish to contractor portal | Read-only view for contractor | 1st of month | — |
| 5 | System | Quarterly aggregate | Publish aggregated score across all projects | — | — |
| 6 | System | Feed into prequalification | Score influences future project bids | — | Score <40%: blacklist recommendation |

## Decision Points

- Score threshold for watch-list (<60%)

- Score threshold for blacklist (<40%)

## Freeze Interaction

N/A

## ERP Integration Points

Contractor scores available in ERP for procurement decisions

## KPIs Captured

- Average contractor score across portfolio

- Score trend (improving/declining)

- Correlation with project outcomes (cost, schedule, quality)

## Boundary & Exclusions

Covers contractor performance on assigned projects. Excludes consultant performance (separate scorecard). Scores reset annually unless project-specific.

## SOW Requirement References

This process flow is mandated by SOW Schedule B requirements: K.1-K.8. Module: KPI & Analytics.

## Acceptance Test References

The following Level 4 Acceptance Tests verify this process flow: P3-010, P3-011

## Configuration Obligations

The Service Provider SHALL configure contractor scoring algorithm (Timeliness 20%, Variation rate 25%, Defect rate 25%, Claims 15%, Response time 15%), monthly scorecard generation, watch-list (<60%) and blacklist (<40%) thresholds, contractor portal read-only view, and prequalification feed.

## Compliance Verification

The Service Provider shall demonstrate this process flow through: (1) End-to-end walkthrough with HAI project data, (2) User acceptance testing per Level 4 test scenarios, (3) Audit trail verification showing all steps logged with timestamps.

# PF-14: Lessons Learned

Module: Quality | SOW References: Q.3, H.3 | RIBA Stages: All (captured), Stages 5-6 (formal review)

## Purpose

Capture lessons learned throughout project lifecycle with classification and conversion to preventive rules for organizational learning.

## Actors & Responsibilities

| Actor | Role | Department |
| --- | --- | --- |
| Any HAI Staff | Submits lessons | Various |
| HAI PM | Reviews and validates | Project Management |
| QA Manager | Classifies lessons | Quality Assurance |

## Step-by-Step Process

| Step | Actor | Action | System Behavior | SLA | Exception |
| --- | --- | --- | --- | --- | --- |
| 1 | Any Staff | Submit lesson learned | Category, root cause, stage, description, impact | — | — |
| 2 | HAI PM | Review and validate | PM assessment: relevant/not relevant | 3 days | Irrelevant → archive |
| 3 | QA Manager | Classify lesson | Informational / Process Improvement / Preventive Rule | 2 days | — |
| 4 | QA Manager | If preventive rule: convert | Add to system checklist or validation rule | 5 days | — |
| 5 | System | Index and search | Searchable by project, stage, category, keyword | — | — |
| 6 | HAI PM | Formal review at Stage 5 | Mandatory gate item: lessons learned handover review | — | — |

## Decision Points

- Relevance assessment (relevant/not relevant)

- Classification decision (informational/improvement/rule)

- Conversion to preventive rule (yes/no)

## Freeze Interaction

N/A

## ERP Integration Points

N/A

## KPIs Captured

- Lessons captured per project

- Conversion rate to preventive rules (%)

- Repeat issue rate (preventing issues via lessons)

## Boundary & Exclusions

Covers operational lessons learned. Excludes strategic/corporate lessons. Formal review required at Stage 5 for gate approval.

## SOW Requirement References

This process flow is mandated by SOW Schedule B requirements: Q.3, H.3. Module: Quality.

## Acceptance Test References

The following Level 4 Acceptance Tests verify this process flow: P3-012

## Configuration Obligations

The Service Provider SHALL configure lessons learned submission form with category/root cause classification, PM validation workflow, QA classification (Informational/Process Improvement/Preventive Rule), searchable index, and mandatory Stage 5 gate review item.

## Compliance Verification

The Service Provider shall demonstrate this process flow through: (1) End-to-end walkthrough with HAI project data, (2) User acceptance testing per Level 4 test scenarios, (3) Audit trail verification showing all steps logged with timestamps.

# PF-15: Handover DLP

Module: Handover & DLP | SOW References: H.1-H.3 | RIBA Stages: Stages 5-7

## Purpose

Manage taking over of works, defect liability period (DLP) tracking, defect closure, and final retention release at DLP completion.

## Actors & Responsibilities

| Actor | Role | Department |
| --- | --- | --- |
| HAI PM | Manages handover | Project Management |
| Contractor | Delivers and supports | Contractor |
| FM Team | Accepts assets | Facilities Management |
| BU | Accepts operations | Business Unit |

## Step-by-Step Process

| Step | Actor | Action | System Behavior | SLA | Exception |
| --- | --- | --- | --- | --- | --- |
| 1 | HAI PM | Initiate handover checklist | As-builts, O&M manuals, training records, test certs, warranties | — | — |
| 2 | Contractor | Upload deliverables | Files indexed against checklist | 10 days | Late submission → SLA escalation |
| 3 | FM Team | Review asset acceptance | Operability, maintainability, documentation completeness | 5 days | Deficiencies → contractor remediation |
| 4 | BU | Confirm operational acceptance | BU sign-off on readiness | 3 days | — |
| 5 | System | Gate 6: Taking Over approved | FM + BU sign-off triggers gate progression | — | — |
| 6 | System | DLP clock auto-starts | Default 12 months per contract terms | — | — |
| 7 | FM/BU | Report defects during DLP | Defect register: description, severity, deadline | — | Each defect logged with SLA |
| 8 | Contractor | Address defects within SLA | Rectification per defect severity SLA | — | Overdue → escalate |
| 9 | FM Team | Verify completion | Inspect rectified defects | — | — |
| 10 | System | Gate 7: In Use & DLP | FM confirms completion, CEO releases retention | — | — |

## Decision Points

- Asset acceptance (FM acceptable/not acceptable)

- Operational acceptance (BU acceptable/not)

- Defect severity classification (Critical/Major/Minor)

- DLP closure decision (complete/continue)

## Freeze Interaction

N/A

## ERP Integration Points

DLP milestones synced to ERP, retention release triggers ERP payment

## KPIs Captured

- Handover completeness % (deliverables vs. checklist)

- Defect closure rate (closed/open)

- DLP duration (actual vs. contractual)

## Boundary & Exclusions

Covers handover through DLP closure. Excludes post-DLP maintenance. Defects logged and tracked in DLP register separate from NCRs.

## SOW Requirement References

This process flow is mandated by SOW Schedule B requirements: H.1-H.3. Module: Handover & DLP.

## Acceptance Test References

The following Level 4 Acceptance Tests verify this process flow: P3-013, P3-014, P3-015

## Configuration Obligations

The Service Provider SHALL configure handover checklist template (as-builts, O&M, training, T&C, warranties), DLP auto-start mechanism, defect register with severity SLA, retention tracker, FM/BU sign-off workflow, and ERP retention release integration.

## Compliance Verification

The Service Provider shall demonstrate this process flow through: (1) End-to-end walkthrough with HAI project data, (2) User acceptance testing per Level 4 test scenarios, (3) Audit trail verification showing all steps logged with timestamps.

# PF-16: Meeting Action Tracking

Module: Integration | SOW References: E.4 | RIBA Stages: All

## Purpose

Manage project meetings with minute capture, action item assignment, deadline tracking, and completion verification.

## Actors & Responsibilities

| Actor | Role | Department |
| --- | --- | --- |
| HAI PM | Creates meeting | Project Management |
| Meeting Attendees | Participate and act | Various |
| System | Tracks completion | Governance |

## Step-by-Step Process

| Step | Actor | Action | System Behavior | SLA | Exception |
| --- | --- | --- | --- | --- | --- |
| 1 | HAI PM | Create meeting | Type (design, site, progress, gate review), agenda, attendees | — | — |
| 2 | Meeting Attendees | Conduct meeting | Minutes captured with action items | — | — |
| 3 | HAI PM | Log action items | Description, responsible party, deadline, priority (High/Medium/Low) | — | — |
| 4 | System | Track status | Open → In Progress → Closed (or Overdue) | Per deadline | — |
| 5 | System | SLA escalation | Overdue actions escalated to responsible party | D+3 reminder, D+7 manager | — |
| 6 | System | Link to modules | Action completion linked to relevant process | — | — |

## Decision Points

- Action priority assignment (High/Medium/Low)

- SLA escalation trigger (action overdue)

## Freeze Interaction

N/A

## ERP Integration Points

N/A (internal platform function)

## KPIs Captured

- Action closure rate (% closed on deadline)

- Overdue action count

- Meeting frequency per project phase

## Boundary & Exclusions

Covers formal meetings only. Excludes ad-hoc discussions. Meeting minutes archived with audit trail.

## SOW Requirement References

This process flow is mandated by SOW Schedule B requirements: E.4. Module: Integration.

## Acceptance Test References

The following Level 4 Acceptance Tests verify this process flow: P3-016

## Configuration Obligations

The Service Provider SHALL configure meeting types (design/site/progress/gate review), minute capture template, action item assignment with priority and deadline, SLA escalation for overdue actions (D+3/D+7), and cross-module action linking.

## Compliance Verification

The Service Provider shall demonstrate this process flow through: (1) End-to-end walkthrough with HAI project data, (2) User acceptance testing per Level 4 test scenarios, (3) Audit trail verification showing all steps logged with timestamps.

# PF-17: External Stakeholder Portal (Contractor/Consultant Portal)

Module: Integration & Access | SOW References: E.1-E.3 | RIBA Stages: Stages 3-6

## Purpose

Provide external users (contractor, consultant) with role-based portal access limited to their project scope with document submission, review tracking, and compliance logging.

## Actors & Responsibilities

| Actor | Role | Department |
| --- | --- | --- |
| HAI Admin | Manages user accounts | HAI Administration |
| Contractor User | Accesses contractor portal | Contractor |
| Consultant User | Accesses consultant portal | Consultant |
| System | Controls access | Governance |

## Step-by-Step Process

| Step | Actor | Action | System Behavior | SLA | Exception |
| --- | --- | --- | --- | --- | --- |
| 1 | HAI Admin | Create external user account | Name, organization, project, role (Contractor/Consultant), permissions | — | — |
| 2 | System | Issue login credentials | Email with portal link and initial password | — | — |
| 3 | External User | Access portal | Role-based view of assigned project only | — | — |
| 4 | Contractor User | Portal: submit docs, view NCRs, submit IPC, view correspondence | Limited to contractor scope | — | — |
| 5 | Consultant User | Portal: submit docs, respond to reviews, access drawings | Limited to consultant scope | — | — |
| 6 | System | Log all external actions | Timestamp, user, action, document/object | — | — |
| 7 | HAI Admin | Manage access | Revoke or modify permissions on demand | — | — |

## Decision Points

- Permission level assignment per role

- Access revocation trigger (project complete, performance issue)

## Freeze Interaction

N/A

## ERP Integration Points

External user activity logged in ERP audit trail

## KPIs Captured

- External user engagement (login frequency, actions per user)

- Portal adoption rate (% of external users active)

- Submission quality from external users (revision rate)

## Boundary & Exclusions

Covers role-based portal access for external parties. Excludes internal HAI access. Each role has defined scope and capabilities.

## SOW Requirement References

This process flow is mandated by SOW Schedule B requirements: E.1-E.3. Module: Integration & Access.

## Acceptance Test References

The following Level 4 Acceptance Tests verify this process flow: P2-022, P2-023

## Configuration Obligations

The Service Provider SHALL configure contractor portal (document submit, NCR view, IPC submit, correspondence view), consultant portal (document submit, review response, drawing access), role-based permission matrix, action logging, and account management workflow.

## Compliance Verification

The Service Provider shall demonstrate this process flow through: (1) End-to-end walkthrough with HAI project data, (2) User acceptance testing per Level 4 test scenarios, (3) Audit trail verification showing all steps logged with timestamps.

# PF-18: Report Generation Export

Module: KPI & Analytics | SOW References: K.4-K.8 | RIBA Stages: All

## Purpose

Generate standard reports (monthly project, budget, KPI, stage status) with export to PDF/Excel and optional scheduled distribution.

## Actors & Responsibilities

| Actor | Role | Department |
| --- | --- | --- |
| HAI PM | Requests reports | Project Management |
| Department Heads | Reviews reports | Various |
| CEO | Reviews portfolio reports | Executive |
| System | Generates reports | Analytics |

## Step-by-Step Process

| Step | Actor | Action | System Behavior | SLA | Exception |
| --- | --- | --- | --- | --- | --- |
| 1 | User | Select report template | Monthly Project, Spatial Coordination vs FFC, KPI Dashboard, Stage Status, etc. | — | — |
| 2 | User | Configure scope | Project(s), date range, detail level | — | — |
| 3 | System | Compile data | Extract from all modules, aggregate, format | — | — |
| 4 | System | Generate report | PDF/Excel format, branded with HAI header | 1 day | — |
| 5 | System | Optional: schedule report | Weekly or monthly auto-generation | — | — |
| 6 | System | Distribute to recipients | Email with report attachment | — | — |

## Decision Points

- Report template selection

- Scope and date range configuration

- Scheduled vs. on-demand generation

## Freeze Interaction

N/A

## ERP Integration Points

ERP data included in financial reports (budget, actuals, forecast)

## KPIs Captured

- Report generation frequency

- Data freshness (lag between data collection and report)

- Distribution coverage (recipients receiving reports)

## Boundary & Exclusions

Covers standard report templates. Excludes ad-hoc custom reports (requires IT support). Reports are read-only exports.

## SOW Requirement References

This process flow is mandated by SOW Schedule B requirements: K.4-K.8. Module: KPI & Analytics.

## Acceptance Test References

The following Level 4 Acceptance Tests verify this process flow: P3-017, P3-018

## Configuration Obligations

The Service Provider SHALL configure standard report templates (Monthly Project, Spatial Coordination vs FFC, KPI Dashboard, Stage Status), HAI-branded PDF/Excel export, scheduled report auto-generation, and email distribution.

## Compliance Verification

The Service Provider shall demonstrate this process flow through: (1) End-to-end walkthrough with HAI project data, (2) User acceptance testing per Level 4 test scenarios, (3) Audit trail verification showing all steps logged with timestamps.

# PF-19: User Role Management

Module: Integration & Access | SOW References: E.1-E.2 | RIBA Stages: N/A (system admin)

## Purpose

Create and manage internal user accounts with role-based access control, project assignment, approval authority levels, and delegation.

## Actors & Responsibilities

| Actor | Role | Department |
| --- | --- | --- |
| System Admin | Manages users | IT Administration |
| HAI PM | Assigns users to projects | Project Management |
| Department Head | Approves role assignment | Department Head |

## Step-by-Step Process

| Step | Actor | Action | System Behavior | SLA | Exception |
| --- | --- | --- | --- | --- | --- |
| 1 | System Admin | Create user account | Name, department, email, initial role (PM, QS, QA, etc.) | — | — |
| 2 | System | Assign role | Role determines: menu visibility, process permissions, approval authority | — | — |
| 3 | HAI PM | Assign user to project | Project role (PM, Reviewer, Inspector, etc.) and scope | — | — |
| 4 | System Admin | Configure authority level | Approval authority per process type per user | — | — |
| 5 | System Admin | Configure delegation | Substitute user, delegation period, scope | — | — |
| 6 | System | Monitor user activity | Login frequency, actions, pending workload | — | — |

## Decision Points

- Role assignment (PM/QS/QA/Finance/etc.)

- Authority level per process

- Delegation approval (who can delegate to whom)

## Freeze Interaction

N/A

## ERP Integration Points

User roles synced to ERP for SSO and system integration

## KPIs Captured

- User adoption rate (active users / total assigned)

- Login frequency (average logins per user)

- Pending workload distribution (balanced vs. concentrated)

## Boundary & Exclusions

Covers internal HAI user management. Excludes external user management (Contractor/Consultant Portal process). Roles are predefined; custom roles require IT governance.

## SOW Requirement References

This process flow is mandated by SOW Schedule B requirements: E.1-E.2. Module: Integration & Access.

## Acceptance Test References

The following Level 4 Acceptance Tests verify this process flow: P1-017, P1-018

## Configuration Obligations

The Service Provider SHALL configure role-based access control with predefined roles (PM/QS/QA/Finance/Admin/Inspector/etc.), project-level user assignment, approval authority matrix per user per process type, delegation mechanism, and user activity monitoring dashboard.

## Compliance Verification

The Service Provider shall demonstrate this process flow through: (1) End-to-end walkthrough with HAI project data, (2) User acceptance testing per Level 4 test scenarios, (3) Audit trail verification showing all steps logged with timestamps.

# PF-20: ERP Integration-Directional Integration

Module: Integration | SOW References: E.1-E.4 | RIBA Stages: Stages 3-6

## Purpose

Sync critical data between SkyStruct and Artan ERP: Contract Award→PO creation, IPC→Payment, Spatial Coordination Actuals, Stage status, with error handling and reconciliation.

## Actors & Responsibilities

| Actor | Role | Department |
| --- | --- | --- |
| SkyStruct System | Initiates sync | SkyStruct Platform |
| Artan ERP | Receives and responds | Artan ERP |
| HAI IT | Troubleshoots failures | IT Operations |
| SkyStruct Support | Escalates issues | Support |

## Step-by-Step Process

| Step | Actor | Action | System Behavior | SLA | Exception |
| --- | --- | --- | --- | --- | --- |
| 1 | SkyStruct | Approved Contract Award → PO creation request | API call to ERP: vendor, amount, schedule, GL account | — | — |
| 2 | ERP | Create PO and return number | PO number and status returned to SkyStruct | 1 day | If failed: retry + manual fallback |
| 3 | SkyStruct | Certified IPC → payment instruction | API call to ERP: certified amount, contractor, GL account | — | — |
| 4 | ERP | Create payment and update actuals | Payment status and actual costs returned | 1 day | If failed: manual payment entry |
| 5 | System | Daily sync: budget actuals | ERP actual spend feeds SkyStruct dashboard | — | — |
| 6 | System | Integration error handling | Failure → auto-retry (3x) then manual fallback + IT alert | — | Escalate to IT if persistent |
| 7 | System | Weekly reconciliation report | Comparison of SkyStruct vs. ERP data, discrepancy log | — | Investigate discrepancies |

## Decision Points

- Integration failure handling (auto-retry vs. manual fallback)

- Reconciliation discrepancy resolution (SkyStruct vs. ERP)

## Freeze Interaction

N/A

## ERP Integration Points

THIS IS the ERP integration flow

## KPIs Captured

- Integration uptime % (successful syncs / total attempts)

- Sync latency (time from action to ERP reflection)

- Reconciliation discrepancy count and resolution time

## Boundary & Exclusions

Covers Contract Award↔PO, IPC↔Payment, Spatial Coordination Actuals sync only. Excludes resource/schedule/other data. Integration is API-based, not file-based.

## SOW Requirement References

This process flow is mandated by SOW Schedule B requirements: E.1-E.4. Module: Integration.

## Acceptance Test References

The following Level 4 Acceptance Tests verify this process flow: P3-001, P3-002, P3-003, P3-004

## Configuration Obligations

The Service Provider SHALL configure API-based bi-directional integration: Contract Award→ERP PO creation, certified IPC→ERP payment instruction, daily budget actuals sync, auto-retry (3x) with manual fallback, weekly reconciliation report, and integration health monitoring dashboard.

## Compliance Verification

The Service Provider shall demonstrate this process flow through: (1) End-to-end walkthrough with HAI project data, (2) User acceptance testing per Level 4 test scenarios, (3) Audit trail verification showing all steps logged with timestamps.

# PF-21: Dashboard Analytics

Module: KPI & Analytics | SOW References: K.1-K.8 | RIBA Stages: All

## Purpose

Real-time dashboards for CEO (portfolio), PM (project), BU (operations) with drill-down, bottleneck detection, and threshold-based alerts.

## Actors & Responsibilities

| Actor | Role | Department |
| --- | --- | --- |
| CEO | Views portfolio dashboard | Executive |
| HAI PM | Views project dashboard | Project Management |
| Department Heads | Views KPI dashboard | Various |
| BU | Views operational dashboard | Business Unit |
| System | Aggregates and displays | Analytics |

## Step-by-Step Process

| Step | Actor | Action | System Behavior | SLA | Exception |
| --- | --- | --- | --- | --- | --- |
| 1 | System | Aggregate real-time data | Pull from all modules: documents, approvals, budget, quality, etc. | — | — |
| 2 | System | CEO Dashboard: portfolio status | Portfolio overview: budget vs FFC, gate status, exposure heat map, top 5 | — | — |
| 3 | System | PM Dashboard: project status | Stage progress %, risk burn-down, authority milestones, bottlenecks | — | — |
| 4 | System | BU Dashboard: operational readiness | Scope completion %, handover readiness, DLP status, milestones | — | — |
| 5 | User | Drill-down capability | Click any KPI → project, department, time period breakdown | — | — |
| 6 | System | Bottleneck panel | Top 5 stalled items: description, responsible party, overdue duration | — | — |
| 7 | System | Push alerts | Threshold-based notifications (budget breach, SLA miss, risk escalation) | — | — |

## Decision Points

- Alert threshold configuration (per KPI)

- Dashboard view permissions (role-based)

## Freeze Interaction

N/A

## ERP Integration Points

ERP financial data feeds dashboard (actual vs. budget)

## KPIs Captured

- Dashboard usage frequency (logins per user)

- Alert response time (notification to action)

- Data refresh rate (latency from event to dashboard)

## Boundary & Exclusions

Covers standard dashboards for CEO/PM/BU/Department. Excludes custom ad-hoc dashboards. Real-time data updates.

## SOW Requirement References

This process flow is mandated by SOW Schedule B requirements: K.1-K.8. Module: KPI & Analytics.

## Acceptance Test References

The following Level 4 Acceptance Tests verify this process flow: P2-024, P2-025, P2-026

## Configuration Obligations

The Service Provider SHALL configure role-based dashboards (CEO portfolio, PM project, BU operational, Department KPI), real-time data aggregation from all modules, drill-down capability, bottleneck detection panel (top 5 stalled items), and threshold-based push alerts.

## Compliance Verification

The Service Provider shall demonstrate this process flow through: (1) End-to-end walkthrough with HAI project data, (2) User acceptance testing per Level 4 test scenarios, (3) Audit trail verification showing all steps logged with timestamps.

# PF-22: Notification Escalation

Module: Governance | SOW References: G.4-G.6 | RIBA Stages: All

## Purpose

Automated notifications for assignments, SLA warnings, approvals, status changes, and escalation chain with user preference configuration.

## Actors & Responsibilities

| Actor | Role | Department |
| --- | --- | --- |
| System | Generates notifications | Governance |
| All Users | Receives notifications | Various |

## Step-by-Step Process

| Step | Actor | Action | System Behavior | SLA | Exception |
| --- | --- | --- | --- | --- | --- |
| 1 | System | Generate notification | Trigger: new assignment, SLA warning, approval needed, status change | — | — |
| 2 | System | Route via channels | In-app, email, mobile push per user preference | — | — |
| 3 | User | Configure notification preferences | Frequency (instant/daily digest), channels, snooze | — | — |
| 4 | System | SLA escalation chain | D+3 reminder to assignee, D+5 escalation to manager, D+7 to PM | — | — |
| 5 | System | Create audit trail entry | Each notification logged with timestamp, user, action | — | — |
| 6 | System | Critical notifications not mutable | Freeze exception, gate rejection, budget breach → cannot be muted | — | — |

## Decision Points

- Notification priority classification (critical/high/normal)

- Escalation trigger timing (D+3/D+5/D+7)

## Freeze Interaction

N/A

## ERP Integration Points

N/A

## KPIs Captured

- Notification delivery rate (successful delivery %)

- Escalation frequency (escalations per project)

- Response time after notification (days to action)

## Boundary & Exclusions

Covers automated system notifications. Excludes manual emails. Critical notifications cannot be disabled by users.

## SOW Requirement References

This process flow is mandated by SOW Schedule B requirements: G.4-G.6. Module: Governance.

## Acceptance Test References

The following Level 4 Acceptance Tests verify this process flow: P1-019, P1-020

## Configuration Obligations

The Service Provider SHALL configure multi-channel notification engine (in-app, email, mobile push), user preference management, D+3/D+5/D+7 SLA escalation chain, critical notification non-mutable list (freeze exception, gate rejection, budget breach), and notification audit trail.

## Compliance Verification

The Service Provider shall demonstrate this process flow through: (1) End-to-end walkthrough with HAI project data, (2) User acceptance testing per Level 4 test scenarios, (3) Audit trail verification showing all steps logged with timestamps.

# PF-23: Predictive Analytics

Module: KPI & Analytics | SOW References: K.5-K.8 | RIBA Stages: All (data from Stage 2+)

## Purpose

Analyze historical trends across portfolio for cost forecasting, schedule prediction, anomaly detection, and benchmark comparison.

## Actors & Responsibilities

| Actor | Role | Department |
| --- | --- | --- |
| System | Collects and analyzes data | Analytics |
| HAI PM | Reviews predictions | Project Management |
| CEO | Reviews portfolio analytics | Executive |

## Step-by-Step Process

| Step | Actor | Action | System Behavior | SLA | Exception |
| --- | --- | --- | --- | --- | --- |
| 1 | System | Collect historical data | All projects: cost, schedule, quality, contractor performance | — | — |
| 2 | System | Trend analysis | Cost deviation trends, schedule slip patterns, contractor trajectories | Monthly | — |
| 3 | System | Predictive models | Project FFC forecast based on burn rate, risk-adjusted schedule forecast | — | — |
| 4 | System | Anomaly detection | Unusual variance patterns flagged for investigation | — | — |
| 5 | System | Benchmark comparison | Project performance vs. portfolio average per KPI | — | — |
| 6 | System | Quarterly analytics report | Auto-generated for CEO with insights and recommendations | Q1/Q2/Q3/Q4 | — |

## Decision Points

- Anomaly threshold configuration (trigger investigation)

- Benchmark criteria (all projects vs. similar project type)

## Freeze Interaction

N/A

## ERP Integration Points

Historical ERP data feeds predictive models (cost history)

## KPIs Captured

- Prediction accuracy (FFC forecast vs. actual at project end)

- Anomaly detection rate (anomalies identified / total projects)

- Benchmark deviation (outliers identified)

## Boundary & Exclusions

Covers portfolio-level predictive analytics. Excludes real-time project-level forecasts (use Dashboard). Models updated quarterly with new data.

## SOW Requirement References

This process flow is mandated by SOW Schedule B requirements: K.5-K.8. Module: KPI & Analytics.

## Acceptance Test References

The following Level 4 Acceptance Tests verify this process flow: P4-001, P4-002, P4-003

## Configuration Obligations

The Service Provider SHALL configure historical data collection from all modules, trend analysis engine (cost deviation, schedule slip, contractor trajectory), predictive FFC model, anomaly detection with configurable thresholds, benchmark comparison, and quarterly analytics report auto-generation.

## Compliance Verification

The Service Provider shall demonstrate this process flow through: (1) End-to-end walkthrough with HAI project data, (2) User acceptance testing per Level 4 test scenarios, (3) Audit trail verification showing all steps logged with timestamps.

# Terms & Conditions

## 1. Binding Nature

All process flow specifications in this document are binding on the Service Provider. Configuration must match the specified actors, steps, system behaviors, SLAs, and decision points exactly.

## 2. Acceptance Criteria

Each process flow will be tested against the Level 4 Acceptance Checklists (HAI-SS-ACL-2026-001-C). A process flow is accepted only when all referenced test scenarios pass.

## 3. Change Management

Modifications require written Change Request per Framework Agreement Clause 10. The Service Provider shall not implement alternative workflows without prior written approval from HAI.

## 4. Non-Compliance

Failure to implement a specified process flow constitutes a deficiency. HAI may withhold milestone payment proportional to the undelivered scope until the deficiency is resolved.

## 5. Audit & Compliance

All process flow executions must generate immutable audit trails. HAI reserves the right to audit system logs at any time to verify compliance with specified workflows.

## 6. Confidentiality

This document and its contents are CONFIDENTIAL. The Service Provider shall not disclose process flow specifications to third parties without written consent from HAI.

## 7. Interpretation

In case of conflict between this document and the SOW, the SOW shall prevail. In case of conflict between this document and the Manufacturing & Construction Roadmap, this document shall prevail for process flow specifications.

## 8. Document Control

This document is version-controlled. Only the latest signed version is valid. Previous versions are archived for audit purposes.

# Sign-Off & Acceptance

By signing below, both parties confirm that the process flow specifications in this document have been reviewed, understood, and accepted as the binding baseline for SkyStruct Platform configuration.

## HAI — House of Architecture & Interiors

| Name: | ___________________________________ |
| --- | --- |
| Title: | ___________________________________ |
| Signature: | ___________________________________ |
| Date: | ___________________________________ |

## SkyStruct Technologies

| Name: | ___________________________________ |
| --- | --- |
| Title: | ___________________________________ |
| Signature: | ___________________________________ |
| Date: | ___________________________________ |