Communication Management Plan

HAI — Employer's Representative | Project [Project Reference]

Prepared by:

HAI Programme Management Office

Date: February 2026

Document No: HAI-[Project Reference]-PM-CMP-0001-R0.0

Status: Draft

# Document Control

| Rev | Date | Description | Prepared By | Reviewed By | Approved By |
| --- | --- | --- | --- | --- | --- |
| R0.0 | Feb 2026 | Initial Draft | HAI PMO | — | — |

# Table of Contents

Purpose & Scope

Definitions & Abbreviations

Project Stakeholders

Communication Objectives

Communication Methods & Channels

Communication Matrix

Meeting Protocols

Document Management

Contractual Communications

Escalation Framework

Distribution & Confidentiality

Reporting Requirements

Language & Cultural Considerations

Review & Update

# 1. Purpose & Scope

## Purpose

This Communication Management Plan establishes the framework for all project communications within the [Project Reference] construction project under HAI's management as Employer's Representative. The plan ensures timely, accurate, and controlled distribution of information to all project stakeholders, maintaining clarity of accountability and compliance with contractual obligations.

## Scope of Application

This plan applies to all communications related to the [Project Reference] project, including:

Governance and programme reporting

Project meetings and coordination

Document submittals and design reviews

Contractual notices and claims management

Quality inspections and HSE communications

Authority submissions and certifications

Handover and project close-out

## Reference to PMI Framework

This plan aligns with the PMI Construction Extension to the PMBOK (Project Management Body of Knowledge), Section 10 — Communications Management. The framework ensures:

Systematic planning of communication activities

Structured management of information flow

Clear escalation pathways for issue resolution

Documented audit trail for compliance and traceability

## FIDIC 2017 Integration

All communications comply with FIDIC 2017 Conditions of Contract requirements, including:

Formal notice procedures (SC 1.3) — Contractor 3 calendar days response

Time-bar requirements for claims (Clause 20.2)

Engineer determination response timelines (Clause 14) Force Majeure notice: 7 CD (SC 19.2). Variation notice: 3 WD from instruction (SC 3.3).

Payment certification cycles

# 2. Definitions & Abbreviations

## Key Terms

| Term | Definition |
| --- | --- |
| ER | Employer's Representative — HAI acting on behalf of Artan Holding |
| DC | Design Consultant — Lead design authority for the project |
| EDMS | Electronic Document Management System (SkyStruct Platform) |
| RACI | Responsible, Accountable, Consulted, Informed — stakeholder communication model |
| MOM | Minutes of Meeting — formal record of meeting discussions and actions |
| RFI | Request for Information — clarification request from contractor |
| TQ | Technical Query — clarification request to consultants |
| NCR | Non-Conformance Report — quality defect identification |
| WIR | Work Inspection Report — on-site quality inspection record |
| MIR | Material Inspection Report — supplier/material verification |
| IPC | Interim Payment Certificate — contractual payment authorization |
| VO | Variation Order — contract modification for scope changes |
| EoT | Extension of Time — contractual schedule adjustment |
| SI | Site Instruction — formal directive to contractor on site |
| CVI | Completion/Compliance Verification Inspection |
| FIDIC | International Federation of Consulting Engineers — contract standard |
| RIBA | Royal Institute of British Architects — project stage framework |
| QCS | Qatar Construction Specification |
| GSAS | Global Sustainability Assessment System |
| QCDD | Qatar Central Design and Development Bureau |
| LTI | Lost Time Injury — HSE incident classification |

# 3. Project Stakeholders

The project involves diverse stakeholder groups, each with distinct communication requirements. A comprehensive stakeholder register is maintained in Appendix A, detailing contact information, escalation points, and preferred communication methods.

## Internal Stakeholders

Artan Holding (Owner) — Strategic decisions, board-level reporting

HAI Team — Programme Director, Project Manager, QS, Design Manager, Site Supervision

## External — Consultants

Lead Design Consultant — Design authority and technical coordination

Specialist Subconsultants — MEP, Structural, Landscape, etc.

## External — Contractors

Main Contractor — Primary execution and coordination

MEP Subcontractor — Mechanical, Electrical, Plumbing systems

Specialist Subcontractors — Façade, Finishes, Fit-out

## External — Authorities & Regulators

QCDD — Central Design and Development Bureau (approvals)

Ashghal — Supreme Committee for Delivery & Legacy

Kahramaa — Utility company (water, electricity connections)

Municipality — Zoning, permits, and compliance

GORD — General Organization for Real Estate Development

## Other Stakeholders

End Users / Tenants — Facility requirements and communications

Community Representatives — Local engagement and liaison

Insurance & Surety Providers — Bond and claim notifications

# 4. Communication Objectives

In alignment with PMI Construction Extension principles, this plan establishes the following communication objectives:

## Timely Distribution of Accurate Information

All information must be current, verified, and error-free before distribution

Distribution timelines must respect decision-making requirements

## Clear Accountability for Information Flow

RACI matrices define ownership, approval, and consultation roles

Each communication item has a designated originator and receiver

## Standardised Formats and Protocols

All communications follow defined templates and naming conventions

Consistent structure ensures rapid comprehension across stakeholders

## Contractual Compliance

All FIDIC 2017 notice requirements are documented and archived

Time-bar deadlines are tracked and escalated proactively

## Audit Trail and Traceability

All communications are logged with timestamp, sender, and recipients

Electronic archive in EDMS provides complete record for dispute resolution

## Escalation Clarity

Four-level escalation framework ensures rapid issue resolution

Clear authority and response timelines at each level

# 5. Communication Methods & Channels

The project employs multiple communication channels, each selected for its suitability to the communication type and stakeholder audience.

## EDMS (SkyStruct Platform)

Primary system for document management, submittals, and approvals

Supports workflow tracking, version control, and audit logging

Mandatory for all formal design, shop drawing, and technical submittals

## Email (Outlook)

Used for formal correspondence, transmittals, and notifications

All contractual communications retain email as official record

Must include distribution list clearly showing To, CC, BCC recipients

## Video Conference (MS Teams)

Remote meetings with screen sharing and recording capability

Suitable for coordination meetings when in-person attendance not possible

Recordings archived for reference; minutes issued within 48 hours

## In-Person Meetings

Progress meetings held on-site for real-time coordination

Commercial discussions requiring sensitivity held in private settings

HSE tool-box talks conducted with full crew participation

## Hard Copy (Registered Mail)

Contractual notices requiring formal delivery per FIDIC Clause 1.3

Authority submissions requiring official documentation

Certified delivery with signature confirmation for time-bar compliance

## Dashboard (Power BI)

Executive reporting and KPI visualisation for Owner briefings

Updated monthly or on-demand by HAI PMO

Provides high-level status without detailed technical information

# 6. Communication Matrix

The Communication Matrix (Appendix B) documents 30 distinct communication items, organized into 8 categories. This section provides a narrative overview of the matrix structure.

## Matrix Organization

The 30 communication items are systematically classified as follows:

| Category | Comm IDs | Key Items | Typical Frequency |
| --- | --- | --- | --- |
| Governance & Reporting | CM-01 to CM-05 | Board reports, monthly reports, forecasts, dashboards | Monthly, weekly, on-demand |
| Meetings | CM-06 to CM-11 | Progress, coordination, commercial, quality, HSE meetings | Weekly to monthly |
| Document Submittals | CM-12 to CM-15 | Design docs, shop drawings, RFI, material submittals | On-demand, per schedule |
| Contractual | CM-16 to CM-20 | Notices, claims, payment apps, variations, EoT | As triggered, monthly |
| Quality & Inspection | CM-21 to CM-23 | NCR, WIR, MIR, CVI | As required, ongoing |
| HSE | CM-24 to CM-25 | Toolbox talks, incident reports, audits | Weekly, as triggered |
| Authority & Cert | CM-26 to CM-27 | Approvals, certifications, licenses | Per authority timeline |
| Handover & Close-out | CM-28 to CM-30 | Final inspections, warranties, lessons learned | Final project stage |

The complete Communication Matrix Excel file (Appendix B) provides detailed ownership, frequency, and distribution details for each of the 30 communication items.

# 7. Meeting Protocols

Effective meeting management is critical to project coordination. This section establishes standardised protocols for all project meetings.

## Agenda & Notice

Agendas issued minimum 5 working days in advance for major meetings; Contractor 48h for non-urgent, Engineer no notice required (SC 3.6)

Agendas issued minimum 2 working days in advance for progress meetings

Ad-hoc emergency meetings may proceed with verbal agenda, followed by written confirmation

## Minutes & Documentation

Minutes of Meeting (MOM) issued within 48 hours of completion (maximum) per SC 3.6

MOM documents discussion, decisions, action items, and owners

MOM signed off by meeting chair and circulated to all attendees within 5 working days

## Action Item Tracking

Each action item assigned to named owner with explicit deadline

Status tracked in shared action register updated monthly

Overdue actions flagged and escalated at next meeting

## Attendance & Delegation

Attendance at designated meetings is mandatory

Non-attendance requires written delegation to a qualified alternate

Repeated non-attendance escalated to senior management

## Standard Meeting Schedule

Nine standard meetings established per meeting schedule (Appendix D):

MTG-01: Executive Steering Committee (monthly or as required)

MTG-02: Project Coordination (bi-weekly)

MTG-03: Progress Meetings (weekly on-site)

MTG-04: Design Review (as required per schedule)

MTG-05: Quality & Compliance (monthly)

MTG-06: HSE Stand-down (weekly before work)

MTG-07: Commercial Review (monthly)

MTG-08: Authority Liaison (quarterly)

MTG-09: Closeout & Handover (final phase)

# 8. Document Management

## Document Repository

All project documents managed via SkyStruct EDMS platform

No parallel document management systems permitted

Documents retained in EDMS for minimum 7 years post-completion (per contract)

## Document Numbering System

All formal project documents follow the numbering convention:

[Project Reference]-[CNT]-[DISC]-[TYPE]-[SEQ]-R[n].[m]

Where:

[CNT] = Contractor/Organization code (e.g., HA, MC for Main Contractor)

[DISC] = Discipline code (e.g., ARC, STR, MEP)

[TYPE] = Document type code (e.g., DRG=drawing, SDL=schedule, RFI)

[SEQ] = Sequential number

R[n].[m] = Revision [major].[minor]

Example: [Project Reference]-MC-MEP-DRG-0245-R1.2 = Main Contractor MEP drawing 0245, revision 1.2

## Review & Approval Workflow

All submittals follow the standardised workflow (PF-01):

Originator → Originator's Design Consultant → Consultant DC (QA) → Consultant Engineer (QC, A/B/C/D) → HAI Engineer (Endorse/Revise)

HAI retains override authority at any stage to reject or require revision.

## Response Times

Design documents: 15 WD, extendable to 22 WD, then deemed rejected (SC 3.1, 4.28.1)

Shop drawings: 15 WD, extendable to 22 WD, then deemed rejected (SC 3.1, 4.28.1)

RFI responses: 3 WD (SC 3.1, 4.28.1)

Material submittals: 10 calendar days for approval

Extensions granted only in writing with documented justification.

# 9. Contractual Communications

FIDIC 2017 Conditions of Contract impose specific requirements for formal communications. This section ensures compliance with all contractual obligations. Notice of Dispute (NOD): 48 hours mandatory deadline (SC 1.1.2.32).

## Notices Under FIDIC Clause 1.3

All notices delivered in writing to specified contractual address

Delivery by registered mail, courier, or hand delivery with receipt

Notices effective upon delivery or receipt acknowledgement

Notice addressee details maintained current in contract administration file

## Time-Bar Requirements (Clause 20.2)

All claims must be notified within 28 CD of event awareness — TIME-BARRED (SC 20.2.1)

Detailed claim: 7 CD — TIME-BARRED (SC 20.2.4). Payment + EOT claims must be simultaneous or void (SC 20.2)

Proactive calendar maintained tracking time-bar expiry dates

Monthly dashboard report to PM tracking all open time-bar items

## Engineer Determination Response (Clause 14)

Engineer general response: 15 WD, ext. 21 WD (SC 1.9) for claims/disputes; response issued in writing with reasoned determination

Response issued in writing with reasoned determination

If response delayed beyond 42 days, contractor entitled to refer to DAB

## Payment Cycle (Clauses 14.3, 14.6, 14.7)

Applications submitted by 28th of month for work performed per SC 14.6.1

Certification issued within 28 CD of application (SC 14.6.1)

Payment due from Owner within 10 CD of certification (SC 14.7)

All payment applications tracked with status: submitted, certified, pending, paid.

## Contractual Communications Register

All contractual communications logged with timestamp in EDMS

Register includes: date, recipient, subject, document reference, response status

Register reviewed monthly and escalated to PM for action items

## Language Requirements

Project language: English — All communications in English (SC 1.4)

Authority submissions: Arabic translation required (with English original retained)

Multilingual meetings: English as primary, Arabic interpretation available if required

# 10. Escalation Framework

A four-level escalation framework ensures issues are resolved at the appropriate authority level with defined timelines.

| Level | Escalation Trigger | Escalated To | Response Time |
| --- | --- | --- | --- |
| Level 1 | Operational issue; site-level resolution possible | Site Supervisor / Site Manager | Same day (4 hours) per SC escalation protocols |
| Level 2 | Project-level issue; requires PM authority | HAI Project Manager | 48 hours per SC escalation protocols |
| Level 3 | Programme-level impact; strategic decision | HAI Programme Director | 5 working days |
| Level 4 | Executive level; Owner decision required | Artan Holding Board / Executive | Immediate briefing |

All escalations documented in writing with issue description, impact, and recommended action.

# 11. Distribution & Confidentiality

## RACI Model

All communications distributed per RACI matrix (Appendix E)

R = Responsible (person who performs the task)

A = Accountable (authority who must approve/sign-off)

C = Consulted (must be asked for input)

I = Informed (must be kept in the loop)

RACI matrix reviewed and updated quarterly or upon stakeholder changes.

## Confidentiality Classification

All documents classified into four tiers:

Public: Releasable to all external parties; no restrictions

Internal: For internal HAI/Artan use only; not for external distribution

Confidential: Commercial or technical sensitivity; restricted access

Restricted: Legal privilege, dispute-related, or board-level sensitive

## Commercial Information Protection

Pricing, cost, and commercial strategy documents restricted to authorised personnel only

No cost or pricing data shared with contractors or consultants outside their scope

Variation pricing held in separate confidential file

## Legal Privilege

All dispute-related communications and legal advice maintain attorney-client privilege

Documents prepared at direction of legal counsel marked with privilege notices

No disclosure without explicit consent from in-house counsel

# 12. Reporting Requirements

## Monthly Progress Report

Issued by 5th of following month

Covers: schedule status, budget forecast, quality metrics, HSE performance, risks, issues, achievements

Audience: HAI PMO, Artan Holding, Design Consultant

## Weekly Progress Report

Issued every Thursday by 14:00

Covers: weekly achievements, schedule progress, critical path items, action item status

Audience: Project team, site coordinator

## Forecast Final Cost

Updated monthly alongside progress report

Tracks budget variance, committed variations, anticipated claims

Includes contingency burn-down and risk assessment

## Executive Dashboard

Updated monthly or on-demand by HAI PMO

High-level visual KPI summary for Owner consumption

Covers: progress %, budget %, schedule status, major risks, HSE metrics

## Stage Gate Report

Produced at completion of each RIBA stage

Confirms stage deliverables, compliance with stage brief, readiness to proceed

Stage sign-off obtained before advancement to next phase

# 13. Language & Cultural Considerations

## Project Language

English is the official language for all contract and technical communications (SC 1.4)

Non-English speakers provided with translation support at meetings as needed

## Authority Submissions

All submissions to Qatari authorities include Arabic translation

English original maintained as the authoritative source document

Professional translator employed to ensure accuracy in both languages

## Cultural Protocols — Qatar

Authority meetings conducted with respect for senior officials and decision-makers

Meetings scheduled outside prayer times when possible

Friday and Saturday are the formal weekend; Sunday is first working day

Ramadan period acknowledged with adjusted working arrangements per local practice

## Gender Sensitivity

Mixed-gender meetings conducted professionally with clear agendas

Site access protocols respect local and international HSE standards

# 14. Review & Update

## Scheduled Review

This plan reviewed quarterly as minimum by HAI PMO and Programme Director

Review assesses: effectiveness of communication channels, stakeholder feedback, emerging issues

## Change Triggers

Plan updated when triggered by:

New stakeholder addition or significant personnel change

Contract amendment affecting communication requirements

Phase transition (RIBA stage advancement)

Reorganisation of HAI or contractor management structure

Lessons learned requiring protocol adjustment

## Amendment Authority

Minor amendments (operational refinement) approved by HAI Project Manager

Major amendments (stakeholder, contract, phase changes) require HAI Programme Director approval

Updated version issued with new revision number and control table entry

# Appendices

The following appendices are referenced throughout this document and maintained as separate Excel files:

Appendix A: Stakeholder Register — Contact details, roles, escalation paths

Appendix B: Communication Matrix — 30 communication items with frequency and owners

Appendix C: Escalation Matrix — Response times and escalation triggers

Appendix D: Meeting Schedule — 9 standard meetings with timing and attendees

Appendix E: Distribution Matrix (RACI) — Stakeholder communication allocation

## Document Approval

This Communication Management Plan has been prepared by HAI Programme Management Office and is subject to review and approval by relevant project authorities.

_____________________________

HAI Project Manager

Date: ___________________

_____________________________

HAI Programme Director

Date: ___________________

_____________________________

Artan Holding Representative

Date: ___________________