HAI SkyStruct Platform

Technical Architecture Document

Software Configurator Blueprint — Supabase + Next.js

Version 1.0 | March 2026

ARADA Governance | House of Architecture & Interiors

Author: Hasan Mollamahmutoglu — Chief Governance Architect

CONFIDENTIAL — INTERNAL USE ONLY

Reference: HAI-GOV-045-R0.0

# Table of Contents

1. Executive Summary

2. Technology Stack

3. System Architecture

4. Database Schema

5. GOV Document → Module Mapping

6. API Route Structure

7. Frontend Component Architecture

8. RBAC Implementation

9. Workflow Engine Design

10. Notification & Escalation System

11. KPI/SLA Monitoring

12. Integration Architecture

13. Infrastructure & Deployment

14. Phased Build Plan

15. Risk Register (Technical)

Appendix A: Entity-Relationship Summary

Appendix B: Environment Variables

# 1. Executive Summary

This document is the technical blueprint for building the HAI SkyStruct Platform — a construction governance system for ARADA / House of Architecture & Interiors projects in Qatar. It translates 75+ governance documents, 31 process flows, 27 data entities, 15 RBAC roles, 52 workflow rules, and 15 KPIs into an implementable software architecture.

The platform will be built using Supabase (PostgreSQL + Auth + Storage + Realtime) as the backend and Next.js 14 (App Router) deployed on Vercel as the frontend. This combination provides managed infrastructure with zero DevOps overhead during the prototype phase, while remaining fully portable to self-hosted infrastructure for production.

## Guiding Principles

Governance-first: Every feature traces back to a GOV document, FIDIC clause, or QCS 2014 requirement.

Contractual precision: SLAs, time-bars, and response codes (A/B/C/D/E) are enforced by the system, not by people.

Three-party approval chain: Contractor → Lead Consultant → ER/HAI is hardcoded into every workflow.

Stage-gated: All 9 stages (0-8, RIBA 2020 aligned) enforce gate passage checklists before progression.

Audit-complete: Every action is logged with who, what, when, from-state, to-state, and IP address.

Portable: Built on open standards (PostgreSQL, REST, React). No vendor lock-in.

# 2. Technology Stack

## 2.1 Core Stack

| Layer | Technology | Version | Purpose |
| --- | --- | --- | --- |
| Database | PostgreSQL (Supabase) | 15+ | Primary data store, RLS policies, triggers |
| Auth | Supabase Auth | Latest | JWT-based authentication, role claims, MFA |
| Storage | Supabase Storage | Latest | Document files, drawings, photos (S3-compatible) |
| Realtime | Supabase Realtime | Latest | Live notifications, dashboard updates |
| Edge Functions | Supabase Edge (Deno) | Latest | Server-side logic, webhooks, scheduled jobs |
| Frontend | Next.js 14 (App Router) | 14.x | SSR/SSG, API routes, React Server Components |
| Hosting | Vercel | Latest | CDN, edge deployment, preview environments |
| Styling | Tailwind CSS + shadcn/ui | 3.x / Latest | Utility-first CSS, accessible components |
| State | Zustand | 4.x | Lightweight client state management |
| Forms | React Hook Form + Zod | Latest | Form handling with schema validation |
| Charts | Recharts | 2.x | Dashboard visualizations, KPI charts |
| Tables | TanStack Table | 8.x | Sortable, filterable data grids |
| PDF Gen | React-PDF / @react-pdf/renderer | Latest | Server-side PDF report generation |
| Email | Resend | Latest | Transactional email notifications |

## 2.2 Development Tools

| Tool | Purpose |
| --- | --- |
| TypeScript | Type safety across frontend and edge functions |
| ESLint + Prettier | Code quality and formatting |
| Vitest | Unit and integration testing |
| Playwright | End-to-end testing |
| GitHub Actions | CI/CD pipeline |
| Supabase CLI | Local development, migrations, type generation |
| dbdiagram.io | Schema visualization |

# 3. System Architecture

## 3.1 Architecture Overview

The system follows a three-tier architecture with clear separation between presentation, business logic, and data layers. Supabase provides the entire backend (database, auth, storage, realtime) through a unified API, eliminating the need for a custom backend server.

Architecture Layers:

Presentation Layer (Next.js on Vercel): React components, pages, layouts. Server-side rendering for initial load, client-side for interactivity. App Router with nested layouts per module.

API Layer (Next.js API Routes + Supabase Edge Functions): Business logic that cannot run client-side. Workflow orchestration, complex validations, PDF generation, email dispatch, scheduled jobs (SLA checks, escalations).

Data Layer (Supabase/PostgreSQL): 27+ tables with Row Level Security (RLS) policies. Triggers for audit logging, cascading status updates, and automated notifications. Views for dashboard aggregations.

Storage Layer (Supabase Storage): Bucket-per-project for document files. Policies mirror RLS. Signed URLs for secure download. Thumbnail generation via Edge Functions.

Realtime Layer (Supabase Realtime): WebSocket subscriptions for live dashboard updates, notification delivery, and collaborative editing indicators.

## 3.2 Data Flow

All client requests flow through the Supabase client library (supabase-js), which handles authentication tokens automatically. For operations requiring server-side logic (workflow transitions, SLA enforcement, escalation triggers), the client calls Next.js API routes, which use the Supabase service role key to bypass RLS when needed.

## 3.3 Security Model

Authentication: Supabase Auth with email/password + optional MFA. JWT tokens with custom claims for role_id and department.

Authorization: PostgreSQL Row Level Security (RLS) on every table. Policies reference auth.uid() and role claims. No data escapes without matching policy.

API Security: All Supabase Edge Functions verify JWT. Next.js API routes use middleware for role checks. CORS restricted to production domain.

Storage Security: Bucket policies mirror table RLS. Files inherit project-level access. Signed URLs expire after 1 hour.

Audit: Trigger-based audit_log table captures every INSERT, UPDATE, DELETE with old/new values, user_id, IP, and timestamp.

# 4. Database Schema

The database schema implements all 27 entities from GOV-024 (L3 Data Model), plus additional tables for notifications, meetings, risk register, and system configuration. All tables use UUIDs as primary keys, have created_at/updated_at timestamps, and are covered by RLS policies.

## 4.1 Entity Register (27 Core + 8 Supporting)

| ID | Entity | Table Name | Key Fields | Relationships |
| --- | --- | --- | --- | --- |
| E-01 | Project | projects | code, name, status, current_stage, gsas_target, pm_id | 1:N → stages, documents, variations, contracts, approvals |
| E-02 | User | profiles | email, full_name, department, role_id, is_active | N:N → projects (via project_members) |
| E-03 | Role | roles | code (R01-R15), name, department, authority_limit | 1:N → profiles |
| E-04 | Contractor | contractors | name, cr_number, trade, status, prequalified | 1:N → contracts, IPCs, scores |
| E-05 | Stage Instance | stage_instances | project_id, stage_number (0-8), status, start/end | N:1 → project, 1:N → gate_items |
| E-06 | Gate Checklist | gate_checklist_items | stage_id, item_text, is_passed, verified_by | N:1 → stage_instance |
| E-07 | Document | documents | number, title, discipline, type, status, revision | N:1 → project, 1:N → reviews, transmittals |
| E-08 | Document Review | document_reviews | doc_id, reviewer_id, response_code (A-E), comments | N:1 → document, N:1 → user |
| E-09 | Transmittal | transmittals | number, from_party, to_party, purpose, date | N:N → documents (via transmittal_docs) |
| E-10 | Correspondence | correspondences | ref_number, type, from, to, subject, due_date | N:1 → project |
| E-11 | Variation | variations | number, title, type, status, amount, time_impact | N:1 → project, N:1 → contract |
| E-12 | IPC | ipcs | number, period_start, period_end, gross_amount, status | N:1 → contract, N:1 → contractor |
| E-13 | Contract | contracts | number, title, type, value, contractor_id, status | N:1 → project, 1:N → variations, IPCs |
| E-14 | Approval | approvals | type, ref_id, ref_table, status, requested_by, decided_by | Polymorphic: links to any approvable entity |
| E-15 | Freeze | freezes | project_id, type (budget/design/scope/regulatory), start, end | N:1 → project, 1:N → freeze_exceptions |
| E-16 | Freeze Exception | freeze_exceptions | freeze_id, reason, requested_by, approved_by | N:1 → freeze |
| E-17 | Authority Sub. | authority_submissions | authority, type (DC1/DC2/BCC/NOC), status, ref | N:1 → project |
| E-18 | IR | inspection_requests | number, type, location, result (Pass/Fail/Cond.) | N:1 → project, 0:1 → NCR |
| E-19 | NCR | ncrs | number, category, severity, corrective_action, status | N:1 → project, 0:1 → IR |
| E-20 | Site Report | site_reports | date, weather, manpower, activities, issues | N:1 → project |
| E-21 | Handover Package | handover_packages | project_id, zone, status, completion_% | N:1 → project |
| E-22 | Warranty | warranties | item, start_date, end_date, contractor_id, status | N:1 → project |
| E-23 | Lesson Learned | lessons_learned | category, description, impact, recommendation | N:1 → project |
| E-24 | KPI Snapshot | kpi_snapshots | kpi_code, project_id, value, rag_status, period | N:1 → project |
| E-25 | Contractor Score | contractor_scores | contractor_id, period, score, dimensions_json | N:1 → contractor |
| E-26 | Audit Log | audit_logs | table_name, record_id, action, old/new_data, user_id, ip | Automatic via triggers |
| E-27 | ERP Sync Record | erp_sync_records | entity_type, entity_id, direction, status, payload | Links to any entity |

## 4.2 Supporting Tables

| Table | Purpose | Key Fields |
| --- | --- | --- |
| project_members | User-Project assignment (N:N) | project_id, user_id, role_in_project |
| notifications | System notifications | user_id, type, title, body, is_read, link |
| escalations | Active escalation records | source_type, source_id, level (L1-L5), due_at |
| meetings | Meeting records | project_id, type, date, attendees_json, minutes |
| action_items | Meeting action items | meeting_id, description, assignee_id, due_date, status |
| risks | Risk register entries | project_id, description, probability, impact, mitigation, owner_id |
| budget_lines | Budget breakdown per contract | contract_id, category, original, revised, committed, actual |
| comments | Polymorphic comments on any entity | ref_table, ref_id, user_id, text, created_at |
| file_attachments | File metadata (Storage refs) | ref_table, ref_id, storage_path, filename, size, mime |
| system_config | Platform configuration values | key, value, category, description |
| gsas_checkpoints | GSAS sustainability tracking | project_id, type, status, score, evidence_path |
| submittal_categories | Category master (A-J, no I) | code, name, description, required_stages |

## 4.3 Enumeration Types (PostgreSQL ENUMs)

| Enum Name | Values |
| --- | --- |
| project_status | active, completed, on_hold, terminated |
| project_type | school, residential, hospitality, fitout, mixed_use |
| stage_number | 0, 1, 2, 3, 4, 5, 6, 7, 8 |
| response_code | A (approved), B (approved_with_comments), C (revise_resubmit), D (rejected), E (not_reviewed) |
| document_discipline | architectural, structural, mep_electrical, mep_mechanical, mep_plumbing, fire, civil, interior, landscape |
| document_type | drawing, specification, report, calculation, schedule, submittal, method_statement, as_built, om_manual |
| document_status | draft, submitted, under_review, approved, rejected, superseded, archived, for_information |
| variation_status | identified, assessed, instructed, valued, agreed, rejected, withdrawn |
| ipc_status | submitted, under_verification, qs_certified, pm_endorsed, finance_reviewed, approved, paid, rejected |
| approval_status | pending, approved, rejected, deferred, escalated |
| freeze_type | budget, design, scope, regulatory |
| authority_name | QCDD, Kahramaa, Ashghal, Civil_Defense |
| submission_type | DC1, DC2, BCC, NOC, load_application, fire_strategy, infrastructure_NOC |
| ir_result | pass, fail, conditional |
| ncr_status | open, corrective_action_submitted, re_inspected, closed |
| rag_status | red, amber, green |
| escalation_level | L1, L2, L3, L4, L5 |
| gsas_target | platinum, gold, silver, bronze |
| submittal_category | A, B, C, D, E, F, G, H, J |

# 5. GOV Document to Module Mapping

Every GOV document translates into a specific software module, database table, API endpoint, or configuration setting. Nothing is ornamental — every document drives implementation.

| GOV Doc | Title | Software Module | Implementation |
| --- | --- | --- | --- |
| GOV-000 | Document Register | System Config | Seed data for document numbering |
| GOV-001 | Implementation Guidebook | Reference | Build guide (this document supersedes) |
| GOV-002 | WBS Schedule | Project Module | Stage/task templates, Gantt integration |
| GOV-003 | Process Flow Register | Workflow Engine | Workflow definitions registry |
| GOV-004 | Cross-Link Index | System Config | Navigation graph, module linking |
| GOV-005 | Stage-Based Org | Project Module | Stage configuration, team allocation |
| GOV-006 | Project Mind Map | Navigation | Interactive system navigation tree |
| GOV-007 | Implementation Roadmap | Reference | Phase planning reference |
| GOV-008 | SOW | Contract | Scope baseline for platform vendor |
| GOV-009 | CEO Presentation | Reference | Executive communication artifact |
| GOV-010 | Training Manual | Help System | In-app help, tooltips, onboarding |
| GOV-011 | System Configuration | System Config | Contract params, module config, integrations |
| GOV-012 | User Roles & Permissions | Auth/RBAC | RLS policies, role claims, module access matrix |
| GOV-013 | Workflow Engine Rules | Workflow Engine | 52 rules, 20 escalations, 39 business rules, 20 automations |
| GOV-014 | Notification Rules | Notifications | 20 notification templates, channels, priorities |
| GOV-015 | Form Template Specs | Forms | Dynamic form schemas, validation rules |
| GOV-016 | Dashboard Specs | Dashboards | 8 role-based dashboards, widgets, KPIs |
| GOV-017 | KPI/SLA Definitions | KPI Module | 15 KPIs, 15 SLAs, 5-level escalation matrix |
| GOV-018 | Audit Trail Spec | Audit Module | Trigger-based logging, compliance reports |
| GOV-019 | Security Policy | Auth/RBAC | Data access controls, sensitivity classifications |
| GOV-020 | Dashboard Wireframes | Dashboards | Visual layout reference for dashboard pages |
| GOV-021 | PF Action Sheets | Workflow Engine | Step-level action definitions per process flow |
| GOV-022 | L1 PF Narratives | Documentation | Process flow descriptions for help system |
| GOV-023 | L2 UI Wireframes | Frontend | Page layout specs for every module screen |
| GOV-024 | L3 Data Model | Database | 27 entities, 152 fields, 36 relationships, 218 enums |
| GOV-025 | L4 Acceptance Checklists | Testing | UAT criteria per module |
| GOV-030 | RACI Matrix | Workflow Engine | Responsibility assignment per process |
| GOV-031 | FIDIC Response Cards | Workflow Engine | Response code actions per clause |
| GOV-032 | Contract Duration Matrix | Business Rules | SLA durations per contract type |
| GOV-033 | Escalation Procedures | Escalation Engine | L1-L5 escalation paths and actions |
| GOV-034 | Gate Passage Checklists | Stage Gate Module | Checklist items per stage transition |
| GOV-035 | Doc Numbering System | Document Module | Auto-numbering rules and format |
| GOV-036 | Communication Plan | Notifications | Stakeholder communication matrix |
| GOV-037 | Communication Mgmt Plan | Notifications | Communication procedures |
| GOV-038 | FIDIC Clause Mapping | Business Rules | Clause → workflow trigger mapping |
| GOV-039 | QCS 2014 Compliance | Quality Module | Compliance checklist per section |
| GOV-040 | Change Management Plan | System Config | Platform change control procedures |
| GOV-041 | UAT Test Plan | Testing | Test cases per module |
| GOV-042 | Migration Spec | Data Migration | Legacy data mapping and ETL |
| GOV-043 | Integration Spec | ERP Integration | API contracts for ERP, email, BIM |
| GOV-044 | Backup & DR | Infrastructure | Backup schedules, RTO/RPO targets |

## 5.1 Process Flow → Feature Mapping

| PF | Process | Frontend Pages | API Routes | Key Tables |
| --- | --- | --- | --- | --- |
| PF-01 | Document Review | /documents, /documents/[id]/review | /api/documents, /api/reviews | documents, document_reviews |
| PF-02 | Correspondence | /correspondence | /api/correspondence | correspondences |
| PF-03 | Variation Order | /variations, /variations/[id] | /api/variations | variations, approvals |
| PF-04 | Procurement | /procurement | /api/procurement | contracts, approvals |
| PF-05 | Stage Gate | /projects/[id]/stages | /api/stages/gate-check | stage_instances, gate_checklist_items |
| PF-06 | Freeze Exception | /freezes | /api/freezes | freezes, freeze_exceptions |
| PF-07 | Authority Submissions | /authority | /api/authority-submissions | authority_submissions |
| PF-08 | IPC Processing | /ipcs, /ipcs/[id] | /api/ipcs | ipcs, approvals |
| PF-09 | Approval Engine | (embedded in all modules) | /api/approvals | approvals |
| PF-10 | Quality Supervision | /quality/ir, /quality/ncr | /api/inspections, /api/ncrs | inspection_requests, ncrs |
| PF-11 | Budget & Cost | /budget | /api/budget | budget_lines, contracts |
| PF-12 | Risk Register | /risks | /api/risks | risks |
| PF-13 | Contractor Performance | /contractors/[id]/score | /api/contractor-scores | contractor_scores |
| PF-14 | Lessons Learned | /lessons | /api/lessons | lessons_learned |
| PF-15 | Handover & DLP | /handover | /api/handover | handover_packages, warranties |
| PF-16 | Meeting & Actions | /meetings | /api/meetings, /api/actions | meetings, action_items |
| PF-17 | External Portal | /portal (separate app) | /api/portal/* | project_members (external) |
| PF-18 | Report Generation | /reports | /api/reports/generate | All tables (read-only) |
| PF-19 | User Management | /admin/users | /api/users | profiles, roles |
| PF-20 | ERP Integration | /admin/erp-sync | /api/erp-sync | erp_sync_records |
| PF-21 | Dashboard & Analytics | /dashboard | /api/dashboard/widgets | kpi_snapshots, all tables |
| PF-22 | Notification & Escalation | (system-wide) | /api/notifications | notifications, escalations |
| PF-23 | Predictive Analytics | /analytics | /api/analytics/predict | kpi_snapshots, risks |

# 6. API Route Structure

The API follows RESTful conventions. Most CRUD operations go directly through the Supabase client (no custom API needed — RLS handles authorization). Custom API routes are only needed for:

Workflow transitions (multi-table transactions with business logic)

Scheduled jobs (SLA checks, escalation triggers, ERP sync)

PDF/report generation

Email dispatch

Complex queries that span multiple tables

## 6.1 Next.js API Routes (/app/api/)

| Route | Method | Purpose | Auth Required |
| --- | --- | --- | --- |
| /api/auth/callback | GET | Supabase auth callback handler | No |
| /api/workflows/transition | POST | Advance workflow state (validates business rules) | Yes (role-checked) |
| /api/workflows/escalate | POST | Trigger manual escalation | Yes (R01-R03) |
| /api/approvals/decide | POST | Record approval/rejection with validation | Yes (authority-checked) |
| /api/documents/generate-number | POST | Generate next document number (atomic) | Yes |
| /api/ipcs/certify | POST | IPC multi-step certification workflow | Yes (R05) |
| /api/variations/assess | POST | Variation assessment with dual-track logic | Yes (R03) |
| /api/stage-gate/check | POST | Validate gate passage checklist | Yes (R01-R02) |
| /api/reports/generate | POST | Generate PDF report | Yes |
| /api/notifications/send | POST | Dispatch notification (email + in-app) | System |
| /api/erp-sync/push | POST | Push data to ERP | System |
| /api/erp-sync/pull | POST | Pull data from ERP | System |
| /api/cron/sla-check | POST | Daily SLA breach check (Vercel Cron) | Cron secret |
| /api/cron/escalation | POST | Daily escalation processor | Cron secret |
| /api/cron/kpi-snapshot | POST | Weekly KPI calculation | Cron secret |
| /api/dashboard/widgets | GET | Aggregated dashboard data | Yes (role-filtered) |
| /api/analytics/predict | POST | Run predictive model | Yes (R01-R05) |

## 6.2 Supabase Edge Functions

| Function | Trigger | Purpose |
| --- | --- | --- |
| on-document-upload | Storage event | Generate thumbnail, extract metadata, virus scan |
| on-status-change | DB webhook | Cascade status updates, trigger notifications |
| on-approval-complete | DB webhook | Advance workflow, notify stakeholders |
| on-sla-breach | Scheduled (daily) | Check all active SLAs, create escalation records |
| on-time-bar-warning | Scheduled (daily) | Check 28-day and 7-day time bars (FIDIC) |
| email-sender | Queue-based | Send transactional emails via Resend |
| erp-sync-worker | Scheduled (hourly) | Bidirectional ERP data synchronization |

# 7. Frontend Component Architecture

## 7.1 App Router Layout Structure

Next.js App Router provides nested layouts. Each module gets its own layout with sidebar navigation:

/app/layout.tsx — Root layout (auth check, theme provider, notification provider)

/app/(auth)/login/page.tsx — Login page

/app/(auth)/forgot-password/page.tsx — Password reset

/app/(dashboard)/layout.tsx — Authenticated layout (sidebar + header + notifications)

/app/(dashboard)/page.tsx — Home dashboard (role-specific)

/app/(dashboard)/projects/page.tsx — Project list

/app/(dashboard)/projects/[id]/layout.tsx — Project context layout

/app/(dashboard)/projects/[id]/page.tsx — Project overview

/app/(dashboard)/projects/[id]/stages/page.tsx — Stage management

/app/(dashboard)/projects/[id]/documents/page.tsx — Document register

/app/(dashboard)/projects/[id]/variations/page.tsx — Variation management

/app/(dashboard)/projects/[id]/ipcs/page.tsx — IPC processing

/app/(dashboard)/projects/[id]/quality/page.tsx — IR + NCR

/app/(dashboard)/projects/[id]/risks/page.tsx — Risk register

/app/(dashboard)/projects/[id]/budget/page.tsx — Budget & cost

/app/(dashboard)/projects/[id]/meetings/page.tsx — Meeting tracker

/app/(dashboard)/projects/[id]/correspondence/page.tsx — Correspondence

/app/(dashboard)/projects/[id]/handover/page.tsx — Handover & DLP

/app/(dashboard)/projects/[id]/authority/page.tsx — Authority submissions

/app/(dashboard)/contractors/page.tsx — Contractor management

/app/(dashboard)/reports/page.tsx — Report generation

/app/(dashboard)/analytics/page.tsx — Predictive analytics

/app/(dashboard)/admin/users/page.tsx — User management

/app/(dashboard)/admin/config/page.tsx — System configuration

/app/(dashboard)/admin/erp-sync/page.tsx — ERP sync monitor

/app/(dashboard)/admin/audit/page.tsx — Audit trail viewer

## 7.2 Shared Components

| Component | Purpose | Used By |
| --- | --- | --- |
| <DataTable /> | Sortable, filterable, paginated table | All list views |
| <ApprovalPanel /> | Inline approval/rejection with response codes | Documents, VOs, IPCs, Contracts |
| <WorkflowTimeline /> | Visual workflow state with history | All workflow entities |
| <FileUploader /> | Drag-drop file upload to Supabase Storage | Documents, IRs, NCRs |
| <CommentThread /> | Polymorphic comment system | All entities |
| <StatusBadge /> | Color-coded status indicator | All entities |
| <SLACountdown /> | Live countdown to SLA deadline | Documents, Correspondence, IPCs |
| <KPICard /> | KPI with RAG indicator and sparkline | Dashboards |
| <GateChecklist /> | Interactive checklist for stage gates | Stage management |
| <NotificationBell /> | Real-time notification dropdown | Header (global) |
| <AuditLog /> | Timeline of changes on any entity | All detail views |
| <FormBuilder /> | Dynamic form from GOV-015 schema | All create/edit views |
| <ResponseCodeSelector /> | A/B/C/D/E picker with implications | Document review, approvals |
| <EscalationBanner /> | Warning banner for approaching/breached SLAs | All list views |

# 8. RBAC Implementation

RBAC is implemented at three levels: Supabase Auth (JWT claims), PostgreSQL RLS (row-level), and Next.js middleware (page-level). This triple-layer approach ensures no data leakage even if one layer is bypassed.

## 8.1 Role Hierarchy (from GOV-012)

| Role ID | Role Name | Department | Authority Limit (QAR) | Module Access Level |
| --- | --- | --- | --- | --- |
| R01 | Programme Director | Executive | Unlimited | Full access all modules |
| R02 | Project Manager | PM | 500,000 | Full access project modules |
| R03 | Contracts Manager | Contracts | 200,000 | Full: Contracts, VOs, IPCs, Claims |
| R04 | Design Manager | Design | 50,000 | Full: Documents, Design, Submittals |
| R05 | Cost Manager | Finance | 100,000 | Full: Budget, IPCs, Cost Reports |
| R06 | QA/QC Manager | Quality | — | Full: Quality, IR, NCR, Site Reports |
| R07 | Document Controller | DocControl | — | Full: EDMS, Transmittals, Numbering |
| R08 | Site Engineer | Site | — | Edit: IR, Site Reports; View: Documents |
| R09 | Planning Engineer | Planning | — | Full: Schedule, Progress; View: Budget |
| R10 | Contractor PM | External | — | Submit: Documents, IPCs; View: Own items |
| R11 | Contractor Staff | External | — | Submit: Documents; View: Own items |
| R12 | Consultant Lead | External | — | Review: Documents; View: Project data |
| R13 | Employer Rep | ER | 200,000 | Full: All modules (ER authority) |
| R14 | System Admin | IT | — | Full: Admin, Config, User Mgmt |
| R15 | Auditor | Governance | — | View-only: All modules + Audit Trail |

## 8.2 RLS Policy Pattern

Every table has RLS enabled. Policies check the user's role from JWT claims. Example for the documents table:

SELECT policy: Users see documents in projects they are members of. R15 (Auditor) sees all. R10/R11 (Contractor) see only their own submissions. INSERT policy: Only R04, R07, R10, R11 can create documents. UPDATE policy: Only the creator or R01/R02/R07 can update. DELETE policy: Only R01, R14 can delete (soft-delete preferred).

# 9. Workflow Engine Design

The workflow engine implements all 52 rules from GOV-013. It is a state-machine-based system where each entity type has defined states and valid transitions. Transitions are guarded by business rules and trigger side effects (notifications, escalations, audit entries).

## 9.1 State Machine Architecture

Each workflow-enabled entity has a status field (PostgreSQL ENUM) and a workflow_definitions table that defines valid transitions. The workflow engine validates every transition against:

Current state → target state is a valid transition

The requesting user has the required role

All pre-conditions are met (e.g., all reviewers have responded)

No active freezes block the transition

SLA has not been breached (or escalation is acknowledged)

## 9.2 Workflow Definitions Table

| Column | Type | Description |
| --- | --- | --- |
| id | UUID | Primary key |
| entity_type | TEXT | Table name (documents, variations, ipcs, etc.) |
| from_status | TEXT | Source state (or NULL for initial) |
| to_status | TEXT | Target state |
| required_role | TEXT[] | Array of role codes that can trigger this transition |
| preconditions | JSONB | Business rule checks (e.g., {"all_reviews_complete": true}) |
| side_effects | JSONB | Actions to execute (e.g., {"notify": ["R01","R02"], "escalate": false}) |
| sla_days | INTEGER | Days allowed in this state before escalation |
| fidic_clause | TEXT | Governing FIDIC clause reference |
| pf_reference | TEXT | Process flow reference (PF-01 to PF-31) |

## 9.3 Time-Bar Enforcement (FIDIC-Critical)

FIDIC 1999 Red Book has strict time-bar provisions. The system enforces these automatically:

28-day notice period for claims (Sub-Clause 20.1): System tracks from event date, warns at day 21, blocks at day 29.

7-day particulars period after notice: Triggered automatically when notice is recorded.

42-day engineer determination period (Sub-Clause 3.5): SLA countdown starts on receipt.

14-day payment certification (Sub-Clause 14.6): IPC certification tracked to the day.

# 10. Notification & Escalation System

Implements GOV-014 (20 notification templates) and GOV-033 (5 escalation levels). Notifications are delivered through three channels: in-app (Supabase Realtime), email (Resend), and optional SMS. Escalation is time-driven with automatic level progression.

## 10.1 Escalation Levels (from GOV-017)

| Level | Trigger | Recipient | Response Time | Action |
| --- | --- | --- | --- | --- |
| L1 - Alert | SLA at 80% | Assignee | Same day | In-app + email reminder |
| L2 - Warning | SLA at 100% | Manager (R02) | 24 hours | Email to manager, flag in dashboard |
| L3 - Escalation | SLA +3 days | Dept Head (R01) | 48 hours | Director notification, item highlighted red |
| L4 - Critical | SLA +7 days | Programme Director | Immediate | Executive dashboard alert, formal notice |
| L5 - Contract | SLA +14 days | Legal/Contracts | Immediate | Contractual notice triggered, time-bar risk |

# 11. KPI/SLA Monitoring

Implements 15 KPIs and 15 SLAs from GOV-017. KPIs are calculated by scheduled jobs and stored as snapshots for trend analysis.

## 11.1 KPI Definitions

| KPI | Metric | Target | Warning | Critical | Frequency |
| --- | --- | --- | --- | --- | --- |
| K.1 | Submittal Response Time | ≤14 CD | 15-21 CD | >21 CD | Per submittal |
| K.2 | Correspondence Response | ≤7 CD | 8-14 CD | >14 CD | Per correspondence |
| K.3 | IPC Processing Time | ≤28 CD | 29-35 CD | >35 CD | Per IPC |
| K.4 | Variation Closure Rate | ≥85% | 70-84% | <70% | Monthly |
| K.5 | Budget Variance | ≤5% | 5-10% | >10% | Monthly |
| K.6 | Schedule Variance | ≤5% | 5-10% | >10% | Monthly |
| K.7 | NCR Closure Rate | ≥90% | 75-89% | <75% | Monthly |
| K.8 | Contractor Performance | ≥80 | 60-79 | <60 | Quarterly |
| K.9 | Risk Mitigation Rate | ≥85% | 70-84% | <70% | Monthly |
| K.10 | HSE Incident Rate | 0 | 1-2 | >2 | Monthly |
| K.11 | Gate Passage On-Time | ≥90% | 75-89% | <75% | Per gate |
| K.12 | Document Approval Rate | ≥80% | 60-79% | <60% | Monthly |
| K.13 | Claims Time-Bar Compliance | 100% | 95-99% | <95% | Per claim |
| K.14 | Handover Completion | ≥95% | 85-94% | <85% | Per zone |
| K.15 | Lesson Learned Capture | ≥1/month | — | 0/quarter | Quarterly |

# 12. Integration Architecture

GOV-043 defines 10 integration points. During prototype phase, we implement email and storage. ERP integration is Phase 7. BIM and scheduling tools are post-MVP.

| Integration | Protocol | Direction | Frequency | Phase |
| --- | --- | --- | --- | --- |
| Supabase Storage (Documents) | S3 API | Bidirectional | Real-time | 1 |
| Email (Resend) | REST API | Outbound | Event-driven | 1 |
| Calendar (Google/Outlook) | CalDAV/API | Bidirectional | Event-driven | 3 |
| ERP Financial Sync | REST API | Bidirectional | Hourly | 7 |
| ERP Status Sync | REST API | Bidirectional | Bi-hourly | 7 |
| BIM Platform | REST/IFC | Read-only | On-demand | Post-MVP |
| Scheduling (Primavera/MS Project) | XML/API | Import | Weekly | Post-MVP |
| GSAS Portal | Web scrape/API | Read-only | Monthly | Post-MVP |
| Municipality Portals | Manual/API | Bidirectional | Per submission | Post-MVP |
| SMS Gateway | REST API | Outbound | Event-driven | Post-MVP |

# 13. Infrastructure & Deployment

## 13.1 Prototype Phase (Supabase Free + Vercel Free)

| Resource | Free Tier Limit | Sufficient for Prototype? |
| --- | --- | --- |
| Supabase Database | 500 MB, 2 projects | Yes — schema + seed data < 50 MB |
| Supabase Auth | 50,000 MAU | Yes — 15 test users |
| Supabase Storage | 1 GB | Yes — limited test documents |
| Supabase Edge Functions | 500K invocations/mo | Yes — development workload |
| Supabase Realtime | 200 concurrent connections | Yes — single user testing |
| Vercel | 100 GB bandwidth, serverless functions | Yes — development traffic |
| Resend | 100 emails/day | Yes — test notifications |

## 13.2 Production Phase (Supabase Pro + Vercel Pro)

When ready for production deployment, upgrade to Supabase Pro ($25/mo) and Vercel Pro ($20/mo). This provides 8 GB database, 100 GB storage, daily backups, and custom domain. For ARADA data sovereignty requirements, Supabase can be self-hosted on a Qatar-region cloud provider (AWS me-south-1 or Azure Qatar).

## 13.3 CI/CD Pipeline

GitHub repository with main (production), staging, and feature branches

Pull request → Vercel preview deployment (automatic)

Merge to staging → Deploy to staging environment

Merge to main → Deploy to production (manual approval)

Supabase migrations tracked in /supabase/migrations/ (SQL files)

Type generation: supabase gen types typescript after migration

# 14. Phased Build Plan

The build is divided into 8 phases over approximately 13 weeks. Each phase produces a deployable increment that can be tested independently. Phases 1-6 are the core platform. Phases 7-8 are hardening and integration.

| Phase | Duration | Deliverables | GOV Dependencies | Tables Created |
| --- | --- | --- | --- | --- |
| Phase 1: Foundation | 2 weeks | Supabase project setup, DB schema (all tables), Auth + RBAC, Project CRUD, User management, Base layout + navigation | GOV-011, 012, 019, 024 | ALL 35 tables, roles, profiles, projects, project_members, system_config |
| Phase 2: Document Core | 2 weeks | Document register, Upload/download, Review workflow, Response codes (A-E), Transmittals, Auto-numbering | GOV-015, 035, PF-01, PF-06, PF-07 | documents, document_reviews, transmittals, file_attachments |
| Phase 3: Financial | 2 weeks | Contract management, Variation workflow, IPC processing (multi-step), Budget tracking, Approval engine | GOV-031, 032, PF-03, PF-04, PF-08, PF-09, PF-11 | contracts, variations, ipcs, budget_lines, approvals |
| Phase 4: Quality & Site | 2 weeks | Inspection requests, NCR management, Site reports, Handover packages, Warranty tracking, Lessons learned | GOV-039, PF-10, PF-14, PF-15 | inspection_requests, ncrs, site_reports, handover_packages, warranties, lessons_learned |
| Phase 5: Workflows & Alerts | 2 weeks | Workflow engine (52 rules), Notification system (3 channels), Escalation engine (L1-L5), Time-bar tracking, SLA monitoring | GOV-013, 014, 017, 033, 038 | workflow_definitions, notifications, escalations |
| Phase 6: Dashboards | 1 week | Role-based dashboards (8), KPI cards with RAG, Charts and trends, Report generation (PDF) | GOV-016, 017, 020, PF-18, PF-21 | kpi_snapshots |
| Phase 7: Integration | 1 week | ERP sync (bidirectional), Email notifications live, External portal (contractor/consultant), Authority submission tracker | GOV-043, PF-17, PF-20 | erp_sync_records |
| Phase 8: UAT & Polish | 2 weeks | UAT execution (GOV-041 test cases), Bug fixes, Performance optimization, Data migration from legacy, Security audit | GOV-025, 041, 042, 044 | No new tables |

## 14.1 Phase 1 Detailed Breakdown (Week 1-2)

Phase 1 is the most critical — it establishes the foundation everything else builds on:

Day 1: Create Supabase project, configure auth settings, set up Next.js repo with TypeScript + Tailwind + shadcn/ui

Day 2: Write and run all 35 table migrations (CREATE TABLE, ENUMs, indexes, foreign keys)

Day 3: Enable RLS on all tables, write SELECT/INSERT/UPDATE/DELETE policies per role

Day 4: Implement auth flow (login, logout, password reset), JWT custom claims for role_id

Day 5: Build base layout (sidebar, header, notification area), role-based menu filtering

Day 6-7: Project CRUD (create, list, view, edit), project member assignment

Day 8: User management (admin page), role assignment, department filtering

Day 9: Stage management (create stage instances per project, gate checklist UI)

Day 10: Seed data (roles, system config, submittal categories, sample project), smoke testing

# 15. Technical Risk Register

| Risk | Probability | Impact | Mitigation |
| --- | --- | --- | --- |
| Supabase free tier limits exceeded during prototype | Low | Medium | Monitor usage, upgrade to Pro ($25/mo) if needed |
| RLS policies too complex causing slow queries | Medium | High | Pre-test with EXPLAIN ANALYZE, use materialized views for dashboards |
| File storage exceeds 1 GB during testing | Medium | Low | Use compressed test files, clean up regularly |
| FIDIC time-bar logic incorrectly implemented | Medium | Critical | Unit test every time-bar scenario, cross-reference GOV-038 |
| Workflow state machine has edge cases | High | High | Comprehensive state transition matrix, property-based testing |
| ERP integration API not available during prototype | High | Low | Mock ERP endpoints, build adapter pattern for later swapout |
| Browser compatibility issues with dashboard | Low | Medium | Test on Chrome, Edge, Safari. Use shadcn/ui (tested components) |
| Data migration from legacy systems fails | Medium | High | ETL scripts with validation, dry-run before production |
| Single developer bottleneck (bus factor = 1) | High | Critical | Comprehensive documentation, clean code, this architecture doc |

# Appendix A: Entity-Relationship Summary

Key relationships between entities (from GOV-024, 36 relationships):

| Parent | Relationship | Child | Cascade | Required |
| --- | --- | --- | --- | --- |
| Project | 1:N | Stage Instance | Delete | Yes |
| Project | 1:N | Document | Delete | Yes |
| Project | 1:N | Correspondence | Delete | Yes |
| Project | 1:N | Variation | Delete | Yes |
| Project | 1:N | Contract | Delete | Yes |
| Project | 1:N | Approval | Delete | Yes |
| Project | 1:N | Authority Submission | Delete | Yes |
| Project | 1:N | Freeze | Delete | Yes |
| Project | 1:N | Risk | Delete | Yes |
| Project | 1:N | KPI Snapshot | Delete | Yes |
| Project | N:N | User (via project_members) | Remove link | Yes |
| Stage Instance | 1:N | Gate Checklist Item | Delete | Yes |
| Document | 1:N | Document Review | Delete | Yes |
| Contract | 1:N | Variation | Restrict | Yes |
| Contract | 1:N | IPC | Restrict | Yes |
| Contractor | 1:N | Contract | Restrict | Yes |
| Contractor | 1:N | IPC | Restrict | Yes |
| Contractor | 1:N | Contractor Score | Delete | Yes |
| Freeze | 1:N | Freeze Exception | Delete | Yes |
| IR | 0:1 | NCR | Set null | No |
| Approval | 1:N | Contract Award | Restrict | Yes |
| Project | 1:1 | Handover Package | Delete | No |

# Appendix B: Environment Variables

Required environment variables for deployment:

| Variable | Description | Example |
| --- | --- | --- |
| NEXT_PUBLIC_SUPABASE_URL | Supabase project URL | https://xxxxx.supabase.co |
| NEXT_PUBLIC_SUPABASE_ANON_KEY | Supabase anonymous (public) key | eyJhbGciOiJIUzI1NiIs... |
| SUPABASE_SERVICE_ROLE_KEY | Supabase service role key (server-only) | eyJhbGciOiJIUzI1NiIs... |
| RESEND_API_KEY | Email service API key | re_xxxxx |
| CRON_SECRET | Secret for Vercel Cron job auth | random-32-char-string |
| NEXT_PUBLIC_APP_URL | Application base URL | https://skystruct.vercel.app |
| ERP_API_URL | ERP system endpoint (Phase 7) | https://erp.arada.qa/api |
| ERP_API_KEY | ERP authentication key (Phase 7) | erp-key-xxxxx |

— End of Document —

This document is the single source of truth for the SkyStruct Platform technical build. All development decisions must trace back to this document or the referenced GOV documents.