HOUSE OF ARCHITECTURE & INTERIORS

ARADA GOVERNANCE

MASTER SUBMITTAL HIERARCHY
& COVER PAGE TEMPLATES

Mapped to FIDIC 1999 Red Book & QCS 2014
(Qatar Construction Specifications)

| Document Number | HAI-GOV-074-R0.0 |
| --- | --- |
| Document Title | Master Submittal Hierarchy & Cover Page Templates |
| Version | R0.0 — Initial Issue |
| Date | March 2026 |
| Author | Hasan Mollamahmutoglu |
| Role | Chief Governance Architect / Employer's Representative |
| Classification | Confidential — Project Governance |
| SkyStruct Reference | PF-01 (Document Review & Submission) |

# Table of Contents

[Update field in Word to generate TOC]

1. Purpose & Scope

2. Definitions & Abbreviations

3. Submittal Classification System

4. Master Submittal Hierarchy

4.1  Category A — Technical Design Submittals

4.2  Category B — Material & Product Submittals

4.3  Category C — Method Statements & Procedures

4.4  Category D — Quality Assurance / Quality Control

4.5  Category E — Health, Safety & Environment (HSE)

4.6  Category F — Progress & Programme

4.7  Category G — Contractual & Commercial

4.8  Category H — Handover & Close-Out

4.9  Category J — Specialist / Regulatory

5. FIDIC Clause Cross-Reference Matrix

6. QCS 2014 Section Cross-Reference Matrix

7. Submittal Workflow (PF-01 Integration)

8. Cover Page Templates

8.1  Template A — Technical Design Submittal

8.2  Template B — Material / Product

8.3  Template C — Method Statement

8.4  Template D — QA/QC

8.5  Template E — HSE

8.6  Template F — Progress / Programme

8.7  Template G — Contractual / Commercial

8.8  Template H — Handover / Close-Out

8.9  Template J — Specialist / Regulatory

Appendix A — Submittal Numbering Convention

Appendix B — Review Response Codes

# 1. Purpose & Scope

This document establishes the master hierarchy of all submittal types required for construction and consultancy contracts administered by HAI / ARADA Governance as the Employer's Representative. It serves three functions:

Classification — Every submittal type is categorized into 9 master categories (A through J, excluding I to avoid confusion with the number 1), creating a single taxonomy used across all HAI-administered projects.

Traceability — Each submittal type is mapped to its governing FIDIC 1999 Red Book clause(s) and the corresponding QCS 2014 section(s), ensuring contractual and regulatory traceability.

Standardization — Standardized cover page templates are provided for each category, ensuring consistent format, review routing, and approval tracking across the SkyStruct Platform (PF-01: Document Review & Submission).

This hierarchy is designed to be used in conjunction with the HAI-GOV-035 Document Numbering System, the HAI-GOV-013 Workflow Engine Rules, and the SkyStruct PF-01 Document Review 8-Step Cycle.

# 2. Definitions & Abbreviations

| Term | Definition |
| --- | --- |
| Submittal | Any document, drawing, sample, calculation, or data submitted by the Contractor to the Engineer/ER for review, approval, or information under the terms of the contract. |
| FIDIC | Federation Internationale des Ingenieurs-Conseils. This document references the FIDIC Conditions of Contract for Construction (1999 Red Book) with Particular Conditions as adopted by the Employer. |
| QCS 2014 | Qatar Construction Specifications 2014, issued by the Public Works Authority (Ashghal). The standard technical specification for all construction in the State of Qatar. |
| ER | Employer's Representative — HAI / ARADA Governance, acting under the authority delegated by the Employer. |
| PF-01 | Process Flow 01: Document Review & Submission (8-Step Cycle) — the SkyStruct workflow governing all submittal processing. |
| IFC | Issued for Construction — drawings/documents approved for site use. |
| IFR | Issued for Review — drawings/documents submitted for consultant/ER review. |
| Shop Drawing | A drawing produced by the Contractor or subcontractor showing fabrication, installation, or erection details not shown on the contract drawings. |
| Method Statement | A document describing how a particular construction activity will be carried out, including resources, sequence, safety measures, and quality controls. |
| MSDS/SDS | Material Safety Data Sheet / Safety Data Sheet — hazard information for materials. |
| NOC | No Objection Certificate — issued by regulatory authorities. |
| BCC | Building Completion Certificate. |

# 3. Submittal Classification System

All submittals are classified into 9 master categories, designated A through J (excluding I). This single-letter prefix forms the first element of the submittal reference number and determines which cover page template is used.

## 3.1 Category Overview

| Code | Category | Description |
| --- | --- | --- |
| A | Technical Design Submittals | Drawings, calculations, design reports, specifications prepared by the Contractor's designer or design subcontractor. |
| B | Material & Product Submittals | Material data sheets, samples, mock-ups, product certificates, test reports, manufacturer warranties. |
| C | Method Statements & Procedures | Construction methodology, temporary works procedures, protection plans, activity-specific procedures. |
| D | Quality Assurance / Quality Control | QA/QC plans, ITP, inspection checklists, test results, NCR responses, calibration certificates. |
| E | Health, Safety & Environment (HSE) | HSE plans, risk assessments, COSHH assessments, emergency procedures, environmental monitoring, incident reports. |
| F | Progress & Programme | Baseline programme, monthly updates, recovery programmes, resource histograms, S-curves, look-ahead schedules. |
| G | Contractual & Commercial | Payment applications (IPC), variations, claims, bonds, insurances, notices, extension of time requests. |
| H | Handover & Close-Out | O&M manuals, as-built drawings, warranty certificates, spare parts lists, testing & commissioning reports, handover documentation. |
| J | Specialist / Regulatory | Authority submissions (DC1/DC2, BCC, NOC), third-party certifications, GSAS/sustainability, fire/civil defense, utility connections. |

## 3.2 Submittal Numbering Convention

Each submittal receives a unique reference following this structure:

[Project]-[Category]-[Discipline]-[Sequential]-[Revision]

| Element | Description | Values |
| --- | --- | --- |
| Project | Project code (e.g., HAI-P01) | HAI-P01 |
| Category | Single letter A through J | A, B, C, D, E, F, G, H, J |
| Discipline | 2-letter discipline code | AR (Arch), ST (Struct), ME (Mech), EL (Elec), CV (Civil), PL (Plumb), FP (Fire), LS (Landscape), ID (Interior), GN (General) |
| Sequential | 4-digit sequential number | 0001, 0002, ... |
| Revision | 2-digit revision | 00, 01, 02, ... |

Example: HAI-P01-A-AR-0015-02

= Project HAI-P01, Technical Design Submittal (A), Architectural (AR), item 15, revision 02

# 4. Master Submittal Hierarchy

The following sections detail every submittal type within each category, including the governing FIDIC clause, applicable QCS 2014 sections, review response time, and the submittal priority (1 = must be approved before work starts, 2 = required during execution, 3 = for information/record).

## 4.1 Category A — Technical Design Submittals

Technical Design submittals encompass all drawings, calculations, and design documentation prepared by the Contractor or their design subcontractors. FIDIC Clause 5.2 requires the Contractor to submit design documents for the Engineer's consent.

| Ref | Submittal Type | FIDIC Clause | QCS 2014 Ref | Review Period | Priority |
| --- | --- | --- | --- | --- | --- |
| A-01 | Shop Drawings | 5.2, 4.1 | QCS 2014 S1 Part 3 | 21 days | 1 |
| A-02 | Fabrication Drawings | 5.2 | QCS 2014 S5, S9 | 21 days | 1 |
| A-03 | Structural Calculations | 5.2, 5.4 | QCS 2014 S5 Part 2 | 21 days | 1 |
| A-04 | MEP Technical Design Drawings | 5.2 | QCS 2014 S21-S27 | 21 days | 1 |
| A-05 | Coordination Drawings (BIM) | 5.2 | QCS 2014 S1 Part 3 | 21 days | 1 |
| A-06 | Temporary Works Technical Design | 4.1, 8.3 | QCS 2014 S1 Part 5 | 14 days | 1 |
| A-07 | Technical Design Calculation Report | 5.2, 5.4 | QCS 2014 S5 Part 2 | 21 days | 1 |
| A-08 | Value Engineering Proposals | 13.2 | N/A | 14 days | 2 |
| A-09 | Technical Design Change Notice | 13.1, 13.3 | N/A | 14 days | 1 |
| A-10 | IFC Drawing Package | 5.2, 5.6 | QCS 2014 S1 Part 3 | 21 days | 1 |
| A-11 | Landscape Technical Design Drawings | 5.2 | QCS 2014 S28 | 21 days | 1 |
| A-12 | Interior Technical Design Submittals | 5.2 | QCS 2014 S1 Part 3 | 21 days | 1 |
| A-13 | Fire Protection Technical Design | 5.2 | QCS 2014 S10 Part 6 | 21 days | 1 |
| A-14 | Specialist System Technical Design | 5.2, 4.4 | QCS 2014 S21-S27 | 21 days | 1 |

## 4.2 Category B — Material & Product Submittals

Material submittals provide evidence that proposed materials and products comply with contract specifications. FIDIC Clause 7.1 obliges the Contractor to carry out manufacture in accordance with the contract and submit samples/test results.

| Ref | Submittal Type | FIDIC Clause | QCS 2014 Ref | Review Period | Priority |
| --- | --- | --- | --- | --- | --- |
| B-01 | Material Data Sheet (TDS) | 7.1 | All applicable sections | 14 days | 1 |
| B-02 | Material Safety Data Sheet (SDS) | 7.1, 6.7 | QCS 2014 S1 Part 6 | 14 days | 1 |
| B-03 | Manufacturer Certificate of Compliance | 7.1 | All applicable sections | 14 days | 1 |
| B-04 | Material Test Report (Lab) | 7.1, 7.3 | QCS 2014 S3-S9 | 14 days | 1 |
| B-05 | Physical Samples | 7.1, 7.2 | QCS 2014 S1 Part 3 | 21 days | 1 |
| B-06 | Mock-Up Submittal | 7.1 | QCS 2014 S1 Part 3 | 28 days | 1 |
| B-07 | Colour / Finish Schedule | 7.1 | QCS 2014 S15, S16 | 14 days | 1 |
| B-08 | Equipment Data Sheet | 7.1 | QCS 2014 S21-S27 | 21 days | 1 |
| B-09 | Product Warranty Certificate | 7.1, 11.1 | QCS 2014 S1 Part 7 | 14 days | 2 |
| B-10 | Import / Origin Certificate | 7.1 | QCS 2014 S1 Part 6 | 14 days | 2 |
| B-11 | Concrete Mix Technical Design | 7.1, 7.3 | QCS 2014 S5 Part 3 | 21 days | 1 |
| B-12 | Asphalt Mix Technical Design | 7.1, 7.3 | QCS 2014 S6 Part 6 | 21 days | 1 |
| B-13 | Steel Mill Certificate | 7.1 | QCS 2014 S9 | 14 days | 1 |
| B-14 | Specialist Product Approval | 7.1, 4.4 | Various | 21 days | 1 |

## 4.3 Category C — Method Statements & Procedures

Method statements describe how specific construction activities will be executed, including sequence, resources, safety measures, and quality controls. FIDIC Clause 4.1 requires the Contractor to provide details of methods of construction.

| Ref | Submittal Type | FIDIC Clause | QCS 2014 Ref | Review Period | Priority |
| --- | --- | --- | --- | --- | --- |
| C-01 | Construction Method Statement | 4.1, 8.3 | QCS 2014 S1 Part 5 | 14 days | 1 |
| C-02 | Temporary Works Procedure | 4.1, 8.3 | QCS 2014 S1 Part 5 | 14 days | 1 |
| C-03 | Excavation & Shoring Method | 4.1 | QCS 2014 S4 Part 2 | 14 days | 1 |
| C-04 | Concrete Pouring Procedure | 4.1 | QCS 2014 S5 Part 3 | 14 days | 1 |
| C-05 | Lifting Plan / Crane Operation | 4.1, 6.7 | QCS 2014 S1 Part 5 | 14 days | 1 |
| C-06 | Demolition Method Statement | 4.1 | QCS 2014 S2 Part 2 | 14 days | 1 |
| C-07 | Piling / Foundation Method | 4.1 | QCS 2014 S4 Part 3 | 14 days | 1 |
| C-08 | Waterproofing Application Method | 4.1 | QCS 2014 S7 Part 2 | 14 days | 1 |
| C-09 | Finishes / Cladding Installation | 4.1 | QCS 2014 S15, S16 | 14 days | 1 |
| C-10 | MEP Installation Procedure | 4.1 | QCS 2014 S21-S27 | 14 days | 1 |
| C-11 | Road Works / Paving Procedure | 4.1 | QCS 2014 S6 | 14 days | 1 |
| C-12 | Hot Weather Concreting Procedure | 4.1 | QCS 2014 S5 Part 3.7 | 14 days | 1 |
| C-13 | Protection of Works Procedure | 4.1, 17.2 | QCS 2014 S1 Part 5 | 14 days | 2 |
| C-14 | Traffic Management Plan | 4.1, 4.13 | QCS 2014 S1 Part 5 | 14 days | 1 |

## 4.4 Category D — Quality Assurance / Quality Control

Quality submittals cover the Contractor's quality management system, inspection and test plans, test results, and non-conformance documentation. FIDIC Clause 4.9 requires the Contractor to institute a quality assurance system.

| Ref | Submittal Type | FIDIC Clause | QCS 2014 Ref | Review Period | Priority |
| --- | --- | --- | --- | --- | --- |
| D-01 | Project Quality Plan (PQP) | 4.9 | QCS 2014 S1 Part 4 | 21 days | 1 |
| D-02 | Inspection & Test Plan (ITP) | 4.9, 7.3 | QCS 2014 S1 Part 4 | 14 days | 1 |
| D-03 | Material Test Result | 7.3 | QCS 2014 S3-S9 | 7 days | 2 |
| D-04 | In-Situ Test Result | 7.3, 12.1 | QCS 2014 S3-S9 | 7 days | 2 |
| D-05 | Non-Conformance Report (NCR) | 7.5, 11.1 | QCS 2014 S1 Part 4 | 7 days | 1 |
| D-06 | NCR Corrective Action Response | 7.5, 11.1 | QCS 2014 S1 Part 4 | 14 days | 1 |
| D-07 | Calibration Certificate | 4.9 | QCS 2014 S1 Part 4 | 14 days | 2 |
| D-08 | Welding Procedure Specification (WPS) | 4.9 | QCS 2014 S9 Part 3 | 14 days | 1 |
| D-09 | Welder Qualification Certificate | 4.9 | QCS 2014 S9 Part 3 | 14 days | 1 |
| D-10 | Pressure Test Report | 7.3, 9.1 | QCS 2014 S22, S24 | 7 days | 2 |
| D-11 | Survey / Setting Out Report | 4.7, 12.1 | QCS 2014 S1 Part 3 | 7 days | 2 |
| D-12 | Inspection Request (IR) | 7.3 | QCS 2014 S1 Part 4 | 24 hours | 2 |

## 4.5 Category E — Health, Safety & Environment (HSE)

HSE submittals cover the Contractor's obligations under FIDIC Clause 6.7 (Health & Safety) and Clause 4.18 (Protection of the Environment), aligned with Qatar's HSE regulations and QCS 2014 requirements.

| Ref | Submittal Type | FIDIC Clause | QCS 2014 Ref | Review Period | Priority |
| --- | --- | --- | --- | --- | --- |
| E-01 | Project HSE Plan | 4.18, 6.7 | QCS 2014 S1 Part 6 | 21 days | 1 |
| E-02 | Activity Risk Assessment (RA) | 6.7 | QCS 2014 S1 Part 6 | 14 days | 1 |
| E-03 | COSHH Assessment | 6.7 | QCS 2014 S1 Part 6 | 14 days | 1 |
| E-04 | Emergency Response Plan | 6.7 | QCS 2014 S1 Part 6 | 14 days | 1 |
| E-05 | Environmental Management Plan | 4.18 | QCS 2014 S1 Part 6 | 21 days | 1 |
| E-06 | Waste Management Plan | 4.18 | QCS 2014 S1 Part 6 | 14 days | 1 |
| E-07 | Noise / Dust Monitoring Report | 4.18 | QCS 2014 S1 Part 6 | 7 days | 2 |
| E-08 | HSE Monthly Report | 6.7 | QCS 2014 S1 Part 6 | 7 days | 3 |
| E-09 | Incident / Accident Report | 6.7 | QCS 2014 S1 Part 6 | 24 hours | 1 |
| E-10 | Permit to Work (PTW) | 6.7 | QCS 2014 S1 Part 6 | 48 hours | 1 |
| E-11 | Hazardous Material Register | 6.7, 4.18 | QCS 2014 S1 Part 6 | 14 days | 1 |
| E-12 | HSE Training Records | 6.7 | QCS 2014 S1 Part 6 | 14 days | 2 |

## 4.6 Category F — Progress & Programme

Programme submittals track the Contractor's schedule obligations under FIDIC Clause 8.3 (Programme) including baseline, updates, recovery, and resource data.

| Ref | Submittal Type | FIDIC Clause | QCS 2014 Ref | Review Period | Priority |
| --- | --- | --- | --- | --- | --- |
| F-01 | Baseline Programme (CPM) | 8.3 | QCS 2014 S1 Part 2 | 21 days | 1 |
| F-02 | Monthly Programme Update | 8.3 | QCS 2014 S1 Part 2 | 7 days | 2 |
| F-03 | Recovery Programme | 8.3, 8.6 | N/A | 14 days | 1 |
| F-04 | Resource Histogram | 8.3 | QCS 2014 S1 Part 2 | 14 days | 2 |
| F-05 | Cash Flow Projection | 8.3, 14.3 | N/A | 14 days | 2 |
| F-06 | Monthly Progress Report | 4.21 | QCS 2014 S1 Part 2 | 7 days | 2 |
| F-07 | 4-Week Look-Ahead Schedule | 8.3 | QCS 2014 S1 Part 2 | Weekly | 2 |
| F-08 | S-Curve (Planned vs Actual) | 8.3 | N/A | Monthly | 2 |
| F-09 | Procurement Schedule | 8.3 | N/A | 14 days | 1 |
| F-10 | Delay Analysis Report | 8.4, 20.1 | N/A | 14 days | 1 |

## 4.7 Category G — Contractual & Commercial

Commercial submittals cover payment applications, variation proposals, claims, bonds, and other contractual correspondence governed by FIDIC Clauses 14 (Contract Price & Payment), 13 (Variations), and 20 (Claims, Disputes & Arbitration).

| Ref | Submittal Type | FIDIC Clause | QCS 2014 Ref | Review Period | Priority |
| --- | --- | --- | --- | --- | --- |
| G-01 | Interim Payment Certificate (IPC) | 14.3, 14.6 | N/A | 28 days | 1 |
| G-02 | Variation Proposal | 13.1, 13.3 | N/A | 14 days | 1 |
| G-03 | Contractor's Claim Notice | 20.1 | N/A | 28 days | 1 |
| G-04 | Extension of Time Request | 8.4, 20.1 | N/A | 42 days | 1 |
| G-05 | Performance Bond | 4.2 | N/A | Prior to start | 1 |
| G-06 | Advance Payment Guarantee | 14.2 | N/A | Prior to advance | 1 |
| G-07 | Insurance Certificates | 18.1, 18.2 | N/A | Prior to start | 1 |
| G-08 | Retention Release Application | 14.9 | N/A | 14 days | 2 |
| G-09 | Subcontractor Approval Request | 4.4 | QCS 2014 S1 Part 2 | 14 days | 1 |
| G-10 | Day-work Records | 12.3, 13.6 | N/A | 7 days | 2 |
| G-11 | Contractual Notice (General) | 1.3, 2.5 | N/A | Per clause | 1 |
| G-12 | Final Statement | 14.11 | N/A | 56 days | 1 |

## 4.8 Category H — Handover & Close-Out

Handover submittals support the transition of the completed works to the Employer, including as-built documentation, O&M manuals, testing & commissioning, and warranty administration under FIDIC Clauses 10 (Taking Over) and 11 (Defects).

| Ref | Submittal Type | FIDIC Clause | QCS 2014 Ref | Review Period | Priority |
| --- | --- | --- | --- | --- | --- |
| H-01 | As-Built Drawings | 5.6, 10.1 | QCS 2014 S1 Part 7 | Prior to TOC | 1 |
| H-02 | Operation & Maintenance Manual | 5.6, 10.1 | QCS 2014 S1 Part 7 | Prior to TOC | 1 |
| H-03 | Testing & Commissioning Plan | 9.1 | QCS 2014 S1 Part 7 | 28 days | 1 |
| H-04 | Testing & Commissioning Report | 9.1, 9.4 | QCS 2014 S1 Part 7 | 14 days | 1 |
| H-05 | Pre-Commissioning Checklist | 9.1 | QCS 2014 S1 Part 7 | 14 days | 1 |
| H-06 | Spare Parts & Tools List | 10.1 | QCS 2014 S1 Part 7 | Prior to TOC | 2 |
| H-07 | Warranty Certificate Package | 11.1, 11.3 | QCS 2014 S1 Part 7 | Prior to TOC | 1 |
| H-08 | Snag List / Defect Schedule | 10.1, 11.1 | N/A | 14 days | 1 |
| H-09 | GSAS Compliance Documentation | N/A | GSAS/QSAS Requirements | Prior to TOC | 1 |
| H-10 | Building User Guide | 10.1 | QCS 2014 S1 Part 7 | Prior to TOC | 2 |
| H-11 | DLP Defect Report | 11.1, 11.2 | N/A | Per defect | 2 |
| H-12 | Final Account Documentation | 14.11, 14.13 | N/A | 56 days | 1 |

## 4.9 Category J — Specialist / Regulatory

Specialist submittals cover regulatory authority approvals, third-party certifications, sustainability compliance, and utility coordination — specific to Qatar's regulatory landscape including Ashghal, Civil Defense, Kahramaa, and GSAS.

| Ref | Submittal Type | FIDIC Clause | QCS 2014 Ref | Review Period | Priority |
| --- | --- | --- | --- | --- | --- |
| J-01 | Technical Design Consultant Approval (DC1/DC2) | N/A | Ashghal DC Process | Per authority | 1 |
| J-02 | Building Completion Certificate (BCC) | N/A | Ashghal/Municipality | Per authority | 1 |
| J-03 | No Objection Certificate (NOC) | N/A | Various authorities | Per authority | 1 |
| J-04 | Fire & Life Safety Review | 4.1 | NFPA / Qatar Civil Defense | 28 days | 1 |
| J-05 | Kahramaa Connection Application | N/A | Kahramaa Regulations | Per authority | 1 |
| J-06 | Qatar Cool Connection Application | N/A | Qatar Cool Standards | Per authority | 1 |
| J-07 | GSAS / Sustainability Certification | N/A | GSAS/QSAS Requirements | Per authority | 1 |
| J-08 | Third-Party Inspection Report | 7.3 | Various | 14 days | 2 |
| J-09 | Road Opening Permit | N/A | Ashghal ROW | Per authority | 1 |
| J-10 | Telecommunication Provider Approval | N/A | Ooredoo/Vodafone | Per authority | 1 |
| J-11 | Environmental Impact Assessment | 4.18 | Qatar EPA | Per authority | 1 |
| J-12 | Heritage / Archaeological Clearance | 4.1 | Qatar Museums Authority | Per authority | 2 |

# 5. FIDIC Clause Cross-Reference Matrix

The following matrix maps key FIDIC 1999 Red Book clauses to the submittal categories that are triggered by or required under each clause.

| FIDIC Clause | Subject | Submittal Refs | Description |
| --- | --- | --- | --- |
| 1.3 | Communications | G-11 | All formal notices and contractual communications |
| 2.5 | Employer's Claims | G-03, G-11 | Counter-claims and employer notices |
| 4.1 | Contractor's General Obligations | A, C, J | Technical Design details, method statements, regulatory |
| 4.2 | Performance Security | G-05 | Performance bond submission |
| 4.4 | Subcontractors | G-09, A-14 | Subcontractor approval, specialist design |
| 4.7 | Setting Out | D-11 | Survey and setting-out verification |
| 4.9 | Quality Assurance | D-01 to D-12 | Full QA/QC documentation suite |
| 4.13 | Rights of Way & Facilities | C-14 | Traffic management and access plans |
| 4.18 | Protection of Environment | E-05 to E-07, J-11 | Environmental plans and monitoring |
| 4.21 | Progress Reports | F-06 | Monthly progress reporting |
| 5.2 | Contractor's Documents | A-01 to A-14 | All design submittals |
| 5.4 | Technical Standards | A-03, A-07 | Calculations and compliance |
| 5.6 | As-Built Documents | H-01, H-02 | As-built drawings and O&M manuals |
| 6.7 | Health & Safety | E-01 to E-12 | Full HSE documentation suite |
| 7.1 | Manner of Execution | B-01 to B-14 | All material and product submittals |
| 7.3 | Inspection | D-03, D-04, D-12 | Test results and inspection requests |
| 7.5 | Defects & Rejection | D-05, D-06 | NCR and corrective actions |
| 8.3 | Programme | F-01 to F-10 | All programme submittals |
| 8.4 | Extension of Time | F-10, G-04 | Delay analysis and EOT requests |
| 9.1 | Tests on Completion | H-03, H-04, H-05 | Testing & commissioning |
| 10.1 | Taking Over | H-01 to H-10 | All handover documentation |
| 11.1 | Completion of Outstanding Work | H-08, H-11 | Snag lists and DLP defects |
| 13.1 | Right to Vary | A-09, G-02 | Technical Design change and variation |
| 14.2 | Advance Payment | G-06 | Advance payment guarantee |
| 14.3 | Application for IPC | G-01 | Payment applications |
| 14.9 | Payment of Retention | G-08 | Retention release |
| 14.11 | Final Statement | G-12, H-12 | Final account documentation |
| 17.2 | Contractor's Care of Works | C-13 | Protection procedures |
| 18.1 | General Insurance Requirements | G-07 | Insurance certificates |
| 20.1 | Contractor's Claims | G-03, G-04 | Claims and EOT |

# 6. QCS 2014 Section Cross-Reference Matrix

The following matrix maps QCS 2014 sections to the submittal categories that contain submittals referenced by those specifications.

| QCS Section | Subject | Key Requirements | Submittal Refs |
| --- | --- | --- | --- |
| S1 | General | Part 2: Programme (F) Part 3: Drawings & Docs (A) Part 4: Quality (D) Part 5: Method Statements (C) Part 6: HSE (E) Part 7: Handover (H) | A, B, C, D, E, F, H |
| S2 | Site Investigation & Demolition | Part 2: Demolition | C-06 |
| S3 | Earthworks | Compaction, grading, fill specs | B-04, D-03 |
| S4 | Foundations | Part 2: Excavation Part 3: Piling | C-03, C-07, D-04 |
| S5 | Concrete Works | Part 2: Structural Technical Design Part 3: Concrete Production | A-03, B-11, C-04, C-12 |
| S6 | Road Works | Part 6: Asphalt | B-12, C-11 |
| S7 | Waterproofing | Part 2: Application methods | B-01, C-08 |
| S8 | Drainage & Sewerage | Pipe specs, installation | A-04, B-01, C-10 |
| S9 | Steelwork | Part 3: Welding | A-02, B-13, D-08, D-09 |
| S10 | Building Works | Part 6: Fire protection | A-13, B-01, C-09 |
| S15 | Painting & Decorating | Finishes, colour schedules | B-07, C-09 |
| S16 | Tiling & Cladding | Material specs, installation | B-05, B-07, C-09 |
| S21-S27 | MEP Services | Mechanical, electrical, plumbing | A-04, A-14, B-08, C-10, D-10 |
| S28 | Landscaping | Landscape design & materials | A-11, B-01 |

# 7. Submittal Workflow (PF-01 Integration)

All submittals, regardless of category, follow the SkyStruct PF-01 Document Review & Submission 8-Step Cycle. The submittal category (A-J) determines which cover page template is auto-generated and which review routing is applied.

## 7.1 The 8-Step Cycle

| Step | Activity | Description |
| --- | --- | --- |
| Step 1 | Contractor Preparation | Contractor prepares submittal package with correct cover page template, supporting documents, and reference number per HAI-GOV-035. |
| Step 2 | Contractor Self-Check | Internal QA review by Contractor's document controller against the ITP and submittal register checklist. |
| Step 3 | Submission to Consultant | Formal submission through SkyStruct with auto-date-stamp, notification to consultant, and review timer initiated. |
| Step 4 | Consultant Technical Review | Consultant reviews against contract drawings, specifications (QCS 2014), and relevant codes. Technical comments logged. |
| Step 5 | ER / HAI Review | Employer's Representative reviews consultant recommendation, checks contractual compliance, applies approval matrix routing. |
| Step 6 | Decision & Response | Response code issued (A/B/C/D/E). For C/D: specific deficiencies listed with clause references. |
| Step 7 | Resubmission (if required) | Contractor addresses comments, updates revision number, resubmits. Previous version archived. |
| Step 8 | Closure & Archive | Approved submittal logged to project register, linked to relevant PFs, IFC stamp applied where applicable. |

## 7.2 Response Codes

| Code | Status | Description |
| --- | --- | --- |
| A | Approved | Submittal approved. Work may proceed. No further submission required. |
| B | Approved with Comments | Work may proceed incorporating noted comments. No resubmission required unless comments are substantive. |
| C | Revise & Resubmit | Submittal contains deficiencies. Work SHALL NOT proceed on affected elements. Revised submittal required. |
| D | Rejected | Submittal does not comply with contract requirements. Complete resubmission required. No work shall proceed. |
| E | For Information Only | Noted for record. No approval action required. Contractor responsible for compliance. |

## 7.3 Review Periods by Priority

Review periods are measured from date of receipt of a complete and conforming submittal. Incomplete or non-conforming submittals are returned without review and do not start the review clock.

| Priority | Implication | Typical Review Period |
| --- | --- | --- |
| 1 — Pre-Approval Required | Work cannot start until approved | 14–28 days depending on complexity |
| 2 — Required During Execution | Must be submitted but work may proceed in parallel | 7–14 days |
| 3 — For Information / Record | Submitted for project records | 7 days acknowledgement |

# 8. Cover Page Templates

The following pages provide standardized cover page templates for each of the 9 submittal categories. Each template is designed to capture all required metadata for the submittal type, facilitate the 8-step review cycle, and integrate with the SkyStruct PF-01 workflow engine. Templates should be populated in the SkyStruct system, which auto-generates the cover page with project-specific data.

SUBMITTAL COVER PAGE TEMPLATE

Category: A — Technical Design Submittal

| Project Name: | [Project Name] |
| --- | --- |
| Contract No: | [Contract Number] |
| Contractor: | [Contractor Name] |
| Consultant: | [Consultant Name] |
| Employer's Rep: | HAI / ARADA Governance |

| FIELD | VALUE |
| --- | --- |
| Submittal Reference No: | [HAI-P01-A-XX-NNNN-RR] |
| Submittal Title: | [Drawing / Calculation Title] |
| Discipline: | [Architectural / Structural / MEP / Civil / ...] |
| Drawing / Document No: | [Original drawing number] |
| Revision: | [Rev XX] |
| Technical Design Stage: | [Concept / Developed / Technical / IFC] |
| FIDIC Clause Reference: | [5.2 / 5.4 / 13.1 / ...] |
| QCS 2014 Section: | [Section reference] |
| Related Submittal Refs: | [Cross-references to other submittals] |
| Priority: | [1 — Pre-Approval / 2 — During Execution / 3 — Info] |
| Required Response Date: | [Date based on review period] |
| No. of Attachments: | [Count] |
| Remarks: | [Any special notes or conditions] |

| ACTION | NAME | SIGNATURE | DATE |
| --- | --- | --- | --- |
| Prepared by (Contractor) |  |  |  |
| Reviewed & Approved by (Lead Consultant) |  |  |  |
| Endorsed by (ER / HAI) |  |  |  |

DECISION:

| A Approved | B Approved w/ Comments | C Revise & Resubmit | D Rejected | E For Information |
| --- | --- | --- | --- | --- |

SUBMITTAL COVER PAGE TEMPLATE

Category: B — Material & Product Submittal

| Project Name: | [Project Name] |
| --- | --- |
| Contract No: | [Contract Number] |
| Contractor: | [Contractor Name] |
| Consultant: | [Consultant Name] |
| Employer's Rep: | HAI / ARADA Governance |

| FIELD | VALUE |
| --- | --- |
| Submittal Reference No: | [HAI-P01-B-XX-NNNN-RR] |
| Submittal Title: | [Material / Product Description] |
| Material / Product: | [Specific material or product name] |
| Manufacturer: | [Manufacturer name] |
| Origin / Country: | [Country of manufacture] |
| Specification Reference: | [QCS 2014 section / spec clause] |
| FIDIC Clause Reference: | [7.1 / 7.3 / ...] |
| Sample Provided: | [Yes / No — if physical sample attached] |
| Test Report Attached: | [Yes / No — lab test reference] |
| Proposed Use / Location: | [Where in the works this material is used] |
| Priority: | [1 / 2 / 3] |
| Required Response Date: | [Date] |
| No. of Attachments: | [Count] |

| ACTION | NAME | SIGNATURE | DATE |
| --- | --- | --- | --- |
| Prepared by (Contractor) |  |  |  |
| Reviewed & Approved by (Lead Consultant) |  |  |  |
| Endorsed by (ER / HAI) |  |  |  |

DECISION:

| A Approved | B Approved w/ Comments | C Revise & Resubmit | D Rejected | E For Information |
| --- | --- | --- | --- | --- |

SUBMITTAL COVER PAGE TEMPLATE

Category: C — Method Statement & Procedure

| Project Name: | [Project Name] |
| --- | --- |
| Contract No: | [Contract Number] |
| Contractor: | [Contractor Name] |
| Consultant: | [Consultant Name] |
| Employer's Rep: | HAI / ARADA Governance |

| FIELD | VALUE |
| --- | --- |
| Submittal Reference No: | [HAI-P01-C-XX-NNNN-RR] |
| Submittal Title: | [Method Statement Title] |
| Activity / Trade: | [Construction activity covered] |
| Location / Zone: | [Area of works] |
| Planned Start Date: | [Date activity is planned to start] |
| FIDIC Clause Reference: | [4.1 / 8.3 / ...] |
| QCS 2014 Section: | [Section reference] |
| Risk Assessment Ref: | [Link to E-02 if applicable] |
| Resources Required: | [Key plant/equipment/labour] |
| Duration: | [Expected activity duration] |
| Priority: | [1 / 2 / 3] |
| Required Response Date: | [Date] |

| ACTION | NAME | SIGNATURE | DATE |
| --- | --- | --- | --- |
| Prepared by (Contractor) |  |  |  |
| Reviewed & Approved by (Lead Consultant) |  |  |  |
| Endorsed by (ER / HAI) |  |  |  |

DECISION:

| A Approved | B Approved w/ Comments | C Revise & Resubmit | D Rejected | E For Information |
| --- | --- | --- | --- | --- |

SUBMITTAL COVER PAGE TEMPLATE

Category: D — Quality Assurance / Quality Control

| Project Name: | [Project Name] |
| --- | --- |
| Contract No: | [Contract Number] |
| Contractor: | [Contractor Name] |
| Consultant: | [Consultant Name] |
| Employer's Rep: | HAI / ARADA Governance |

| FIELD | VALUE |
| --- | --- |
| Submittal Reference No: | [HAI-P01-D-XX-NNNN-RR] |
| Submittal Title: | [QA/QC Document Title] |
| Type: | [PQP / ITP / Test Result / NCR / IR / Calibration / ...] |
| Work Package / Element: | [Specific work element] |
| Location / Grid: | [Location reference] |
| FIDIC Clause Reference: | [4.9 / 7.3 / 7.5 / 12.1 / ...] |
| QCS 2014 Section: | [Section reference] |
| ITP Reference: | [Link to applicable ITP] |
| Test Standard / Method: | [BS / ASTM / ISO reference] |
| Result: | [Pass / Fail / N/A] |
| NCR Reference (if any): | [NCR number if related] |
| Priority: | [1 / 2 / 3] |

| ACTION | NAME | SIGNATURE | DATE |
| --- | --- | --- | --- |
| Prepared by (Contractor) |  |  |  |
| Reviewed & Approved by (Lead Consultant) |  |  |  |
| Endorsed by (ER / HAI) |  |  |  |

DECISION:

| A Approved | B Approved w/ Comments | C Revise & Resubmit | D Rejected | E For Information |
| --- | --- | --- | --- | --- |

SUBMITTAL COVER PAGE TEMPLATE

Category: E — Health, Safety & Environment

| Project Name: | [Project Name] |
| --- | --- |
| Contract No: | [Contract Number] |
| Contractor: | [Contractor Name] |
| Consultant: | [Consultant Name] |
| Employer's Rep: | HAI / ARADA Governance |

| FIELD | VALUE |
| --- | --- |
| Submittal Reference No: | [HAI-P01-E-XX-NNNN-RR] |
| Submittal Title: | [HSE Document Title] |
| Type: | [HSE Plan / RA / COSHH / Incident / PTW / ...] |
| Activity / Area: | [Activity or area covered] |
| FIDIC Clause Reference: | [4.18 / 6.7] |
| QCS 2014 Section: | [S1 Part 6] |
| Risk Level: | [High / Medium / Low] |
| Regulatory Requirement: | [Qatar HSE reg reference if applicable] |
| Validity Period: | [From — To dates if time-limited] |
| Priority: | [1 / 2 / 3] |
| Required Response Date: | [Date] |

| ACTION | NAME | SIGNATURE | DATE |
| --- | --- | --- | --- |
| Prepared by (Contractor) |  |  |  |
| Reviewed & Approved by (Lead Consultant) |  |  |  |
| Endorsed by (ER / HAI) |  |  |  |

DECISION:

| A Approved | B Approved w/ Comments | C Revise & Resubmit | D Rejected | E For Information |
| --- | --- | --- | --- | --- |

SUBMITTAL COVER PAGE TEMPLATE

Category: F — Progress & Programme

| Project Name: | [Project Name] |
| --- | --- |
| Contract No: | [Contract Number] |
| Contractor: | [Contractor Name] |
| Consultant: | [Consultant Name] |
| Employer's Rep: | HAI / ARADA Governance |

| FIELD | VALUE |
| --- | --- |
| Submittal Reference No: | [HAI-P01-F-GN-NNNN-RR] |
| Submittal Title: | [Programme / Report Title] |
| Type: | [Baseline / Update / Recovery / Look-Ahead / S-Curve / ...] |
| Reporting Period: | [From — To dates] |
| FIDIC Clause Reference: | [8.3 / 8.4 / 4.21 / 14.3] |
| Overall Progress (%): | [Planned vs Actual] |
| Critical Path Affected: | [Yes / No — describe if Yes] |
| Software Used: | [Primavera P6 / MS Project / ...] |
| Priority: | [1 / 2 / 3] |
| Required Response Date: | [Date] |

| ACTION | NAME | SIGNATURE | DATE |
| --- | --- | --- | --- |
| Prepared by (Contractor) |  |  |  |
| Reviewed & Approved by (Lead Consultant) |  |  |  |
| Endorsed by (ER / HAI) |  |  |  |

DECISION:

| A Approved | B Approved w/ Comments | C Revise & Resubmit | D Rejected | E For Information |
| --- | --- | --- | --- | --- |

SUBMITTAL COVER PAGE TEMPLATE

Category: G — Contractual & Commercial

| Project Name: | [Project Name] |
| --- | --- |
| Contract No: | [Contract Number] |
| Contractor: | [Contractor Name] |
| Consultant: | [Consultant Name] |
| Employer's Rep: | HAI / ARADA Governance |

| FIELD | VALUE |
| --- | --- |
| Submittal Reference No: | [HAI-P01-G-GN-NNNN-RR] |
| Submittal Title: | [Document Title] |
| Type: | [IPC / Variation / Claim / EOT / Bond / Insurance / Notice / ...] |
| FIDIC Clause Reference: | [Specific clause triggering this submittal] |
| Contract Value Impact: | [Amount if financial — QAR] |
| Time Impact: | [Days if schedule-related] |
| Notice Date: | [Date of first notice if claim/EOT] |
| Time-Bar Deadline: | [Contractual deadline for submission] |
| Supporting Documents: | [List of attached evidence] |
| Priority: | [1 / 2 / 3] |
| Required Response Date: | [Date per FIDIC timelines] |

| ACTION | NAME | SIGNATURE | DATE |
| --- | --- | --- | --- |
| Prepared by (Contractor) |  |  |  |
| Reviewed & Approved by (Lead Consultant) |  |  |  |
| Endorsed by (ER / HAI) |  |  |  |

DECISION:

| A Approved | B Approved w/ Comments | C Revise & Resubmit | D Rejected | E For Information |
| --- | --- | --- | --- | --- |

SUBMITTAL COVER PAGE TEMPLATE

Category: H — Handover & Close-Out

| Project Name: | [Project Name] |
| --- | --- |
| Contract No: | [Contract Number] |
| Contractor: | [Contractor Name] |
| Consultant: | [Consultant Name] |
| Employer's Rep: | HAI / ARADA Governance |

| FIELD | VALUE |
| --- | --- |
| Submittal Reference No: | [HAI-P01-H-XX-NNNN-RR] |
| Submittal Title: | [Handover Document Title] |
| Type: | [As-Built / O&M / T&C / Warranty / Snag / Final Account / ...] |
| System / Zone: | [Building system or zone covered] |
| FIDIC Clause Reference: | [5.6 / 9.1 / 10.1 / 11.1 / 14.11] |
| QCS 2014 Section: | [S1 Part 7] |
| TOC Target Date: | [Taking Over Certificate target date] |
| DLP Period: | [Start — End dates] |
| Warranty Duration: | [Duration per spec section] |
| Priority: | [1 / 2 / 3] |
| Required Response Date: | [Date] |

| ACTION | NAME | SIGNATURE | DATE |
| --- | --- | --- | --- |
| Prepared by (Contractor) |  |  |  |
| Reviewed & Approved by (Lead Consultant) |  |  |  |
| Endorsed by (ER / HAI) |  |  |  |

DECISION:

| A Approved | B Approved w/ Comments | C Revise & Resubmit | D Rejected | E For Information |
| --- | --- | --- | --- | --- |

SUBMITTAL COVER PAGE TEMPLATE

Category: J — Specialist / Regulatory

| Project Name: | [Project Name] |
| --- | --- |
| Contract No: | [Contract Number] |
| Contractor: | [Contractor Name] |
| Consultant: | [Consultant Name] |
| Employer's Rep: | HAI / ARADA Governance |

| FIELD | VALUE |
| --- | --- |
| Submittal Reference No: | [HAI-P01-J-XX-NNNN-RR] |
| Submittal Title: | [Document Title] |
| Authority / Body: | [Ashghal / Civil Defense / Kahramaa / GSAS / ...] |
| Application Type: | [DC1 / DC2 / BCC / NOC / Connection / ...] |
| FIDIC Clause Reference: | [If applicable] |
| Regulatory Reference: | [Qatar regulation / code reference] |
| Application Date: | [Date submitted to authority] |
| Expected Response Date: | [Authority processing timeline] |
| Fees Paid: | [Yes / No — amount if applicable] |
| Status: | [Submitted / Under Review / Approved / Rejected] |
| Priority: | [1 / 2 / 3] |

| ACTION | NAME | SIGNATURE | DATE |
| --- | --- | --- | --- |
| Prepared by (Contractor) |  |  |  |
| Reviewed & Approved by (Lead Consultant) |  |  |  |
| Endorsed by (ER / HAI) |  |  |  |

DECISION:

| A Approved | B Approved w/ Comments | C Revise & Resubmit | D Rejected | E For Information |
| --- | --- | --- | --- | --- |

# Appendix A — Submittal Numbering Convention

The full submittal numbering convention integrates with the HAI-GOV-035 Document Numbering System. The structure is designed to be machine-parseable for SkyStruct auto-routing and human-readable for site use.

Format: [Project]-[Category]-[Discipline]-[Seq]-[Rev]

Example: HAI-P01-B-ME-0023-01

= Project HAI-P01, Material/Product Submittal (B), Mechanical discipline (ME), sequential item 23, revision 01.

| Code | Discipline |
| --- | --- |
| AR | Architectural |
| ST | Structural |
| ME | Mechanical |
| EL | Electrical |
| PL | Plumbing |
| FP | Fire Protection |
| CV | Civil |
| LS | Landscape |
| ID | Interior Technical Design |
| GN | General / Multi-discipline |
| IT | IT / Low Current |
| VT | Vertical Transport (Lifts) |

# Appendix B — Review Response Codes

Standard response codes used on all submittal cover pages. These codes align with the SkyStruct PF-01 workflow and the HAI-GOV-013 Workflow Engine Rules.

| Code | Status | Condition | Action Required |
| --- | --- | --- | --- |
| A | Approved | No restrictions | Work may proceed as submitted. Submittal archived as approved. |
| B | Approved with Comments | Minor comments only | Work may proceed incorporating comments. No resubmission unless comments are substantive. Reviewer's comments become part of the approved record. |
| C | Revise & Resubmit | Deficiencies found | Work on affected elements SHALL NOT proceed until revised submittal is approved. Contractor to address all comments and resubmit with updated revision number. |
| D | Rejected | Non-compliant | Submittal does not meet contract requirements. Complete new submittal required. May trigger NCR if work was done based on unapproved submittal. |
| E | For Information | Record only | Noted for project records. No formal approval action. Contractor remains responsible for compliance with contract requirements. |